## Base AOL
Documento | Titulo | Disciplina AOL | Disciplina origem | Revisao | Contabilizar | Status AOL | Motivo desconsiderado | Status documento | Issue Status | Last transmittal purpose | 14-Tr_Aol-Fabrication | Diretorio | Observacao admin
11413-PVN-DAE-BONGA-000027A 3N1_DAE_UPDATED | 11413-PVN-DAE-BONGA-00027_A01_A02_A03_BN DED - SCH COMPLETION..., CONTRACTOR & SUBCONTRACTOR CO-LOCATION, & CONTRACTOR & SUBCONTRACTOR CO-LOCATION | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
11413-PVN-DAE-BONGA-00004 | PROJECT VARIANCE NOTIFICATION (PVN) FORM-0004: OVERDUE DELIVERABLES NOTICE | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
11413-PVN-DAE-BONGA-00006 | SPECIALIST POWER SYSTEM STUDIES VENDOR | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
11413-PVN-DAE-BONGA-00007 | PROJECT VARIANCE NOTIFICATION - PVN FOR BONGA NORTH D.E.D SCHEDULE ACCELERATION | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
11413-PVN-DAE-BONGA-00009 | DYNAMIC SIMULATION FOR WATER INJECTION SYSTEM | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
11413-PVN-DAE-BONGA-0001 | PROJECT VARIANCE NOTIFICATION (PVN) FORM | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
11413-PVN-DAE-BONGA-00010 | EXPENSES_FOR_1ST_AND_PRIORITY_0&1_MODEL_REVIEW_WORKSHOPS | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
11413-PVN-DAE-BONGA-00011 | RELOCATION_OF_BOARDING_VALVE_PANEL.XLSX | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
11413-PVN-DAE-BONGA-00012 | IMPACT OF WIP SINGLE LIFT INSTALLATION.XLSX | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
11413-PVN-DAE-BONGA-00013 | REIMBURSEMENT FOR ADDITIONAL EFFORTS REQUIRED FOR CORROSION | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
11413-PVN-DAE-BONGA-00014 | HUMAN FACTOR ENGINEERING | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
11413-PVN-DAE-BONGA-00015 | TELECOMS SCOPE EXECUTION | PMT | AA - PROJECT MANAGEMENT | A02 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
11413-PVN-DAE-BONGA-00016 | OVERTIME COST EXPENDED FOR 60% DESIGN REVIEW | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
11413-PVN-DAE-BONGA-00020 | LEGRANT CABLE TRAY CHANGE | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
11413-PVN-DAE-BONGA-00021 | IMPLEMENTATION OF A01 FIRE AND GAS DETECTORS MAPPING EXERCISE REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
11413-PVN-DAE-BONGA-00022 | HEAT TRACING SYSTEM | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
11413-PVN-DAE-BONGA-00023 | MATERIAL SUBSTITUTION REQUEST FOR TAM26 SPECIAL PIPE SUPPORTS | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
11413-PVN-DAE-BONGA-00025 | STRUCTURAL INTEGRITY REPAIRS | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
11413-PVN-DAE-BONGA-00026 | EXPENSES FOR 3RD CONSTRUCTABILITY REVIEW WORKSHOP - COPY | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
11413-PVN-DAE-BONGA-00027 | BONGA NORTH D.E.D - SCHEDULE COMPLETION DATE EXTENSION (BUSINESS TRIP & EXTENDED STAY) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
11413-PVN-DAE-BONGA-00027A | CONTRACTOR AND SUBCONTRACTOR CO-LOCATION | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
11413-PVN-DAE-BONGA-00027B | 11413-PVN-DAE-BONGA-00027B_A01_SCHEDULE COMPLETION DATE EXTENSION_(5DEC25-13MAR26) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
11413-PVN-DAE-BONGA-00027C | SCHEDULE COMPLETION DATE EXTENSION (FORECAST TO COMPLETION) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
11413-PVN-DAE-BONGA-00028 | STRENGTHEN OF EXISTING METHANOL INJECTION SKID | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
11413-PVN-DAE-BONGA-00029 | BONGA NORTH EPC 1 DED CHANGE IN F&G DEVICES MODELLING INPUT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
11413-PVN-DAE-BONGA-00030 | CHANGE IN DESIGN SAFETY CASE SCOPE_SUPERSEDES | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
11413-PVN-DAE-BONGA-00031 | PIPE STRESS ANALYSIS OF GRE PIPING SYSTEM | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
11413-PVN-DAE-BONGA-00031_WITHDRAWN | WITHDRAWN_CHANGE IN DESIGN SAFETY CASE SCOPE_WITHDRAWN | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
11413-PVN-DAE-BONGA-00032 | UNDER DECK ASSESSMENT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
11413-PVN-DAE-BONGA-00033 | ADDITIONAL DAY FOR DESIGN SAFETY CASE WORKS | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
11413-PVN-DAE-BONGA-00034 | EMERGENCY SYSTEMS SURVIVABILITY ANALYSIS (ESSA) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
11413-PVN-DAE-BONGA-00035 | COMPLETION OF ELECTRICAL CABLE TRAY SUPPORT MR2 LEVEL 4 CHANGE OF SPECIFICATION TO UNISTRUTS | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
BNO-000133-300-IN-2105-002-AOL-00001 | ORIFICE SIZING CALCULATION SHEET - RESTRICTION ORIFICE | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  |  |  | BNO / 03-VENDOR / WIKA / PO_000133-RESTRICTION ORIFICE
BNO-000133-300-IN-7880-002-AOL-00001 | RESTRICTION ORIFICE PLATE WITH RTJ HOLDER RING | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / WIKA / PO_000133-RESTRICTION ORIFICE
BNO-000133-300-JA-6611-002-AOL-00001 | VENDOR DOCUMENT REGISTER LIST (VDRL) - RESTRICTION ORIFICE | IT / IM | JA - IM | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / WIKA / PO_000133-RESTRICTION ORIFICE
BNO-000339-300-IN-2105-008-AOL-00001 | TECHNICAL DATASHEET / SPECIFICATION - TEMPERATURE INDICATING TRANSMITTER | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  |  |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_000339-TEMP_INDCT_TRANSMITTER
BNO-000339-300-IN-2105-008-AOL-00002 | WAKE FREQUENCY CALCULATION (WFC) - TEMPERATURE INDICATING TRANSMITTER | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | TRANSMITTAL |  |  |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_000339-TEMP_INDCT_TRANSMITTER
BNO-000339-300-IN-4018-008-AOL-00001-001 | GENERAL ARRANGEMENT DRAWING (GAD) (ALONG WITH BILL OF MATERIAL) - TEMPERATURE INDICATING TRANSMITTER | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_000339-TEMP_INDCT_TRANSMITTER
BNO-000339-300-IN-4018-008-AOL-00002-001 | WIRING DIAGRAM - TEMPERATURE INDICATING TRANSMITTER | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  |  |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_000339-TEMP_INDCT_TRANSMITTER
BNO-000339-300-JA-6611-008-AOL-00001 | VENDOR DATA REGISTER LIST (VDRL) - TEMPERATURE INDICATING TRANSMITTER | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_000339-TEMP_INDCT_TRANSMITTER
BNO-000339-300-OA-4811-008-AOL-00001 | OPERATION MANUAL - TEMPERATURE INDICATING TRANSMITTER | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | TRANSMITTAL |  |  |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_000339-TEMP_INDCT_TRANSMITTER
BNO-000339-300-QA-5733-008-AOL-00001 | INSPECTION AND TEST PLAN - TEMPERATURE INDICATING TRANSMITTER | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_000339-TEMP_INDCT_TRANSMITTER
BNO-000339-300-RA-1580-008-AOL-00003 | ENCLOSURE HAZARDOUS AREA CERTIFICATE -TEMPERATURE INDICATING TRANSMITTER | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_000339-TEMP_INDCT_TRANSMITTER
BNO-000339-300-RA-1580-008-AOL-00005 | SIL CERTIFICATE IN ACCORDANCE WITH IEC-61508 / IEC - 61511 (ONLY FOR APPLICABLE TAGS) - TEMPERATURE INDICATING TRANSMITTER | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_000339-TEMP_INDCT_TRANSMITTER
BNO-000339-300-RA-6068-008-AOL-00001 | PAINTING PROCEDURE - TEMPERATURE INDICATING TRANSMITTER | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_000339-TEMP_INDCT_TRANSMITTER
BNO-000339-300-SA-6028-008-AOL-00001 | PACKING AND PRESERVATION PROCEDURE - TEMPERATURE INDICATING TRANSMITTER | SA - LOGISTICS | SA - LOGISTICS | R01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_000339-TEMP_INDCT_TRANSMITTER
BNO-000483-300-JA-6611-040-AOL-00001 | VENDOR DOCUMENT REQUIREMENTS LIST (VDRL) | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / PROSERV / PO_00483-SLIP_STREAM_SAND_SAMPLING
BNO-000483-300-MP-4018-040-AOL-00001-001 | GENERAL ARRANGEMENT (GA) DRAWINGS | PIPING | MP - PIPING | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PROSERV / PO_00483-SLIP_STREAM_SAND_SAMPLING
BNO-000542-300-AA-3347-091-SESL-00001 | MINUTES OF MEETING | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-5765-091-SESL-00001 | BONGA NORTH PROJECT SCHEDULE | PMT | AA - PROJECT MANAGEMENT | R02 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW | 4/10/2025 | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-5798-091-SESL-00001 | BONGA NORTH PROJECT EXECUTION PLAN | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL | 4/9/2025 | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-6944-091-SESL-00001 | WEEKLY PROJECT STATUS REPORT NO.1 | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-6944-091-SESL-00004 | WEEKLY PROJECT STATUS REPORT NO.4 | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-6944-091-SESL-00006 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-6944-091-SESL-00007 | WEEKLY PEOJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-6944-091-SESL-00008 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-6944-091-SESL-00009 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-6944-091-SESL-00010 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-6944-091-SESL-00011 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-6944-091-SESL-00012 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-6944-091-SESL-00013 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-6944-091-SESL-00014 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-6944-091-SESL-00015 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-6944-091-SESL-00017 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-6944-091-SESL-00018 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-6944-091-SESL-00019 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-6944-091-SESL-00020 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | NOT ISSUED |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-6944-091-SESL-00021 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-6944-091-SESL-00022 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | NOT ISSUED |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-6944-091-SESL-00023 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | NOT ISSUED |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-6944-091-SESL-00024 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-6944-091-SESL-00025 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | NOT ISSUED |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-6944-091-SESL-00026 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-6944-091-SESL-00027 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-6944-091-SESL-00028 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-6944-091-SESL-00029 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-6944-091-SESL-00031 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-6944-091-SESL-00032 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-6944-091-SESL-00033 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00007 | TECHNICAL QUERY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00008 | TECHNICAL QUERY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00009 | TECHNICAL QUERY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00010 | TECHNICAL QUERY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00011 | TQR FOR BPCS GATEWAY CABINET AND MAIN SERVER CABINET POWER REQUIREMENTS | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00012 | TECHNICAL QUERY - IO LIST REV02 TECHNICAL QUERIES FOR ESS | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00013 | TECHNICL QUERY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | REJECTED | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00014 | TECHNICAL QUERY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | REJECTED | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00015 | TECHNICAL QUERY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | REJECTED | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00016 | TECHNICAL QUERY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00017 | TECHNICAL QUERY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | REJECTED | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00018 | TECHNICAL QUERY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00019 | TECHNICAL QUERY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00020 | TECHNICAL QUERY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00021 | TECHNICAL QUERY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00022 | TECHNICAL QUERY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00023 | TECHNICAL QUERY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00024 | TECHNICAL QUERY- NG-20117-TQ-024 | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00025 | TECHNICAL QUERY - NG-20117-TQ-025 | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00026 | TECHNICAL QUERY - NG-20117-TQ-026 | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00027 | TECHNICAL QUERY - NG-20117-TQ-027 | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00028 | TECHNICAL QUERY - NG-20117-TQ-028 | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00029 | TECHNICAL QUERY - NG-20117-TQ-029 | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00030 | TECHNICAL QUERY (TQ) NG-20117-TQ-030 | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00031 | TECHNICAL QUERY (TQ) NG-20117-TQ-031 | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00033 | TECHNICAL QUERY - NG-20117-TQ-033 | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00034 | TECHNICAL QUERY - MCS-DCS SERIAL DATABASE / MCS DCS FUNCTION BLOCKS | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00035 | TECHNICAL QUERY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00036 | NG-20117-TQ-036 - TECHNICAL QUERY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00037 | NG-20117-TQ-037 - TECHNICAL QUERY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00038 | NG-20117-TQ-038 - TECHNICAL QUERY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00039 | NG-20117-TQ-039- TECHNICAL QUERY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00040 | TECHNICAL QUERY - NG-20117-TQ-040 | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00041 | TECHNICAL QUERY - NG-20117-TQ-041 | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00042 | TECHNICAL QUERY - :NG-20117-TQ-042 | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00043 | NG-20117-TQ-043 - TECHNICAL QUERY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00044 | TECHNICAL QUERY - NG-20117-TQ-044 | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00045 | TECHNICAL QUERY - NG-20117-TQ-045 | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00046 | NG-20117-TQ-046 - TECHNICAL QUERY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00047 | NG-201117-TQ-047 - TECHNICAL QUERY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00048 | NG-20117-TQ-048 - TECHNICAL QUERY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00049 | NG-20117-TQ-049 - TECHNICAL QUERY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00050 | NG-20117-TQ-050 - TECHNICAL QUERY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00051 | NG-20117-TQ-051 -TECHNICAL QUERY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00052 | NG-20117-TQ-052 -TECHNICAL QUERY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00053 | TECHNICAL QUERY - REQUEST FOR BONGA MAIN ESS FROZEN PT2 FILES | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00054 | TECHNICAL QUERY - NG-20117-TQ-054 | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00055 | NG-20117-TQ-055 - TECHNICAL QUERY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00056 | TECHNICAL QUERY- NG-20117-TQ-056 | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00057 | NG-20117-TQ-057 - TECHNICAL QUERY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00058 | NG-20117-TQ-058 - TECHNICAL QUERY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-AA-8502-091-SESL-00059 | TQ - SUBSEA DATASHEET FOR CHOKE VALVES AND SDV VALVES | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-HX-5798-091-SESL-00001 | BONGA NORTH PROJECT HSE PLAN | TECHNICAL SAFETY | HX - HSE | R02 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-0580-091-SESL-00001 | HARDWARE I/O LIST ANALYSIS REPORT | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-0708-081-SESL-00001 | BONGA NORTH CYBERSECURITY ASSESSMENT | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-1216-081-SESL-00001 | BONGA NORTH POWER AND HEAT CALCULATIONS | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-1216-081-SESL-00002 | BPCS POWER AND HEAT CALCULATIONS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-1222-081-SESL-00001 | BONGA NORTH - SIL DATA AND RELIABILITY CALCULATION | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-1453-081-SESL-00001 | BONGA NORTH SAFETY COMPLIANCE CERTIFICATE | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-1580-081-SESL-00001 | BONGA NORTH TEST EQUIPMENT CALIBRATION CERTIFICATES | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-1907-081-SESL-00001 | BONGA NORTH MAC EQUIPMENT BROCHURES AND CATALOGUES | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-2347-081-SESL-00001-001 | BONGA NORTH TYPICAL LOOP DIAGRAMS | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED | 5/19/2025 | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-2347-081-SESL-00002 | BONGA NORTH HARDWARE FAT PROCEDURE | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-2347-081-SESL-00003-001 | BONGA NORTH LOOP SHEET - BPCS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-2347-081-SESL-00004-001 | BONGA NORTH FIBRE OPTIC COMMUNICATION DRAWING | INSTRUMENTATION | IN - INSTRUMENTATION | R02 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-2347-083-SESL-00001-001 | BONGA NORTH LOOP SHEET - ESS | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-2347-083-SESL-00002-001 | BONGA NORTH LOOP SHEET - F&G | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-3004-081-SESL-00001 | BONGA NORTH FBM EQUIPMENT REPORT | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-3304-081-SESL-00001 | BONGA NORTH BPCS APPLICATION SOFTWARE UPDATES | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-3328-081-SESL-00001 | BONGA NORTH MAC INSTALLATION MANUAL | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00001-001 | BONGA NORTH CABINET GENERAL ASSEMBLY DRAWING - BPCS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00002-001 | BONGA NORTH MODULE BPCS PROCESSOR CABINET J-8161-CP-01 G.A. (EXTERNAL) | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00003-001 | BONGA NORTH MODULE BPCS FBM CABINET J-8163-CP-01 G.A. (EXTERNAL) | INSTRUMENTATION | IN - INSTRUMENTATION | C03 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00004-001 | MARSHALLING CABINETS (J-8162-CP-01 & J-8162-CP-02) G.A. (EXTERNAL AND INTERNAL) | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00005-001 | BONGA NORTH MODULE BPCS POWER DISTRIBUTION CABINET J-8160-CP-01 G.A. (EXTERNAL) | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00006-001 | BONGA NORTH MODULE BPCS GATEWAY CABINET J-8161-CP-03 G.A EXTERNAL AND INTERNAL | INSTRUMENTATION | IN - INSTRUMENTATION | C03 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00007-001 | BONGA NORTH MODULE BPCS FBM CABINET J-XXXX-CP-01 G.A. (INTERNAL) | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00008-001 | BONGA NORTH NETWORK INTERCONNECTION DIAGRAM | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00009-001 | MODULE BPCS POWER DISTRIBUTION CABINET AC POWER DISTRIBUTION WIRING DRAWING J-8160-CP-01 INDEX SHEET | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 2 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00010-001 | SSCB MAC POWER SUPPLY DISTRIBUTION BLOCK DIAGRAM | INSTRUMENTATION | IN - INSTRUMENTATION | C03 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00011-001 | BONGA NORTH MODULE BPCS PROCESSOR CABINET J-8161-CP-01 AC POWER DISTRIBUTION WIRING DRAWING | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00012-001 | BONGA NORTH MODULE BPCS FBM CABINET J-8163-CP-01 AC POWER DISTRIBUTION WIRING DRAWING | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00013-001 | BONGA NORTH MODULE BPCS PROCESSOR CABINET J-8161-CP-01 DC POWER DISTRIBUTION | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00014-001 | BONGA NORTH MODULE BPCS FBM CABINET J-8163-CP-01 DC POWER DISTRIBUTION | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00015-001 | BONGA NORTH MODULE BPCS MARSHALLING CABINET J-8162-CP-01 & J-8162-CP-02 DC POWER DISTRIBUTION | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00016-001 | BONGA NORTH MODULE BPCS POWER DISTRIBUTION CABINET J-8160-CP-01 DC POWER DISTRIBUTION | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00017-001 | BONGA NORTH I.S. WARNING LABEL-BPCS-LOCAL PANEL | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00018-001 | BONGA NORTH - REMOTE PANELS (EEX NALC) | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00019-001 | BONGA NORTH MODULE BPCS / SSDS EARTHING ARRANGMENT | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00020-001 | BONGA NORTH REMOTE IO PANELS INTERNAL AND EXTERNAL GENERAL ARRANGEMENT DRAWINGS | INSTRUMENTATION | IN - INSTRUMENTATION | R02 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00021-001 | MODULE BPCS GATEWAY CABINET 1 AC POWER DISTRIBUTION WIRING DRAWING J-8162-CP-03 | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00022-001 | BONGA NORTH REMOTE FBM CABINETS INTERNAL WIRING (MCC CABINET) | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00023-001 | BONGA NORTH SYSTEM BLOCK ARCHITECTURE DIAGRAM | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00025-001 | MODULE BPCS GATEWAY CABINET 1 DC POWER DISTRIBUTION WIRING DRAWING J-8162-CP-03 | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 2 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00026-001 | BONGA NORTH MODULE REMOTE IO PANELS WIRING | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00027-001 | BONGA NORTH MODULE BPCS MARSHALLING CABINET J-XXXX-CP-01 G.A. (EXTERNAL) | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00028-001 | BONGA NORTH MODUE BPCS POWER DISTRIBUTION CABINET J-XXXX-CP-01 G.A. (EXTERNAL) | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00029-001 | BONGA NORTH CABINET POWER AND GROUNDING DRAWINGS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00030-001 | REMOTE JUNCTION BOX J-8120-JB-40 | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | CANCELADO | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00031-001 | REMOTE JUNCTION BOX J-8120-JB-41 | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | CANCELADO | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00032-001 | REMOTE JUNCTION BOX J-8120-JB-42 | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00033-001 | REMOTE JUNCTION BOX J-8120-JB-43 | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00034-001 | REMOTE JUNCTION BOX J-8120-JB-44 | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00035-001 | BONGA NORTH MODULE BPCS GATEWAY CABINET 2 J-8161-CP-04 GENERAL ARRANGEMENT DRAWING | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-081-SESL-00036-001 | MODULE BPCS GATEWAY CABINET 2 AC POWER DISTRIBUTION WIRING DRAWING J-8161-CP-04 | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4018-083-SESL-00001-001 | BONGA NORTH ESS CABINET GENERAL ARRANGEMENT DRAWING | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4024-081-SESL-00001-001 | BONGA NORTH TYPICAL CABINET DRAWING (PER TYPE) | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED | 5/26/2025 | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4180-081-SESL-00001-001 | SERIAL MOBILE TEST KIT DRAWING AND BOM | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 2 | AFC/AFU - APPROVED | 5/5/2025 | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4180-081-SESL-00002-001 | HARDWARE MOBILE TEST KIT DRAWING AND BOM | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED | 5/5/2025 | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4306-091-SESL-00003 | BONGA NORTH OTS BILL OF MATERIALS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4306-091-SESL-00004 | BONGA NORTH HARDWARE BILL OF MATERIALS | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4306-091-SESL-00005 | BONGA NORTH SOFTWARE BILL OF MATERIALS | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4308-081-SESL-00001 | BONGA NORTH SYSTEM CABLE SCHEDULE | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4327-081-SESL-00001 | BONGA NORTH - IO ALLOCATION BPCS | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4327-081-SESL-00002 | MAPPING LIST | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4327-081-SESL-00003 | MAPPING LIST (PACKAGE INTERFACES) | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4327-081-SESL-00005 | IO DATABASE | INSTRUMENTATION | IN - INSTRUMENTATION | R02 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4327-083-SESL-00001 | BONGA NORTH - IO ALLOCATION ESS | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4354-081-SESL-00001 | BONGA NORTH SPARE PART LIST | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4380-081-SESL-00001 | BONGA NORTH SOFTWARE LICENSES | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4811-081-SESL-00001 | BONGA NORTH MAC OPERATION MANUAL | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-4880-081-SESL-00001 | SIMULATION SYSTEM MANUAL | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-5880-081-SESL-00001 | BONGA NORTH - BPCS CPU LOADING | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6028-081-SESL-00001 | BONGA NORTH PRESERVATION STORAGE | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6028-081-SESL-00007 | CONFIGURATION AND CHANGE MANAGEMENT PROCEDURE | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6061-081-SESL-00001 | BONGA NORTH SAFETY SYSTEM INTERNAL TEST PROCEDURE BPCS ESS F&G | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6061-081-SESL-00004 | BONGA NORTH ICSS TIE-IN WITH BONGA MAIN HARDWARE | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00001 | BONGA NORTH SAT PROCEDURE - REMOTE JB | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00002 | BONGA NORTH HARDWARE FAT PROCEDURE | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00003 | BONGA NORTH HARDWARE FAT REPORT | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00004 | BONGA NORTH SOFTWARE FAT PROCEDURE | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00005 | BONGA NORTH SOFTWARE FAT REPORT | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00006 | BONGA NORTH FAT PROCEDURE FOR OTS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00007 | BONGA NORTH FAT REPORT FOR OTS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00008 | BONGA NORTH HARDWARE SAT PROCEDURE | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00009 | BONGA NORTH SOFTWARE SAT PROCEDURE | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00010 | BONGA NORTH SAT PROCEDURE - OTS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00011 | BONGA NORTH HARDWARE SAT REPORT | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00012 | BONGA NORTH SOFTWARE SAT REPORT | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00013 | BONGA NORTH SAT - OTS REPORT | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00014 | SAND MONITORING TEST CASE | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00015 | BONGA NORTH INTEGRATED FACTORY ACCEPTANCE TEST PROCEDURE (SSCB INTEGRATOR) | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00016 | BONGA NORTH INTEGRATED FACTORY ACCEPTANCE TEST PROCEDURE (SSCB INTEGRATOR) REPORT | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00017 | CONTROL SYSTEM EXECUTION STRATEGY | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00018 | BONGA NORTH SITE INSTALLATION TEST & RECORDS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00019 | BONGA NORTH SAT REPORT - REMOTE JB | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00020 | BONGA NORTH - INTEGRATED FACTORY ACCEPTANCE TEST REPORT - WATERFLOOD | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00021 | BONGA NORTH - INTEGRATED FACTORY ACCEPTANCE TEST PROCEDURE – WATERFLOOD | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00022 | BONGA NORTH - INTEGRATED FACTORY ACCEPTANCE TEST PROCEDURE - SUBSEA | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00023 | BONGA NORTH FAT - SUBSEA SYSTEMS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00024 | SITE INSTALLATION & TEST - WATER INJECTION WELL PROTECTION | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00025 | SITE INSTALLATION & TEST - CHEMICAL STORAGE & INJECTION | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00026 | FACTORY ACCEPTANCE TEST PROCEDURE - ELECTRICAL | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00027 | SITE INSTALLATION & TEST - SAND MONITORING | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00028 | SITE INSTALLATION & TEST - CARGO HANDLING HOT OIL & PIGGING | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00029 | SITE INSTALLATION & TEST - CHEMICAL INJECTION PUMP WELL ALIGNMENT | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00030 | SITE INSTALLATION & TEST - BPCS ALARM HANDLING & SUPPRESSION | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00031 | SITE INSTALLATION & TEST - MISC APPS SUBSEA | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00032 | SITE INSTALLATION & TEST - SUBSEA OPERATOR SUPPORT GRAPHICS DISPLAYS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00033 | SITE INSTALLATION & TEST - MEASUREMENT VALIDATION & COMPARISON | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00034 | SITE INSTALLATION & TEST - F&G MATRIX | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00035 | MODEL VALIDATION TEST PROCEDURE - OTS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00036 | BONGA NORTH SUBSEA MISCELLANEOUS APPLICATIONS FAT | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00037 | BONGA NORTH BPCS REMOTE JUNCTION BOX FAT CASE | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | TRANSMITTAL |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00038 | BONGA NORTH FAT REPORT - CHEMICAL INJECTION & STORAGE | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00039 | BONGA NORTH FAT REPORT - METHANOL INJECTION REPORT | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00040 | BONGA NORTH FAT REPORT - WATERFLOOD | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00041 | BONGA NORTH FAT REPORT - SUBSEA SYSTEMS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-081-SESL-00042 | BONGA NORTH BPCS REMOTE JUNCTION BOX FAT REPORT | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-083-SESL-00001 | BONGA NORTH ESS HARDWARE FAT PROCEDURE | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6067-083-SESL-00002 | ESS HARDWARE FAT REPORT | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6180-081-SESL-00001 | MATERIAL HANDLING PACKING AND TRANSPORTATION PROCEDURE | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-6180-081-SESL-00002 | MAC ASSET REGISTER | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7731-081-SESL-00001-001 | BONGA NORTH ICSS NETWORK ARCHITECTURE DETAILED DRAWINGS | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 2 | AFC/AFU - APPROVED | 5/12/2025 | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7731-081-SESL-00002-001 | BONGA NORTH NETWORK TOPOLOGY DIAGRAM | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7731-081-SESL-00003-001 | BONGA NORTH MESH ARCHITECTURE DRAWING | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7770-081-SESL-00001 | FUNCTIONAL DESIGN SPECIFICATION (FDS)(OTS) | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7770-081-SESL-00002 | PDS - BONGA NORTH TRICONEX FUNCTION BLOCK LIBRARY | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7770-081-SESL-00003 | PDS - BONGA NORTH FOXBORO FUNCTION BLOCK LIBRARY | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7770-081-SESL-00004 | PDS - WATER INJECTION WELL PROTECTION | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7770-081-SESL-00005 | PDS - CHEMICAL STORAGE & INJECTION (CLEAN AND TRACKED) | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7770-081-SESL-00006 | PDS - WELL TEST SEPERATION & WELL DONE | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7770-081-SESL-00007 | PDS - SAND MONITORING | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7770-081-SESL-00008 | PDS - CARGO HANDLING HOT OIL & PIGGING | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7770-081-SESL-00009 | PDS - C&E RIG INITIATED SUBSEA SHUTDOWN | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7770-081-SESL-00010 | PDS - CHEMICAL INJECTION PUMP WELL ALIGNMENT | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7770-081-SESL-00011 | PDS - ESS WATCHDOG APPLICATION | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7770-081-SESL-00012 | PDS - FIRE DAMPER TESTING | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7770-081-SESL-00013 | PDS - BPCS ALARM HANDLING & SUPPRESSION | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7770-081-SESL-00014 | PDS - MISC APPS SUBSEA - TRACKED | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7770-081-SESL-00015 | PDS - MEASUREMENT VALIDATION & COMPARISON | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7770-081-SESL-00016 | DETAILED DESIGN SPECIFICATION (DDD) | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7770-081-SESL-00017 | CONTROL SYSTEM EXECUTION STRATEGY | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7770-081-SESL-00018 | WATERFLOOD PDS (GB0107.202.302.07)-TRACKED AND CLEAN | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7770-081-SESL-00019 | SAND MONITORING PDS (GB0107.202.104.06)-TRACKED AND CLEAN | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7770-081-SESL-00020 | ALARM SUPPRESSION PDS GB0107.202.516-TRACKED AND CLEAN | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7770-081-SESL-00021 | CARGO PDS GB0107.202.427-TRACKED AND CLEAN | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7770-081-SESL-00022 | WELL TEST PDS GB0107.202.106-TRACKED AND CLEAN | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7770-081-SESL-00023 | PDS GRAPHICS/HMI SCREENS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | TRANSMITTAL |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7770-081-SESL-00024 | FUNCTIONAL DESIGN SPECIFICATION (FDS)(BPCS. ESS) | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7771-081-SESL-00001 | BONGA NORTH SYSTEM CONFIGURATION | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7880-081-SESL-00001 | BONGA NORTH INTERFACE SPECIFICATION - SCU | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7880-081-SESL-00002 | BONGA NORTH INTERFACE SPECIFICATION - HVAC | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7880-081-SESL-00003 | BONGA ESS MODPACK J-8331-CP-01 MOD 01 | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7880-081-SESL-00004 | BONGA NORTH BACKUP SUMMARY DISPLAY PANEL MODPACK J-8341-AP-01MOD 01 | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7880-081-SESL-00005 | BONGA NORTH MODBUS INTERFACE MODPACK | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-7880-081-SESL-00006 | BONGA NORTH BPCS INTERFACES MODPACK | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-IN-8502-091-SESL-00001 | TQR - IO TYPE DETAILS FOR ESS LOOP TYP. DETAILS | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | TRANSMITTAL |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-JA-6611-091-SESL-00001 | BONGA NORTH MAC MASTER DOCUMENT REGISTER | IT / IM | JA - IM | R05 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW | 5/8/2025 | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-NA-4810-081-SESL-00001 | BONGA NORTH MAC MAINTENANCE MANUAL | NA - MAINTENANCE | NA - MAINTENANCE | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-QA-5798-091-SESL-00001 | BONGA NORTH PROJECT QUALITY ASSURANCE AND QUALITY SYSTEM PLAN | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-QA-5798-091-SESL-00002 | BONGA NORTH INSPECTION AND TEST PLAN | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-QA-5798-091-SESL-00004 | BONGA NORTH OBSOLESCENCE MANAGEMENT DOCUMENT | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000542-300-QA-5798-091-SESL-00006 | SOFTWARE DEVELOPMENT PLAN | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SCHNEIDER / PO_000542-(MAC)
BNO-000649-300-IN-2105-021-PETR-00007 | DATASHEETS FOR HYDRAULIC HAND VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | R03 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROLVALVES / PO_000649-HAND VALVES
BNO-000649-300-IN-2105-021-PETR-00021 | SIZING CALCULATION SHEET WITH TORQUE/THRUST SUMMARY TABLE FOR VALVE/ACTUATOR COMBINATION (TORQUE TABLE) FOR HYDRAULIC HAND VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000649-HAND VALVES
BNO-000649-300-IN-4018-021-PETR-00002 | GENERAL ARRANGEMENT DRAWING (VALVE WITH ACTUATOR, CONTROL PANEL AND ACCESSORIES). | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / PETROLVALVES / PO_000649-HAND VALVES
BNO-000649-300-IN-4018-021-PETR-00003 | CROSS SECTIONAL DRAWINGS WITH BILL OF MATERIAL | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / PETROLVALVES / PO_000649-HAND VALVES
BNO-000649-300-IN-4018-021-PETR-00004 | ACTUATOR GA DRAWINGS FOR HYDRAULIC HAND VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000649-HAND VALVES
BNO-000649-300-IN-4018-021-PETR-00005 | NAMEPLATE DRAWING FOR VALVES FOR HYDRAULIC HAND VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / PETROLVALVES / PO_000649-HAND VALVES
BNO-000649-300-IN-4018-021-PETR-00006 | NAMEPLATE DRAWING FOR ACTUATORS FOR HYDRAULIC HAND VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000649-HAND VALVES
BNO-000649-300-OA-4811-021-PETR-00016 | OPERATION MANUAL FOR ACTUATORS FOR HYDRAULIC HAND VALVES | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROLVALVES / PO_000649-HAND VALVES
BNO-000649-300-QA-5733-021-PETR-00011 | INSPECTION AND TEST PLAN FOR VALVES FOR HYDRAULIC HAND VALVES | QA - QUALITY | QA - QUALITY | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000649-HAND VALVES
BNO-000649-300-QA-5733-021-PETR-00012 | INSPECTION AND TEST PLAN FOR ACTUATORS FOR PNEUMATIC ACTUATED ON-OFF_ BLOWDOWN AND SHUTDOWN VALVES | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | TRANSMITTAL |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000649-HAND VALVES
BNO-000649-300-QA-5733-021-PETR-00013 | FAT TEST PROCEDURE/S (VALVE AND ACTUATOR ASSEMBLY) FOR HYDRAULIC HAND VALVES | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000649-HAND VALVES
BNO-000649-300-QA-5733-021-PETR-00014 | ACTUATOR TESTING PROCEDURES FOR HYDRAULIC HAND VALVES | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 4 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000649-HAND VALVES
BNO-000649-300-QA-5733-021-PETR-00015 | PROJECT QUALITY PLAN FOR HYDRAULIC HAND VALVES | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROLVALVES / PO_000649-HAND VALVES
BNO-000649-300-RA-6068-021-PETR-00001 | PAINTING PROCEDURE FOR VALVE - HYDRAULIC HAND VALVES | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROLVALVES / PO_000649-HAND VALVES
BNO-000649-300-RA-6068-021-PETR-00024 | PAINTING PROCEDURE FOR ACTUATORS FOR HYDRAULIC HAND VALVES | MATERIALS | RA - MATERIALS | A02 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000649-HAND VALVES
BNO-000649-300-SA-6028-021-PETR-00010 | PACKING_ HANDLING_ PRESERVATION AND TRANSPORTATION PROCEDURE FOR HYDRAULIC HAND VALVES | SA - LOGISTICS | SA - LOGISTICS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000649-HAND VALVES
BNO-000669-300-FA-5803-004-PETR-00001 | ENGINEERING. FABRICATION. INSPECTION AND TESTING SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROLVALVES / PO_000669-HYDRAULIC_BRDG_VALVES
BNO-000669-300-IN-1580-004-PETR-00001 | FAILURE DATA / SIL CERTIFICATE IN ACCORDANCE WITH IEC-61508 / IEC- 61511 | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROLVALVES / PO_000669-HYDRAULIC_BRDG_VALVES
BNO-000669-300-IN-1580-004-PETR-00002 | HAZARDOUS AREA AND PROTECTION DEGREE CERTIFICATE (CENELEC)_ACTUATORS | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROLVALVES / PO_000669-HYDRAULIC_BRDG_VALVES
BNO-000669-300-IN-2105-004-PETR-00001 | TECHNICAL DATASHEET / SPECIFICATION | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROLVALVES / PO_000669-HYDRAULIC_BRDG_VALVES
BNO-000669-300-IN-2105-004-PETR-00002 | SIZING CALCULATION SHEET WITH TORQUE/THRUST SUMMARY TABLE FOR VALVE/ACTUATOR COMBINATION (TORQUE TABLE) | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000669-HYDRAULIC_BRDG_VALVES
BNO-000669-300-IN-2105-040-PETR-00001 | DATA SHEETS FOR HYDRAULIC BOARDING SHUTDOWN VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | R03 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROLVALVES / PO_000669-HYDRAULIC_BRDG_VALVES
BNO-000669-300-IN-4018-004-PETR-00001 | WIRING DIAGRAM (ACCESSORIES) | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000669-HYDRAULIC_BRDG_VALVES
BNO-000669-300-IN-4354-004-PETR-00001 | SPARE PART LISTS FOR TWO YEARS (INCLUDING COMPONENTS LIST WITH REF. MANUFACTURER/MODEL N°.) | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROLVALVES / PO_000669-HYDRAULIC_BRDG_VALVES
BNO-000669-300-IN-7880-004-PETR-00001 | OVERALL DIMENSIONS DRAWING 14" - COMBINED SLAB GATE VALVE | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000669-HYDRAULIC_BRDG_VALVES
BNO-000669-300-IN-7880-004-PETR-00002 | CROSS SECTION DRAWING WITH BILL OF MATERIAL - 14" - COMBINED SLAB GATE VALVE | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000669-HYDRAULIC_BRDG_VALVES
BNO-000669-300-IN-7880-004-PETR-00003 | ACTUATOR GA DRAWINGS | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000669-HYDRAULIC_BRDG_VALVES
BNO-000669-300-IN-7880-004-PETR-00004 | NAMEPLATE DRAWING FOR ACTUATORS FOR HYDRAULIC BORDING SHUTDOWN VALVES | NÃO SE APLICA | NÃO SE APLICA | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / PETROLVALVES / PO_000669-HYDRAULIC_BRDG_VALVES
BNO-000669-300-IN-7880-004-PETR-00005 | NAMEPLATE DRAWING FOR ACTUATORS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROLVALVES / PO_000669-HYDRAULIC_BRDG_VALVES
BNO-000669-300-IN-7880-004-PETR-00006 | OVERALL DIMENSIONS DRAWING 7.1/16" - SLAB GATE VALVE | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000669-HYDRAULIC_BRDG_VALVES
BNO-000669-300-IN-7880-004-PETR-00007 | OVERALL DIMENSIONS DRAWING 12" - COMBINED SLAB GATE VALVE | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ENGINEERING CONSOLIDATION | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000669-HYDRAULIC_BRDG_VALVES
BNO-000669-300-IN-7880-004-PETR-00008 | CROSS SECTION DRAWING WITH BILL OF MATERIAL - 7.1/16" - SLAB GATE VALVE | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / PETROLVALVES / PO_000669-HYDRAULIC_BRDG_VALVES
BNO-000669-300-IN-7880-004-PETR-00009 | CROSS SECTION DRAWING WITH BILL OF MATERIAL - 12" - COMBINED SLAB GATE VALVE | PIPING | MP - PIPING | A01 | NAO |  | Diretorio Vendor | ENGINEERING CONSOLIDATION | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000669-HYDRAULIC_BRDG_VALVES
BNO-000669-300-IN-7880-004-PETR-00010 | ACTUATOR ASSEMBLY DRAWINGS WITH PART LIST AND SECTIONAL DRAWING WITH BILL OF MATERIALS (BOM) FOR HYDRAULIC BOARDING SHUTDOWN VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROLVALVES / PO_000669-HYDRAULIC_BRDG_VALVES
BNO-000669-300-JA-4372-004-PETR-00001 | DATABOOK | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROLVALVES / PO_000669-HYDRAULIC_BRDG_VALVES
BNO-000669-300-JA-6611-004-PETR-00001 | DOCUMENTS / DRAWINGS LIST | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROLVALVES / PO_000669-HYDRAULIC_BRDG_VALVES
BNO-000669-300-OA-4811-004-PETR-00001 | OPERATION MANUAL FOR VALVES | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROLVALVES / PO_000669-HYDRAULIC_BRDG_VALVES
BNO-000669-300-OA-4811-004-PETR-00002 | OPERATION MANUAL FOR ACTUATORS FOR HYDRAULIC BORDING SHUTDOWN VALVES | OA - OPERATIONS | OA - OPERATIONS | A02 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000669-HYDRAULIC_BRDG_VALVES
BNO-000669-300-QA-5733-004-PETR-00001 | INSPECTION AND TEST PLAN FOR VALVES | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000669-HYDRAULIC_BRDG_VALVES
BNO-000669-300-QA-5733-004-PETR-00002 | INSPECTION AND TEST PLAN FOR ACTUATORS FOR HYDRAULIC BORDING SHUTDOWN VALVES | QA - QUALITY | QA - QUALITY | A03 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000669-HYDRAULIC_BRDG_VALVES
BNO-000669-300-QA-5733-004-PETR-00003 | PROJECT QUALITY PLAN FOR HYDRAULIC BOARDING SHUTDOWN VALVES | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROLVALVES / PO_000669-HYDRAULIC_BRDG_VALVES
BNO-000669-300-QA-6050-004-PETR-00001 | FAT TEST PROCEDURE/S (VALVE AND ACTUATOR ASSEMBLY) | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000669-HYDRAULIC_BRDG_VALVES
BNO-000669-300-QA-6050-004-PETR-00002 | ACTUATOR TESTING PROCEDURES FOR HYDRAULIC BORDING SHUTDOWN VAL | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / PETROLVALVES / PO_000669-HYDRAULIC_BRDG_VALVES
BNO-000669-300-RA-1580-004-PETR-00001 | MATERIAL CERTIFICATE | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROLVALVES / PO_000669-HYDRAULIC_BRDG_VALVES
BNO-000669-300-RA-6068-004-PETR-00001 | PAINTING PROCEDURE FOR VALVES | MATERIALS | RA - MATERIALS | A03 | NAO |  | Diretorio Vendor | TRANSMITTAL | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000669-HYDRAULIC_BRDG_VALVES
BNO-000669-300-RA-6068-004-PETR-00002 | PAINTING PROCEDURE FOR ACTUATORS FOR HYDRAULIC BORDING SHUTDOWN VALVES | MATERIALS | RA - MATERIALS | A02 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000669-HYDRAULIC_BRDG_VALVES
BNO-000669-300-SA-6028-004-PETR-00001 | PACKING. HANDLING. PRESERVATION AND TRANSPORTATION PROCEDURE | SA - LOGISTICS | SA - LOGISTICS | C01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000669-HYDRAULIC_BRDG_VALVES
BNO-000672-300-FA-5803-040-PETR-00001 | ENGINEERING_FABRICATION_INSPECTION AND TESTING SCHEDULE - CONTROL VALVES | FA - COST AND PLANNING | FA - COST AND PLANNING | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000672-CONTROL_VALVES
BNO-000672-300-IN-1580-040-PETR-00001 | CALIBRATION CERTIFICATE - CONTROL VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROLVALVES / PO_000672-CONTROL_VALVES
BNO-000672-300-IN-1580-040-PETR-00002 | ENCLOSURE HAZARDOUS AREA AND PROTECTION DEGREE CERTIFICATE - CONTROL VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROLVALVES / PO_000672-CONTROL_VALVES
BNO-000672-300-IN-2105-040-PETR-00001 | TECHNICAL DATASHEET / SPECIFICATION - CONTROL VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | CANCELADO | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROLVALVES / PO_000672-CONTROL_VALVES
BNO-000672-300-IN-2105-040-PETR-00002 | CONTROL VALVE AND ACTUATOR SIZING CALCULATION & DATASHEET - CONTROL VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000672-CONTROL_VALVES
BNO-000672-300-IN-4354-040-PETR-00001 | SPARE PARTS FOR PRE-COMMISSIONING_COMMISSIONING AND START-UP AND SPARE PARTS FOR TWO YEARS - CONTROL VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROLVALVES / PO_000672-CONTROL_VALVES
BNO-000672-300-IN-4354-040-PETR-00002 | SPARE PART LISTS FOR TWO YEARS - CONTROL VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / PETROLVALVES / PO_000672-CONTROL_VALVES
BNO-000672-300-IN-4354-040-PETR-00003 | COMPONENT LIST WITH REF. MANUFACTURER/MODEL NO. | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / PETROLVALVES / PO_000672-CONTROL_VALVES
BNO-000672-300-IN-7880-040-PETR-00001 | GENERAL ARRANGEMENT DRAWING WITH WEIGHT - CONTROL VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / PETROLVALVES / PO_000672-CONTROL_VALVES
BNO-000672-300-IN-7880-040-PETR-00002 | IDENTIFICATION PLATE DRAWINGS - CONTROL VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / PETROLVALVES / PO_000672-CONTROL_VALVES
BNO-000672-300-IN-7880-040-PETR-00003 | CROSS SECTIONAL DRAWING - CONTROL VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | C04 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / PETROLVALVES / PO_000672-CONTROL_VALVES
BNO-000672-300-IN-7880-040-PETR-00004 | PNEUMATIC / WIRING SCHEMATIC DIAGRAM - CONTROL VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / PETROLVALVES / PO_000672-CONTROL_VALVES
BNO-000672-300-JA-4372-040-PETR-00001 | DATABOOK - CONTROL VALVES | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROLVALVES / PO_000672-CONTROL_VALVES
BNO-000672-300-JA-6611-040-PETR-00001 | DOCUMENTS / DRAWINGS LIST - CONTROL VALVES | IT / IM | JA - IM | C01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000672-CONTROL_VALVES
BNO-000672-300-OA-4811-040-PETR-00001 | INSTALLATION. OPERATION AND MAINTENANCE INSTRUCTIONS - CONTROL VALVES | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | ENGINEERING CONSOLIDATION |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROLVALVES / PO_000672-CONTROL_VALVES
BNO-000672-300-QA-5733-040-PETR-00001 | INSPECTION AND TEST PLAN (FAT AND SAT) - CONTROL VALVES | QA - QUALITY | QA - QUALITY | C03 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / PETROLVALVES / PO_000672-CONTROL_VALVES
BNO-000672-300-QA-5733-040-PETR-00002 | FAT PROCEDURE FOR CONTROL VALVE | QA - QUALITY | QA - QUALITY | R02 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROLVALVES / PO_000672-CONTROL_VALVES
BNO-000672-300-QA-5880-040-PETR-00001 | QUALITY ASSURANCE AND QUALITY SYSTEM PLAN - CONTROL VALVES | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / PETROLVALVES / PO_000672-CONTROL_VALVES
BNO-000672-300-RA-1580-040-PETR-00001 | MATERIAL CERTIFICATE - CONTROL VALVES | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROLVALVES / PO_000672-CONTROL_VALVES
BNO-000672-300-RA-6068-040-PETR-00001 | PAINTING PROCEDURE - CONTROL VALVES | MATERIALS | RA - MATERIALS | A02 | NAO |  | Diretorio Vendor | TRANSMITTAL | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000672-CONTROL_VALVES
BNO-000672-300-SA-6028-040-PETR-00001 | PACKING_HANDLING_ PRESERVATION AND TRANSPORTATION PROCEDURE - CONTROL VALVES | SA - LOGISTICS | SA - LOGISTICS | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / PETROLVALVES / PO_000672-CONTROL_VALVES
BNO-000686-300-BA-7756-004-AOL-00001 | BEND FABRICATION MARKING PROCEDURE | CONSTRUCTION | BA - CONSTRUCTION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / PFF_GROUP / PO_000686-5D_BEND
BNO-000686-300-JA-6611-004-AOL-00001 | DOCUMENT LIST | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / PFF_GROUP / PO_000686-5D_BEND
BNO-000686-300-MP-2321-004-AOL-00001 | BEND FABRICATION DRAWING | PIPING | MP - PIPING | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PFF_GROUP / PO_000686-5D_BEND
BNO-000686-300-QA-5733-004-AOL-00001 | BEND FABRICATION INSPECTION AND TEST PLAN | QA - QUALITY | QA - QUALITY | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PFF_GROUP / PO_000686-5D_BEND
BNO-000703-300-FA-5803-021-PETR-00001 | ENGINEERING_ FABRICATION_ INSPECTION AND TESTING SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROLVALVES / PO_000703-SHUTDOWN_VALVES
BNO-000703-300-IN-1580-021-PETR-00001 | FAILURE DATA / SIL CERTIFICATE IN ACCORDANCE WITH IEC-61508 / IEC- 61511 | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROLVALVES / PO_000703-SHUTDOWN_VALVES
BNO-000703-300-IN-1580-021-PETR-00002 | HAZARDOUS AREA AND PROTECTION DEGREE CERTIFICATE (CENELEC)_ACTUATORS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROLVALVES / PO_000703-SHUTDOWN_VALVES
BNO-000703-300-IN-2105-021-PETR-00001 | TECHNICAL DATASHEET / SPECIFICATION | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000703-SHUTDOWN_VALVES
BNO-000703-300-IN-2105-021-PETR-00002 | SIZING CALCULATION SHEET WITH TORQUE/THRUST SUMMARY TABLE FOR VALVE/ACTUATOR COMBINATION (TORQUE TABLE) | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000703-SHUTDOWN_VALVES
BNO-000703-300-IN-4018-021-PETR-00001 | GENERAL ARRANGEMENT DRAWING (VALVE WITH ACTUATOR CONTROL PANEL AND ACCESSORIES).DIMENSIONAL DRAWINGS WITH WEIGHT | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / PETROLVALVES / PO_000703-SHUTDOWN_VALVES
BNO-000703-300-IN-4018-021-PETR-00002 | WIRING DIAGRAM (ACCESSORIES) | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000703-SHUTDOWN_VALVES
BNO-000703-300-IN-4354-021-PETR-00001 | SPARE PART LISTS FOR TWO YEARSINCL. COMPONENTS LIST WITH REF. MANUFACTURER/MODEL N°. | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROLVALVES / PO_000703-SHUTDOWN_VALVES
BNO-000703-300-IN-7880-021-PETR-00001 | DOCUMENTS / CROSS SECTIONAL DRAWINGS WITH BILL OF MATERIAL FOR ACTUATOR. | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / PETROLVALVES / PO_000703-SHUTDOWN_VALVES
BNO-000703-300-IN-7880-021-PETR-00002 | ACTUATOR GA DRAWINGS | INSTRUMENTATION | IN - INSTRUMENTATION | A04 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000703-SHUTDOWN_VALVES
BNO-000703-300-IN-7880-021-PETR-00003 | NAMEPLATE DRAWING FOR VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | A04 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000703-SHUTDOWN_VALVES
BNO-000703-300-IN-7880-021-PETR-00004 | NAMEPLATE DRAWING FOR ACTUATORS | INSTRUMENTATION | IN - INSTRUMENTATION | A04 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000703-SHUTDOWN_VALVES
BNO-000703-300-IN-7880-021-PETR-00005 | ACTUATOR ASSEMBLY DRAWINGS WITH PART LIST AND SECTIONAL DRAWING WITH BILL OF MATERIALS (BOM) FOR HYDRAULIC SHUTDOWN VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 4 | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / PETROLVALVES / PO_000703-SHUTDOWN_VALVES
BNO-000703-300-JA-4372-021-PETR-00001 | DATABOOK | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROLVALVES / PO_000703-SHUTDOWN_VALVES
BNO-000703-300-JA-6611-021-PETR-00001 | DOCUMENTS / DRAWINGS LIST | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 |  |  | BNO / 03-VENDOR / PETROLVALVES / PO_000703-SHUTDOWN_VALVES
BNO-000703-300-OA-4811-021-PETR-00001 | OPERATION MANUAL FOR VALVES | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROLVALVES / PO_000703-SHUTDOWN_VALVES
BNO-000703-300-OA-4811-021-PETR-00002 | OPERATION MANUAL FOR ACTUATORS | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000703-SHUTDOWN_VALVES
BNO-000703-300-QA-5733-021-PETR-00001 | INSPECTION AND TEST PLAN FOR VALVES | QA - QUALITY | QA - QUALITY | A04 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / PETROLVALVES / PO_000703-SHUTDOWN_VALVES
BNO-000703-300-QA-5733-021-PETR-00002 | INSPECTION AND TEST PLAN FOR ACTUATORS | QA - QUALITY | QA - QUALITY | C02 | NAO |  | Diretorio Vendor | TRANSMITTAL |  | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / PETROLVALVES / PO_000703-SHUTDOWN_VALVES
BNO-000703-300-QA-5733-021-PETR-00003 | FAT TEST PROCEDURE/S (VALVE AND ACTUATOR ASSEMBLY) | QA - QUALITY | QA - QUALITY | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 4 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000703-SHUTDOWN_VALVES
BNO-000703-300-QA-5733-021-PETR-00004 | ACTUATOR TESTING PROCEDURES | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000703-SHUTDOWN_VALVES
BNO-000703-300-QA-5733-021-PETR-00005 | PROJECT QUALITY PLAN | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROLVALVES / PO_000703-SHUTDOWN_VALVES
BNO-000703-300-QA-5733-021-PETR-00015 | PROJECT QUALITY PLAN FOR HYDRAULIC BOARDING SHUTDOWN VALVES | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | CANCELADO | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROLVALVES / PO_000703-SHUTDOWN_VALVES
BNO-000703-300-RA-1580-021-PETR-00001 | MATERIAL CERTIFICATE | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROLVALVES / PO_000703-SHUTDOWN_VALVES
BNO-000703-300-RA-6068-021-PETR-00001 | PAINTING PROCEDURE FOR VALVES | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROLVALVES / PO_000703-SHUTDOWN_VALVES
BNO-000703-300-RA-6068-021-PETR-00002 | PAINTING PROCEDURE FOR ACTUATORS | MATERIALS | RA - MATERIALS | A03 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000703-SHUTDOWN_VALVES
BNO-000703-300-SA-6028-021-PETR-00001 | PACKING HANDLING PRESERVATION AND TRANSPORTATION PROCEDURE | SA - LOGISTICS | SA - LOGISTICS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000703-SHUTDOWN_VALVES
BNO-000704-300-FA-5803-040-PETR-00001 | ENGINEERING, FABRICATION, INSPECTION AND TESTING SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-1580-040-PETR-00001 | SIL CERTIFICATE IN ACCORDANCE WITH IEC-61508 / IEC- 61511 | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-1580-040-PETR-00002 | HAZARDOUS AREA AND PROTECTION DEGREE CERTIFICATE (CENELEC)_ACTUATORS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-2105-040-PETR-00001 | TECHNICAL DATASHEET / SPECIFICATION | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-2105-040-PETR-00002 | SIZING CALCULATION SHEET WITH TORQUE/THRUST SUMMARY TABLE FOR VALVE/ACTUATOR COMBINATION (TORQUE TABLE) | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-4018-040-PETR-00001 | OVERALL DIMENSIONS DRAWING 14" - BALL VALVE | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-4018-040-PETR-00002 | OVERALL DIMENSIONS DRAWING 8" - BALL VALVE | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-4018-040-PETR-00003 | OVERALL DIMENSIONS DRAWING 10" - BALL VALVE | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-4018-040-PETR-00004 | OVERALL DIMENSIONS DRAWING 8" - BALL VALVE | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-4018-040-PETR-00005 | OVERALL DIMENSIONS DRAWING 2" -WEDGE GATE VALVE | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-4018-040-PETR-00006 | WIRING DIAGRAM FOR PNEUMATIC ACTUATED ON-OFF BLOWDOWN AND SHUTDOWN VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-4018-040-PETR-00007 | SCHEMATIC DIAGRAMS FOR PNEUMATIC ACTUATED ON-OFF BLOWNDOWN AND SHUTDOWN VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-4018-040-PETR-00008 | OVERALL DIMENSIONS DRAWING 4" - BALL VALVE_ TAG. 04-SDV-810 | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-4018-040-PETR-00009 | OVERALL DIMENSIONS DRAWING 2" - BALL VALVE_ TAG. 44-SDV-502 | INSTRUMENTATION | IN - INSTRUMENTATION | R02 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-4018-040-PETR-00010 | WIRING DIAGRAMS FOR TAG. 40-XV-833 FOR PNEUMATIC ACTUATED ON-OFF BLOWDOWN AND SHUTDOWN VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | R02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-4018-040-PETR-00011 | SCHEMATIC DIAGRAMS FOR TAG. 40-XV-833 FOR PNEUMATIC ACTUATED ON-OFF BLOWDOWN AND SHUTDOWN VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-4018-040-PETR-00012 | OVERALL DIMENSIONS DRAWING 24" - TOV AJ SERIES VALVE_ TAG.40-XV-833 | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-4018-040-PETR-00013 | OVERALL DIMENSIONS DRAWING 1/2" - BALL VALVE TAG. 04-SDV-467_ 04-SDV-469 | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-4354-040-PETR-00001 | SPARE PART LISTS FOR TWO YEARS INCL. COMPONENTS LIST WITH REF. MANUFACTURER/MODEL N°. | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-7880-040-PETR-00001 | CROSS SECTION DRAWING WITH BILL OF MATERIAL - 14" - BALL VALVE | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-7880-040-PETR-00002 | NAMEPLATE DRAWING FOR VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-7880-040-PETR-00003 | NAMEPLATE DRAWING FOR ACTUATORS FOR PNEUMATIC ACTUATED ON-OFF BLOWDOWN AND SHUTDOWN VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-7880-040-PETR-00004 | ACTUATOR GA DRAWINGS | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-7880-040-PETR-00005 | CROSS SECTION DRAWING WITH BILL OF MATERIAL 24" - TOV AJ SERIES VALVE_ TAG.40-XV-833 | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-7880-040-PETR-00006 | CROSS SECTION DRAWING WITH BILL OF MATERIAL - 1/2" - BALL VALVE TAG. 04-SDV-467 & 04-SDV-469 | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-7880-040-PETR-00007 | CROSS SECTION DRAWINGWITH BILL OF MATERIAL 8" - BALL VALVE- TAG. 04-BDV-472 | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-7880-040-PETR-00008 | CROSS SECTION DRAWING WITH BILL OF MATERIAL - 10" - BALL VALVE | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-7880-040-PETR-00009 | CROSS SECTION DRAWING WITH BILL OF MATERIAL - 8" - BALL VALVE TAG. 04-BDV-492 | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-7880-040-PETR-00010 | CROSS SECTION DRAWING WITH BILL OF MATERIAL - 2" - WEDGE GATE VALVE | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-7880-040-PETR-00011 | CROSS SECTION DRAWING WITH BILL OF MATERIAL AND DIMENSION - 2" - BALL VALVES - ENERGY | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-7880-040-PETR-00012 | CROSS SECTION DRAWING WITH BILL OF MATERIAL AND DIMENSION - 4" - BALL VALVES - ENERGY | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-7880-040-PETR-00013 | ACTUATOR GA DRAWING FOR TAG. 40-XV-833 FOR PNEUMATIC ACTUATED ON-OFF BLOWNDOWN AND SHUTDOWN VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-IN-7880-040-PETR-00014 | ACTUATOR ASSEMBLY DRAWINGS WITH PART LIST AND SECTIONAL DRAWING WITH BILL OF MATERIALS (BOM) FOR PNEUMATIC ACTUATED ON-OFF_ BLOWDOWN AND SHUTDOWN VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-JA-4372-040-PETR-00001 | DATA BOOK | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-JA-6611-040-PETR-00001 | DOCUMENTS /DRAWINGS LIST | IT / IM | JA - IM | R02 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-OA-4811-040-PETR-00001 | OPERATION MANUAL FOR VALVES | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | ENGINEERING CONSOLIDATION | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-OA-4811-040-PETR-00002 | OPERATION MANUAL FOR ACTUATORS | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-QA-5733-040-PETR-00001 | INSPECTION AND TEST PLAN FOR VALVES | QA - QUALITY | QA - QUALITY | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-QA-5733-040-PETR-00002 | INSPECTION AND TEST PLAN FOR ACTUATORS | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-QA-5733-040-PETR-00003 | QUALITY CONTROL PLAN FOR TRIPLE OFF-SET BUTTERFLY VALVES FOR PNEUMATIC ACTUATED ON-OFF _ BLOWDOWN AND SHUTDOWN VALVES | QA - QUALITY | QA - QUALITY | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-QA-5733-040-PETR-00004 | INSPECTION AND TEST PLAN FOR ACTUATORS (ONLY TAG 40-XV-833) FOR PNEUMATIC ACTUATED ON-OFF BLOWDOWN AND SHUTDOWN VALVES | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | TRANSMITTAL | IFA RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-QA-5733-040-PETR-00005 | PROJECT QUALITY PLAN FOR PNEUMATIC ACTUATED ON-OFF_ BLOWDOWN AND SHUTDOWN VALVES | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-QA-6050-040-PETR-00001 | FAT TEST PROCEDURE/S (VALVE AND ACTUATOR ASSEMBLY) | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-QA-6050-040-PETR-00002 | ACTUATOR TESTING PROCEDURES | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-QA-6050-040-PETR-00003 | FAT TEST PROCEDURE FOR TRIPPLE OFF SET BUTTERFLY VALVES FOR PNEUMATIC ACTUATED ON-OFF BLOWDOWN AND SHUTDOWN VALVE | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-RA-1580-040-PETR-00001 | MATERIAL CERTIFICATE (COMPLETE PACKAGE OF MTC NDE RECORDS FAT REPORTS ETC) | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-RA-6068-040-PETR-00001 | PAINTING PROCEDURE FOR VALVES | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-RA-6068-040-PETR-00002 | PAINTING PROCEDURE FOR ACTUATORS | MATERIALS | RA - MATERIALS | A05 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000704-300-SA-6028-040-PETR-00001 | PACKING PRESERVATION HANDLING AND TRANSPORTATION PROCEDURE | SA - LOGISTICS | SA - LOGISTICS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROLVALVES / PO_000704-PNEUMATIC_AND_BDNW_VALVES
BNO-000803-300-EA-4018-073-POWI-00001 | BILL OF MATERIALS - MV | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_000803-SWITCHBOARD_MOD
BNO-000803-300-EA-4018-073-POWI-00002 | GENERAL ARRANGEMENT 6.6KV SWITCHBOARD SB-7340-D-01 | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_000803-SWITCHBOARD_MOD
BNO-000803-300-EA-4018-073-POWI-00003 | ENGRAVING DRAWING COMPARTMENT LABEL | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_000803-SWITCHBOARD_MOD
BNO-000803-300-EA-4018-073-POWI-00004 | SCHEMATIC DIAGRAM VACCUM CONTRACTOR TRANSFORMER FEEDER | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_000803-SWITCHBOARD_MOD
BNO-000803-300-EA-4018-073-POWI-00005 | COMPARTMENT MATRIX | ELECTRICAL | EA - ELECTRICAL | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / POWELL / PO_000803-SWITCHBOARD_MOD
BNO-000803-300-EA-4018-073-POWI-00006 | GENERAL ARRANGEMENT | ELECTRICAL | EA - ELECTRICAL | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / POWELL / PO_000803-SWITCHBOARD_MOD
BNO-000803-300-EA-4018-073-POWI-00007 | LABEL DRAWING | ELECTRICAL | EA - ELECTRICAL | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / POWELL / PO_000803-SWITCHBOARD_MOD
BNO-000803-300-EA-4018-073-POWI-00008 | SCHEMATIC DIAGRAM 250A MCCB FDR | ELECTRICAL | EA - ELECTRICAL | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / POWELL / PO_000803-SWITCHBOARD_MOD
BNO-000803-300-EA-4018-073-POWI-00009 | BILL OF MATERIALS - LV | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_000803-SWITCHBOARD_MOD
BNO-000803-300-JA-6611-073-POWI-00001 | SUPPLIER DOCUMENT REGISTER | IT / IM | JA - IM | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_000803-SWITCHBOARD_MOD
BNO-000803-300-QA-5733-073-POWI-00001 | SUMMARY SPECIFICATION | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / POWELL / PO_000803-SWITCHBOARD_MOD
BNO-000803-300-QA-5733-073-POWI-00003 | INSPECTION AND TEST PLAN | QA - QUALITY | QA - QUALITY | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / POWELL / PO_000803-SWITCHBOARD_MOD
BNO-000803-300-QA-5793-073-POWI-00001 | SCOPE OF WORK - MODIFY 2-OFF 400A VCU FEEDER | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_000803-SWITCHBOARD_MOD
BNO-000803-300-QA-5793-073-POWI-00002 | SCOPE OF WORK - SUPPLY 1 NEW 250A MCCB FEEDER | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / POWELL / PO_000803-SWITCHBOARD_MOD
BNO-000803-300-QA-5880-073-POWI-00002 | QUALITY PLAN | QA - QUALITY | QA - QUALITY | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 4 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / POWELL / PO_000803-SWITCHBOARD_MOD
BNO-000803-300-QA-6050-073-POWI-00001 | FACTORY ACCEPTANCE TEST PROCEDURE | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_000803-SWITCHBOARD_MOD
BNO-000803-300-VA-1453-073-POWI-00001 | INTERNAL TEST CERTIFICATES | VA - PROCUREMENT | VA - PROCUREMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_000803-SWITCHBOARD_MOD
BNO-000803-300-VA-1453-073-POWI-00002 | FACTORY ACCEPTANCE TEST CERTIFICATES | VA - PROCUREMENT | VA - PROCUREMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_000803-SWITCHBOARD_MOD
BNO-000803-300-VA-1453-073-POWI-00003 | CERTIFCATE OF CONFORMITY | VA - PROCUREMENT | VA - PROCUREMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_000803-SWITCHBOARD_MOD
BNO-000815-300-BA-6065-040-AOL-00001 | WELDING PROCEDURE SPECIFICATION (WPS) & PQRS | CONSTRUCTION | BA - CONSTRUCTION | R01 | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000815-BALL_VALVES
BNO-000815-300-FA-5803-040-AOL-00001 | PRODUCTION SCHEDULE / MANUFACTURING TIMELINE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000815-BALL_VALVES
BNO-000815-300-JA-6611-040-AOL-00001 | VENDOR DATA REGISTER LIST (VDRL) | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000815-BALL_VALVES
BNO-000815-300-MP-2105-040-AOL-00001 | BALL VALVES DATASHEETS | PIPING | MP - PIPING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000815-BALL_VALVES
BNO-000815-300-MP-4018-040-AOL-00001 | BALL VALVES GENERAL ARRANGEMENT (GA) DRAWINGS | PIPING | MP - PIPING | A05 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000815-BALL_VALVES
BNO-000815-300-MP-4354-040-AOL-00001 | SPARE PARTS LIST & RECOMMENDED SPARES | PIPING | MP - PIPING | R01 | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000815-BALL_VALVES
BNO-000815-300-MX-6067-040-AOL-00001 | NDE PROCEDURES | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000815-BALL_VALVES
BNO-000815-300-OA-4811-040-AOL-00001 | O&M MANUALS | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000815-BALL_VALVES
BNO-000815-300-QA-5733-040-AOL-00001 | INSPECTION & TEST PLAN (ITP) FOR BALL VALVES | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000815-BALL_VALVES
BNO-000815-300-QA-6050-040-AOL-00001 | MANUFACTURING QUALITY PLAN (MQP) | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000815-BALL_VALVES
BNO-000815-300-QA-6050-040-AOL-00002 | DIMENSIONAL CONTROL PROCEDURE. | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000815-BALL_VALVES
BNO-000815-300-QA-6050-040-AOL-00003 | PRESSURE TESTING PROCEDURE | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000815-BALL_VALVES
BNO-000815-300-QA-6050-040-AOL-00004 | FORGING / CASTING PROCEDURES | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000815-BALL_VALVES
BNO-000815-300-QA-6050-040-AOL-00005 | PACKING PRESERVATION & MARKING PROCEDURE | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000815-BALL_VALVES
BNO-000815-300-QA-6050-040-AOL-00006 | GENERAL FAT PROCEDURE FOR MANUAL VALVES | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000815-BALL_VALVES
BNO-000815-300-RA-1580-040-AOL-00001 | MATERIAL TEST CERTIFICATES (MTC) | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000815-BALL_VALVES
BNO-000815-300-RA-6068-040-AOL-00001 | PAINTING PROCEDURE FOR DHV MANUAL VALVES (APPLICABLE TO ALL DHV VALVE TYPES) | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000815-BALL_VALVES
BNO-000815-300-VA-1453-040-AOL-00001 | CERTIFICATE OF COMPLIANCE (COC) | VA - PROCUREMENT | VA - PROCUREMENT | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000815-BALL_VALVES
BNO-000815-300-VA-4305-040-AOL-00001 | LIST OF SUB SUPPLIERS | VA - PROCUREMENT | VA - PROCUREMENT | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000815-BALL_VALVES
BNO-000816-300-BA-6065-040-AOL-00001 | WELDING PROCEDURE SPECIFICATION (WPS) & PQRS | CONSTRUCTION | BA - CONSTRUCTION | R01 | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000816-CHECK_VALVES
BNO-000816-300-FA-5803-040-AOL-00001 | PRODUCTION SCHEDULE / MANUFACTURING TIMELINE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000816-CHECK_VALVES
BNO-000816-300-JA-6611-040-AOL-00001 | VENDOR DATA REGISTER LIST (VDRL) | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000816-CHECK_VALVES
BNO-000816-300-MP-2105-040-AOL-00001 | CHECK VALVES DATASHEETS | PIPING | MP - PIPING | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000816-CHECK_VALVES
BNO-000816-300-MP-4018-040-AOL-00001 | CHECK VALVES GENERAL ARRANGEMENT (GA) DRAWINGS | PIPING | MP - PIPING | A04 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000816-CHECK_VALVES
BNO-000816-300-MP-4354-040-AOL-00001 | SPARE PARTS LIST & RECOMMENDED SPARES | PIPING | MP - PIPING | R01 | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000816-CHECK_VALVES
BNO-000816-300-MX-6067-040-AOL-00001 | NDE PROCEDURES FOR MANUAL VALVES | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000816-CHECK_VALVES
BNO-000816-300-OA-4811-040-AOL-00001 | O&M MANUALS | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000816-CHECK_VALVES
BNO-000816-300-QA-5733-040-AOL-00001 | INSPECTION & TEST PLAN (ITP) FOR GLOBE VALVES | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000816-CHECK_VALVES
BNO-000816-300-QA-6050-040-AOL-00001 | MANUFACTURING QUALITY PLAN (MQP) | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000816-CHECK_VALVES
BNO-000816-300-QA-6050-040-AOL-00002 | DIMENSIONAL CONTROL PROCEDURE. | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000816-CHECK_VALVES
BNO-000816-300-QA-6050-040-AOL-00003 | PRESSURE TESTING PROCEDURE | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000816-CHECK_VALVES
BNO-000816-300-QA-6050-040-AOL-00004 | FORGING/CASTING PROCEDURES | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000816-CHECK_VALVES
BNO-000816-300-QA-6050-040-AOL-00005 | PACKING PRESERVATION & MARKING PROCEDURE | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000816-CHECK_VALVES
BNO-000816-300-RA-1580-040-AOL-00001 | MATERIAL TEST CERTIFICATES (MTC) | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000816-CHECK_VALVES
BNO-000816-300-RA-6068-040-AOL-00001 | PAINTING PROCEDURE | MATERIALS | RA - MATERIALS | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000816-CHECK_VALVES
BNO-000816-300-VA-1453-040-AOL-00001 | CERTIFICATE OF COMPLIANCE (COC) | VA - PROCUREMENT | VA - PROCUREMENT | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000816-CHECK_VALVES
BNO-000816-300-VA-4305-040-AOL-00001 | LIST OF SUB SUPPLIERS | VA - PROCUREMENT | VA - PROCUREMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000816-CHECK_VALVES
BNO-000817-300-BA-6065-040-AOL-00001 | WELDING PROCEDURE SPECIFICATION (WPS) & PQRS | CONSTRUCTION | BA - CONSTRUCTION | R01 | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000817-GATE_VALVES
BNO-000817-300-FA-5803-040-AOL-00001 | PRODUCTION SCHEDULE / MANUFACTURING TIMELINE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000817-GATE_VALVES
BNO-000817-300-JA-6611-040-AOL-00001 | VENDOR DATA REGISTER LIST (VDRL) | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000817-GATE_VALVES
BNO-000817-300-MP-2105-040-AOL-00001 | GATE VALVES DATASHEETS | PIPING | MP - PIPING | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000817-GATE_VALVES
BNO-000817-300-MP-4018-040-AOL-00001 | GATE VALVES GENERAL ARRANGEMENT (GA) DRAWINGS | PIPING | MP - PIPING | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000817-GATE_VALVES
BNO-000817-300-MP-4354-040-AOL-00001 | SPARE PARTS LIST & RECOMMENDED SPARES | PIPING | MP - PIPING | R01 | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000817-GATE_VALVES
BNO-000817-300-MX-6067-040-AOL-00001 | NDE PROCEDURES | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000817-GATE_VALVES
BNO-000817-300-OA-4811-040-AOL-00001 | O&M MANUALS | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000817-GATE_VALVES
BNO-000817-300-QA-5733-040-AOL-00001 | INSPECTION & TEST PLAN (ITP) FOR GATE VALVES | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000817-GATE_VALVES
BNO-000817-300-QA-6050-040-AOL-00001 | MANUFACTURING QUALITY PLAN (MQP) | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000817-GATE_VALVES
BNO-000817-300-QA-6050-040-AOL-00002 | DIMENSIONAL CONTROL PROCEDURE. | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000817-GATE_VALVES
BNO-000817-300-QA-6050-040-AOL-00003 | PRESSURE TESTING PROCEDURE | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000817-GATE_VALVES
BNO-000817-300-QA-6050-040-AOL-00004 | FORGING/CASTING PROCEDURES | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000817-GATE_VALVES
BNO-000817-300-QA-6050-040-AOL-00005 | PACKING PRESERVATION & MARKING PROCEDURE | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000817-GATE_VALVES
BNO-000817-300-RA-1580-040-AOL-00001 | MATERIAL TEST CERTIFICATES (MTC) | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000817-GATE_VALVES
BNO-000817-300-RA-6068-040-AOL-00001 | PAINTING PROCEDURE | MATERIALS | RA - MATERIALS | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000817-GATE_VALVES
BNO-000817-300-VA-1453-040-AOL-00001 | CERTIFICATE OF COMPLIANCE (COC) | VA - PROCUREMENT | VA - PROCUREMENT | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000817-GATE_VALVES
BNO-000817-300-VA-4305-040-AOL-00001 | LIST OF SUB SUPPLIERS | VA - PROCUREMENT | VA - PROCUREMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000817-GATE_VALVES
BNO-000818-300-BA-6065-040-AOL-00001 | WELDING PROCEDURE SPECIFICATION (WPS) & PQRS | CONSTRUCTION | BA - CONSTRUCTION | R01 | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000818-DB_AND_BLEED_VALVES
BNO-000818-300-FA-5803-040-AOL-00001 | PRODUCTION SCHEDULE / MANUFACTURING TIMELINE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000818-DB_AND_BLEED_VALVES
BNO-000818-300-JA-6611-040-AOL-00001 | VENDOR DATA REGISTER LIST | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000818-DB_AND_BLEED_VALVES
BNO-000818-300-MP-2105-040-AOL-00001 | DOUBLE BLOCK AND BLEEDVALVES DATASHEETS | PIPING | MP - PIPING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000818-DB_AND_BLEED_VALVES
BNO-000818-300-MP-4018-040-AOL-00001 | DOUBLE BLOCK AND BLEED VALVES GENERAL ARRANGEMENT (GA) DRAWINGS | PIPING | MP - PIPING | A04 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000818-DB_AND_BLEED_VALVES
BNO-000818-300-MP-4354-040-AOL-00001 | SPARE PARTS LIST & RECOMMENDED SPARES | PIPING | MP - PIPING | R01 | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000818-DB_AND_BLEED_VALVES
BNO-000818-300-MX-6067-040-AOL-00001 | NDE PROCEDURES | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000818-DB_AND_BLEED_VALVES
BNO-000818-300-OA-4811-040-AOL-00001 | O&M MANUALS | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000818-DB_AND_BLEED_VALVES
BNO-000818-300-QA-5733-040-AOL-00001 | INSPECTION & TEST PLAN (ITP) FOR DBB VALVES | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000818-DB_AND_BLEED_VALVES
BNO-000818-300-QA-6050-040-AOL-00001 | MANUFACTURING QUALITY PLAN (MQP) | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000818-DB_AND_BLEED_VALVES
BNO-000818-300-QA-6050-040-AOL-00002 | DIMENSIONAL CONTROL PROCEDURE. | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000818-DB_AND_BLEED_VALVES
BNO-000818-300-QA-6050-040-AOL-00003 | PRESSURE TESTING PROCEDURE | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000818-DB_AND_BLEED_VALVES
BNO-000818-300-QA-6050-040-AOL-00004 | FORGING/CASTING PROCEDURES | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000818-DB_AND_BLEED_VALVES
BNO-000818-300-QA-6050-040-AOL-00005 | PACKING PRESERVATION & MARKING PROCEDURE | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000818-DB_AND_BLEED_VALVES
BNO-000818-300-RA-1580-040-AOL-00001 | MATERIAL TEST CERTIFICATES (MTC) | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000818-DB_AND_BLEED_VALVES
BNO-000818-300-RA-6068-040-AOL-00001 | PAINTING PROCEDURE | MATERIALS | RA - MATERIALS | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000818-DB_AND_BLEED_VALVES
BNO-000818-300-VA-1453-040-AOL-00001 | CERTIFICATE OF COMPLIANCE (COC) | VA - PROCUREMENT | VA - PROCUREMENT | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000818-DB_AND_BLEED_VALVES
BNO-000818-300-VA-4305-040-AOL-00001 | LIST OF SUB SUPPLIERS | VA - PROCUREMENT | VA - PROCUREMENT | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000818-DB_AND_BLEED_VALVES
BNO-000819-300-BA-6065-040-AOL-00001 | WELDING PROCEDURE SPECIFICATION (WPS) & PQRS | CONSTRUCTION | BA - CONSTRUCTION | R01 | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000819-NEEDLE_VALVES
BNO-000819-300-FA-5803-040-AOL-00001 | PRODUCTION SCHEDULE / MANUFACTURING TIMELINE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000819-NEEDLE_VALVES
BNO-000819-300-JA-6611-040-AOL-00001 | VENDOR DATA REGISTER LIST (VDRL) | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000819-NEEDLE_VALVES
BNO-000819-300-MP-2105-040-AOL-00001 | NEEDLE VALVES DATASHEETS | PIPING | MP - PIPING | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000819-NEEDLE_VALVES
BNO-000819-300-MP-4018-040-AOL-00001 | NEEDLE VALVES GENERAL ARRANGEMENT (GA) DRAWINGS | PIPING | MP - PIPING | A04 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000819-NEEDLE_VALVES
BNO-000819-300-MP-4354-040-AOL-00001 | SPARE PARTS LIST & RECOMMENDED SPARES | PIPING | MP - PIPING | R01 | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000819-NEEDLE_VALVES
BNO-000819-300-MX-6067-040-AOL-00001 | NDE PROCEDURES | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000819-NEEDLE_VALVES
BNO-000819-300-OA-4811-040-AOL-00001 | O&M MANUALS | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000819-NEEDLE_VALVES
BNO-000819-300-QA-5733-040-AOL-00001 | INSPECTION & TEST PLAN (ITP) FOR GLOBE VALVES | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000819-NEEDLE_VALVES
BNO-000819-300-QA-6050-040-AOL-00001 | MANUFACTURING QUALITY PLAN (MQP) | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000819-NEEDLE_VALVES
BNO-000819-300-QA-6050-040-AOL-00002 | DIMENSIONAL CONTROL PROCEDURE. | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000819-NEEDLE_VALVES
BNO-000819-300-QA-6050-040-AOL-00003 | PRESSURE TESTING PROCEDURE | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000819-NEEDLE_VALVES
BNO-000819-300-QA-6050-040-AOL-00004 | FORGING/CASTING PROCEDURES | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000819-NEEDLE_VALVES
BNO-000819-300-QA-6050-040-AOL-00005 | PACKING PRESERVATION & MARKING PROCEDURE | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000819-NEEDLE_VALVES
BNO-000819-300-RA-1580-040-AOL-00001 | MATERIAL TEST CERTIFICATES (MTC) | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000819-NEEDLE_VALVES
BNO-000819-300-RA-6068-040-AOL-00001 | PAINTING PROCEDURE | MATERIALS | RA - MATERIALS | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000819-NEEDLE_VALVES
BNO-000819-300-VA-1453-040-AOL-00001 | CERTIFICATE OF COMPLIANCE (COC) | VA - PROCUREMENT | VA - PROCUREMENT | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000819-NEEDLE_VALVES
BNO-000819-300-VA-4305-040-AOL-00001 | LIST OF SUB SUPPLIERS | VA - PROCUREMENT | VA - PROCUREMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_000819-NEEDLE_VALVES
BNO-000901-300-MP-2321-004-AOL-00001 | SWEEPOLET DRAWING | NÃO SE APLICA | NÃO SE APLICA | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / MEGA / PO_000901-FITTINGS
BNO-000963-300-JA-6611-091-AOL-00001 | VENDOR DOCUMENT REGISTER TPCO - HEAVY WALL PIPES | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  | 07/09/2025 | BNO / 03-VENDOR / TPCO / PO_000963-HEAVY WALL PIPES
BNO-000963-300-QA-5733-091-AOL-00001 | MANUFACTURING PROCEDURE SPECIFICATION FOR TPCO HEAVY WALL PIPES | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / TPCO / PO_000963-HEAVY WALL PIPES
BNO-000963-300-RA-1580-091-AOL-00001 | MATERIAL TEST CERTIFICATES | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / TPCO / PO_000963-HEAVY WALL PIPES
BNO-001029-300-BA-6065-040-AOL-00001 | WELDING PROCEDURE SPECIFICATION (WPS) & PQRS | CONSTRUCTION | BA - CONSTRUCTION | R01 | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_001029-GLOBE_VALVES
BNO-001029-300-FA-5803-040-AOL-00001 | PRODUCTION SCHEDULE / MANUFACTURING TIMELINE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_001029-GLOBE_VALVES
BNO-001029-300-JA-6611-040-AOL-00001 | VENDOR DATA REGISTER LIST (VDRL) | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_001029-GLOBE_VALVES
BNO-001029-300-MP-2105-040-AOL-00001 | GLOBE VALVES DATASHEETS | PIPING | MP - PIPING | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_001029-GLOBE_VALVES
BNO-001029-300-MP-4018-040-AOL-00001 | GLOBE VALVES GENERAL ARRANGEMENT (GA) DRAWINGS | PIPING | MP - PIPING | A04 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_001029-GLOBE_VALVES
BNO-001029-300-MP-4354-040-AOL-00001 | SPARE PARTS LIST & RECOMMENDED SPARES | PIPING | MP - PIPING | R01 | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_001029-GLOBE_VALVES
BNO-001029-300-MX-6067-040-AOL-00001 | NDE PROCEDURES | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_001029-GLOBE_VALVES
BNO-001029-300-OA-4811-040-AOL-00001 | O&M MANUALS | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_001029-GLOBE_VALVES
BNO-001029-300-QA-5733-040-AOL-00001 | INSPECTION & TEST PLAN (ITP) FOR GLOBE VALVES | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_001029-GLOBE_VALVES
BNO-001029-300-QA-6050-040-AOL-00001 | MANUFACTURING QUALITY PLAN (MQP) | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_001029-GLOBE_VALVES
BNO-001029-300-QA-6050-040-AOL-00002 | DIMENSIONAL CONTROL PROCEDURE. | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_001029-GLOBE_VALVES
BNO-001029-300-QA-6050-040-AOL-00003 | PRESSURE TESTING PROCEDURE | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_001029-GLOBE_VALVES
BNO-001029-300-QA-6050-040-AOL-00004 | FORGING/CASTING PROCEDURES | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_001029-GLOBE_VALVES
BNO-001029-300-QA-6050-040-AOL-00005 | PACKING PRESERVATION & MARKING PROCEDURE | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_001029-GLOBE_VALVES
BNO-001029-300-RA-1580-040-AOL-00001 | MATERIAL TEST CERTIFICATES (MTC) | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_001029-GLOBE_VALVES
BNO-001029-300-RA-6068-040-AOL-00001 | PAINTING PROCEDURE | MATERIALS | RA - MATERIALS | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_001029-GLOBE_VALVES
BNO-001029-300-VA-1453-040-AOL-00001 | CERTIFICATE OF COMPLIANCE (COC) | VA - PROCUREMENT | VA - PROCUREMENT | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_001029-GLOBE_VALVES
BNO-001029-300-VA-4305-040-AOL-00001 | LIST OF SUB SUPPLIERS | VA - PROCUREMENT | VA - PROCUREMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DHV_VALVE_AND_FOUNDRY / PO_001029-GLOBE_VALVES
BNO-001050-300-FA-5803-004-AOL-00001 | BOARDING VALVES PANEL SKID - ENGINEERING. FABRICATION. INSPECTION AND TESTING SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROCONTROLS / PO_001050-BOARDING_PANEL
BNO-001050-300-IN-1580-004-AOL-00001 | BOARDING VALVES PANEL SKID - SIL CERTIFICATES IN ACCORDANCE WITH IEC - 61508 / IEC - 61511 | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROCONTROLS / PO_001050-BOARDING_PANEL
BNO-001050-300-IN-1580-004-AOL-00002 | BOARDING VALVES PANEL SKID - ENCLOSURE HAZARDOUS AREA AND DNV (ATEX) CERTIFICATE | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROCONTROLS / PO_001050-BOARDING_PANEL
BNO-001050-300-IN-2105-004-AOL-00001 | BOARDING VALVES PANEL SKID - TECHNICAL DATA SHEET OF ELECTRIC MOTORS | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROCONTROLS / PO_001050-BOARDING_PANEL
BNO-001050-300-IN-2105-004-AOL-00002 | BOARDING VALVES PANEL SKID - DATA SHEET HYDRAULIC PUMPS | INSTRUMENTATION | IN - INSTRUMENTATION | R02 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROCONTROLS / PO_001050-BOARDING_PANEL
BNO-001050-300-IN-2105-004-AOL-00003 | BOARDING VALVES PANEL SKID - TECHNICAL DATA SHEET FOR INSTRUMENTS. VALVES AND SPARES | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROCONTROLS / PO_001050-BOARDING_PANEL
BNO-001050-300-IN-2105-004-AOL-00004 | BOARDING VALVES PANEL SKID - PROCESS DATA SHEET RESPECTING TO PRESSURE (MIN/NORMAL/MAX) AND RETURN LINE | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROCONTROLS / PO_001050-BOARDING_PANEL
BNO-001050-300-IN-2105-004-AOL-00005 | BOARDING VALVES PANEL SKID - SIZING CALCULATION SHEET (ACCUMULATOR AND RESERVOIR) | INSTRUMENTATION | IN - INSTRUMENTATION | A04 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROCONTROLS / PO_001050-BOARDING_PANEL
BNO-001050-300-IN-4018-004-AOL-00001-001 | BOARDING VALVES PANEL SKID - GENERAL ARRANGEMENT DRAWING | INSTRUMENTATION | IN - INSTRUMENTATION | A04 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROCONTROLS / PO_001050-BOARDING_PANEL
BNO-001050-300-IN-4018-004-AOL-00002-001 | BOARDING VALVES PANEL SKID - DIMENSIONAL DRAWING FOR JUNCTION BOXES | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / PETROCONTROLS / PO_001050-BOARDING_PANEL
BNO-001050-300-IN-4018-004-AOL-00003-001 | BOARDING VALVES PANEL SKID - IDENTIFICATION PLATE | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROCONTROLS / PO_001050-BOARDING_PANEL
BNO-001050-300-IN-4018-004-AOL-00004-001 | BOARDING VALVES PANEL SKID - SCHEMATIC DRAWING | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / PETROCONTROLS / PO_001050-BOARDING_PANEL
BNO-001050-300-IN-4018-004-AOL-00005-001 | BOARDING VALVES PANEL SKID - JUNCTION BOX WIRING DIAGRAM JB | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROCONTROLS / PO_001050-BOARDING_PANEL
BNO-001050-300-IN-4354-004-AOL-00001 | BOARDING VALVES PANEL SKID - SET POINT LIST | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROCONTROLS / PO_001050-BOARDING_PANEL
BNO-001050-300-IN-4354-004-AOL-00002 | BOARDING VALVES PANEL SKID - COMPONENT PART LIST | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROCONTROLS / PO_001050-BOARDING_PANEL
BNO-001050-300-IN-4354-004-AOL-00006 | BOARDING VALVES PANEL SKID - LIST OF SPECIAL TOOLS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROCONTROLS / PO_001050-BOARDING_PANEL
BNO-001050-300-JA-6611-004-AOL-00001 | BOARDING VALVES PANEL SKID - VENDOR DOCUMENT REQUIREMENTS LIST | IT / IM | JA - IM | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROCONTROLS / PO_001050-BOARDING_PANEL
BNO-001050-300-NA-4354-004-AOL-00003 | BOARDING VALVES PANEL SKID - SPARE PART LISTS (2 YEARS OPERATIONAL) | NA - MAINTENANCE | NA - MAINTENANCE | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROCONTROLS / PO_001050-BOARDING_PANEL
BNO-001050-300-NA-4354-004-AOL-00004 | BOARDING VALVES PANEL SKID - SPARE PART LISTS (COMMISSIONING) | NA - MAINTENANCE | NA - MAINTENANCE | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROCONTROLS / PO_001050-BOARDING_PANEL
BNO-001050-300-NA-4354-004-AOL-00005 | BOARDING VALVES PANEL SKID - CAPITAL SPARE PARTS LIST | NA - MAINTENANCE | NA - MAINTENANCE | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROCONTROLS / PO_001050-BOARDING_PANEL
BNO-001050-300-OA-4811-004-AOL-00001 | BOARDING VALVES PANEL SKID - INSTALLATION AND MAINTENANCE INSTRUCTIONS MANUAL | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROCONTROLS / PO_001050-BOARDING_PANEL
BNO-001050-300-QA-5733-004-AOL-00001 | BOARDING VALVES PANEL SKID - INSPECTION AND TEST PLAN | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROCONTROLS / PO_001050-BOARDING_PANEL
BNO-001050-300-QA-6050-004-AOL-00001 | BOARDING VALVES PANEL SKID - HANDLING AND TRANSPORTATION PROCEDURE | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROCONTROLS / PO_001050-BOARDING_PANEL
BNO-001050-300-QA-6050-004-AOL-00002 | BOARDING VALVES PANEL SKID - FAT PROCEDURE | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROCONTROLS / PO_001050-BOARDING_PANEL
BNO-001050-300-QA-6050-004-AOL-00003 | BOARDING VALVES PANEL SKID - SAT PROCEDURE | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROCONTROLS / PO_001050-BOARDING_PANEL
BNO-001050-300-QA-6050-004-AOL-00004 | BOARDING VALVES PANEL SKID - QUALITY ASSURANCE AND QUALITY SYSTEM PLAN | QA - QUALITY | QA - QUALITY | R02 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROCONTROLS / PO_001050-BOARDING_PANEL
BNO-001050-300-RA-1580-004-AOL-00001 | BOARDING VALVES PANEL SKID - MATERIAL CERTIFICATES | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROCONTROLS / PO_001050-BOARDING_PANEL
BNO-001050-300-RA-1580-004-AOL-00002 | BOARDING VALVES PANEL SKID - CALIBRATION CERTIFICATES | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PETROCONTROLS / PO_001050-BOARDING_PANEL
BNO-001050-300-RA-6068-004-AOL-00005 | BOARDING VALVES PANEL SKID - PAINTING PROCEDURE | MATERIALS | RA - MATERIALS | A02 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PETROCONTROLS / PO_001050-BOARDING_PANEL
BNO-001050-300-SA-6028-004-AOL-00001 | BOARDING VALVES PANEL SKID - PACKING AND PRESERVATION PROCEDURE | SA - LOGISTICS | SA - LOGISTICS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PETROCONTROLS / PO_001050-BOARDING_PANEL
BNO-001141-300-JA-6611-008-AOL-00001 | VENDOR DOCUMENT REGISTER LIST - QUICK OPENING END CLOSURES FOR PIG LAUNCHER AND RECEIVER (QOE-A-0820J /K) | IT / IM | JA - IM | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / CELEROS / PO_001141-PIG_LAUNCHER
BNO-001141-300-MS-1379-008-AOL-00001 | FEA DESIGN CALCULATIONS QUICK OPENING END CLOSURES FOR PIG LAUNCHER AND RECEIVER (QOE-A-0820J /K) | MECHANICAL | MS - MECHANICAL STATIC | A01 | NAO |  | Diretorio Vendor | TRANSMITTAL |  |  |  | BNO / 03-VENDOR / CELEROS / PO_001141-PIG_LAUNCHER
BNO-001141-300-MS-1580-008-AOL-00001 | CERTIFICATION DATA PACKAGE - QUICK OPENING END CLOSURES FOR PIG LAUNCHER AND RECEIVER (QOE-A-0820J /K) | MECHANICAL | MS - MECHANICAL STATIC | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / CELEROS / PO_001141-PIG_LAUNCHER
BNO-001141-300-MS-2105-008-AOL-00001 | TECHNICAL DATASHEET OF 16" CLOSURE TAG A-0820J/K - QUICK OPENING END CLOSURES FOR PIG LAUNCHER AND RECEIVER (QOE-A-0820J /K) | MECHANICAL | MS - MECHANICAL STATIC | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / CELEROS / PO_001141-PIG_LAUNCHER
BNO-001141-300-MS-2105-008-AOL-00002 | TERMINATION DETAIL - QUICK OPENING END CLOSURES FOR PIG LAUNCHER AND RECEIVER (QOE-A-0820J /K) | MECHANICAL | MS - MECHANICAL STATIC | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / CELEROS / PO_001141-PIG_LAUNCHER
BNO-001141-300-MS-4018-008-AOL-00001 | GA DRAWING & PARTS LIST QUICK OPENING END CLOSURES FORPIG LAUNCHER AND RECEIVER (QOE-A-0820J /K) (GAD) | MECHANICAL | MS - MECHANICAL STATIC | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / CELEROS / PO_001141-PIG_LAUNCHER
BNO-001141-300-OA-4811-008-AOL-00001 | OPERATIONAL INSTRUCTION MANUAL - QUICK OPENING END CLOSURES FOR PIG LAUNCHER AND RECEIVER (QOE-A-0820J /K) | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / CELEROS / PO_001141-PIG_LAUNCHER
BNO-001141-300-QA-5733-008-AOL-00001 | QUALITY ASSURANCE PROCEDURE - QUICK OPENING END CLOSURES FOR PIG LAUNCHER AND RECEIVER (QOE-A-0820J /K) | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / CELEROS / PO_001141-PIG_LAUNCHER
BNO-001141-300-QA-5733-008-AOL-00002 | INSPECTION AND TEST PLAN - QUICK OPENING END CLOSURES FOR PIG LAUNCHER AND RECEIVER (QOE-A-0820J /K) | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / CELEROS / PO_001141-PIG_LAUNCHER
BNO-001141-300-RA-6068-008-AOL-00001 | PAINTING PROCEDURE - QUICK OPENING END CLOSURES FOR PIG LAUNCHER AND RECEIVER (QOE-A-0820J /K) | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | TRANSMITTAL |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / CELEROS / PO_001141-PIG_LAUNCHER
BNO-001205-300-JA-6611-040-AOL-00001 | VDRL FOR RIVIT | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / RIVIT / PO_001205-PIPES-SUPER DUPLEX
BNO-001205-300-QA-5733-040-AOL-00001 | QUALITY CONTROL PLAN / ITP | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / RIVIT / PO_001205-PIPES-SUPER DUPLEX
BNO-001205-300-QA-5733-040-AOL-00002 | WELDING BOOK / WB | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / RIVIT / PO_001205-PIPES-SUPER DUPLEX
BNO-001252-300-BC-4354-004-AOL-00001 | LIST OF SPARES FOR COMISSIONING | BC - COMMISSIONING | BC - COMMISSIONING | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / ABB / PO_001252-(SB-7401A_MODIF)
BNO-001252-300-BC-4354-004-AOL-00002 | SPARE PARTS LIST FOR 2 YEARS | BC - COMMISSIONING | BC - COMMISSIONING | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / ABB / PO_001252-(SB-7401A_MODIF)
BNO-001252-300-CB-3328-004-AOL-00001 | WORK METHOD STATEMENT/INSTALLATION PROCEDURE | CB - ARCHITECTURAL | CB - ARCHITECTURAL | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / ABB / PO_001252-(SB-7401A_MODIF)
BNO-001252-300-EA-2384-004-AOL-00001 | ESSENTIAL LOADS SWITCHBOARD SB-7401A/B-E-01 - DESIGN BOOK FOR NEW SECTIONS | ELECTRICAL | EA - ELECTRICAL | A04 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / ABB / PO_001252-(SB-7401A_MODIF)
BNO-001252-300-FA-5765-004-AOL-00001 | PROJECT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 4 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / ABB / PO_001252-(SB-7401A_MODIF)
BNO-001252-300-HX-0709-004-AOL-00001 | MODIFICATION WORK RISK ASSESSMENT | TECHNICAL SAFETY | HX - HSE | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / ABB / PO_001252-(SB-7401A_MODIF)
BNO-001252-300-JA-6611-040-AOL-00001 | SUPPLIER LIST | IT / IM | JA - IM | A01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / ABB / PO_001252-(SB-7401A_MODIF)
BNO-001252-300-OA-4811-004-AOL-00001 | INSTALATION OPERATION AND MAINTENANCE MANUAL | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / ABB / PO_001252-(SB-7401A_MODIF)
BNO-001252-300-QA-1580-004-AOL-00001 | INTERNAL TEST CERTIFICATES | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / ABB / PO_001252-(SB-7401A_MODIF)
BNO-001252-300-QA-5733-004-AOL-00001 | INSPECTION AND TEST PLAN | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / ABB / PO_001252-(SB-7401A_MODIF)
BNO-001252-300-QA-5733-004-AOL-00002 | TEST RECORD FORMS | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / ABB / PO_001252-(SB-7401A_MODIF)
BNO-001252-300-QA-5798-004-AOL-00001 | QUALITY PLAN | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / ABB / PO_001252-(SB-7401A_MODIF)
BNO-001252-300-QA-6050-004-AOL-00001 | FACTORY ACCEPTANCE TEST PROCEDURE | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / ABB / PO_001252-(SB-7401A_MODIF)
BNO-001252-300-SA-6028-004-AOL-00001 | STORAGE &PRESERVATION PROCEDURE | SA - LOGISTICS | SA - LOGISTICS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / ABB / PO_001252-(SB-7401A_MODIF)
BNO-001252-300-SA-6028-004-AOL-00002 | PACKING SPECIFICATION | SA - LOGISTICS | SA - LOGISTICS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / ABB / PO_001252-(SB-7401A_MODIF)
BNO-001252-300-VA-1453-004-AOL-00001 | CERTIFICATE OF CONFORMITY | VA - PROCUREMENT | VA - PROCUREMENT | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / ABB / PO_001252-(SB-7401A_MODIF)
BNO-001369-300-FA-5803-002-AOL-00001 | ENGINEERING FABRICATION INSPECTION AND TESTING SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / FLOWSERVE / PO_001369-SMART-CHOKE VALVES
BNO-001369-300-IN-2105-002-AOL-00001 | SPECIFICATION SHEET | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / FLOWSERVE / PO_001369-SMART-CHOKE VALVES
BNO-001369-300-IN-3328-002-AOL-00001 | INSTALLATION OPERATION AND MAINTENANCE MANUALS | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / FLOWSERVE / PO_001369-SMART-CHOKE VALVES
BNO-001369-300-IN-4018-002-AOL-00001 | GENERAL ARRANGEMENT DRAWING WITH ELECTRICAL SCHEMATIC POSITIONER AND NAMEPLATE DRAWING - SMART CHOKE VALVE | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / FLOWSERVE / PO_001369-SMART-CHOKE VALVES
BNO-001369-300-IN-6067-002-AOL-00001 | TEST PROCEDURE | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / FLOWSERVE / PO_001369-SMART-CHOKE VALVES
BNO-001369-300-IN-7880-002-AOL-00001 | EQUIPMENT BROCHURES AND CATALOGUES | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / FLOWSERVE / PO_001369-SMART-CHOKE VALVES
BNO-001369-300-JA-4372-002-AOL-00001 | DATABOOK | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / FLOWSERVE / PO_001369-SMART-CHOKE VALVES
BNO-001369-300-JA-6611-002-AOL-00001 | VENDOR DATA REGISTER LIST FOR SMART-CHOKE VALVES (VDRL) | IT / IM | JA - IM | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / FLOWSERVE / PO_001369-SMART-CHOKE VALVES
BNO-001369-300-NA-4354-002-AOL-00001 | SPARE PARTS FOR PRE-COMMISSIONING COMMISSIONING AND START-UP | NA - MAINTENANCE | NA - MAINTENANCE | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / FLOWSERVE / PO_001369-SMART-CHOKE VALVES
BNO-001369-300-NA-4354-002-AOL-00002 | SPARE PART LISTS FOR TWO YEARS | NA - MAINTENANCE | NA - MAINTENANCE | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / FLOWSERVE / PO_001369-SMART-CHOKE VALVES
BNO-001369-300-OA-4811-002-AOL-00001 | PACKING SHIPPING AND PRESERVATION PROCEDURE | OA - OPERATIONS | OA - OPERATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / FLOWSERVE / PO_001369-SMART-CHOKE VALVES
BNO-001369-300-QA-1580-002-AOL-00001 | SAFETY INTEGRITY LEVEL (SIL) CERTIFICATES | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / FLOWSERVE / PO_001369-SMART-CHOKE VALVES
BNO-001369-300-QA-1580-002-AOL-00002 | ENCLOSURE HAZARDOUS AREA AND PROTECTION DEGREE CERTIFICATE | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / FLOWSERVE / PO_001369-SMART-CHOKE VALVES
BNO-001369-300-QA-1580-002-AOL-00003 | MATERIAL TEST CERTIFICATE | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / FLOWSERVE / PO_001369-SMART-CHOKE VALVES
BNO-001369-300-QA-1580-002-AOL-00004 | CALIBRATION TEST CERTIFICATE | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / FLOWSERVE / PO_001369-SMART-CHOKE VALVES
BNO-001369-300-QA-3880-002-AOL-00001 | INSPECTION REPORT | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / FLOWSERVE / PO_001369-SMART-CHOKE VALVES
BNO-001369-300-QA-5733-002-AOL-00001 | INSPECTION AND TEST PLAN | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / FLOWSERVE / PO_001369-SMART-CHOKE VALVES
BNO-001369-300-QA-6050-002-AOL-00001 | QUALITY ASSURANCE AND QUALITY SYSTEM PLAN | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / FLOWSERVE / PO_001369-SMART-CHOKE VALVES
BNO-001369-300-RA-6068-002-AOL-00001 | PAINTING PROCEDURE | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / FLOWSERVE / PO_001369-SMART-CHOKE VALVES
BNO-001438-300-BA-6065-040-AOL-00001 | WELDING PROCEDURE SPECIFICATION (WPS) & PQRS | CONSTRUCTION | BA - CONSTRUCTION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / NEWAY / PO_001438-API6A_MANUAL_VALVES
BNO-001438-300-FA-5803-040-AOL-00001 | PRODUCTION SCHEDULE / MANUFACTURING TIMELINE | FA - COST AND PLANNING | FA - COST AND PLANNING | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / NEWAY / PO_001438-API6A_MANUAL_VALVES
BNO-001438-300-JA-6611-040-AOL-00001 | VENDOR DATA REGISTER LIST (VDRL) | IT / IM | JA - IM | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / NEWAY / PO_001438-API6A_MANUAL_VALVES
BNO-001438-300-MP-2105-040-AOL-00001 | BALL VALVES DATASHEETS | PIPING | MP - PIPING | C01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / NEWAY / PO_001438-API6A_MANUAL_VALVES
BNO-001438-300-MP-2105-040-AOL-00002 | CHECK VALVES DATASHEETS | PIPING | MP - PIPING | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / NEWAY / PO_001438-API6A_MANUAL_VALVES
BNO-001438-300-MP-2105-040-AOL-00003 | DBB VALVES DATASHEETS | NÃO SE APLICA | NÃO SE APLICA | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / NEWAY / PO_001438-API6A_MANUAL_VALVES
BNO-001438-300-MP-2105-040-AOL-00004 | DUAL SPRING CHECK VALVES DATASHEETS | PIPING | MP - PIPING | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / NEWAY / PO_001438-API6A_MANUAL_VALVES
BNO-001438-300-MP-4018-040-AOL-00001-001 | BALL VALVES GENERAL ARRANGEMENT (GA) DRAWINGS | PIPING | MP - PIPING | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / NEWAY / PO_001438-API6A_MANUAL_VALVES
BNO-001438-300-MP-4018-040-AOL-00002-001 | CHECK VALVES 10.000 PSI GENERAL ARRANGEMENT (GA) DRAWINGS | PIPING | MP - PIPING | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / NEWAY / PO_001438-API6A_MANUAL_VALVES
BNO-001438-300-MP-4018-040-AOL-00003-001 | DBB VALVES 10.000 PSI GENERAL ARRANGEMENT (GA) DRAWINGS | PIPING | MP - PIPING | C02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / NEWAY / PO_001438-API6A_MANUAL_VALVES
BNO-001438-300-MP-4018-040-AOL-00004-001 | VALVES NAMEPLATE DRAWINGS | PIPING | MP - PIPING | C01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / NEWAY / PO_001438-API6A_MANUAL_VALVES
BNO-001438-300-MP-4018-040-AOL-00005-001 | DUAL SPRING CHECK VALVES GENERAL ARRANGEMENT (GA) DRAWINGS | PIPING | MP - PIPING | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / NEWAY / PO_001438-API6A_MANUAL_VALVES
BNO-001438-300-MP-4018-040-AOL-00006-001 | DBB VALVES 10.000 PSI GENERAL ARRANGEMENT (GA) DRAWINGS | PIPING | MP - PIPING | A02 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / NEWAY / PO_001438-API6A_MANUAL_VALVES
BNO-001438-300-MP-4354-040-AOL-00001 | SPARE PARTS LIST & RECOMMENDED SPARES | PIPING | MP - PIPING | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / NEWAY / PO_001438-API6A_MANUAL_VALVES
BNO-001438-300-MP-4354-040-AOL-00002 | SPARE PARTS LIST & RECOMMENDED SPARES - NEWAY DUAL SPRING CHECK VALVES | PIPING | MP - PIPING | R01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / NEWAY / PO_001438-API6A_MANUAL_VALVES
BNO-001438-300-MX-6067-040-AOL-00001 | NEWAY NDE PROCEDURES | MECHANICAL | MX - OVERAL MECHANICAL | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / NEWAY / PO_001438-API6A_MANUAL_VALVES
BNO-001438-300-OA-4811-040-AOL-00001 | O&M MANUALS | OA - OPERATIONS | OA - OPERATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / NEWAY / PO_001438-API6A_MANUAL_VALVES
BNO-001438-300-QA-5733-040-AOL-00001 | INSPECTION & TEST PLAN (ITP) FOR MANUAL VALVES | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / NEWAY / PO_001438-API6A_MANUAL_VALVES
BNO-001438-300-QA-6050-040-AOL-00001 | MANUFACTURING QUALITY PLAN (MQP) | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / NEWAY / PO_001438-API6A_MANUAL_VALVES
BNO-001438-300-QA-6050-040-AOL-00002 | PRESSURE TESTING PROCEDURE | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / NEWAY / PO_001438-API6A_MANUAL_VALVES
BNO-001438-300-QA-6050-040-AOL-00004 | PACKING PRESERVATION & MARKING PROCEDURE | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / NEWAY / PO_001438-API6A_MANUAL_VALVES
BNO-001438-300-RA-1580-040-AOL-00001 | MATERIAL TEST CERTIFICATES (MTC) | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / NEWAY / PO_001438-API6A_MANUAL_VALVES
BNO-001438-300-RA-6068-040-AOL-00001 | NEWAY PAINTING PROCEDURE | MATERIALS | RA - MATERIALS | A02 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / NEWAY / PO_001438-API6A_MANUAL_VALVES
BNO-001438-300-VA-1453-040-AOL-00001 | CERTIFICATE OF COMPLIANCE (COC) | VA - PROCUREMENT | VA - PROCUREMENT | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / NEWAY / PO_001438-API6A_MANUAL_VALVES
BNO-001438-300-VA-4305-040-AOL-00001 | LIST OF SUB SUPPLIERS | VA - PROCUREMENT | VA - PROCUREMENT | C01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / NEWAY / PO_001438-API6A_MANUAL_VALVES
BNO-001537-300-JA-6611-021-AOL-00001 | BARRED TEE SDRL | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 |  |  | BNO / 03-VENDOR / NANFANG / PO_001537-BARRED TEE
BNO-001537-300-MP-4018-021-AOL-00001-001 | BARRED TEE DRAWING | PIPING | MP - PIPING | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 2 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / NANFANG / PO_001537-BARRED TEE
BNO-001537-300-QA-5733-021-AOL-00001 | INSPECTION & TEST PLAN (ITP) FOR BARRED TEE | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / NANFANG / PO_001537-BARRED TEE
BNO-001537-300-QA-5733-021-AOL-00002 | INSPECTION & TEST PLAN (ITP) FOR FITTINGS | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / NANFANG / PO_001537-BARRED TEE
BNO-001537-300-QA-6065-021-AOL-00001 | WELDING PROCEDURE SPECIFICATION (WPS) & PQR FOR BARRED TEE | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / NANFANG / PO_001537-BARRED TEE
BNO-001686-300-BA-6065-040-AOL-00001 | WPS & PQR FOR SDSS FITTINGS | CONSTRUCTION | BA - CONSTRUCTION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PFF_GROUP / PO_001686-FITTINGS SDSS
BNO-001686-300-JA-6611-040-AOL-00001 | VENDOR DOCUMENT REGISTER LIST | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PFF_GROUP / PO_001686-FITTINGS SDSS
BNO-001686-300-QA-5733-040-AOL-00001 | INSPECTION AND TEST PLAN FOR SDSS FITTINGS | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PFF_GROUP / PO_001686-FITTINGS SDSS
BNO-001798-300-FA-5803-044-AOL-00001 | ENGINEERING. FABRICATION. INSPECTION AND TESTING SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001798-CORIOLIS_FLOWMETER
BNO-001798-300-IN-2105-044-AOL-00001 | TECHNICAL DATASHEET / SPECIFICATION CORIOLIS FLOW METERS PROJECT | INSTRUMENTATION | IN - INSTRUMENTATION | R03 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001798-CORIOLIS_FLOWMETER
BNO-001798-300-IN-2105-044-AOL-00002 | SIZING CALCULATION SHEET | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001798-CORIOLIS_FLOWMETER
BNO-001798-300-IN-4018-044-AOL-00001-001 | GENERAL ARRANGEMENT DRAWING (GAD) CORIOLIS FLOW METERS | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001798-CORIOLIS_FLOWMETER
BNO-001798-300-IN-4018-044-AOL-00002-001 | WIRING DIAGRAM CORIOLIS FLOW METERS | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001798-CORIOLIS_FLOWMETER
BNO-001798-300-IN-4018-044-AOL-00003-001 | IDENTIFICATION PLATES DRAWINGS CORIOLIS FLOW METERS | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001798-CORIOLIS_FLOWMETER
BNO-001798-300-JA-4372-044-AOL-00001 | DATABOOK | IT / IM | JA - IM | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001798-CORIOLIS_FLOWMETER
BNO-001798-300-JA-6611-044-AOL-00001 | VENDOR DATA REGISTER LIST (VDRL) CORIOLIS FLOW METERS | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001798-CORIOLIS_FLOWMETER
BNO-001798-300-NA-4354-044-AOL-00001 | SPARE PART LISTS FOR TWO YEARS | NA - MAINTENANCE | NA - MAINTENANCE | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001798-CORIOLIS_FLOWMETER
BNO-001798-300-OA-4811-044-AOL-00001 | OPERATION MANUAL | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001798-CORIOLIS_FLOWMETER
BNO-001798-300-QA-5733-044-AOL-00001 | INSPECTION AND TEST PLAN | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001798-CORIOLIS_FLOWMETER
BNO-001798-300-RA-1580-044-AOL-00001 | MATERIAL CERTIFICATE | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001798-CORIOLIS_FLOWMETER
BNO-001798-300-RA-1580-044-AOL-00002 | CALIBRATION CERTIFICATE | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001798-CORIOLIS_FLOWMETER
BNO-001798-300-RA-1580-044-AOL-00003 | ENCLOSURE HAZARDOUS AREA CERTIFICATE | MATERIALS | RA - MATERIALS | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001798-CORIOLIS_FLOWMETER
BNO-001798-300-RA-6068-044-AOL-00001 | PAINTING PROCEDURE | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001798-CORIOLIS_FLOWMETER
BNO-001798-300-SA-6028-044-AOL-00001 | PACKING AND PRESERVATION PROCEDURE | SA - LOGISTICS | SA - LOGISTICS | R01 | NAO |  | Diretorio Vendor | ENGINEERING CONSOLIDATION |  |  |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001798-CORIOLIS_FLOWMETER
BNO-001806-300-AA-6944-083-AOL-00001 | PRODUCTION SCHEDULE FOR DRAEGER DETECTORS (POINT GD & OPGD) | PMT | AA - PROJECT MANAGEMENT | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / DRAEGER / PO_001806-GAS_DETECTOR
BNO-001806-300-IN-1580-083-AOL-00001 | SIL CERTIFICATES FOR OPEN PATH GAS DETECTORS | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DRAEGER / PO_001806-GAS_DETECTOR
BNO-001806-300-IN-1580-083-AOL-00002 | ENCLOSURE HAZARDOUS AREA AND PROTECTION DEGREE CERTIFICATE FOR OPEN PATH DETECTION | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / DRAEGER / PO_001806-GAS_DETECTOR
BNO-001806-300-IN-1580-083-AOL-00003 | SIL CERTIFICATES FOR POINT TYPE GAS DETECTORS | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / DRAEGER / PO_001806-GAS_DETECTOR
BNO-001806-300-IN-1580-083-AOL-00004 | ENCLOSURE HAZARDOUS AREA AND PROTECTION DEGREE CERTIFICATE FOR POINT TYPE DETECTOR | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / DRAEGER / PO_001806-GAS_DETECTOR
BNO-001806-300-IN-2105-083-AOL-00001 | TECHNICAL DATASHEET/SPECIFICATION - POINT TYPE GAS DETECTOR | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DRAEGER / PO_001806-GAS_DETECTOR
BNO-001806-300-IN-2105-083-AOL-00002 | TECHNICAL DATASHEET/SPECIFICATION - OPEN PATH GAS DETECTOR | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DRAEGER / PO_001806-GAS_DETECTOR
BNO-001806-300-IN-2105-083-AOL-00003 | PAINTING PROCEDURE - POINT TYPE GAS DETECTOR | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / DRAEGER / PO_001806-GAS_DETECTOR
BNO-001806-300-IN-4018-083-AOL-00001 | DIMENSIONAL DRAWING - POINT TYPE GAS DETECTOR | INSTRUMENTATION | IN - INSTRUMENTATION | A04 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / DRAEGER / PO_001806-GAS_DETECTOR
BNO-001806-300-IN-4018-083-AOL-00002 | DIMENSIONAL DRAWING - OPEN PATH GAS DETECTOR | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / DRAEGER / PO_001806-GAS_DETECTOR
BNO-001806-300-JA-4372-083-AOL-00001 | MANUFACTURING DATA BOOK | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DRAEGER / PO_001806-GAS_DETECTOR
BNO-001806-300-JA-6611-083-AOL-00001 | DOCUMENTS/DRAWING LIST - OPEN PATH AND POINT TYPE DETECTORS | IT / IM | JA - IM | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / DRAEGER / PO_001806-GAS_DETECTOR
BNO-001806-300-NA-4354-083-AOL-00001 | SPARE PARTS LIST - OPEN PATH GAS DETECTOR | NA - MAINTENANCE | NA - MAINTENANCE | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / DRAEGER / PO_001806-GAS_DETECTOR
BNO-001806-300-NA-4354-083-AOL-00002 | SPARE PARTS LIST - POINT TYPE GAS DETECTOR | NA - MAINTENANCE | NA - MAINTENANCE | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / DRAEGER / PO_001806-GAS_DETECTOR
BNO-001806-300-QA-5733-083-AOL-00001 | INSPECTION AND TEST PLAN - FIRE AND GAS DETECTION | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / DRAEGER / PO_001806-GAS_DETECTOR
BNO-001806-300-QA-5733-083-AOL-00002 | FACTORY ACCEPTANCE TEST (FAT) PROCEDURE | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / DRAEGER / PO_001806-GAS_DETECTOR
BNO-001806-300-QA-5733-083-AOL-00003 | FACTORY ACCEPTANCE TEST (FAT) RECORDS | QA - QUALITY | QA - QUALITY | R02 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / DRAEGER / PO_001806-GAS_DETECTOR
BNO-001853-300-FA-5803-002-AOL-00001 | (PIG SIGNALLER) ENGINEERING FABRICATION INSPECTION AND TESTING SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-FA-5803-002-AOL-01001 | (SAND DETECTOR) ENGINEERING FABRICATION INSPECTION AND TESTING SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 2 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-IN-1580-002-AOL-00001 | (PIG SIGNALLER) ENCLOSURE HAZARDOUS AREA AND PROTECTION DEGREE CERTIFICATE | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-IN-1580-002-AOL-00002 | (PIG SIGNALLER) CERTIFICATE OF CONFORMITY | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-IN-1580-002-AOL-00003 | (PIG SIGNALLER) EU DECLARATION OF CONFORMITY | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-IN-1580-002-AOL-00004 | (PIG SIGNALLER) MATERIAL CERTIFICATES TSE.DS2I.SA00.A11 WITH PMI TEST REPORT | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-IN-1580-002-AOL-01001 | (SAND DETECTOR) ENCLOSURE HAZARDOUS AREA AND PROTECTION DEGREE CERTIFICATE | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-IN-1580-002-AOL-01002 | (SAND DETECTOR) CERTIFICATE OF CONFORMITY | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-IN-1580-002-AOL-01003 | (SAND DETECTOR) EU DECLARATION OF CONFORMITY | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-IN-1580-002-AOL-01004 | (SAND DETECTOR) MATERIAL CERTIFICATES TSE.DS2I.SA00.A10 WITH PMI TEST REPORT | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-IN-2105-002-AOL-00001 | (PIG SIGNALLER) TECHNICAL DATASHEET/SPECIFICATION | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-IN-2105-002-AOL-00002 | (PIG SIGNALLER) MODBUS MAPPING FOR PIG DETECTOR | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-IN-2105-002-AOL-01001 | (SAND DETECTOR) TECHNICAL DATASHEET/SPECIFICATION | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-IN-2105-002-AOL-01002 | (SAND DETECTOR) MODBUS MAPPING FOR SAND MONITOR | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-IN-2105-002-AOL-01003 | (SAND DETECTOR) SOFTWARE MANUAL | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-IN-4018-002-AOL-00001 | (PIG SIGNALLER) IDENTIFICATION PLATES DRAWINGS - SAND DETECTOR CLAMPON DSP PARTICLE MONITOR EX IA | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-IN-4018-002-AOL-00002 | (PIG SIGNALLER) WIRING DIAGRAM | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-IN-4018-002-AOL-01001 | IDENTIFICATION PLATE DRAWING - SAND DETECTOR CLAMPON DSP PARTICLE MONITOR EX IA | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-IN-4018-002-AOL-01002 | (SAND DETECTOR) WIRING DIAGRAM | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-IN-4354-002-AOL-00003 | (PIG SIGNALLER) SPARE PARTS LIST | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-IN-4354-002-AOL-01001 | (SAND DETECTOR) SPARE PARTS LIST | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-IN-7880-002-AOL-00001 | (PIG SIGNALLER) DIMENSIONAL DRAWING WITH WEIGHT | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-IN-7880-002-AOL-01001 | (SAND DETECTOR) DIMENSIONAL DRAWING WITH WEIGHT & COMPONENT LIST | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-JA-4372-002-AOL-00001 | (PIG SIGNALLER) DATABOOK INDEX | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-JA-4372-002-AOL-00002 | (PIG SIGNALLER) DATABOOK | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-JA-4372-002-AOL-01001 | (SAND DETECTOR) DATABOOK INDEX | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-JA-4372-002-AOL-01002 | (SAND DETECTOR) DATABOOK | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-JA-6611-002-AOL-00001 | DOCUMENT/DRAWING LIST (PIG SIGNALLER) | IT / IM | JA - IM | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-JA-6611-002-AOL-01001 | DOCUMENT/DRAWING LIST (SAND DETECTOR) | IT / IM | JA - IM | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-OA-4811-002-AOL-00001 | (PIG SIGNALLER) INSTALLATION AND MAINTENANCE INSTRUCTIONS | OA - OPERATIONS | OA - OPERATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-OA-4811-002-AOL-01001 | (SAND DETECTOR) INSTALLATION AND MAINTENANCE INSTRUCTIONS | OA - OPERATIONS | OA - OPERATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-QA-5733-002-AOL-00001 | (PIG SIGNALLER) FACTORY ACCEPTANCE TEST PROCEDURE - TOPSIDE PIG DETECTION SYSTEM | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-QA-5733-002-AOL-00002 | (PIG SIGNALLER) FAT REPORT PIG DETECTOR | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-QA-5733-002-AOL-00003 | (PIG SIGNALLER) QA PLAN WITH INSPECTION AND TEST PLAN | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-QA-5733-002-AOL-00004 | (PIG SIGNALLER) PMI PROCEDURE | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-QA-5733-002-AOL-01001 | (SAND DETECTOR) FACTORY ACCEPTANCE TEST PROCEDURE - TOPSIDE PARTICLE MONITORING SYSTEM | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-QA-5733-002-AOL-01002 | (SAND DETECTOR) FAT REPORT - SAND MONITOR | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-QA-5733-002-AOL-01003 | (SAND DETECTOR) QA PLAN WITH INSPECTION AND TEST | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-QA-5733-002-AOL-01004 | (SAND DETECTOR) PMI PROCEDURE | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-SA-6028-002-AOL-00001 | (PIG SIGNALLER) PACKING AND PRESERVATION PROCEDURE | SA - LOGISTICS | SA - LOGISTICS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001853-300-SA-6028-002-AOL-01001 | (SAND DETECTOR) HANDLING TRANSPORTATION AND PRESERVATION PROCEDURE | SA - LOGISTICS | SA - LOGISTICS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / CLAMPON / PO_001853-PIG_SIGNALER_AND_SAND_DTC
BNO-001925-300-FA-5803-040-AOL-00001 | PRESSURE RELIEF VALVES - MANUFACTURING SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / EMERSON / PO_001925-PRESS. RELIEF VALVE
BNO-001925-300-IN-2105-040-AOL-00001 | PRESSURE RELIEF VALVES - SIZING AND SELECTION REPORT | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | TRANSMITTAL |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / EMERSON / PO_001925-PRESS. RELIEF VALVE
BNO-001925-300-IN-2105-040-AOL-00002 | PRESSURE RELIEF VALVES - CALCULATION REPORT | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / EMERSON / PO_001925-PRESS. RELIEF VALVE
BNO-001925-300-IN-4018-040-AOL-00001-001 | PRESSURE RELIEF VALVES - DIMENSIONAL DRAWING | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / EMERSON / PO_001925-PRESS. RELIEF VALVE
BNO-001925-300-IN-4018-040-AOL-00002-001 | PRESSURE RELIEF VALVES - IDENTIFICATION PLATES DRAWINGS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / EMERSON / PO_001925-PRESS. RELIEF VALVE
BNO-001925-300-JA-4372-040-AOL-00001 | PRESSURE RELIEF VALVES - DATA BOOK | IT / IM | JA - IM | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / EMERSON / PO_001925-PRESS. RELIEF VALVE
BNO-001925-300-JA-6611-040-AOL-00001 | PRESSURE RELIEF VALVES - DOCUMENTS/DRAWINGLIST | IT / IM | JA - IM | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / EMERSON / PO_001925-PRESS. RELIEF VALVE
BNO-001925-300-NA-4354-040-AOL-00001 | PRESSURE RELIEF VALVES - SPARE PART LIST FOR 2 YEARS | NA - MAINTENANCE | NA - MAINTENANCE | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / EMERSON / PO_001925-PRESS. RELIEF VALVE
BNO-001925-300-NA-4354-040-AOL-00002 | PRESSURE RELIEF VALVES - SERIES CATALOGUE | NA - MAINTENANCE | NA - MAINTENANCE | C01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / EMERSON / PO_001925-PRESS. RELIEF VALVE
BNO-001925-300-QA-5733-040-AOL-00001 | PRESSURE RELIEF VALVES - INSPECTION AND TEST PLAN (FAT AND SAT) | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / EMERSON / PO_001925-PRESS. RELIEF VALVE
BNO-001925-300-QA-5733-040-AOL-00002 | PRESSURE RELIEF VALVES - FUNCTIONAL TEST PROCEDURE | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / EMERSON / PO_001925-PRESS. RELIEF VALVE
BNO-001925-300-QA-5733-040-AOL-00003 | PRESSURE RELIEF VALVES - PACKING AND STORAGE PROCEDURE | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / EMERSON / PO_001925-PRESS. RELIEF VALVE
BNO-001925-300-QA-5733-040-AOL-00004 | PRESSURE RELIEF VALVES - HYDRO TEST PROCEDURE | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / EMERSON / PO_001925-PRESS. RELIEF VALVE
BNO-001925-300-QA-5733-040-AOL-00005 | PRESSURE RELIEF VALVES - PMI PROCEDURE | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / EMERSON / PO_001925-PRESS. RELIEF VALVE
BNO-001925-300-RA-1580-040-AOL-00001 | PRESSURE RELIEF VALVES - MATERIAL CERTIFICATE | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / EMERSON / PO_001925-PRESS. RELIEF VALVE
BNO-001925-300-RA-1580-040-AOL-00002 | PRESSURE RELIEF VALVES - CALIBRATION CERTIFICATE | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / EMERSON / PO_001925-PRESS. RELIEF VALVE
BNO-001925-300-RA-1580-040-AOL-00003 | PRESSURE RELIEF VALVES - MANUFACTURER'S DATA REPORT (ASME UV FORM) | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / EMERSON / PO_001925-PRESS. RELIEF VALVE
BNO-001925-300-RA-6068-040-AOL-00001 | PRESSURE RELIEF VALVES - PAINTING PROCEDURE | MATERIALS | RA - MATERIALS | R02 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / EMERSON / PO_001925-PRESS. RELIEF VALVE
BNO-001926-300-FA-5803-008-AOL-00001 | ENGINEERING. FABRICATION. INSPECTION AND TESTING SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001926-PRESS_INDCT_TRANSMITER
BNO-001926-300-IN-2105-008-AOL-00001 | TECHNICAL DATASHEET / SPECIFICATION FOR PRESSURE INDICATING TRANSMITTER AND DIFFERENTIAL PRESSURE INDICATING TRANSMITTER | INSTRUMENTATION | IN - INSTRUMENTATION | R04 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001926-PRESS_INDCT_TRANSMITER
BNO-001926-300-IN-4018-008-AOL-00001-001 | GENERAL ARRANGEMENT DRAWING (GAD) (ALONG WITH BILL OF MATERIAL) FOR PRESSURE INDICATING TRANSMITTER AND DIFFERENTIAL PRESSURE INDICATING TRANSMITTER PROJECT | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001926-PRESS_INDCT_TRANSMITER
BNO-001926-300-IN-4018-008-AOL-00002-001 | WIRING DIAGRAM FOR PRESSURE INDICATING TRANSMITTER AND DIFFERENTIAL PRESSURE INDICATING TRANSMITTER | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001926-PRESS_INDCT_TRANSMITER
BNO-001926-300-IN-4018-008-AOL-00003-001 | IDENTIFICATION PLATES DRAWINGS FOR PRESSURE INDICATING TRANSMITTER AND DIFFERENTIAL PRESSURE INDICATING TRANSMITTER PROJECT | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001926-PRESS_INDCT_TRANSMITER
BNO-001926-300-JA-4372-008-AOL-00001 | DATABOOK (WITH INDEX) | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001926-PRESS_INDCT_TRANSMITER
BNO-001926-300-JA-6611-008-AOL-00001 | VENDOR DATA REGISTER LIST (VDRL) FOR PRESSURE INDICATING TRANSMITTER AND DIFFERENTIAL PRESSURE INDICATING TRANSMITTER | IT / IM | JA - IM | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION | IFA RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001926-PRESS_INDCT_TRANSMITER
BNO-001926-300-NA-4354-008-AOL-00001 | SPARE PART LISTS FOR TWO YEARS FOR PRESSURE INDICATING TRANSMITTER AND DIFFERENTIAL PRESSURE INDICATING TRANSMITTER | NA - MAINTENANCE | NA - MAINTENANCE | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001926-PRESS_INDCT_TRANSMITER
BNO-001926-300-OA-4811-008-AOL-00001 | OPERATION MANUAL FOR PRESSURE INDICATING TRANSMITTER AND DIFFERENTIAL PRESSURE INDICATING TRANSMITTER | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001926-PRESS_INDCT_TRANSMITER
BNO-001926-300-QA-5733-008-AOL-00001 | ITP FOR PRESSURE INDICATING TRANSMITTER AND DIFFERENTIAL PRESSURE INDICATING TRANSMITTER | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001926-PRESS_INDCT_TRANSMITER
BNO-001926-300-RA-1580-008-AOL-00001 | MATERIAL CERTIFICATE | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001926-PRESS_INDCT_TRANSMITER
BNO-001926-300-RA-1580-008-AOL-00002 | CALIBRATION CERTIFICATE | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001926-PRESS_INDCT_TRANSMITER
BNO-001926-300-RA-1580-008-AOL-00003 | ENCLOSURE HAZARDOUS AREA CERTIFICATE FOR PRESSURE INDICATING TRANSMITTER AND DIFFERENTIAL PRESSURE INCATING TRANSMITTER | MATERIALS | RA - MATERIALS | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001926-PRESS_INDCT_TRANSMITER
BNO-001926-300-RA-1580-008-AOL-00004 | PMI TEST REPORT | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001926-PRESS_INDCT_TRANSMITER
BNO-001926-300-RA-1580-008-AOL-00005 | SIL CERTIFICATE IN ACCORDANCE WITH IEC-61508/IEC-61511 (ONLY FOR APPLICABLE TAGS) FOR PRESSURE INDICATING TRANSMITTER AND DIFFERENTIAL PRESSURE INDICATING TRANSMITTER | MATERIALS | RA - MATERIALS | C02 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001926-PRESS_INDCT_TRANSMITER
BNO-001926-300-RA-6068-008-AOL-00001 | PAINTING PROCEDURE FOR PRESSURE INDICATING TRANSMITTER AND DIFFERENTIAL PRESSURE INDICATING TRANSMITTER | MATERIALS | RA - MATERIALS | R03 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001926-PRESS_INDCT_TRANSMITER
BNO-001926-300-SA-6028-008-AOL-00001 | PACKING AND PRESERVATION PROCEDURE FOR PRESSURE INDICATING TRANSMITTER AND DIFFERENTIAL PRESSURE INCATING TRANSMITTER | SA - LOGISTICS | SA - LOGISTICS | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / ENDRESS_AND_HAUSER / PO_001926-PRESS_INDCT_TRANSMITER
BNO-001927-300-JA-6611-040-AOL-00001 | BASKET STRAINER (SP-08814) - DOCUMENTS/DRAWING LIST | IT / IM | JA - IM | C02 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / BARTON / PO_001927-STRAINER
BNO-001927-300-MS-1379-040-AOL-00001 | BASKET STRAINER (SP-08814) - DESIGN CALCULATIONS | MECHANICAL | MS - MECHANICAL STATIC | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / BARTON / PO_001927-STRAINER
BNO-001927-300-MS-2105-040-AOL-00001 | BASKET STRAINER (SP-08814) - EQUIPMENT DATA SHEETS | MECHANICAL | MS - MECHANICAL STATIC | C01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / BARTON / PO_001927-STRAINER
BNO-001927-300-MX-4018-040-AOL-00001-001 | BASKET STRAINER (SP-08814) - GENERAL ARRANGEMENT TO WATERFLOOD INJECTION PUMP (P-4047) (GAD) | PIPING | MP - PIPING | C02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / BARTON / PO_001927-STRAINER
BNO-001927-300-NA-4354-040-AOL-00001 | BASKET STRAINER (SP-08814) - SPARE PARTS RECOMMENDED LIST | PIPING | MP - PIPING | C02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / BARTON / PO_001927-STRAINER
BNO-001927-300-QA-5733-040-AOL-00001 | BASKET STRAINER (SP-08814) - INSPECTION & TEST PLAN | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / BARTON / PO_001927-STRAINER
BNO-001927-300-QA-5733-040-AOL-00002 | BASKET STRAINER (SP-08814) - HYDRO TEST REPORT | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / BARTON / PO_001927-STRAINER
BNO-001927-300-QA-5733-040-AOL-00003 | BASKET STRAINER (SP-08814) - PMI TEST RESULTS | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / BARTON / PO_001927-STRAINER
BNO-001927-300-QA-6050-040-AOL-00001 | BASKET STRAINER (SP-08814) - HYDROTEST PROCEDURE | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / BARTON / PO_001927-STRAINER
BNO-001927-300-RA-1580-040-AOL-00001 | BASKET STRAINER (SP-08814) - MATERIAL CERTIFICATES 3.1 | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / BARTON / PO_001927-STRAINER
BNO-001927-300-RA-6068-040-AOL-00001 | BASKET STRAINER (SP-08814) - PAINTING & COATING PROCEDURE | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / BARTON / PO_001927-STRAINER
BNO-001954-300-FA-5803-040-AOL-00001 | GLOBE VALVES - PRODUCTION SCHEDULE / MANUFACTURING TIMELINE | FA - COST AND PLANNING | FA - COST AND PLANNING | A02 | NAO |  | Diretorio Vendor | ENGINEERING CONSOLIDATION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / NEWAY / PO_001954-API6A_GLOBE_VALVES
BNO-001954-300-JA-6611-040-AOL-00001 | GLOBE VALVES - VENDOR DATA REGISTER LIST | IT / IM | JA - IM | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / NEWAY / PO_001954-API6A_GLOBE_VALVES
BNO-001954-300-MP-2105-040-AOL-00001 | GLOBE VALVES - DATASHEETS | PIPING | MP - PIPING | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / NEWAY / PO_001954-API6A_GLOBE_VALVES
BNO-001954-300-MX-4024-040-AOL-00001-001 | GLOBE VALVES - 10.000 PSI GENERAL ARRANGEMENT (GA) DRAWINGS | PIPING | MP - PIPING | C02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / NEWAY / PO_001954-API6A_GLOBE_VALVES
BNO-001954-300-NA-4354-040-AOL-00001 | GLOBE VALVES - SPARE PARTS LIST & RECOMMENDED SPARES | NA - MAINTENANCE | NA - MAINTENANCE | C01 | NAO |  | Diretorio Vendor | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / NEWAY / PO_001954-API6A_GLOBE_VALVES
BNO-001954-300-RA-1580-040-AOL-00001 | GLOBE VALVES - MATERIAL TEST CERTIFICATES (MTC) | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / NEWAY / PO_001954-API6A_GLOBE_VALVES
BNO-001954-300-VA-1453-040-AOL-00001 | GLOBE VALVES - CERTIFICATE OF COMPLIANCE (COC) | VA - PROCUREMENT | VA - PROCUREMENT | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / NEWAY / PO_001954-API6A_GLOBE_VALVES
BNO-001962-300-IN-2105-008-AOL-00001 | INSTRUMENT DATA SHEET OF PRESSURE GAUGE | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / WIKA / PO_001962-PRESSURE GAUGE AND TEMPERATURE GAUGE
BNO-001962-300-IN-2105-008-AOL-00002 | INSTRUMENT DATA SHEET OF TEMPERATURE GAUGE | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFA - ISSUED FOR APPROVAL | 11/11/2025 | BNO / 03-VENDOR / WIKA / PO_001962-PRESSURE GAUGE AND TEMPERATURE GAUGE
BNO-001962-300-IN-4018-008-AOL-00001-001 | INSTRUMENT GENERAL ARRANGEMENT DRAWING OF PRESSURE GAUGE | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / WIKA / PO_001962-PRESSURE GAUGE AND TEMPERATURE GAUGE
BNO-001962-300-IN-4018-008-AOL-00002-001 | INSTRUMENT GENERAL ARRANGEMENT DRAWING OF TEMPERATURE GAUGE | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL | 11/15/2025 | BNO / 03-VENDOR / WIKA / PO_001962-PRESSURE GAUGE AND TEMPERATURE GAUGE
BNO-001962-300-JA-6611-003-AOL-00001 | VENDOR DOCUMENT REGISTER LIST OF PRESSURE GAUGE AND TEMPERATURE GAUGE | IT / IM | JA - IM | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION | IFA RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW | 11/2/2025 | BNO / 03-VENDOR / WIKA / PO_001962-PRESSURE GAUGE AND TEMPERATURE GAUGE
BNO-001962-300-NA-4354-008-AOL-00001 | INSTRUMENT CATALOGUE OF PRESSURE GAUGE AND TEMPERATURE GAUGE | NA - MAINTENANCE | NA - MAINTENANCE | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL | 11/5/2025 | BNO / 03-VENDOR / WIKA / PO_001962-PRESSURE GAUGE AND TEMPERATURE GAUGE
BNO-001962-300-NA-4354-008-AOL-00002 | ITEM LIST (TAG NO. LIST) OF PRESSURE GAUGE AND TEMPERATURE GAUGE | NA - MAINTENANCE | NA - MAINTENANCE | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFI - ISSUED FOR INFORMATION | 11/11/2025 | BNO / 03-VENDOR / WIKA / PO_001962-PRESSURE GAUGE AND TEMPERATURE GAUGE
BNO-001962-300-OA-4811-008-AOL-00001 | OPERATING INSTRUCTION (INSTALLATION OPERATION AND MAINTENANCE) OF PRESSURE GAUGE AND TEMPERATURE GAUGE | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL | 11/15/2025 | BNO / 03-VENDOR / WIKA / PO_001962-PRESSURE GAUGE AND TEMPERATURE GAUGE
BNO-001962-300-QA-5733-008-AOL-00001 | INSPECTION AND TEST PLAN OF PRESSURE GAUGE | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | TRANSMITTAL |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / WIKA / PO_001962-PRESSURE GAUGE AND TEMPERATURE GAUGE
BNO-001962-300-QA-5733-008-AOL-00002 | INSPECTION AND TEST PLAN OF TEMPERATURE GAUGE | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | TRANSMITTAL |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / WIKA / PO_001962-PRESSURE GAUGE AND TEMPERATURE GAUGE
BNO-001962-300-QA-5733-008-AOL-00003 | INSPECTION RELEASE CERTIFICATES (IRN) | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  | 27-DEC-2025 | BNO / 03-VENDOR / WIKA / PO_001962-PRESSURE GAUGE AND TEMPERATURE GAUGE
BNO-001962-300-QA-5733-008-AOL-00004 | TEST AND INSPECTION PROCEDURE/ FACTORY ACCEPTANCE TEST (CALIBRATION PROCEDURE) | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | TRANSMITTAL |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / WIKA / PO_001962-PRESSURE GAUGE AND TEMPERATURE GAUGE
BNO-001962-300-RA-1580-008-AOL-00001 | DECLARATION OF CONFORMITY (EC ATEX EMC PED) OF PRESSURE GAUGE AND TEMPERATURE GAUGE | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL | 11/17/2025 | BNO / 03-VENDOR / WIKA / PO_001962-PRESSURE GAUGE AND TEMPERATURE GAUGE
BNO-001962-300-RA-1580-008-AOL-00002 | CERTIFICATES/ TEST REPORT OF PRESSURE GAUGE AND TEMPERATURE GAUGE | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  | 27-DEC-2025 | BNO / 03-VENDOR / WIKA / PO_001962-PRESSURE GAUGE AND TEMPERATURE GAUGE
BNO-001962-300-SA-6028-008-AOL-00001 | TRANSPORTATION PACKING AND STORAGE OF PRESSURE GAUGE AND TEMPERATURE GAUGE | SA - LOGISTICS | SA - LOGISTICS | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION | IFA RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW | 11/15/2025 | BNO / 03-VENDOR / WIKA / PO_001962-PRESSURE GAUGE AND TEMPERATURE GAUGE
BNO-001963-300-FA-5803-040-AOL-00001 | MANUFACTURING SCHEDULE - ULTRASONIC FLOWMETER | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PANAMETRICS / PO_001963-ULTRASONIC FLOWMETER
BNO-001963-300-IN-2105-040-AOL-00001 | TECHNICAL DATASHEET / SPECIFICATION - ULTRASONIC FLOWMETER | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PANAMETRICS / PO_001963-ULTRASONIC FLOWMETER
BNO-001963-300-IN-2105-040-AOL-00002 | COMPONENTS LIST WITH REF. MANUFACTURER/MODEL N°. (BOM) - ULTRASONIC FLOWMETER | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PANAMETRICS / PO_001963-ULTRASONIC FLOWMETER
BNO-001963-300-IN-2105-040-AOL-00003 | SIZING CALCULATION SHEET - ULTRASONIC FLOWMETER | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PANAMETRICS / PO_001963-ULTRASONIC FLOWMETER
BNO-001963-300-IN-4018-040-AOL-00001-001 | DIMENSIONAL DRAWING - ULTRASONIC FLOWMETER | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PANAMETRICS / PO_001963-ULTRASONIC FLOWMETER
BNO-001963-300-JA-4372-040-AOL-00001 | DATABOOK - ULTRASONIC FLOWMETER | IT / IM | JA - IM | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PANAMETRICS / PO_001963-ULTRASONIC FLOWMETER
BNO-001963-300-JA-4372-040-AOL-00002 | DATABOOK INDEX - ULTRASONIC FLOWMETER | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PANAMETRICS / PO_001963-ULTRASONIC FLOWMETER
BNO-001963-300-JA-6611-040-AOL-00001 | DOCUMENTS/DRAWING LIST - ULTRASONIC FLOWMETER | IT / IM | JA - IM | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PANAMETRICS / PO_001963-ULTRASONIC FLOWMETER
BNO-001963-300-NA-4354-040-AOL-00001 | SPARE PART LIST FOR 2 YEARS - ULTRASONIC FLOWMETER | NA - MAINTENANCE | NA - MAINTENANCE | R02 | NAO |  | Diretorio Vendor | ENGINEERING CONSOLIDATION |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PANAMETRICS / PO_001963-ULTRASONIC FLOWMETER
BNO-001963-300-NA-4354-040-AOL-00002 | SPARE PARTS FOR PRE-COMMISSIONING. COMMISSIONING AND STARTUP - ULTRASONIC FLOWMETER | NA - MAINTENANCE | NA - MAINTENANCE | R02 | NAO |  | Diretorio Vendor | ENGINEERING CONSOLIDATION |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PANAMETRICS / PO_001963-ULTRASONIC FLOWMETER
BNO-001963-300-OA-4811-040-AOL-00004 | INSTALLATION. OPERATING & MAINTENANCE MANUALS COMBINED - ULTRASONIC FLOWMETER | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / PANAMETRICS / PO_001963-ULTRASONIC FLOWMETER
BNO-001963-300-QA-1580-040-AOL-00001 | SIL CERTIFICATE IN ACCORDANCE WITH IEC-61508 / IEC-61511-1 - ULTRASONIC FLOWMETER | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PANAMETRICS / PO_001963-ULTRASONIC FLOWMETER
BNO-001963-300-QA-5733-040-AOL-00001 | INSPECTION AND TEST PLAN (FAT AND SAT) - ULTRASONIC FLOWMETER | QA - QUALITY | QA - QUALITY | C02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / PANAMETRICS / PO_001963-ULTRASONIC FLOWMETER
BNO-001963-300-QA-5733-040-AOL-00002 | CALIBRATION PROCEDURE - ULTRASONIC FLOWMETER | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / PANAMETRICS / PO_001963-ULTRASONIC FLOWMETER
BNO-001963-300-RA-1580-040-AOL-00002 | ENCLOSURE HAZARDOUS AREA AND PROTECTION DEGREE CERTIFICATE - ULTRASONIC FLOWMETER | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PANAMETRICS / PO_001963-ULTRASONIC FLOWMETER
BNO-001963-300-RA-1580-040-AOL-00003 | MATERIAL TRACEABILITY CERTIFICATES - ULTRASONIC FLOWMETER | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PANAMETRICS / PO_001963-ULTRASONIC FLOWMETER
BNO-001963-300-RA-1580-040-AOL-00004 | MATERIAL TEST CERTIFICATE - ULTRASONIC FLOWMETER | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / PANAMETRICS / PO_001963-ULTRASONIC FLOWMETER
BNO-001963-300-RA-6068-040-AOL-00001 | PAINTING PROCEDURE - ULTRASONIC FLOWMETER | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / PANAMETRICS / PO_001963-ULTRASONIC FLOWMETER
BNO-001963-300-SA-6028-040-AOL-00001 | PRESERVATION. PACKING. MARKING . SHIPPING PROCEDURE - ULTRASONIC FLOWMETER | SA - LOGISTICS | SA - LOGISTICS | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PANAMETRICS / PO_001963-ULTRASONIC FLOWMETER
BNO-002135-300-AA-6944-083-AOL-00001 | PRODUCTION SCHEDULE FOR IR FLAME DETECTORS | PMT | AA - PROJECT MANAGEMENT | C01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / DETRONICS / PO_002135-IR_FLAME_DETECTOR
BNO-002135-300-IN-1580-083-AOL-00001 | SIL CERTIFICATES FOR FLAME DETECTOR | INSTRUMENTATION | IN - INSTRUMENTATION | A04 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS | IFA RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / DETRONICS / PO_002135-IR_FLAME_DETECTOR
BNO-002135-300-IN-1580-083-AOL-00002 | ENCLOSURE HAZARDOUS AREA AND PROTECTION DEGREE CERTIFICATE | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / DETRONICS / PO_002135-IR_FLAME_DETECTOR
BNO-002135-300-IN-2105-083-AOL-00001 | TECHNICAL DATASHEET/SPECIFICATION - IR FLAME DETECTOR | INSTRUMENTATION | IN - INSTRUMENTATION | A04 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / DETRONICS / PO_002135-IR_FLAME_DETECTOR
BNO-002135-300-IN-4018-083-AOL-00001 | DIMENSIONAL DRAWING - IR FLAME DETECTOR | INSTRUMENTATION | IN - INSTRUMENTATION | A05 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / DETRONICS / PO_002135-IR_FLAME_DETECTOR
BNO-002135-300-JA-6611-083-AOL-00001 | VENDOR DATA REGISTER LIST (VDRL) IR FLAME DETECTORS | IT / IM | JA - IM | A02 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / DETRONICS / PO_002135-IR_FLAME_DETECTOR
BNO-002135-300-NA-4354-083-AOL-00001 | SPARE PARTS LIST | NA - MAINTENANCE | NA - MAINTENANCE | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / DETRONICS / PO_002135-IR_FLAME_DETECTOR
BNO-002701-300-FA-5803-040-AOL-00001 | ENGINEERING_ FABRICATION_ INSPECTION AND TESTING SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / COSASCO / PO_002701-CORROSION_DETECTOR
BNO-002701-300-IN-1580-040-AOL-00001 | EXPLOSION PROOF CERTIFICATE | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 4 | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / COSASCO / PO_002701-CORROSION_DETECTOR
BNO-002701-300-IN-2105-040-AOL-00001 | WAKE FREQUENCY CALCULATION | INSTRUMENTATION | IN - INSTRUMENTATION | R03 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / COSASCO / PO_002701-CORROSION_DETECTOR
BNO-002701-300-IN-2105-040-AOL-00002 | POWER REQUIREMENTS CORROSION DETECTOR | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS | IFR RETURNED AS CODE 2 |  |  | BNO / 03-VENDOR / COSASCO / PO_002701-CORROSION_DETECTOR
BNO-002701-300-IN-2105-040-AOL-00003 | TECHNICAL DATASHEET (ISS) | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / COSASCO / PO_002701-CORROSION_DETECTOR
BNO-002701-300-IN-2105-040-AOL-00004 | DETAILED & COMPLETE TECHNICAL INFORMATION | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / COSASCO / PO_002701-CORROSION_DETECTOR
BNO-002701-300-IN-2105-040-AOL-00005 | LIST OF SPECIAL TOOLS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / COSASCO / PO_002701-CORROSION_DETECTOR
BNO-002701-300-IN-4018-040-AOL-00001-001 | DIMENSIONAL OUTLINE DRAWINGS | INSTRUMENTATION | IN - INSTRUMENTATION | R02 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / COSASCO / PO_002701-CORROSION_DETECTOR
BNO-002701-300-IN-4018-040-AOL-00002 | NAMEPLATE DRAWINGS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS | IFR RETURNED AS CODE 2 |  |  | BNO / 03-VENDOR / COSASCO / PO_002701-CORROSION_DETECTOR
BNO-002701-300-IN-4018-040-AOL-00003 | BILL OF MATERIALS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / COSASCO / PO_002701-CORROSION_DETECTOR
BNO-002701-300-JA-4372-040-AOL-00001 | VENDOR DATA BOOK | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / COSASCO / PO_002701-CORROSION_DETECTOR
BNO-002701-300-JA-6611-040-AOL-00001 | VENDOR DOCUMENT REQUIREMENTS LIST (VDRL) | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / COSASCO / PO_002701-CORROSION_DETECTOR
BNO-002701-300-NA-4354-040-AOL-00001 | RECOMMENDED START-UP / COMMISSIONING SPARE PARTS LIST | NA - MAINTENANCE | NA - MAINTENANCE | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / COSASCO / PO_002701-CORROSION_DETECTOR
BNO-002701-300-NA-4354-040-AOL-00002 | RECOMMENDED 2-YEAR OPERATIONAL SPARE PARTS LIST | NA - MAINTENANCE | NA - MAINTENANCE | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / COSASCO / PO_002701-CORROSION_DETECTOR
BNO-002701-300-OA-4811-040-AOL-00001 | INSTALLATION, OPERATION, AND MAINTENANCE MANUALS CORROSION DETECTOR | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | ENGINEERING CONSOLIDATION |  |  |  | BNO / 03-VENDOR / COSASCO / PO_002701-CORROSION_DETECTOR
BNO-002701-300-QA-5733-040-AOL-00001 | INSPECTION AND TEST PLAN | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / COSASCO / PO_002701-CORROSION_DETECTOR
BNO-002701-300-QA-5733-040-AOL-00002 | NDE PROCEDURE | QA - QUALITY | QA - QUALITY | A02 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / COSASCO / PO_002701-CORROSION_DETECTOR
BNO-002701-300-QA-5733-040-AOL-00003 | PMI PROCEDURE | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / COSASCO / PO_002701-CORROSION_DETECTOR
BNO-002701-300-QA-5733-040-AOL-00004 | FAT PROCEDURE CORROSION DETECTOR | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / COSASCO / PO_002701-CORROSION_DETECTOR
BNO-002701-300-QA-5733-040-AOL-00005 | HYDROTEST PROCEDURE | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / COSASCO / PO_002701-CORROSION_DETECTOR
BNO-002701-300-QA-5733-040-AOL-00006 | PAINTING PROCEDURE | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / COSASCO / PO_002701-CORROSION_DETECTOR
BNO-002701-300-RA-1580-040-AOL-00001 | MATERIAL TEST CERTIFICATES | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / COSASCO / PO_002701-CORROSION_DETECTOR
BNO-002701-300-RA-1580-040-AOL-00002 | CERTIFIED TEST REPORTS_ CERTS_ DATA AND CURVES | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / COSASCO / PO_002701-CORROSION_DETECTOR
BNO-002701-300-RA-1580-040-AOL-00003 | PROBE CERTIFICATES | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / COSASCO / PO_002701-CORROSION_DETECTOR
BNO-002701-300-RA-1580-040-AOL-00004 | CERTIFICATE OF COMPLIANCE | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / COSASCO / PO_002701-CORROSION_DETECTOR
BNO-002701-300-SA-6028-040-AOL-00001 | PACKING / SHIPPING / PRESERVATION PROCEDURE | SA - LOGISTICS | SA - LOGISTICS | C01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION | AFC/AFU RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / COSASCO / PO_002701-CORROSION_DETECTOR
BNO-002729-300-EA-2105-004-AOL-00001 | DATASHEET - ELECTRICAL CABLES | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | TRANSMITTAL |  |  |  | BNO / 03-VENDOR / PRYSMIAN / PO_02729-CABLES
BNO-002729-300-IN-2105-004-AOL-00001 | DATASHEET - INSTRUMENT CABLES | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / PRYSMIAN / PO_02729-CABLES
BNO-002729-300-JA-6611-004-AOL-00001 | VENDOR DOCUMENT REQUIREMENTS LIST (VDRL) - CABLES | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / PRYSMIAN / PO_02729-CABLES
BNO-002729-300-QA-1580-004-AOL-00002 | TYPE TEST REPORT (ABS CERTIFICATION) - PRYSMIAN CABLES | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / PRYSMIAN / PO_02729-CABLES
BNO-002729-300-QA-5733-004-AOL-00001 | INSPECTION AND TEST PLAN – ELECTRICAL CABLES | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | TRANSMITTAL |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / PRYSMIAN / PO_02729-CABLES
BNO-002729-300-QA-5733-004-AOL-00002 | INSPECTION AND TEST PLAN - INSTRUMENT CABLES | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | TRANSMITTAL |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / PRYSMIAN / PO_02729-CABLES
BNO-002729-300-QA-6050-004-AOL-00001 | QUALITY ASSURANCE AND QUALITY SYSTEM PLAN - PRYSMIAN CABLES | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / PRYSMIAN / PO_02729-CABLES
BNO-002729-300-SA-6028-004-AOL-00001 | PACKING, PRESERVATION, HANDLING AND TRANSPORTATION PROCEDURE - PRYSMIAN CABLES | SA - LOGISTICS | SA - LOGISTICS | A02 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / PRYSMIAN / PO_02729-CABLES
BNO-018578-300-AA-6944-040-SULZER-00001 | PROGRESS REPORTS | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-AA-6944-040-SULZER-00002 | SITE SURVEY REPORT - SHELL BONGA FPSO | PMT | AA - PROJECT MANAGEMENT | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-BA-4802-040-SULZER-00003 | COMMISSIONING PROCEDURE (PRE-COMMISSIONING) | BC - COMMISSIONING | BC - COMMISSIONING | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-BA-4802-040-SULZER-00004 | SPECIAL & COMMSIONING TOOLS LIST - COMMISSIONING EQUIPMENT LIST / CONSUMERABLES LIST | BC - COMMISSIONING | BC - COMMISSIONING | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | 4/7/2025 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-BA-4802-040-SULZER-00005 | PUMP COMMISSIONING SPARES LIST - UPGRADED WATERFLOOD INJECTION PUMP (P-4046A) | CONSTRUCTION | BA - CONSTRUCTION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  | 6/6/2025 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-BA-6065-040-SULZER-00001 | WELD PROCEDURE SPECIFICATION & QUALIFICATION - UPGRADED WATERFLOOD INJECTION PUMP | CONSTRUCTION | BA - CONSTRUCTION | A03 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-FA-5803-040-SULZER-00001 | PRODUCTION SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | A04 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-HS-2107-040-SULZER-00001 | MATERIAL SAFETY DATA SHEETS | TECHNICAL SAFETY | HS - SAFETY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-IN-2105-040-SULZER-00001 | INSTRUMENT DATA SHEETS - UPGRADED WATERFLOOD INJECTION PUMP (P-4046A) | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-IN-2335-040-SULZER-00001-001 | SEAL SYSTEM INSTRUMENT HOOK UP DRAWING | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  | 4/25/2025 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-IN-4780-040-SULZER-00001-001 | PUMP LOGIC DIAGRAM | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  | 9/5/2025 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-IN-6612-040-SULZER-00001 | PUMP CABLE LIST | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | 9/5/2025 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-IN-6612-040-SULZER-00002 | PUMP INSTRUMENT INDEX - SCHEDULE | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-IN-7770-040-SULZER-00001 | PUMP CONTROL PHILOSOPHY - UPGRADED WATERFLOOD INJECTION PUMP (P-4046A) | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-IN-8880-040-SULZER-00001-001 | PUMP INSTRUMENT WIRING DIAGRAM | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  | 6/20/2025 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-JA-4372-040-SULZER-00001 | SUPPLIER DOCUMENT REGISTER | IT / IM | JA - IM | A04 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-MP-4018-040-SULZER-00005-001 | DOUBLE BLOCK & BLEED VALVE GA DRAWING - UPGRADED WATERFLOOD INJECTION PUMP (P-4046A) | PIPING | MP - PIPING | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-MR-2105-040-SULZER-00001 | PUMP DATA SHEET - UPGRADED WATERFLOOD INJECTION PUMP (P-4046A) | MECHANICAL | MR - MECHANICAL ROTATING | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-MR-2105-040-SULZER-00002 | PUMP NOISE LEVEL DATA SHEETS | MECHANICAL | MR - MECHANICAL ROTATING | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-MR-2105-040-SULZER-00003 | PUMP UTILITY CONSUMPTION LIST | MECHANICAL | MR - MECHANICAL ROTATING | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  | 4/25/2025 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-MR-4018-040-SULZER-00001-001 | GEARBOX OUTLINE DRAWING & 3D MODEL (CUSTOMER TO SUPPLY) | MECHANICAL | MR - MECHANICAL ROTATING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-MR-4018-040-SULZER-00002-001 | COUPLING DRAWING - UPGRADED WATERFLOOD INJECTION PUMP (P-4046A) | MECHANICAL | MR - MECHANICAL ROTATING | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-MR-4018-040-SULZER-00003-001 | PUMP GENERAL ARRANGEMENT DRAWING | MECHANICAL | MR - MECHANICAL ROTATING | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-MR-4018-040-SULZER-00004-001 | PUMP CROSS SECTION DRAWING - UPGRADED WATERFLOOD INJECTION PUMP (P-4046A) | MECHANICAL | MR - MECHANICAL ROTATING | A01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-MR-4018-040-SULZER-00005-001 | PUMP NAME - DUTY PLATE DRAWING (P-4046A) | MECHANICAL | MR - MECHANICAL ROTATING | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-MR-7180-040-SULZER-00001 | HYDROSTATIC TEST PROCEDURE | MECHANICAL | MR - MECHANICAL ROTATING | A04 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | 3/28/2025 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-MR-7180-040-SULZER-00002 | PUMP BASEPLATE ANALYSIS | MECHANICAL | MR - MECHANICAL ROTATING | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | 4/7/2025 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-MR-7180-040-SULZER-00003 | CASTING REPAIR PROCEDURE - SUCTION CASE - UPGRADED WATERFLOOD INJECTION PUMP (P-4046A) | MECHANICAL | MR - MECHANICAL ROTATING | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-MR-7180-040-SULZER-00004 | PUMP TORSIONAL ANALYSIS - UPGRADED WATERFLOOD INJECTION PUMP (P-4045A) | MECHANICAL | MR - MECHANICAL ROTATING | R03 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 |  | 4/20/2025 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-MR-7771-040-SULZER-00001 | PUMP PERFORMANCE CURVE | MECHANICAL | MR - MECHANICAL ROTATING | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-MR-8226-040-SULZER-00001 | PUMP LATERAL ANALYSIS - UPGRADED WATERFLOOD INJECTION PUMP (P-4046A) | MECHANICAL | MR - MECHANICAL ROTATING | A03 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-MX-2321-040-SULZER-00001-001 | MECHANICAL SEAL DRAWING - UPGRADED WATERFLOOD INJECTION PUMP (P-4046A) | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 4 |  | 4/25/2025 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-MX-2321-040-SULZER-00002-001 | SEAL SYSTEM DRAWING | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  | 4/25/2025 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-MX-4018-040-SULZER-00001 | ACOUSTIC ENCLOSURE GA DRAWING - UPGRADED WATERFLOOD INJECTION PUMP (P-4046A) | MECHANICAL | MX - OVERAL MECHANICAL | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-MX-6065-040-SULZER-00001 | BASEPLATE WPS/PQR - UPGRADED WATERFLOOD INJECTION PUMP (P-4046A) | MECHANICAL | MX - OVERAL MECHANICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-MX-6067-040-SULZER-00002 | PUMP PERFORMANCE TEST PROCEDURE | MECHANICAL | MX - OVERAL MECHANICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | 10/13/2025 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-MX-6180-040-SULZER-00001 | PUMP WEIGHT CONTROL / WEIGHING PROCEDURE - UPGRADED WATERFLOOD INJECTION PUMP (P-4046A) | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 |  | 3/28/2025 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-MX-6612-040-SULZER-00010 | LIST OF EQUIPMENT (EX-CERTIFIED) | MECHANICAL | MX - OVERAL MECHANICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-MX-7180-040-SULZER-00018 | COMPUTATION FLUID DYNAMICS REPORT (INFO ONLY) | MECHANICAL | MX - OVERAL MECHANICAL | A04 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-NA-4354-040-SULZER-00001 | LIST OF RECOMMENDED SPARE PARTS FOR COMMISSIONING STARTUP AND NORMAL MAINTENANCE PURPOSES | NA - MAINTENANCE | NA - MAINTENANCE | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-NA-4354-040-SULZER-00002 | PUMP OPERATING SPARES LIST - UPGRADED WATERFLOOD INJECTION PUMP (P-4046A) | NA - MAINTENANCE | NA - MAINTENANCE | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-OA-4811-040-SULZER-00001 | COUPLING INSTALLATION_ OPERATION & MAINTENANCE MANUAL - UPGRADED WATERFLOOD INJECTION PUMP (P-4046A) | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  | 12/12/2025 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-OA-4811-040-SULZER-00002 | PUMP I O&M MANUAL INDEX | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-OA-4811-040-SULZER-00003 | SEAL SYSTEM OPERATION & MAINTENANCE MANUAL | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  | 12/12/2025 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-OA-4811-040-SULZER-00004 | MECHANICAL SEAL OPERATION & MAINTENANCE MANUAL | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  | 4/25/2025 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-OA-4811-040-SULZER-00005 | PUMP INSTALLATION OPERATION & MAINTENANCE MANUAL | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 1 |  | 12/2/2025 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-OA-4811-040-SULZER-00006 | PUMP LUBRICATION SCHEDULE | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-PX-2310-040-SULZER-00001 | PUMP CAUSE & EFFECT - UPGRADED WATERFLOOD INJECTION PUMP (P-4046A) | PROCESS | PX - PROCESS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-PX-2365-040-SULZER-00001-001 | PUMP P&I DIAGRAM - UPGRADED WATERFLOOD INJECTION PUMP (P-4046A) | PROCESS | PX - PROCESS | C03 | NAO |  | Diretorio Vendor | ENGINEERING CONSOLIDATION |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-QA-5733-040-SULZER-00001 | PUMP INSPECTION & TEST PLAN | QA - QUALITY | QA - QUALITY | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-RA-1580-040-SULZER-00001 | PUMP CERTIFICATION DATA BOOK | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  | 10/4/2026 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-RA-1580-040-SULZER-00002 | PUMP CERTIFICATION DATA BOOK INDEX | MATERIALS | RA - MATERIALS | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW | 9/5/2025 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-RA-6038-040-SULZER-00001 | NDT PROCEDURE (NDT- VT OF CASTINGS) | MATERIALS | RA - MATERIALS | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | 3/28/2025 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-RA-6038-040-SULZER-00002 | NDT PROCEDURE (NDT - VT OF WELDED PIPEWORK) | MATERIALS | RA - MATERIALS | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW | 3/28/2025 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-RA-6038-040-SULZER-00003 | NDT PROCEDURE (NDT - VT OF MACHINED SURFACES) | MATERIALS | RA - MATERIALS | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | 3/28/2025 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-RA-6038-040-SULZER-00004 | NDT PROCEDURE (NDT - VT OF STRUCTURAL FABRICATION) | MATERIALS | RA - MATERIALS | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | 3/28/2025 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-RA-6038-040-SULZER-00005 | NDT PROCEDURE (NDT - LIQUID PENETRANT EXAMINATION) | MATERIALS | RA - MATERIALS | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | 3/28/2025 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-RA-6038-040-SULZER-00006 | NDT PROCEDURE (NDT - POSITIVE MATERIAL IDENTIFICATION) | MATERIALS | RA - MATERIALS | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | 3/28/2025 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-RA-6038-040-SULZER-00007 | NDT PROCEDURE (NDT - MAGNETIC PARTICLE TESTING) | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-RA-6038-040-SULZER-00008 | NDT PROCEDURE (NDT UT AUST/AUST-FERRITIC FORGINGS) | MATERIALS | RA - MATERIALS | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  | 3/28/2025 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-RA-6038-040-SULZER-00009 | NDT PROCEDURE (RT OF CASTINGS) | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 |  |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-RA-6038-040-SULZER-00010 | NDT (RT - WELDED JOINTS ASME) - UPGRADED WATERFLOOD INJECTION PUMP (P-4046A) | MATERIALS | RA - MATERIALS | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | 3/28/2025 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-RA-6068-040-SULZER-00002 | SURFACE PREPARATION & PAINT PROCEDURE | MATERIALS | RA - MATERIALS | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | 3/28/2025 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-RA-6068-040-SULZER-00003 | PMI PROCEDURE | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  | 3/28/2025 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-RA-6068-040-SULZER-00004 | BARREL FORGING WELD PROCEDURE SPECIFICATION (WPS) & PROCEDURE QUALIFICATION RECORD (PQR) - UPGRADED WATERFLOOD INJECTION PUMP (P-4046A) | MATERIALS | RA - MATERIALS | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-RA-6068-040-SULZER-00005 | CASTING REPAIR PROCEDURE - IMPELLERS - UPGRADED WATERFLOOD INJECTION PUMP (P-4046A) | MATERIALS | RA - MATERIALS | A03 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-RA-6080-040-SULZER-00005 | CASTING REPAIR PROCEDURE - IMPELLERS - UPGRADED | MATERIALS | RA - MATERIALS | R02 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 |  |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-RA-7180-040-SULZER-00009 | PUMP PERFORMANCE TEST REPORT (INCLUDES VIBRATION ANALYSIS) | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  | 1/16/2026 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-SA-6028-040-SULZER-00001 | PROTECTION & PRESERVATION FOR STORAGE | SA - LOGISTICS | SA - LOGISTICS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  | 3/28/2025 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-SA-6028-040-SULZER-00005 | PACKING AND SHIPPMENT LIST & SCHEDULE | SA - LOGISTICS | SA - LOGISTICS | R01 | NAO |  | Diretorio Vendor | ENGINEERING CONSOLIDATION |  |  | 2/27/2026 | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-018578-300-VA-4305-040-SULZER-00001 | LIST OF MAJOR SUB-MANUFACTURERS_SUB SUPPLIERS - UPGRADED WATERFLOOD INJECTION PUMP (P-4046A) | VA - PROCUREMENT | VA - PROCUREMENT | A03 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SULZER / PO_018578-WI PUMP (P-4046A)
BNO-260191-300-AA-0780-091-POWI-00001 | SNEPCO BONGA NORTH SSCB - LNTP VALIDATION REPORT | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-AA-0780-091-POWI-00002 | SNEPCO BONGA NORTH SSCB - LNTP RISK REGISTER | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-AA-0780-091-POWI-00003 | SNEPCO BONGA NORTH SSCB - LNTP CLARIFICATION REGISTER | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-AA-5760-091-POWI-00001 | SNEPCO BONGA NORTH SSCB - PROJECT EXECUTION PLAN (PEP) | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-AA-7205-091-POWI-00001 | TECHNICAL QUERY 0001 - PROJECT SUPPLEMENTARY INFORMATION | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-AA-7205-091-POWI-00002 | TECHNICAL QUERY 0002 - PROPOSAL FOR HOT-DIP GALVANISED CABLE TRAY/LADDER FOR INTERNAL CONTAINMENT INSTEAD OF SS316 | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-AA-7205-091-POWI-00003 | TECHNICAL QUERY 0003 - CONFIRMATION FOR LIGHTING CONTROL STRATEGY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-AA-7205-091-POWI-00004 | TECHNICAL QUERY 0004 - DROPPED OBJECT PROTECTION | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-AA-7205-091-POWI-00005 | TECHNICAL QUERY 0005 - CONFORMATION OF DOOR TYPE AND AIRLOCK REQUIREMENTS | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-AA-7205-091-POWI-00008 | TECHNICAL QUERY 0008 - SSCB STOOL DESIGN & INSTALLATION PHILOSOPHY - OPTION SELECT | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-AA-7205-091-POWI-00009 | TECHNICAL QUERY 0009 - BATTERY MODULE OPEN FRAME EXTENSION BY 5.540M | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-BC-4354-091-POWI-00001 | RECOMM INSTALLATION COMMISSIONING AND START UP SPARES LIST | BC - COMMISSIONING | BC - COMMISSIONING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-BC-5799-091-POWI-00001 | COMMISSIONING AND START UP PROCEDURE | BC - COMMISSIONING | BC - COMMISSIONING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-BC-6180-091-POWI-00001 | SEA FASTENING DETAILS | BC - COMMISSIONING | BC - COMMISSIONING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CB-2408-016-POWI-00036-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - ARCHITECTURAL GENERAL ARRANGEMENT | CB - ARCHITECTURAL | CB - ARCHITECTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CB-2408-016-POWI-00040-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - ARCHITECTURAL GENERAL ARRANGEMENT | CB - ARCHITECTURAL | CB - ARCHITECTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CB-3328-091-POWI-00001 | ERECTION AND INSTALLATION PROCEDURES | CB - ARCHITECTURAL | CB - ARCHITECTURAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CB-7303-016-POWI-00001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - MATERIAL REQUISTION - DOORS | CB - ARCHITECTURAL | CB - ARCHITECTURAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CB-7303-016-POWI-00002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - MATERIAL REQUISTION - INSULATION | CB - ARCHITECTURAL | CB - ARCHITECTURAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CB-7771-016-POWI-00002 | DOORS AND REMOVABLE PANEL DATA SHEETS | CB - ARCHITECTURAL | CB - ARCHITECTURAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CB-7771-016-POWI-00003 | INSULATION DATA SHEETS | CB - ARCHITECTURAL | CB - ARCHITECTURAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CB-7771-016-POWI-00004 | FURNITURE AND MISCELLANEOUS DATA SHEETS | CB - ARCHITECTURAL | CB - ARCHITECTURAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00001-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - FLOOR PRIMARY AND SECONDARY STEELWORK | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00002-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - ROOF PRIMARY AND SECONDARY STEELWORK | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00003-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - WALL PRIMARY STEELWORK - ELEVATION SHEET 1 (EXTERNAL VIEW) | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00003-002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - WALL PRIMARY STEELWORK - ELEVATION SHEET 2 (EXTERNAL VIEW) | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00003-003 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - WALL PRIMARY STEELWORK - END ELEVATION (EXTERNAL VIEW) | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00004-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - PRIMARY FRAMING DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00005-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - FLOOR PRIMARY AND SECONDARY STEELWORK | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00006-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - ROOF PRIMARY AND SECONDARY STEELWORK | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00007-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - WALL PRIMARY STEELWORK - ELEVATION SHEET 1 (EXTERNAL VIEW) | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00007-002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - WALL PRIMARY STEELWORK - ELEVATION SHEET 2 (EXTERNAL VIEW) | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00008-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - WALL PRIMARY STEELWORK - END ELEVATION (EXTERNAL VIEW) | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00009-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - PRIMARY FRAMING DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00010-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - FLOOR PRIMARY AND SECONDARY STEELWORK | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00011-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - ROOF PRIMARY AND SECONDARY STEELWORK | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00012-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - WALL PRIMARY STEELWORK - ELEVATION SHEET 1 (EXTERNAL VIEW) | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00012-002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - WALL PRIMARY STEELWORK - ELEVATION SHEET 2 (EXTERNAL VIEW) | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00013-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - WALL PRIMARY STEELWORK - END ELEVATION (EXTERNAL VIEW) | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00014-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - PRIMARY FRAMING DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00015-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - FLOOR PLATE | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00016-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - ROOF PLATE | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00017-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - SECONDARY FRAMING + PADEYE DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00018-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - FLOOR PLATE | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00019-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - ROOF PLATE | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00020-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - SECONDARY FRAMING + PADEYE DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00021-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - FLOOR PLATE | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00022-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - ROOF PLATE | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00023-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - SECONDARY FRAMING + PADEYE DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00024-001 | SNEPCO BONGA NORTH SSCB PACKAGE ACCESS PLATFORMS - OVERALL ARRANGEMENT | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00025-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - SEALING PLATE + SUPPORT STEEL | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00026-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - CLADDING AND DOOR FRAMING DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00027-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - SEALING PLATE SUPPORT DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00028-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - SEALING PLATE + SUPPORT STEEL | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00029-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - CLADDING AND DOOR FRAMING DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00030-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - SEALING PLATE SUPPORT DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00031-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - SEALING PLATE + SUPPORT STEEL | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00032-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - CLADDING AND DOOR FRAMING DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00033-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - SEALING PLATE SUPPORT DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00034-001 | STRUCTURAL GENERAL NOTES | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00035-001 | SNEPCO BONGA NORTH SSCB PACKAGE OVERALL ISOMETRIC ASSEMBLY | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00037-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - PFP LAYOUT | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00038-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - PFP DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00039-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - INTERNAL ELEVATIONS SHEET 1 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00039-002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - INTERNAL ELEVATIONS SHEET 2 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00039-003 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - INTERNAL ELEVATIONS SHEET 3 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00039-004 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - INTERNAL ELEVATIONS SHEET 4 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00041-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - PFP LAYOUT | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00042-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - PFP DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00043-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - INTERNAL ELEVATIONS SHEET 1 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00043-002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - INTERNAL ELEVATIONS SHEET 2 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00043-003 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - INTERNAL ELEVATIONS SHEET 3 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00043-004 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - INTERNAL ELEVATIONS SHEET 4 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00044-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - ARCHITECTURAL GENERAL ARRANGEMENT | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00045-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - PFP LAYOUT | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00046-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - PFP DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00047-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - INTERNAL ELEVATIONS SHEET 1 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00047-002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - INTERNAL ELEVATIONS SHEET 2 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00047-003 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - INTERNAL ELEVATIONS SHEET 3 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-2408-016-POWI-00047-004 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - INTERNAL ELEVATIONS SHEET 4 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-CS-8180-010-POWI-00001 | SNEPCO BONGA NORTH SSCB PACKAGE - LNTP STRUCTURAL DESIGN REPORT | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-0980-074-POWI-00001-001 | BLOCK DIAGRAM FOR ELECTRICAL SYSTEM | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-1380-074-POWI-00001 | SHORT SYSTEM CALCULATIONS | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-1380-076-POWI-00001 | BATTERY CHARGE/ DISCHARGE CALCULATIONS | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-1401-091-POWI-00001 | EQUIPMENT INCLUDING CIRCUIT BREAKERS AND RELAYS CATALOG AND CERTIFICATES | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-2310-091-POWI-00001 | CAUSE AND EFFECT MATRIX | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-2335-091-POWI-00001-001 | ELECTRICAL HOOK-UP DRAWINGS | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-2384-074-POWI-00001 | PROTECTION AND METERING SINGLE LINE DRAWING | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-2384-074-POWI-00007-001 | SNEPCO BONGA NORTH SSCB EXTERNAL (WALKWAYS & STAIRS) SINGLE LINE DIAGRAM NOURMAL DB | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-2384-074-POWI-00008-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - PLATFORMS ELECTRICAL SINGLE LINE DIAGRAM EMERGENCY DB | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-2384-076-POWI-00001-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - DB-7660-N-01 - ELECTRICAL LIGHTING & SP SINGLE LINE DIAGRAM NORMAL DB | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-2384-076-POWI-00002-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - DB-7491-N-01 - EMERGENCY LIGHTING & SP DISTRIBUTION BOARD SINGLE LINE DIAGRAM | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-2384-076-POWI-00003-001 | SNEPCO BONGA NORTH SSCB INSTRUMENT & CONTROL ROOM BUILDING LIGHTING & SMALL POWER SINGLE LINE DIAGRAM | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-2384-076-POWI-00004-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - DB-7492-N-01 400V ESSENTIAL LIGHTING & SMALL POWER DB SINGLE LINE DIAGRAM | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-2384-076-POWI-00005-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM BUILDING LIGHTING & SMALL POWER SINGLE LINE DIAGRAM | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-2384-076-POWI-00006-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM BUILDING LIGHTING & SMALL POWER SINGLE LINE DIAGRAM | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-2384-091-POWI-00001-001 | SINGLE LINE ELECTRICAL DRAWINGS | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-2389-091-POWI-00001-001 | MOTOR TERMINAL BOX DRAWINGS | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-2580-091-POWI-00001-001 | SCHEMATIC DIAGRAMS FOR ELECTRICAL | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-2901-074-POWI-00001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL CABLE SIZING CALCULATION FOR LIGHTING AND SAMLL POWER CIRCUITS IN ESSENTIAL DISTRIBUTION BOARD SCHEDULE DB-7492-N-01 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-2901-074-POWI-00002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL CABLE SIZING CALCULATION FOR LIGHTING CIRCUITS IN EMERGENCY DISTRIBUTION BOARD SCHEDULE DB-7491-N-01 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-2901-076-POWI-00001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - ELECTRICAL LIGHTING CALCULATION | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-2901-076-POWI-00002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - ELECTRICAL LIGHTING CALCULATION | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-2901-076-POWI-00003 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - ELECTRICAL LIGHTING CALCULATION | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-2901-076-POWI-00004 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - PLATFORMS ELECTRICAL LIGHTING CALCULATION | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-2901-076-POWI-00005 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL CABLE SIZING CALCULATION FOR LIGHTING AND SAMLL POWER CIRCUITS IN NORMAL DISTRIBUTION BOARD SCHEDULE DB-7660-N-01 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4012-091-POWI-00001-001 | ELECTRICAL JUNCTIONBOX DRAWINGS | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4018-073-POWI-00016-001 | GENERAL ARRANGEMENT 6.6KV SWITCHBOARD MCC-7355-D-01 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4018-074-POWI-00001-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - ELECTRICAL CABLE CONTAINMENT LAYOUT | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4018-074-POWI-00001-002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - ELECTRICAL CABLE CONTAINMENT LAYOUT | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4018-074-POWI-00002-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - ELECTRICAL (HVAC) CABLE CONTAINMENT LAYOUT | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4018-074-POWI-00004-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL EQUIPMENT MOUNTING ELEVATION DETAIL 1 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4018-074-POWI-00004-002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL EQUIPMENT MOUNTING ELEVATION DETAIL 1 SHEET 2 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4018-074-POWI-00004-003 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL EQUIPMENT MOUNTING ELEVATION DETAIL 1 SHEET 3 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4018-074-POWI-00004-004 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL EQUIPMENT MOUNTING ELEVATION DETAIL 1 SHEET 4 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4018-074-POWI-00005-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT & CONTROL ROOM BUILDING - LADDER RACK AND CABLE TRAY LAYOUT | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4018-074-POWI-00006-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - ELECTRICAL (HVAC) CABLE CONTAINMENT LAYOUT | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4018-074-POWI-00008-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL EQUIPMENT MOUNTING ELEVATION DETAIL 1 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4018-074-POWI-00008-002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL EQUIPMENT MOUNTING ELEVATION DETAIL 1 - SHEET 2 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4018-074-POWI-00008-003 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL EQUIPMENT MOUNTING ELEVATION DETAIL 1 - SHEET 3 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4018-074-POWI-00012-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL EQUIPMENT MOUNTING ELEVATION DETAIL 1 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4018-074-POWI-00012-002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL EQUIPMENT MOUNTING ELEVATION DETAIL 1 - SHEET 2 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4018-074-POWI-00012-003 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL EQUIPMENT MOUNTING ELEVATION DETAIL 1 - SHEET 3 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4018-074-POWI-00013-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - PLATFORMS ELECTRICAL CABLE CONTAINMENT LAYOUT 1 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4018-074-POWI-00015-001 | ELECTRICAL EQUIPMENT ASSEMBLY & DETAIL DRAWING | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4018-074-POWI-00017-001 | GENERAL ARRANGEMENT SB-7446-E-01 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4018-074-POWI-00018-001 | GENERAL ARRANGEMENT MCC-7456-E-01 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4018-074-POWI-00019-001 | GENERAL ARRANGEMENT MCC-7457-E-01 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4018-074-POWI-00020-001 | SNEPCO BONGA NORTH SSCB PACKAGE - SWITCHGEAR ELECTRICAL & INSTRUMENTATION ROOM MODULES LOWER LEVEL LAYOUT | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4018-074-POWI-00021-001 | SNEPCO BONGA NORTH SSCB PACKAGE - MODULES ROOF & BATTERY ROOM MODULE LAYOUT | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4018-075-POWI-00009-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM BUILDING LADDER RACK AND CABLE TRAY LAYOUT SHT 1 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4018-075-POWI-00010-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - ELECTRICAL (HVAC) CABLE CONTAINMENT LAYOUT | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4018-075-POWI-00014-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - PLATFORMS ELECTRICAL LIGHTING & SP EQUIP. LAYOUT | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4018-076-POWI-00003-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - ELECTRICAL LIGHTING & SMALL POWER EQUIPMENT LAYOUT | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4018-076-POWI-00007-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - ELECTRICAL LIGHTING & SMALL POWER EQUIPMENT LAYOUT | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4018-076-POWI-00011-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - ELECTRICAL LIGHTING & SMALL POWER EQUIPMENT LAYOUT | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4018-091-POWI-00001-001 | ELECTRICAL EQUIPMENT NAMEPLATE DRAWINGS (LABEL DRAWINGS) | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4018-091-POWI-00002-001 | MCT DRAWINGS | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4306-074-POWI-00002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - ELECTRICAL BILL OF MATERIALS | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4306-074-POWI-00004 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - ELECTRICAL BILL OF MATERIALS - INTERNAL AREAS | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4306-074-POWI-00005 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - PLATFORMS ELECTRICAL BILL OF MATERIALS | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4306-076-POWI-00003 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - ELECTRICAL BILL OF MATERIALS | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4306-091-POWI-00001 | ELECTRICAL MATERIAL LIST (BILL OF MATERIALS) | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4308-074-POWI-00002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - ELECTRICAL CABLE SCHEDULE | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4308-074-POWI-00003 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - ELECTRICAL CABLE SCHEDULE | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4308-074-POWI-00005 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - PLATFORMS ELECTRICAL CABLE SCHEDULE | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4308-074-POWI-00013 | ELECTRICAL CABLE LIST | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4308-075-POWI-00004 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - ELECTRICAL CABLE SCHEDULE | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4308-091-POWI-00001 | CONTROL AND INDICATION SCHEDULE | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4308-091-POWI-00002 | MCT (MULTI CABLE TRANSIT) LIST | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4308-091-POWI-00005 | ELECTRICAL CABLE LIST (INTERCONNECTING CABLE SCHEDULE) - EXCLUDES FIELD CABLING | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4319-074-POWI-00001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ESSENTIAL POWER DISTRIBUTION BOARD LOAD SCHEDULE DB-7492-N-01 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4319-074-POWI-00002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - EMERGENCY POWER DISTRIBUTION BOARD LOAD SCHEDULE DB-7491-N-01 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4319-076-POWI-00001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - NORMAL POWER DISTRIBUTION BOARD LOAD SCHEDULE DB-7660-N-01 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4329-091-POWI-00001 | ELECTRICAL EQUIPMENT LOAD LIST (COMPARTMENT DETAILS REPORT) | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-4329-091-POWI-00002 | CONSUMERS LIST FOR EACH VOLTAGE LEVEL (UTILITIES SCHEDULE) | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-7753-091-POWI-00001 | PROTECTION RELAY SETTING SCHEDULE | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-7771-091-POWI-00001 | EQUIPMENT SPECIFICATION SUMMARY SHEET | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-7771-091-POWI-00002 | ELECTRICAL EQUIPMENT DATA SHEETS (PANEL SUMMARY SPECIFICATION) | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-7771-091-POWI-00005 | CURRENT & POTENTIAL (CT/VT) TRANSFORMERS CURVES | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-7880-074-POWI-00002 | ELECTRICAL SYSTEM SPECIFICATION | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-7880-075-POWI-00001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - LIGHTING VENDOR STATEMENT OF REQUIREMENTS | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-8260-073-POWI-00001 | POWER SYSTEM ANALYSIS DATA | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-8260-091-POWI-00001 | ELECTRICAL PROTECTION STUDY | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-8804-091-POWI-00001 | TERMINAL LAYOUT | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-8804-091-POWI-00002-001 | ELECTRICAL CONNECTION DIAGRAM (INTERCONNECTION DIAGRAM) | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-EA-8880-091-POWI-00001-001 | MOTOR WIRING DIAGRAMS | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-FA-5803-091-POWI-00001 | FABRICATION / PRODUCTION SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-HS-1439-091-POWI-00001 | SAFETY SUMMARY | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-HS-2107-091-POWI-00001 | SAFETY EQUIPMENT - TECHNICAL SPECIFICATIONS AND DATA SHEETS | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-HS-2107-091-POWI-00002 | SAFETY DATA SHEET - M17 | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-HS-2374-091-POWI-00001-001 | AREA CLASSIFICATION DATA LIST | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-HS-2374-091-POWI-00002-001 | AREA CLASSIFICATION DRAWINGS | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-HS-4306-091-POWI-00001 | SAFETY MATERIAL LIST | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-HS-5798-091-POWI-00001 | SAFETY PLAN | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-HS-6180-091-POWI-00001 | SAFETY SIGNALLING PLAN | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-HS-8249-091-POWI-00001 | SAFETY STUDIES | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-HX-0709-091-POWI-00001 | RISK ANALYSIS | TECHNICAL SAFETY | HX - HSE | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-HX-1601-091-POWI-00001 | MATERIALS INSTALLED IN HAZARDOUS AREA LIST | TECHNICAL SAFETY | HX - HSE | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-HX-2318-065-POWI-00001-001 | SNEPCO BONGA NORTH SSCB PACKAGE - SNEPCO BONGA NORTH SSCB PACKAGE MODULE SWITCHGEAR ELECTRICAL & INSTRUMENTATION ROOM SSCB LOWER LEVEL SAFETY LAYOUT | TECHNICAL SAFETY | HX - HSE | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-HX-2318-065-POWI-00002-001 | SNEPCO BONGA NORTH SSCB PACKAGE - SNEPCO BONGA NORTH SSCB PACKAGE MODULE MODULE ROOF & BATTERY ROOM SSCB UPPER LEVEL SAFETY LAYOUT | TECHNICAL SAFETY | HX - HSE | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-HX-5880-091-POWI-00001 | H S & E PLAN | TECHNICAL SAFETY | HX - HSE | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-HX-7880-061-POWI-00001 | SNEPCO BONGA NORTH SSCB - PASSIVE FIRE PROTECTION CALCULATIONS | TECHNICAL SAFETY | HX - HSE | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-0980-074-POWI-00001-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - FIRE & GAS CABLE BLOCK DIAGRAM | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-0980-074-POWI-00002-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - INSTRUMENT CABLE BLOCK DIAGRAM | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-0980-074-POWI-00003-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - TELECOM CABLE BLOCK DIAGRAM | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-0980-074-POWI-00003-002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - TELECOM CABLE BLOCK DIAGRAM | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-0980-074-POWI-00003-003 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - TELECOM CABLE BLOCK DIAGRAM | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-0980-074-POWI-00004-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - FIRE & GAS CABLE BLOCK DIAGRAM | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-0980-074-POWI-00005-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - INSTRUMENT CABLE BLOCK DIAGRAM | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-0980-074-POWI-00006-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - TELECOM CABLE BLOCK DIAGRAM | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-0980-074-POWI-00006-002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - TELECOM CABLE BLOCK DIAGRAM | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-0980-074-POWI-00006-003 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - TELECOM CABLE BLOCK DIAGRAM | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-0980-074-POWI-00007-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - FIRE & GAS CABLE BLOCK DIAGRAM | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-0980-074-POWI-00007-002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - FIRE & GAS CABLE BLOCK DIAGRAM | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-0980-076-POWI-00008-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - INSTRUMENT CABLE BLOCK DIAGRAM | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-0980-076-POWI-00009-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - TELECOM CABLE BLOCK DIAGRAM | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-0980-076-POWI-00009-002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - TELECOM CABLE BLOCK DIAGRAM | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-0980-076-POWI-00009-003 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - TELECOM CABLE BLOCK DIAGRAM | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-0980-091-POWI-00001 | BLOCK DIAGRAM | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-1580-091-POWI-00001 | EQUIPMENT CATALOG AND CERTIFICATES | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-2105-074-POWI-00001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - INSTRUMENT DATASHEET - GAS DETECTION | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-2105-074-POWI-00002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - INSTRUMENT DATASHEET - MAC ESD PBSOUNDER & BEACON | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-2105-074-POWI-00003 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - INSTRUMENT DATASHEET - SMOKE & HEAT DETECTION | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-2105-074-POWI-00004 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - INSTRUMENT DATASHEET - GAS DETECTION | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-2105-074-POWI-00005 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - INSTRUMENT DATASHEET - MAC ESD PB SOUNDER & BEACON | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-2105-074-POWI-00006 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - INSTRUMENT DATASHEET - SMOKE & HEAT DETECTION | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-2105-076-POWI-00007 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - INSTRUMENT DATASHEET - GAS DETECTION | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-2105-076-POWI-00008 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - INSTRUMENT DATASHEET - MAC ESD PB SOUNDER & BEACON | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-2105-076-POWI-00009 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - INSTRUMENT DATASHEET - SMOKE & HEAT DETECTION | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-2105-091-POWI-00001 | INSTRUMENT DATA SHEETS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-2389-091-POWI-00001-001 | INTERCONNECTION DIAGRAM | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-3375-091-POWI-00001 | HMI SCREENS LAYOUT | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-4180-091-POWI-00001 | INSTRUMENTATION PANEL DRAWINGS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-4180-091-POWI-00002 | INSTRUMENTATION JUNCTIONBOX DRAWINGS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-4180-091-POWI-00003 | EQUIPMENT SUPPLIED GENERAL ARRANGEMENT | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-4302-091-POWI-00001 | INSTRUMENT SET POINT LIST | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-4306-074-POWI-00001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - BILL OF MATERIALS - F&G BULKS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-4306-074-POWI-00002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - BILL OF MATERIALS - F&G BULKS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-4306-074-POWI-00005 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - BILL OF MATERIALS - INSTRUMENT BULKS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-4306-074-POWI-00006 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - BILL OF MATERIALS - INSTRUMENT BULKS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-4306-076-POWI-00003 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - BILL OF MATERIALS - F&G BULKS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-4306-076-POWI-00007 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - BILL OF MATERIALS - INSTRUMENT BULKS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-4308-074-POWI-00001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - INSTRUMENT CABLE SCHEDULE | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-4308-074-POWI-00002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - INSTRUMENT CABLE SCHEDULE | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-4308-076-POWI-00003 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - INSTRUMENT CABLE SCHEDULE | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-4308-091-POWI-00001 | INSTRUMENT CABLE LIST | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-4327-091-POWI-00001 | I/O LIST | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-4380-091-POWI-00001 | MATERIALS INSTALLED IN HAZARDOUS AREA LIST | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-6612-091-POWI-00001 | INSTRUMENT LIST | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-8804-074-POWI-00001-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - FIRE & GAS EQUIPMENT LAYOUT | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-8804-074-POWI-00002-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - INSTRUMENT EQUIPMENT LAYOUT | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-8804-074-POWI-00003-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM - TELECOM EQUIPMENT LAYOUT | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-8804-074-POWI-00004-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - FIRE & GAS EQUIPMENT LAYOUT | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-8804-074-POWI-00005-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - INSTRUMENT EQUIPMENT LAYOUT | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-8804-074-POWI-00006-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT ROOM - TELECOM EQUIPMENT LAYOUT | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-8804-076-POWI-00007-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - FIRE & GAS EQUIPMENT LAYOUT | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-8804-076-POWI-00008-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - INSTRUMENT EQUIPMENT LAYOUT | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-8804-076-POWI-00009-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BATTERY ROOM - TELECOM EQUIPMENT LAYOUT | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-IN-8804-091-POWI-00001 | INSTRUMENT OUTLINE/DETAIL AND TERMINATION DRAWINGS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-JA-4372-091-POWI-00001 | DATA BOOK INDEX | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-JA-4372-091-POWI-00002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM ELECTRICAL DRAWING REGISTER | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-JA-4372-091-POWI-00003 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT DRAWING REGISTER | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-JA-6611-091-POWI-00001 | DOCUMENT SCHEDULE | IT / IM | JA - IM | R02 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-MH-1580-091-POWI-00001 | EQUIPMENT CATALOG AND CERTIFICATES | MECHANICAL | MH - HVAC | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-MH-2105-017-POWI-00001 | HVAC EQUIPMENT DATA SHEETS | MECHANICAL | MH - HVAC | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-MH-3328-017-POWI-00001-001 | HVAC SYSTEM - TYPICAL INSTALLATION DETAILS DRAWINGS | MECHANICAL | MH - HVAC | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-MH-4018-017-POWI-00001-001 | VENTILATION INLET & OUTLET PLAN SHOWING ALL DETAILS OF MAIN INLETS & OUTLETS NECESSARY FOR AREA CLASSIFICATION DRAWING | MECHANICAL | MH - HVAC | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-MH-4311-017-POWI-00001-001 | HVAC EQUIPMENT LIST | MECHANICAL | MH - HVAC | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-MH-4380-017-POWI-00001 | HVAC MATERIAL LIST | MECHANICAL | MH - HVAC | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-MH-4380-017-POWI-00002 | HVAC SYSTEM - LIST OF SPECIAL TOOLES | MECHANICAL | MH - HVAC | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-MH-7180-017-POWI-00001 | HVAC EQUIPMENT PERFORMANCE CURVES | MECHANICAL | MH - HVAC | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-MH-7739-017-POWI-00001 | HVA SYSTEM DETAILED DESCRIPTION AND OPERATION & MAINTENANCE MANUAL IN PORTUGUESE LANGUAGE | MECHANICAL | MH - HVAC | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-MH-7753-017-POWI-00001-001 | ELECTRICAL DIAGRAM ELECTRICAL DIAGRAM AND CAUSE & EFFECT MATRIX MAY BE EXECUTED BY OTHERS DISCIPLINES BUT SHALL BE SUPPORTED BY HVAC DISCIPLINE | MECHANICAL | MH - HVAC | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-MR-7771-091-POWI-00001 | MOTOR PERFORMANCE CURVES | MECHANICAL | MR - MECHANICAL ROTATING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-MS-1379-016-POWI-00001 | SNEPCO BONGA NORTH SSCB - THERMAL INSULATION CALCULATIONS. | MECHANICAL | MS - MECHANICAL STATIC | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-MS-8370-091-POWI-00001 | MECHANICAL HANDLING REPORT | MECHANICAL | MS - MECHANICAL STATIC | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-MS-8370-091-POWI-00002-001 | SSCB - MECHANICAL HANDLING LAY-OUT DRAWINGS | MECHANICAL | MS - MECHANICAL STATIC | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-MS-8370-091-POWI-00002-002 | SSCB - MECHANICAL HANDLING LAY-OUT DRAWINGS | MECHANICAL | MS - MECHANICAL STATIC | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-MS-8370-091-POWI-00003 | SSCB - MECHANICAL HANDLING STUDY | MECHANICAL | MS - MECHANICAL STATIC | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-MS-8370-091-POWI-00004 | SSCB - MECHANICAL HANDLING LIST OF SPECIAL TOOLS | MECHANICAL | MS - MECHANICAL STATIC | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-MX-1580-091-POWI-00001 | EQUIPMENT CATALOG AND CERTIFICATES | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-MX-2105-091-POWI-00001 | MECHANICAL EQUIPMENT DATA SHEETS | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-MX-2105-091-POWI-00010 | EQUIPMENT NOISE LEVEL DATA SHEETS | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-MX-2580-091-POWI-00001 | PASSIVE FIRE PROTECTION SYSTEM - DESIGN DRAWINGS | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-MX-2580-091-POWI-00001-001 | CROSS SECTION DRAWING / EXPLODED VIEW DIAGRAM WITH PARTS LIST | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-MX-2580-091-POWI-00002-001 | MECHANICAL SEAL DRAWING | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-MX-4024-091-POWI-00001-001 | MECHANICAL EQUIPMENT NAMEPLATE DRAWINGS | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-MX-6180-016-POWI-00001 | WEIGHT CONTROL REPORT | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-MX-6612-091-POWI-00001 | EQUIPMENT SCHEDULE | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-MX-7771-091-POWI-00001 | PERFORMANCE CURVES | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-NA-4354-091-POWI-00001 | RECOMMENDED SPARES FOR TWO YEARS OPERATION | NA - MAINTENANCE | NA - MAINTENANCE | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-NA-6034-091-POWI-00001 | LUBE OIL & OPERATING FLUIDS SCHEDULE | NA - MAINTENANCE | NA - MAINTENANCE | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-OA-4316-091-POWI-00001 | UTILITIES CONSUMPTION LIST | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-OA-4316-091-POWI-00002 | UTILITIES CONSUMPTION LIST | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-OA-4811-091-POWI-00001 | DATA BOOK | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-OA-4811-091-POWI-00002 | DATA BOOK | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-OA-5705-091-POWI-00001 | DISPATCH DOSSIER | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-OA-6039-091-POWI-00001 | INSTALLATION OPERATION AND MAINTENANCE MANUAL | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-QA-1580-091-POWI-00001 | EQUIPMENT HAZARDOUS AREA CERTIFICATES | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-QA-1580-091-POWI-00002 | CLASSIFICATION SOCIETY CERTIFICATES | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-QA-1580-091-POWI-00003 | MATERIAL TEST CERTIFICATES | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-QA-1580-091-POWI-00004 | PRESSURE TEST CERTIFICATES | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-QA-1580-091-POWI-00005 | INSTRUMENT TEST AND CALIBRATION CERTIFICATES | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-QA-5733-091-POWI-00001 | SNEPCO BONGA NORTH SSCB PROJECT - INSPECTION & TEST PLAN | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-QA-5733-091-POWI-00002 | INSPECTION AND TEST PLAN | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-QA-5798-091-POWI-00001 | SNEPCO BONGA NORTH SSCB PROJECT - QUALTIY PLAN | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-QA-5798-091-POWI-00002 | QUALITY PLAN | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-QA-5798-091-POWI-00003 | SNEPCO BONGA NORTH SSCB PACKAGE - QUALITY CONTROL PLAN | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-QA-6050-091-POWI-00001 | FACTORY ACCEPTANCE TEST REPORT | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-QA-6180-016-POWI-00003 | WEIGHT PROCEDURE | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-QA-6180-016-POWI-00004 | WPS / WPQRS | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-QA-6180-091-POWI-00001 | PRESSURE TEST PROCEDURES | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-QA-6180-091-POWI-00002 | PERFORMANCE TESTING AND ACCEPTANCE TEST PROCEDURES | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-QA-6180-091-POWI-00005 | NON-DESTRUCTIVE EXAMINATION PROCEDURES (NDE) | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-RA-6068-090-POWI-00001 | SURFACE PREPARATION AND PAINTING PROCEDURE | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-RA-6068-091-POWI-00002 | HOT DIPPED GALVANIZED PROCEDURE | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-RA-6068-092-POWI-00003 | SURFACE PREPARATION AND INTERNAL COATING | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-SA-6028-091-POWI-00001 | LIST OF SPECIAL TOOLS | SA - LOGISTICS | SA - LOGISTICS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-SA-6028-091-POWI-00002 | UNPACKING AND PRESERVATION PROCEDURE | SA - LOGISTICS | SA - LOGISTICS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-SA-6028-091-POWI-00003 | LIST OF SPECIAL TOOLS | SA - LOGISTICS | SA - LOGISTICS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-SA-6033-016-POWI-00001 | ARCHITECTURE DATA SHEETS | SA - LOGISTICS | SA - LOGISTICS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-SA-6033-091-POWI-00001-001 | LIFTING ARRANGEMENT DRAWING | SA - LOGISTICS | SA - LOGISTICS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-TA-0980-086-POWI-00001-001 | TELECOM CONNECTION DIAGRAM | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-TA-0980-086-POWI-00002-001 | TELECOM JUNCTIONBOX DRAWINGS | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-TA-0980-091-POWI-00001-001 | MCT DRAWINGS | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-TA-2105-086-POWI-00001 | TELECOM EQUIPMENT DATA SHEETS | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-TA-3309-086-POWI-00001 | TELECOM MATERIAL LIST | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-TA-4018-086-POWI-00001-001 | TELECOMMUNICATIONS GENERAL ARRANGEMENT CABLE ROUTING & SUPPORT PLAN. | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-TA-4024-091-POWI-00001-001 | NAMEPLATE DRAWINGS | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-TA-4308-086-POWI-00001 | TELECOM CABLE LIST | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-260191-300-TA-4308-091-POWI-00001 | MCT (MULTI CABLE TRANSIT) LIST | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_260191-SSCB MODULE_LNPT
BNO-262884-300-AA-0709-091-POWI-10001 | RISK REGISTER | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-0709-091-POWI-10002 | RISK MANGEMENT PLAN | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-5798-091-POWI-10001 | PROJECT EXECUTION PLAN | PMT | AA - PROJECT MANAGEMENT | R02 | NAO |  | Diretorio Vendor | ENGINEERING CONSOLIDATION |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-5800-091-POWI-10001 | INTERFACE MANAGEMENT PLAN | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-5880-091-POWI-10001 | COMMUNICATION PLAN | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10001 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10002 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10003 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10004 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10005 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10006 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10007 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10008 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10009 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10010 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10011 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10012 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10013 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10014 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10016 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10017 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10018 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10019 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10020 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10025 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10026 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10027 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10028 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10029 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10030 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10031 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10032 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10033 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10034 | WEEKLY PROJECT STATUS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10035 | WEEKLY PROJECT REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10036 | PROJECT REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10037 | PROJECT REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10038 | PROJECT REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-AA-6944-091-POWI-10100 | PROGRESS MEASUREMENT SYSTEM | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-BA-6065-091-POWI-10001 | WELDING PROCEDURE | CONSTRUCTION | BA - CONSTRUCTION | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-BC-4354-091-POWI-10002 | RECOMM INSTALLATION COMMISSIONING AND START UP SPARES LIST | BC - COMMISSIONING | BC - COMMISSIONING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-BC-6180-091-POWI-10001 | COMMISSIONING AND START UP PROCEDURE | BC - COMMISSIONING | BC - COMMISSIONING | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-BC-6180-091-POWI-10002 | COMMISSIONING AND START UP PROCEDURE | BC - COMMISSIONING | BC - COMMISSIONING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-CB-2307-016-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - EQUIPMENT SUPPORT DETAIL DRAWING | CB - ARCHITECTURAL | CB - ARCHITECTURAL | A04 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 4 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-CB-2307-016-POWI-10002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - FLOOR AND WALL PENETRATION LAYOUT AND DETAILS DRAWING | CB - ARCHITECTURAL | CB - ARCHITECTURAL | A04 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-CB-3309-016-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - MATERIAL REQUISITION - DOORS | CB - ARCHITECTURAL | CB - ARCHITECTURAL | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-CB-3309-016-POWI-10002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - MATERIAL REQUISITION - INSULATION | CB - ARCHITECTURAL | CB - ARCHITECTURAL | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-CB-4018-016-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ARCHITECTURAL LAYOUT & SECTION DETAIL | CB - ARCHITECTURAL | CB - ARCHITECTURAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-CB-7880-016-POWI-10001 | ARCHITECTURE DATA SHEETS | CB - ARCHITECTURAL | CB - ARCHITECTURAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-CB-7880-016-POWI-10002 | ERECTION AND INSTALLATION PROCEDURES | CB - ARCHITECTURAL | CB - ARCHITECTURAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | AFD - APPROVED FOR DESIGN |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-CS-2332-016-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - STOOLS FOUNDATION LOADING INFORMATION AND DETAILS DRAWING | STRUCTURAL | CS - STRUCTURAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-CS-2358-016-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - STRUCTURAL STEEL CONNECTION DETAIL | STRUCTURAL | CS - STRUCTURAL | A05 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-CS-2358-091-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - TEMPORARY LIFTING INSTALLATION AIDS DETAIL DRAWING | STRUCTURAL | CS - STRUCTURAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-CS-2408-016-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - STRUCTURAL GENERAL NOTES | STRUCTURAL | CS - STRUCTURAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-CS-2408-016-POWI-10001-001 | STRUCTURAL STEEL FRAMING PLAN & ELEVATION | STRUCTURAL | CS - STRUCTURAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-CS-2408-016-POWI-10002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - STRUCTURAL WALL AND DECK PLATE ARRANGEMENT | STRUCTURAL | CS - STRUCTURAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-CS-2408-016-POWI-10003 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HANDRAIL - PLATFORM & STAIRS LAYOUT AND DETAIL DRAWING | STRUCTURAL | CS - STRUCTURAL | A04 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-CS-2408-016-POWI-10004 | SSCB PACKAGE MODULE OVERALL ISOMETRIC ASSEMBLY | STRUCTURAL | CS - STRUCTURAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-CS-2408-016-POWI-10005 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE DRAINAGE & PPE GUTTER LAYOUT AND DETAIL DRAWING (3 SHEETS) | STRUCTURAL | CS - STRUCTURAL | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-CS-4018-016-POWI-10001-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - OVERALL ISOMETRIC ASSEMBLY | STRUCTURAL | CS - STRUCTURAL | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-CS-4018-016-POWI-10002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HANDRAIL PLATFORM & STAIRS LAYOUT AND DETAIL DRAWING (13 SHEET) | STRUCTURAL | CS - STRUCTURAL | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-CS-8180-016-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE - STRUCTURAL DESIGN REPORT - INSERVICE ANALYSIS | STRUCTURAL | CS - STRUCTURAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-CS-8180-016-POWI-10002 | SNEPCO BONGA NORTH SSCB PACKAGE - STRUCTURAL DESIGN REPORT - PRESERVICE ANALYSIS | STRUCTURAL | CS - STRUCTURAL | A04 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-CS-8180-016-POWI-10003 | SNEPCO BONGA NORTH SSCB PACKAGE - STRUCTURAL DESIGN REPORT - FATIGUE ANALYSIS | STRUCTURAL | CS - STRUCTURAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-CS-8180-016-POWI-10004 | SNEPCO BONGA NORTH SSCB PACKAGE - MISCELANEOUS CALCULATION DESIGN REPORT | STRUCTURAL | CS - STRUCTURAL | A03 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION | IFA RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-0980-076-POWI-10001 | COMPARTMENT DETAILS REPORT 6.6KV SWITCHBOARD - MCC-7355-D-01 | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | TRANSMITTAL | IFA RETURNED AS CODE 4 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-0980-076-POWI-10002 | COMPARTMENT DETAILS REPORT 400V SWITCHBOARD - SB-7446-E-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | TRANSMITTAL |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-0980-076-POWI-10003 | COMPARTMENT DETAILS REPORT 400V SWITCHBOARD - MCC-7456-E-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-0980-076-POWI-10004 | COMPARTMENT DETAILS REPORT 400V SWITCHBOARD - MCC-7457-E-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS | IFA RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-1380-072-POWI-10001 | BATTERY CALCULATION SHEETS UPS | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-1401-076-POWI-10001 | EQUIPMENT INCLUDING CIRCUIT BREAKERS AND RELAYS CATALOG AND CERTIFICATES | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-1580-076-POWI-10101 | EQUIPMENT, INCLUDING CIRCUIT BREAKERS AND RELAYS, CATALOG AND CERTIFICATES | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2105-076-POWI-10001 | ELECTRICAL EQUIPMENT DATA SHEETS (COMPARTMENT MATRIX) - 400V SWITCHBOARDS | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2105-076-POWI-10002 | UTILITIES SCHEDULE - 6.6KV SWITCHBOARD | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2105-076-POWI-10003 | UTILITIES SCHEDULE - 400V SWITCHBOARDS | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2105-076-POWI-10004 | DRIVE RATING MATRIX 400V SWITCHBOARD FEEDER CIRCUITS | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2180-072-POWI-10001 | CUSTOMER DATASHEET - UPS-7246-V-01 AND UPS-7247-V-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2180-072-POWI-10002 | CUSTOMER DATASHEET - UPS-7557-F-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2180-072-POWI-10003 | CUSTOMER DATASHEET - UPS-7555-F-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2180-072-POWI-10004 | CUSTOMER DATASHEET - UPS-7556A-F-01 AND UPS-7556B-F-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2180-074-POWI-10001 | TECHNICAL DATASHEETS FOR TRANSFORMERS | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | AFD - APPROVED FOR DESIGN |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2180-074-POWI-10002 | WEIGHT DATA SHEETS FOR TRANSFORMERS | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2180-076-POWI-10002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL INSTRUMENT & TELECOM CABLE DATASHEET | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Diretorio Vendor | CANCELADO |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2384-072-POWI-10001 | SINGLE LINE DIAGRAM FOR UPS-7246-V-01 & UPS-7247-V-01 | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2384-072-POWI-10002 | SINGLE LINE DIAGRAM FOR UPS-7557-F-01 | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2384-072-POWI-10003 | SINGLE LINE DIAGRAM FOR UPS-7555-F-01 | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2384-072-POWI-10004 | SINGLE LINE DIAGRAM FOR UPS-7556A-F-01 & UPS-7556B-F-01 | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2384-076-POWI-10001-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - LIGHTING AND SMALL POWER - SINGLE LINE DIAGRAM NORMAL DB | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2384-076-POWI-10002-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - LIGHTING AND SMALL POWER - SINGLE LINE DIAGRAM ESSENTIAL DB | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ENGINEERING CONSOLIDATION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2384-076-POWI-10003-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - LIGHTING AND SMALL POWER - SINGLE LINE DIAGRAM EMERGENCY DB | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2384-076-POWI-10004 | SINGLE LINE DIAGRAM - 6.6KV SWITCHBOARD MCC-7355-D-01 | ELECTRICAL | EA - ELECTRICAL | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2384-076-POWI-10005 | SINGLE LINE DIAGRAM - 400V SWITCHBOARD SB-7446-E-01 TIERS FAA - FAF | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2384-076-POWI-10007 | SINGLE LINE DIAGRAM - 400V SWITCHBOARD MCC-7456-E-01 | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2384-076-POWI-10008 | SINGLE LINE DIAGRAM - 400V SWITCHBOARD MCC-7457-E-01 | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2384-076-POWI-10009 | SINGLE LINE DIAGRAM - 400V SWITCHBOARD SB-7446-E-01 TIERS RAD - RAC | 3D - BIM MANAGEMENT | 3D - BIM MANAGEMENT | A04 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2384-076-POWI-10010 | SINGLE LINE DIAGRAM - 400V SWITCHBOARD SB-7446-E-01 TIER RAB | ELECTRICAL | EA - ELECTRICAL | A04 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2384-076-POWI-10011 | SINGLE LINE DIAGRAM - 400V SWITCHBOARD MCC-7456-E-01 TIERS RAF - RAC | ELECTRICAL | EA - ELECTRICAL | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-006-POWI-10002 | SCHEMATIC DIAGRAM DOL STARTER EPC3/HPU PACKAGE 2.2KW (TYPE 4) | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-017-POWI-10001 | SCHEMATIC DIAGRAM DOL STARTER HVAC LOADS 75KW (TYPE 3) | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-040-POWI-10001 | SCHEMATIC DIAGRAM 132KW VFD FEEDER | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-054-POWI-10001 | SCHEMATIC DIAGRAM DOL STARTER EPC3/HPU PACKAGE >=7.5KW <=15KW (TYPE 4) | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-072-POWI-10001 | SCHEMATIC DIAGRAM FOR UPS-7246-V-01 & UPS-7247-V-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-072-POWI-10002 | SCHEMATIC DIAGRAM FOR UPS-7557-F-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-072-POWI-10003 | SCHEMATIC DIAGRAM FOR UPS-7555-F-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-072-POWI-10004 | SCHEMATIC DIAGRAM FOR UPS-7556A-F-01 & UPS-7556B-F-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-073-POWI-10001 | SCHEMATIC DIAGRAM - BPCS COMPONENT CONNECTIONS MCC-7355-D-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-073-POWI-10002 | SCHEMATIC DIAGRAM - BPCS IO CONNECTIONS MCC-7355-D-01 | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS | IFA RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-074-POWI-10001 | ELECTRICAL SCHEMATIC AND WIRING DIAGRAM FOR TRANSFORMERS | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-074-POWI-10002 | SCHEMATIC DIAGRAM ARC FLASH DETECTION INCOMER A MCC-7456-E-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-074-POWI-10003 | SCHEMATIC DIAGRAM ARC FLASH DETECTION INCOMER B MCC-7456-E-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-074-POWI-10004 | SCHEMATIC DIAGRAM - BPCS COMPONENT CONNECTIONS SB-7446-E-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-074-POWI-10005 | SCHEMATIC DIAGRAM - BPCS IO CONNECTIONS SB-7446-E-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-074-POWI-10006 | SCHEMATIC DIAGRAM - BPCS COMPONENT CONNECTIONS MCC-7456-E-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-074-POWI-10007 | SCHEMATIC DIAGRAM - BPCS IO CONNECTIONS MCC-7456-E-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-074-POWI-10008 | SCHEMATIC DIAGRAM - BPCS COMPONENT CONNECTIONS MCC-7457-E-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-074-POWI-10009 | SCHEMATIC DIAGRAM - BPCS IO CONNECTIONS MCC-7457-E-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-074-POWI-10010 | SCHEMATIC DIAGRAM PURGE PANEL SUPPLY FUSESWITCH FEEDER | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-074-POWI-10011 | SCHEMATIC DIAGRAM 16A CONTRACTOR FEEDER DUCT HEATER | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-074-POWI-10012 | SCHEMATIC DIAGRAM 80A CONTRACTOR FEEDER DUCT HEATER | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10001 | SCHEMATIC DIAGRAM - INCOMER A MCC-7355-D-01 | ELECTRICAL | EA - ELECTRICAL | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10002 | SCHEMATIC DIAGRAM - INCOMER B MCC-7355-D-01 | ELECTRICAL | EA - ELECTRICAL | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10003 | SCHEMATIC DIAGRAM - BUS TIE MCC-7355-D-01 | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10004 | SCHEMATIC DIAGRAM - BUS EARTH & AUXILIARY SUPPLIES | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10005 | SCHEMATIC DIAGRAM - TRANSFORMER FEEDER | ELECTRICAL | EA - ELECTRICAL | A04 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10006-001 | SCHEMATIC DIAGRAM DISTRIBUTION BOARD DB-7660-N-01 | ELECTRICAL | EA - ELECTRICAL | A03 | NAO |  | Diretorio Vendor | TRANSMITTAL |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10007-001 | SCHEMATIC DIAGRAM DISTRIBUTION BOARD DB-7491-N-01 | ELECTRICAL | EA - ELECTRICAL | A03 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10008-001 | SCHEMATIC DIAGRAM DISTRIBUTION BOARD DB-7492-N-01 | ELECTRICAL | EA - ELECTRICAL | A03 | NAO |  | Diretorio Vendor | TRANSMITTAL |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10009 | SCHEMATIC DIAGRAMS FOR ELECTRICAL - INTERCONNECTION 6.6KV SWITCHBOARD MCC-7355-D-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10010 | SCHEMATIC DIAGRAMS FOR ELECTRICAL - INTERCONNECTION ANTI-CON HEATERS 400V SWITCHBOARD SB-7446-E-01 | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10011 | SCHEMATIC DIAGRAMS FOR ELECTRICAL - INTERCONNECTION ANTI-CON HEATERS 400V SWITCHBOARD MCC-7456-E-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10012 | SCHEMATIC DIAGRAMS FOR ELECTRICAL - INTERCONNECTION 400V SWITCHBOARD MCC-7457-E-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10013 | SCHEMATIC DIAGRAM INCOMER A 400V SWITCHBOARD MCC-7456-E-01 | ELECTRICAL | EA - ELECTRICAL | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10014 | SCHEMATIC DIAGRAM - INCOMER 400V SWITCHBOARD MCC-7457-E-01 | ELECTRICAL | EA - ELECTRICAL | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10015 | SCHEMATIC DIAGRAM - INCOMER A 400V SWITCHBOARD SB-7446-E-01 | ELECTRICAL | EA - ELECTRICAL | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10016 | SCHEMATIC DIAGRAM - INCOMER B 400V SWITCHBOARD SB-7446-E-01 | ELECTRICAL | EA - ELECTRICAL | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10017 | SCHEMATIC DIAGRAM - ACB FEEDER 400V SWITCHBOARD SB-7446-E-01 | ELECTRICAL | EA - ELECTRICAL | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10018 | SCHEMATIC DIAGRAM - INCOMER B 400V SWITCHBOARD MCC-7456-E-01 | ELECTRICAL | EA - ELECTRICAL | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 4 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10019 | SCHEMATIC DIAGRAM <=200A FUSESWITCH FEEDER | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10020 | SCHEMATIC DIAGRAM >200A FUSESWITCH FEEDER | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10021 | SCHEMATIC DIAGRAM 90KW SOFT STARTER | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10022 | SCHEMATIC DIAGRAM 18.5KW VFD FEEDER | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10023 | SCHEMATIC DIAGRAM BUS EARTH AND AUXILIARY SUPPLIES BUS 'B' | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10024 | SCHEMATIC DIAGRAM INTERCONNECTION BUSWIRING 400V SWITCHBOARD SB-7446-E-01 | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10025 | SCHEMATIC DIAGRAM INTERCONNECTION BUSWIRING 400V SWITCHBOARD MCC-7456-E-01 | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10026 | SCHEMATIC DIAGRAM ARC FLASH DETECTION INCOMER A SB-7446-E-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10027 | SCHEMATIC DIAGRAM ARC FLASH DETECTION INCOMER B SB-7446-E-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10028 | SCHEMATIC DIAGRAM 63A CONTACTOR FEEDER LUBE OIL HEATER | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10029 | SCHEMATIC DIAGRAM 125A CONTACTOR FEEDER WELDING SOCKET OUTLET | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10030 | SCHEMATIC DIAGRAM DOL STARTER STANDARD <=5.5KW (TYPE 1) | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10031 | SCHEMATIC DIAGRAM DOL STARTER STANDARD >=7.5KW <=22KW (TYPE 1) | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10032 | SCHEMATIC DIAGRAM DOL STARTER STANDARD 30-37.5KW (TYPE 1) | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10033 | SCHEMATIC DIAGRAM DOL STARTER SOLAR PACKAGE 15KW <=22KW (TYPE 2) | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10034 | SCHEMATIC DIAGRAM DOL STARTER HVAC LOADS <=5.5KW (TYPE 3) | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10035 | SCHEMATIC DIAGRAM DOL STARTER HVAC LOADS 15KW (TYPE 3) | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10036 | SCHEMATIC DIAGRAM DOL STARTER HVAC LOADS >=30KW <75KW (TYPE 3) | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-2580-076-POWI-10037 | SCHEMATIC DIAGRAM DOL STARTER STANDARD <=5.5KW (TYPE 1) C/W MOTOR HEATER | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-3328-076-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - CABLE LADDER & TRAY FILLING REPORT | ELECTRICAL | EA - ELECTRICAL | R02 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-3328-091-POWI-10001 | PROTECTION RELAY SETTING SCHEDULE - 6.6KV SWITCHBOARD MCC-7355-D-01 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-3328-091-POWI-10002 | PROTECTION RELAY SETTING SCHEDULE - 400V SWITCHBOARD SB-7446-E-01 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-3328-091-POWI-10003 | PROTECTION RELAY SETTING SCHEDULE - 400V SWITCHBOARD MCC-7456-E-01 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4005-076-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - CABLE LADDER AND CABLE TRAY - LAYOUT | ELECTRICAL | EA - ELECTRICAL | R02 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4005-076-POWI-10002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - CABLE ROUTING SCHEDULE | ELECTRICAL | EA - ELECTRICAL | R02 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-017-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - GENERAL ARRANGEMENT FOR HVAC DUCT HEATER THYRISTOR CONTROL PANEL. | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | TRANSMITTAL | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-072-POWI-10001 | GENERAL ARRANGEMENT DRAWING FOR UPS-7246-V-01 & UPS-7247-V-01 | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-072-POWI-10002 | GENERAL ARRANGEMENT DRAWING FOR UPS-7557-F-01 | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-072-POWI-10003 | GENERAL ARRANGEMENT DRAWING FOR UPS-7555-F-01 | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-072-POWI-10004 | GENERAL ARRANGEMENT DRAWING FOR UPS-7556A-F-01 & UPS-7556B-F-01 | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-072-POWI-10005 | BATTERY ISOLATOR DRAWING FOR IS-7246-V-01 & IS-7247-V-01 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-072-POWI-10006 | BATTERY ISOLATOR DRAWING FOR IS-7557-F-01 & IS-7557-F-02 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-072-POWI-10007 | BATTERY ISOLATOR DRAWING FOR IS-7555-F-01 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-072-POWI-10008 | BATTERY ISOLATOR DRAWING FOR IS-7556A-F-01 & IS-7556B-F-01 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-072-POWI-10009 | BATTERY RACK DRAWING FOR BAT-7246-V-01 & BAT-7247-V-01 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-072-POWI-10010 | BATTERY RACK DRAWING FOR BAT-7555-F-01 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-072-POWI-10011 | BATTERY RACK DRAWING FOR BAT-7556A-F-01 & BAT-7556B-F-01 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-072-POWI-10012 | BATTERY RACK DRAWING FOR BAT-7557-F-01 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-073-POWI-10001-001 | GENERAL ARRANGEMENT - 6.6KV SWITCHBOARD MCC-7355-D-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-073-POWI-10002 | GENERAL ARRANGEMENT 6.6KV SWITCHBOARD MCC-7355-D-01 - ARC DUCT LAYOUT | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-073-POWI-10003-001 | GENERAL ARRANGEMENT - 400V SWITCHBOARD - SB-7446-E-01 | ELECTRICAL | EA - ELECTRICAL | A06 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-073-POWI-10004-001 | GENERAL ARRANGEMENT - 400V SWITCHBOARD - MCC-7456-E-01 | ELECTRICAL | EA - ELECTRICAL | A06 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-073-POWI-10005-001 | GENERAL ARRANGEMENT - 400V SWITCHBOARD - MCC-7457-E-01 | ELECTRICAL | EA - ELECTRICAL | A04 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-073-POWI-10006-001 | GENERAL ARRANGEMENT - DISTRIBUTION BOARD - DB-7660-N-01 AND DB-749*-N-01 | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-073-POWI-10007 | CASTELL INTERLOCK 6.6KV SWITCHBOARD | ELECTRICAL | EA - ELECTRICAL | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-074-POWI-10001 | GENERAL ARRANGEMENT FOR DRAWING TRANSFORMERS | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-074-POWI-10002 | NAMEPLATE FORMAT DRAWING FOR TRANSFORMERS | ELECTRICAL | EA - ELECTRICAL | A05 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-074-POWI-10003 | GENERAL ARRANGEMENT DRAWING FOR RETENTION BUND | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | CANCELADO | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-091-POWI-10001 | ELECTRICAL EQUIPMENT NAMEPLATE DRAWINGS (LABEL DRAWINGS) - MAIN TAG & RATING PLATE 6.6KV SWITCHBOARD MCC-7355-D-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-091-POWI-10002 | ELECTRICAL EQUIPMENT NAMEPLATE DRAWINGS (LABEL DRAWINGS) - COMPARTMENT TAG PLATE 6.6KV SWITCHBOARD MCC-7355-D-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-091-POWI-10003-001 | ELECTRICAL EQUIPMENT NAMEPLATE DRAWINGS (LABEL DRAWINGS) - MAIN TAG & RATING PLATE 400V SWITCHBOARD SB-7446-E-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-091-POWI-10004-001 | COMPARTMENT TAG PLATE 400V SWITCHBOARD SB-7446-E-01 | ELECTRICAL | EA - ELECTRICAL | A04 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-091-POWI-10005-001 | ELECTRICAL EQUIPMENT NAMEPLATE DRAWINGS (LABEL DRAWINGS) - MAIN TAG & RATING PLATE 400V SWITCHBOARD MCC-7456-E-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-091-POWI-10006-001 | COMPARTMENT TAG PLATE 400V SWITCHBOARD MCC-7456-E-01 | ELECTRICAL | EA - ELECTRICAL | A05 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-091-POWI-10007-001 | ELECTRICAL EQUIPMENT NAMEPLATE DRAWINGS (LABEL DRAWINGS) - MAIN TAG & RATING PLATE 400V SWITCHBOARD MCC-7457-E-01 | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-091-POWI-10008-001 | COMPARTMENT TAG PLATE 400V SWITCHBOARD MCC-7457-E-01 | ELECTRICAL | EA - ELECTRICAL | A04 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-091-POWI-10009-001 | ELECTRICAL EQUIPMENT NAMEPLATE DRAWINGS (LABEL DRAWINGS) - MAIN TAG & RATING PLATE DISTRIBUTION BOARD DB-7660-N-01 | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | TRANSMITTAL |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-091-POWI-10010-001 | ELECTRICAL EQUIPMENT NAMEPLATE DRAWINGS (LABEL DRAWINGS) - MAIN TAG & RATING PLATE DISTRIBUTION BOARD DB-7491-N-01 | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | TRANSMITTAL |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4018-091-POWI-10011-001 | ELECTRICAL EQUIPMENT NAMEPLATE DRAWINGS (LABEL DRAWINGS) - MAIN TAG & RATING PLATE DISTRIBUTION BOARD DB-7492-N-01 | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | TRANSMITTAL |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4024-076-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - LIGHTING AND SMALL POWER EQUIPMENT - LAYOUT | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4025-091-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - LIGHTING AND SMALL POWER - CABLE SCHEDULE | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4025-091-POWI-10002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - LIGHTING AND SMALL POWER - BLOCK DIAGRAM | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4025-091-POWI-10003 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - LIGHTING AND SMALL POWER - INTERCONNECTION WIRING DIAGRAM | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4306-076-POWI-10001 | ELECTRICAL MATERIAL LIST (BILL OF MATERIALS) - 6.6KV SWITCHBOARD MCC-7355-D-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4306-076-POWI-10002 | ELECTRICAL MATERIAL LIST (BILL OF MATERIALS) - 400V SWITCHBOARD SB-7446-E-01 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4306-076-POWI-10003 | ELECTRICAL MATERIAL LIST (BILL OF MATERIALS) - 400V SWITCHBOARD MCC-7456-E-01 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4306-076-POWI-10004 | ELECTRICAL MATERIAL LIST (BILL OF MATERIALS) - 400V SWITCHBOARD MCC-7457-E-01 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4306-076-POWI-10005 | ELECTRICAL MATERIAL LIST (BILL OF MATERIALS) - DISTRIBUTION BOARD DB-7660-N-01 DB-7491-N-01 & DB-7492-N-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4306-076-POWI-10010 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE ELECTRICAL BULK MATERIAL (SCOPE OF WS) | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4308-076-POWI-10001 | ELECTRICAL CABLE LIST | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | TRANSMITTAL | IFA RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4329-076-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - LOAD LIST NORMAL DB - ESSENTIAL DB AND EMERGENCY DB | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4380-074-POWI-10001 | LIST OF SUB-VENDOR AND SUB-SUPPLIED ITEMS FOR TRANSFORMERS | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4380-074-POWI-10002 | CATALOGUE DATA/LIST OF ACCESSORIES FOR TRANSFORMERS | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4380-076-POWI-10002 | EX REGISTER | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-4606-076-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL LIGHTING CALCULATION | ELECTRICAL | EA - ELECTRICAL | A03 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-6067-072-POWI-10001 | FAT PROCEDURE | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-6067-074-POWI-10001 | PERFORMANCE TESTING & FACTORY / FIELD ACCEPTANCE TEST (FAT) PROCEDURE FOR TRANSFORMERS | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-6180-074-POWI-10001 | SITE INSTALLATION & TEST PROCEDURE | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS | IFR RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-7180-072-POWI-10001 | TEST REPORTS - PEW 1100-220/230-EN-D | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-7180-072-POWI-10002 | ACCEPTANCE TEST REPORTS (FAT) - PEW 1100-220/230-EN-D | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-7180-072-POWI-10003 | TEST REPORTS - SDC 125-100 | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-7180-072-POWI-10004 | ACCEPTANCE TEST REPORTS (FAT) - SDC 125-100 | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-7180-072-POWI-10005 | TEST REPORTS - SDC 48-100 | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-7180-072-POWI-10006 | ACCEPTANCE TEST REPORTS (FAT) - SDC 48-100 | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-7180-072-POWI-10007 | TEST REPORTS - SDC 24-400 | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-7180-072-POWI-10008 | ACCEPTANCE TEST REPORTS (FAT) - SDC 24-400 | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-7180-074-POWI-10001 | FACTORY ACCEPTANCE TEST (FAT) REPORTS FOR TRANSFORMERS | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-7180-083-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - FIRE AND GAS DEVICES IFAT PROCEDURE | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-7180-091-POWI-10017 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - IFAT PROCEDURE | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-7770-074-POWI-10001 | ARC FLASH DETECTION 400V LV SWITCHBOARD MCC-7456-E-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-7770-076-POWI-10001 | CURRENT & POTENTIAL (CT/VT) TRANSFORMERS CURVES - 6.6KV SWITCHBOARD MCC-7355-D-01 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-7770-076-POWI-10013 | ARC FLASH DETECTION 6.6KV SWITCHBOARD MCC-7355-D-01 | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-7770-076-POWI-10014 | ARC FLASH DETECTION 400V LV SWITCHBOARD SB-7446-E-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-7771-076-POWI-10001 | PANEL SUMMARY SPECIFICATION 6.6KV SWITCHBOARD MCC-7355-D-01 | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-7771-076-POWI-10002 | PANEL SUMMARY SPECIFICATION 400V SWITCHBOARD SB-7446-E-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-7771-076-POWI-10003 | PANEL SUMMARY SPECIFICATION 400V SWITCHBOARD MCC-7456-E-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-7771-076-POWI-10004 | PANEL SUMMARY SPECIFICATION 400V SWITCHBOARD MCC-7457-E-01 | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-7771-076-POWI-10005 | SAFOP TOR REPORT | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-7771-076-POWI-10006 | SAFOP CLOSEOUT REPORT | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-7880-074-POWI-10101 | LIST OF SUB-VENDOR AND SUB-SUPPLIED ITEMS FOR TRANSFORMERS | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-8804-074-POWI-10001 | COMMUNICATIONS DIAGRAM - 400V SWITCHBOARD: MCC-7457-E-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-8804-076-POWI-10001 | COMMUNICATION DIAGRAM 6.6KV SWITCHBOARD MCC-7355-D-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-8804-076-POWI-10002-001 | COMMUNICATION DIAGRAM - 400V SWITCHBOARD SB-7446-E-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-8804-076-POWI-10003-001 | COMMUNICATIONS DIAGRAM - 400V SWITCHBOARD MCC-7456-E-01 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-8804-091-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - MULTI CABLE TRANSIT - SCHEDULE | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-8804-091-POWI-10002-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - MULTI CABLE TRANSIT - LAYOUT | ELECTRICAL | EA - ELECTRICAL | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-EA-8809-091-POWI-10001-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - EARTHING - LAYOUT | ELECTRICAL | EA - ELECTRICAL | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-FA-5803-091-POWI-10001 | PROJECT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 4 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-FA-5803-091-POWI-10002 | FABRICATION / PRODUCTION SCHEDULE- L2 | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-HX-2107-091-POWI-10001 | SAFETY EQUIPMENT AND MISCELLANEOUS DATA SHEETS | TECHNICAL SAFETY | HX - HSE | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-HX-2318-091-POWI-10001 | ESCAPE ROUTE SAFETY EQUIPMENT & SAFETY SIGN | TECHNICAL SAFETY | HX - HSE | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-HX-5798-091-POWI-10001 | H S & E PLAN | TECHNICAL SAFETY | HX - HSE | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-IN-0901-074-POWI-10001-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - FIRE & GAS SYSTEM - BLOCK DIAGRAM | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-IN-1580-074-POWI-10001 | EQUIPMENT HAZARDOUS AREA CERTIFICATES | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-IN-2105-076-POWI-10001 | INSTRUMENTATION DATA SHEET - HVAC PACU | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-IN-2180-076-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - F&G BULK DATASHEET | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-IN-2180-076-POWI-10002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL INSTRUMENT & TELECOM CABLE DATASHEET | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-IN-2312-017-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - CAUSE & EFFECTS CHART | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | TRANSMITTAL | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-IN-2335-017-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE HVAC SYSTEM - INSTRUMENTS - HOOK-UP (6 SHEETS) | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-IN-2347-074-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - FIRE AND GAS LOOP DRAWING | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-IN-3328-074-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - EIT TYPICAL INSTALLATION DETAIL DRAWING INSTRUMENT INSTALLATION DETAIL | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-IN-3328-074-POWI-10002-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - FIRE AND GAS TYPICAL INSTALLATION DETAIL | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-IN-3328-074-POWI-10003 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM -TYPICAL INSTALLATION DETAILS | ELECTRICAL | EA - ELECTRICAL | A03 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-IN-3328-091-POWI-10001 | PASSIVE FIRE PROTECTION INSTALLATION AND REPAIR PROCEDURE | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | CANCELADO | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-IN-4018-073-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - CONTROL PANEL GA INCLUDING COMPONENT LIST | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ENGINEERING CONSOLIDATION | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-IN-4018-074-POWI-10001-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - EQUIPMENT PLAN - LAYOUT | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-IN-4018-083-POWI-10001 | FIRE AND GAS JUNCTION BOX - GENERAL ARRANGEMENT DRAWING | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-IN-4024-074-POWI-10001-001 | FIRE & GAS EQUIPMENT - LAYOUT | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS | IFA RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-IN-4308-074-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - FIRE AND GAS CABLE SCHEDULE | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-IN-4327-073-POWI-10003-001 | SCHEMATIC DIAGRAM - INTERCONNECTION WIRING I/O EQUIPMENT | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-IN-4380-074-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSTRUMENT INDEX | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-IN-4380-074-POWI-10002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - FIRE AND GAS INSTRUMENT INDEX | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-IN-4380-074-POWI-10003 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - FIRE AND GAS INSTRUMENTS BULK MTO | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-IN-7180-083-POWI-10001 | F&G LAYOUT REVIEW REPORT | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-IN-7771-074-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - FIRE AND GAS DEVICES CATALOGUE | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-IN-8804-074-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - FIRE AND GAS INTERCONNECTION WIRING | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-JA-4372-091-POWI-10001 | VENDOR DATA BOOK INDEX | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-JA-4372-091-POWI-10002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - ELECTRICAL ROOM ELECTRICAL DRAWING REGISTER | IT / IM | JA - IM | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-JA-4372-091-POWI-10003 | VENDOR DATA BOOK INDEX | IT / IM | JA - IM | A03 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-JA-4372-091-POWI-10004 | TQ REGISTER | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-JA-6611-091-POWI-10001 | DOCUMENT SCHEDULE | IT / IM | JA - IM | R05 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-0502-091-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - FAT PROCEDURE - EQUIPMENT | MECHANICAL | MH - HVAC | R01 | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-0502-091-POWI-10002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - FAT PROCEDURE - VENTILATION FAN | MECHANICAL | MH - HVAC | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-0502-091-POWI-10003 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - FAT PROCEDURE - DUCT INLINE | MECHANICAL | MH - HVAC | R02 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-0580-091-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - HVAC SYSTEM - FAT REPORT - EQUIPMENT | MECHANICAL | MH - HVAC | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-0580-091-POWI-10002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - FAT REPORT - VENTILATION FAN | MECHANICAL | MH - HVAC | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-0580-091-POWI-10003 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - FAT REPORT - DUCT INLINE | MECHANICAL | MH - HVAC | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-1206-017-POWI-10001 | BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - DUCT PRESSURE DROP CALCULATION | MECHANICAL | MH - HVAC | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-1580-076-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - CERTIFICATE - EQUIPMENT | MECHANICAL | MH - HVAC | R01 | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-1580-076-POWI-10002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - CERTIFICATE - VENTILATION FAN | MECHANICAL | MH - HVAC | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-2103-076-POWI-10002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - MOTOR DATA SHEETS - PACU / VENTILATION FAN | MECHANICAL | MH - HVAC | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-2105-076-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - CONTROL PANEL DATASHEET | MECHANICAL | MH - HVAC | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-2105-076-POWI-10002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - EQUIPMENT DATA SHEET - VENTILATION FAN | MECHANICAL | MH - HVAC | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-2105-076-POWI-10003 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - DUCT INLINE DATA SHEET | MECHANICAL | MH - HVAC | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-2106-076-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - PURGING PANEL DATA SHEET | MECHANICAL | MH - HVAC | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-2106-076-POWI-10002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - INSTRUMENTATION DATA SHEET - LOOSE SUPPLY | MECHANICAL | MH - HVAC | R01 | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-2365-076-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - PIPING AND INSTRUMENT DIAGRAMS (P&IDS) - OUTDOOR PACKAGED UNIT | MECHANICAL | MH - HVAC | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-2409-091-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - DUCTING AND INSTRUMENT DIAGRAMS (D&IDS) | MECHANICAL | MH - HVAC | A04 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-3328-076-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - INSTALLATION / OPERATION / AND MAINTENANCE MANUAL (IOM) | MECHANICAL | MH - HVAC | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-4018-073-POWI-10002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - GENERAL ARRANGEMENT DRAWINGS - VENTILATION FAN | MECHANICAL | MH - HVAC | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-4018-073-POWI-10003 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - GENERAL ARRANGEMENT DRAWINGS - DUCT INLINE | MECHANICAL | MH - HVAC | A02 | NAO |  | Diretorio Vendor | TRANSMITTAL | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-4018-073-POWI-10004 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - NAME PLATE DETAIL | MECHANICAL | MH - HVAC | A03 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-4018-073-POWI-10005 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - PURGING PANEL GA INCLUDING COMPONENT LIST | MECHANICAL | MH - HVAC | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-4024-076-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - DUCTING LAYOUT AND SECTION DETAILS | MECHANICAL | MH - HVAC | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-4327-076-POWI-10002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - I/O LIST | MECHANICAL | MH - HVAC | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-4329-076-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - POWER AND UTILTIES CONSUMPTION LIST | MECHANICAL | MH - HVAC | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-4354-091-POWI-10004 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - RECOMMENDED SPARE PARTS LIST | MECHANICAL | MH - HVAC | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-4380-091-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - MODBUS TABLE | MECHANICAL | MH - HVAC | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-4380-091-POWI-10002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - HMI SCREENS | MECHANICAL | MH - HVAC | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-5505-091-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - EQUIPMENT TECHNICAL SPECIFICATION AND CONTROL PHILOSOPHY | MECHANICAL | MH - HVAC | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-5505-091-POWI-10002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - INSTRUMENTATION DATA SHEET - LOOSE SUPPLY | MECHANICAL | MH - HVAC | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-6067-091-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - HVAC SYSTEM - SAT PROCEDURE | MECHANICAL | MH - HVAC | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-6067-091-POWI-10002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - HVAC SYSTEM - SAT REPORT | MECHANICAL | MH - HVAC | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-6612-091-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - EQUIPMENT TAG REGISTER | MECHANICAL | MH - HVAC | R01 | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-7771-076-POWI-10001 | TECHNICAL SPECIFICATION FOR SSCB | MECHANICAL | MH - HVAC | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-7771-091-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - HEAT LOAD CALCULATION REPORT | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-8804-074-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - SYSTEM CABLE BLOCK / INTERCONNECTION DIAGRAM | MECHANICAL | MH - HVAC | A01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-8880-074-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - EQUIPMENT CONTROL PANEL WIRING DIAGRAMS - HVAC MASTER CONTROL PANEL | MECHANICAL | MH - HVAC | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MH-8880-074-POWI-10002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - PURGING PANEL WIRING DIAGRAM | MECHANICAL | MH - HVAC | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MP-4338-076-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - PIPING ISOMETRIC | PIPING | MP - PIPING | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MP-4338-076-POWI-10002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - PIPING SUPPORT LOCATION LAYOUT & DETAIL | PIPING | MP - PIPING | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MP-4338-076-POWI-10003 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - PIPING ISOMETRIC | PIPING | MP - PIPING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MP-4338-076-POWI-10004 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - PIPING ISOMETRIC | PIPING | MP - PIPING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MP-4338-076-POWI-10005 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - PIPING ISOMETRIC | PIPING | MP - PIPING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MP-4338-076-POWI-10006 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - PIPING ISOMETRIC | PIPING | MP - PIPING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MP-4338-076-POWI-10007 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - PIPING ISOMETRIC | PIPING | MP - PIPING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MP-4338-076-POWI-10008 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - PIPING ISOMETRIC | PIPING | MP - PIPING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MP-4338-076-POWI-10009 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - PIPING ISOMETRIC | PIPING | MP - PIPING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MP-4338-076-POWI-10010 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - PIPING ISOMETRIC | PIPING | MP - PIPING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MP-4338-076-POWI-10011 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - PIPING ISOMETRIC | PIPING | MP - PIPING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MP-4338-076-POWI-10012 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - PIPING ISOMETRIC | PIPING | MP - PIPING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MX-6180-091-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE -WEIGHING PROCEDURE | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MX-7180-091-POWI-10001 | WEIGHT CONTROL REPORT | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MX-7180-091-POWI-10001-002 | WEIGHT CONTROL REPORT | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MX-7180-091-POWI-10001-003 | WEIGHT CONTROL REPORT | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MX-7180-091-POWI-10001-004 | WEIGHT CONTROL REPORT | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MX-7180-091-POWI-10001-005 | WEIGHT CONTROL REPORT | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MX-7180-091-POWI-10001-006 | WEIGHT CONTROL REPORT | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MX-7180-091-POWI-10002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE -MECHANICAL HANDLING STUDY/REPORT | MECHANICAL | MX - OVERAL MECHANICAL | A02 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-MX-7770-091-POWI-10001 | EQUIPMENT SCHEDULE | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-NA-4354-072-POWI-10001 | SPARE PARTS LIST | NA - MAINTENANCE | NA - MAINTENANCE | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-NA-4354-091-POWI-10002 | RECOMM INSTALLATION. COMMISSIONING AND START UP SPARES LIST | BC - COMMISSIONING | BC - COMMISSIONING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-OA-4811-072-POWI-10001 | OPERATION INSTALLATION AND MAINTENANCE MANUAL - PEW 1100-220/230-EN-D | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-OA-4811-072-POWI-10002 | OPERATION INSTALLATION AND MAINTENANCE MANUAL - SDC 125-100 | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-OA-4811-072-POWI-10003 | OPERATION INSTALLATION AND MAINTENANCE MANUAL - SDC 48-100 | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-OA-4811-072-POWI-10004 | OPERATION INSTALLATION AND MAINTENANCE MANUAL - SDC 24-400 | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-OA-4811-076-POWI-10001 | INSTALLATION / OPERATION AND MAINTENANCE MANUAL - TYPE 439 LV SWITCHGEAR - INSTALLATION & COMMISSIONING PROCEDURE | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-OA-4811-076-POWI-10002 | INSTALLATION / OPERATION AND MAINTENANCE MANUAL - TYPE 439 LV SWITCHGEAR - OPERATING & MAINTENANCE PROCEDURE | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-OA-4811-076-POWI-10003 | INSTALLATION / OPERATION AND MAINTENANCE MANUAL - TYPE 298 MV SWITCHGEAR - USER GUIDE VD4 FOR CIRCUIT BREAKER CUBICLE | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-OA-4811-076-POWI-10004 | INSTALLATION / OPERATION AND MAINTENANCE MANUAL - TYPE 298 MV SWITCHGEAR - USER GUIDE FOR VACUUM CONTACTOR CUBICLE | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-OA-4811-076-POWI-10010 | OPERATION AND MAINTENANCE MANUAL INDEX | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-OA-4811-076-POWI-10011 | INSTALLATION/ OPERATION AND MAINTENANCE MANUAL | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-OA-4811-076-POWI-10020 | OPERATION AND MAINTENANCE MANUAL INDEX | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-OA-4811-076-POWI-10021 | INSTALLATION / OPERATION AND MAINTENANCE MANUAL | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-OA-5980-076-POWI-10001 | VENDOR DATA BOOK | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-OA-5980-076-POWI-10002 | VENDOR DATA BOOK | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-OA-6180-072-POWI-10001 | BATTERY OPERATION & INSTALLATION MANUAL / PRESERVATION AND STORAGE PROCEDURE - PEW 1100-220/230-EN-D | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-OA-6180-072-POWI-10002 | BATTERY OPERATION & INSTALLATION MANUAL / PRESERVATION AND STORAGE PROCEDURE - SDC 125-100 | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-OA-6180-072-POWI-10003 | BATTERY OPERATION & INSTALLATION MANUAL / PRESERVATION AND STORAGE PROCEDURE - SDC 48-100 | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-OA-6180-072-POWI-10004 | BATTERY OPERATION & INSTALLATION MANUAL / PRESERVATION AND STORAGE PROCEDURE - SDC 24-400 | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-OA-7880-076-POWI-10001 | DISPATCH DOSSIER | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-0880-091-POWI-10001 | FACTORY ACCEPTANCE TEST REPORT - 6.6KV SWITCHBOARD MCC-7355-D-01 | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-0880-091-POWI-10002 | FACTORY ACCEPTANCE TEST REPORT - 400V SWITCHBOARD SB-7446-E-01 | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-0880-091-POWI-10003 | FACTORY ACCEPTANCE TEST REPORT - 400V SWITCHBOARD MCC-7456-E-01 | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-0880-091-POWI-10004 | FACTORY ACCEPTANCE TEST REPORT - 400V SWITCHBOARD MCC-7457-E-01 | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-0880-091-POWI-10005 | FACTORY ACCEPTANCE TEST REPORT - DISTRIBUTION BOARD DB-7660-N-01/ DB-7491-N-01 & DB-7492-N-01 | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-1580-072-POWI-10001 | CERTIFICATE OF WARRANTY - PEW 1100-220/230-EN-D | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-1580-072-POWI-10002 | CERTIFICATE OF WARRANTY - SDC 125-100 | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-1580-072-POWI-10003 | CERTIFICATE OF WARRANTY - SDC 48-100 | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-1580-072-POWI-10004 | CERTIFICATE OF WARRANTY - SDC 24-400 | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-1580-074-POWI-10001 | ISO 9001 CERTIFICATION FOR TRANSFORMERS | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-1580-074-POWI-10002 | MATERIAL TEST CERTIFICATES FOR TRANSFORMERS | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-1580-074-POWI-10003 | CERTIFICATE OF COMPLIANCE / DECLARATION OF CONFORMITY FOR TRANSFORMERS | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-1580-074-POWI-10004 | CERTIFICATE OF ORIGIN FOR TRANSFORMERS | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-1580-074-POWI-10005 | INGRESS PROTECTION (IP) CERTIFICATE FOR TRANSFORMERS | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-1580-074-POWI-10006 | TYPE TEST CERTIFICATES FOR TRANSFORMERS | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-1580-091-POWI-10001 | MATERIAL TEST CERTIFICATES | QA - QUALITY | QA - QUALITY | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-1580-091-POWI-10002 | WELDER QUALIFICATION AND CERTIFICATE REGISTER | QA - QUALITY | QA - QUALITY | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-1580-091-POWI-10003 | CERTIFICATION RECORD - TYPE439 SWITCHGEAR TESTED TO BS EN IEC 61439 & IEC TR 61641 | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-1580-091-POWI-10004 | CERTIFICATION RECORD- ABB VD4 CIRCUIT BREAKER / TOSHIBA CV-6HA CONTACTOR AND TYPE298 SWITCHGEAR | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-1580-091-POWI-10005 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM -WELDER REGISTER AND CERTIFICATE | QA - QUALITY | QA - QUALITY | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-1580-091-POWI-10006 | SNEPCO BONGA NORTH SSCB PROJECT- WELDERS AND WELDING OPERATOR REGISTER & CERTIFICATE FOR PIPING | QA - QUALITY | QA - QUALITY | R02 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-1580-091-POWI-10007 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - WELDERS & WELDING OPERATOR REGISTER & CERTIFICATES FOR DUCTING SPOOL | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-3880-073-POWI-10101 | ROUTINE TEST REPORT - 6.6KV SWITCHBOARD MCC-7355-D-01 | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-3880-074-POWI-10102 | ROUTINE TEST REPORT - 400V SWITCHBOARD SB-7446-E-01 | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-3880-074-POWI-10103 | ROUTINE TEST REPORT - 400V SWITCHBOARD MCC-7456-E-01 | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-3880-074-POWI-10104 | ROUTINE TEST REPORT - 400V SWITCHBOARD MCC-7457-E-01 | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-3880-076-POWI-10105 | ROUTINE TEST REPORT - DISTRIBUTION BOARD DB-7660-N-01 | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-3880-076-POWI-10106 | ROUTINE TEST REPORT - DISTRIBUTION BOARD DB-7491-N-01 | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-3880-076-POWI-10107 | ROUTINE TEST REPORT - DISTRIBUTION BOARD DB-7492-N-01 | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-3880-091-POWI-10001 | DIMENSION CONTROL PROCEDURE | QA - QUALITY | QA - QUALITY | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-5733-072-POWI-10001 | INSPECTION & TEST PLAN (ITP) | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-5733-074-POWI-10001 | INSPECTION AND TEST PLAN FOR TRANSFORMERS | QA - QUALITY | QA - QUALITY | R02 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-5733-074-POWI-10002 | INSPECTION RELEASE NOTES FOR TRANSFORMERS | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-5733-091-POWI-10001 | INSPECTION AND TEST PLAN | QA - QUALITY | QA - QUALITY | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-5733-091-POWI-10002 | INSPECTION & TEST PLAN FOR STRUCTURE | QA - QUALITY | QA - QUALITY | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-5733-091-POWI-10003 | INSPECTION & TEST PLAN FOR ARCHITECTURAL | QA - QUALITY | QA - QUALITY | A03 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-5733-091-POWI-10004 | INSPECTION & TEST PLAN FOR ELECTRICAL & INSTRUMENT | QA - QUALITY | QA - QUALITY | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-5733-091-POWI-10005 | INSPECTION & TEST PLAN FOR BLASTING PAINTING | QA - QUALITY | QA - QUALITY | A05 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-5733-091-POWI-10006 | INSPECTION & TEST PLAN FOR HVAC | QA - QUALITY | QA - QUALITY | A02 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-5733-091-POWI-10007 | HVAC SYSTEM - ITP FOR PACU BATTERY ROOM EXHAUSTS FAN AND CONTROL PANEL PURGE PANEL | QA - QUALITY | QA - QUALITY | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-5733-091-POWI-10008 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSPECTION & TEST PLAN FOR PIPING | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-5798-091-POWI-10001 | QHSE PLAN | IT / IM | JA - IM | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-5798-091-POWI-10002 | QUALITY PLAN | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-5798-091-POWI-10003 | SNEPCO BONGA NORTH SSCB PROJECT - QUALITY PLAN | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-5798-091-POWI-10004 | QUALITY AUDIT PLAN | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-5880-091-POWI-10001 | PERFORMANCE TESTING AND ACCEPTANCE TEST PROCEDURES - 6.6KV SWITCHBOARD MCC-7355-D-01 | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-5880-091-POWI-10002 | PERFORMANCE TESTING AND ACCEPTANCE TEST PROCEDURES - 400V SWITCHBOARD SB-7446-E-01 / MCC-7456-E-01 & MCC-7457-E-01 | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-5880-091-POWI-10003 | PERFORMANCE TESTING AND ACCEPTANCE TEST PROCEDURES - DISTRIBUTION BOARD DB-7660-N-01 / DB-7491-N-01 & DB-7492-N-01 | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-5880-091-POWI-10004 | CONSUMABLE CONTROL PROCEDURE | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-5880-091-POWI-10005 | MATERIAL RECEIVING / STORAGE PROCEDURE | QA - QUALITY | QA - QUALITY | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6050-017-POWI-10102 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM - FAT REPORT- EQUIPMENT | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6050-073-POWI-10105 | FACTORY ACCEPTANCE TEST REPORT - 6.6KV SWITCHBOARD MCC-7355-D-01 | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6050-074-POWI-10106 | FACTORY ACCEPTANCE TEST REPORT - 400V SWITCHBOARD SB-7446-E-01 | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6050-074-POWI-10107 | FACTORY ACCEPTANCE TEST REPORT - 400V SWITCHBOARD MCC-7456-E-01 | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6050-074-POWI-10108 | FACTORY ACCEPTANCE TEST REPORT - 400V SWITCHBOARD MCC-7457-E-01 | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6050-076-POWI-10109 | FACTORY ACCEPTANCE TEST REPORT - DISTRIBUTION BOARD DB-7660-N-01 | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6050-076-POWI-10110 | FACTORY ACCEPTANCE TEST REPORT - DISTRIBUTION BOARD DB-7491-N-01 | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6050-076-POWI-10111 | FACTORY ACCEPTANCE TEST REPORT - DISTRIBUTION BOARD DB-7492-N-01 | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6050-091-POWI-10001 | NON-CONFORMANCE AND CORRECTIVE ACTION PROCEDURE(S) | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6050-091-POWI-10002 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - NDE - MPI. DPT. RT. UT. PMI PROCEDURE FOR PIPING | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | TRANSMITTAL | IFA RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6050-091-POWI-10003 | PICKING & PASSIVATION PROCEDURE | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6050-091-POWI-10004 | FLANGE MANAGEMENT PROCEDURE | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6050-091-POWI-10005 | HYDROTEST PROCEDURE | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6050-091-POWI-10006 | FLUSHING & DRYING PROCEDURE | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6180-091-POWI-10001 | WEIGHT PROCEDURE | QA - QUALITY | QA - QUALITY | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6180-091-POWI-10002 | WPS / WPQRS | QA - QUALITY | QA - QUALITY | A04 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6180-091-POWI-10003 | NON-DESTRUCTIVE EXAMINATION PROCEDURES (NDE) | QA - QUALITY | QA - QUALITY | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6180-091-POWI-10004 | NDE - MPI PROCEDURE FOR STRUCTURE | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6180-091-POWI-10005 | NDE - RT PROCEDURE FOR STRUCTURE | QA - QUALITY | QA - QUALITY | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6180-091-POWI-10006 | NDE - DPT PROCEDURE FOR STRUCTURE | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6180-091-POWI-10007 | NDT OPERATORS QUALIFICATION REGISTER & CERTIFICATES | QA - QUALITY | QA - QUALITY | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6180-091-POWI-10008 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - HVAC SYSTEM -WPS/ PQR/ NDT/ QUALITY CONTROL DOCUMENT | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6180-091-POWI-10009 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - FLAME STRAIGHTENING PROCEDURE | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6180-091-POWI-10010 | SSCB PACKAGE MODULE - HEAT STRAIGHTENING PROCEDURE | QA - QUALITY | QA - QUALITY | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6180-091-POWI-10011 | SSCB PACKAGE MODULE - WELD REPAIR PROCEDURE | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6180-091-POWI-10012 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - BUTTERING WELDING PROCEDURE | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6180-091-POWI-10013 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - MECHANICAL COMPLETION PROCEDURE | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6180-091-POWI-10014 | WELDING PROCEDURE AND WELDER OPERATOR QUALIFICATION FOR INSULATION PIN | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6180-091-POWI-10015 | SNEPCO BONGA NORTH SSCB PROJECT- WPS/ WPQRS FOR PIPING | QA - QUALITY | QA - QUALITY | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6180-091-POWI-10016 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - INSPECTION PROCEDURE | QA - QUALITY | QA - QUALITY | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6180-091-POWI-10018 | FAT AND IFAT PHILOSOPHY | OA - OPERATIONS | OA - OPERATIONS | R02 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6180-091-POWI-10019 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - WELDING PROCEDURE SPECIFICATION/WPQRS FOR DUCTING SPOOL | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6950-091-POWI-10001 | ROUTINE TEST REPORT - 6.6KV SWITCHBOARD MCC-7355-D-01 | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6950-091-POWI-10002 | ROUTINE TEST REPORT - 400V SWITCHBOARD SB-7446-E-01 | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6950-091-POWI-10003 | ROUTINE TEST REPORT - 400V SWITCHBOARD MCC-7456-E-01 | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6950-091-POWI-10004 | ROUTINE TEST REPORT - 400V SWITCHBOARD MCC-7457-E-01 | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-QA-6950-091-POWI-10005 | ROUTINE TEST REPORT - DISTRIBUTION BOARD DB-7660-N-01/ DB-7491-N-01 & DB-7492-N-01 | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-RA-6068-074-POWI-10001 | SURFACE PREPARATION AND COATING PROCEDURE FOR TRANSFORMERS | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-RA-6068-091-POWI-10001 | SURFACE PREPARATION AND PAINTING PROCEDURE | MATERIALS | RA - MATERIALS | A06 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-RA-6068-091-POWI-10002 | PAINTING PROCEDURE | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-RA-6068-091-POWI-10003 | SURFACE PREPARATION AND INTERNAL COATING | MATERIALS | RA - MATERIALS | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-RA-6068-091-POWI-10004 | PASSIVE FIRE PROTECTION INSTALLATION AND REPAIR PROCEDURE | MATERIALS | RA - MATERIALS | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-RA-6068-091-POWI-10005 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - PURGE PANEL - SURFACE PREPARATION & PAINTING PROCEDURE | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-RA-7005-074-POWI-10001 | SURFACE PREPARATION AND COATINGS REPORTS FOR TRANSFORMERS | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-RA-7880-091-POWI-10002 | HOT DIPPED GALVANIZED PROCEDURE | MATERIALS | RA - MATERIALS | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-SA-4322-074-POWI-10001 | PACKING AND SHIPPING LIST FOR TRANSFORMERS | SA - LOGISTICS | SA - LOGISTICS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-SA-4322-091-POWI-10001 | LIST OF SPECIAL TOOLS - 6.6KV SWITCHBOARD MCC-7355-D-01 | SA - LOGISTICS | SA - LOGISTICS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-SA-6028-037-POWI-10001 | EXPORT PACKING SPECIFICATION | SA - LOGISTICS | SA - LOGISTICS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-SA-6028-072-POWI-10001 | PACKING - UNPACKING AND STORAGE PROCEDURE: AIR / OVERSEAS / OVERLAND TRANSPORT - GUTOR MY | SA - LOGISTICS | SA - LOGISTICS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-SA-6028-074-POWI-10001 | SHIPPING HANDLING & STORAGE PROCEDURE FOR TRANSFORMERS | SA - LOGISTICS | SA - LOGISTICS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-SA-6033-091-POWI-10001 | LIFTING & TRANSPORTATION ARRANGEMENT DRAWING | SA - LOGISTICS | SA - LOGISTICS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-SA-6180-091-POWI-10004 | UNPACKING AND PRESERVATION PROCEDURE | SA - LOGISTICS | SA - LOGISTICS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-TA-3328-074-POWI-10001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - TELECOMS TYPICAL INSTALLATION DETAILS | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A04 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-TA-4018-076-POWI-10001-001 | SNEPCO BONGA NORTH SSCB PACKAGE MODULE - TELECOM EQUIPMENT - LAYOUT | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-TA-4018-076-POWI-10001-002 | TELECOM EQUIPMENT - LAYOUT | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | X | NAO |  | Diretorio Vendor | CANCELADO |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-262884-300-VA-6036-091-POWI-10001 | PROJECT MATERIAL CONTROL PROCEDURE | VA - PROCUREMENT | VA - PROCUREMENT | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / POWELL / PO_262884-SSCB MODULE_DED
BNO-40000538-300-AA-6944-009-GEVEKE-00001 | PROGRESS REPORTS (MONTHLY) OCTOBER 2025 | PMT | AA - PROJECT MANAGEMENT | A04 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-AA-6944-009-GEVEKE-00002 | PROGRESS REPORTS (MONTHLY) MAY 2025 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-AA-6944-009-GEVEKE-00003 | PROGRESS REPORTS (MONTHLY) JUNE 2025 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-AA-6944-009-GEVEKE-00004 | PROGRESS REPORTS (MONTHLY) JULY 2025 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-AA-6944-009-GEVEKE-00005 | PROGRESS REPORTS (MONTHLY) AUGUST 2025 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-AA-6944-009-GEVEKE-00006 | PROGRESS REPORTS (MONTHLY) SEPTEMBER 2025 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-AA-6944-009-GEVEKE-00007 | PROGRESS REPORTS (MONTHLY) OCTOBER 2025 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-AA-6944-009-GEVEKE-00008 | PROGRESS REPORTS (MONTHLY) OCTOBER 2025 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-AA-6944-009-GEVEKE-00009 | PROGRESS REPORTS (MONTHLY) NOVEMBER 2025 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-AA-6944-009-GEVEKE-00010 | PROGRESS REPORTS (MONTHLY) NOVEMBER 2025 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-AA-6944-009-GEVEKE-00011 | PROGRESS REPORTS (MONTHLY) DECEMBER 2025 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-AA-6944-009-GEVEKE-00012 | PROGRESS REPORTS (MONTHLY) DECEMBER 2025 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-AA-6944-009-GEVEKE-00013 | PROGRESS REPORTS (MONTHLY) JANUARY 2026 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-AA-6944-009-GEVEKE-00014 | PROGRESS REPORTS (MONTHLY) JANUARY 2026 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-AA-6944-009-GEVEKE-00015 | PROGRESS REPORTS (MONTHLY) FEBRUARY 2026 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-AA-6944-009-GEVEKE-00016 | PROGRESS REPORTS (MONTHLY) FEBRUARY 2026 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-AA-6944-009-GEVEKE-00017 | PROGRESS REPORTS (MONTHLY) MARCH 2026 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-AA-6944-009-GEVEKE-00018 | PROGRESS REPORTS (MONTHLY) MARCH 2026 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-AA-6944-009-GEVEKE-00019 | PROGRESS REPORTS (MONTHLY) APRIL 2026 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-AA-6944-009-GEVEKE-00020 | PROGRESS REPORT (MONTHLY) APRIL 2026 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-AA-6944-009-GEVEKE-00021 |  | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-AA-6944-009-GEVEKE-00022 |  | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-BA-6065-009-GEVEKE-00001 | BASEPLATE WELD PROCEDURE SPECIFICATION (WPS) AND QUALIFICATION (WPQ) RECORDS INCL WELDPLAN | STRUCTURAL | CS - STRUCTURAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-BA-6065-009-GEVEKE-00002 | PIPING WELD PROCEDURE SPECIFICATION (WPS) AND QUALIFICATION (WPQ) RECORDS INCL WELDPLAN | STRUCTURAL | CS - STRUCTURAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-CS-2105-0-09-GEVEKE-00001 | WEIGHT REPORT METHANOL INJECTION SKID | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-CS-2105-009-GEVEKE-00002 | WEIGHT REPORT METHANOL INJECTION SKID | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-EA-2105-009-GEVEKE-00001 | ELECTRICAL EQUIPMENT DATA SHEETS | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-EA-2105-009-GEVEKE-00002 | MOTOR DATA SHEETS METHANOL INJECTION SKID | ELECTRICAL | EA - ELECTRICAL | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-EA-7180-009-GEVEKE-00001 | FACTORY ACCEPTANCE TEST REPORT CORROSION INHIBITOR INJECTION SKID | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-EA-7180-009-GEVEKE-00002 | FACTORY ACCEPTANCE TEST REPORT METHANOL INJECTION SKID | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-EA-7180-009-GEVEKE-00003 | FAT PROCEDURE | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-FA-5803-009-GEVEKE-00001 | ENGINEERING. FABRICATION. AND DELIVERY SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-FA-5803-009-GEVEKE-00002 | PRODUCTION TEST RESULTS (INC WELDING) | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-IN-1580-009-GEVEKE-00001 | INSTRUMENT TEST / CALIBRATION CERTIFICATE | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-IN-2105-009-GEVEKE-00001 | INSTRUMENT DATA SHEETS - DIFFERENTIAL PRESSURE TRANSMITTER | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-IN-2105-009-GEVEKE-00002 | INSTRUMENT DATA SHEETS - PRESSURE TRANSMITTER | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-IN-2105-009-GEVEKE-00003 | INSTRUMENT DATA SHEETS - PRESSURE GAUGE | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-IN-2105-009-GEVEKE-00004 | INSTRUMENT DATA SHEETS - CALIBRATOR | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-IN-2105-009-GEVEKE-00005 | INSTRUMENT DATA SHEETS - STRAINER | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-IN-2105-009-GEVEKE-00006 | INSTRUMENT DATA SHEETS - PULSATION DAMPENER | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-IN-2105-009-GEVEKE-00007 | INSTRUMENT DATA SHEETS - PRESSURE RELIEF VALVE | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-IN-2105-009-GEVEKE-00008 | INSTRUMENT DATA SHEETS - CHECK VALVE | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-IN-2105-009-GEVEKE-00009 | INSTRUMENT DATA SHEETS - FLOW METER | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-IN-2105-009-GEVEKE-00010 | INSTRUMENT DATA SHEETS - SHUT DOWN VALVE | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-IN-2105-009-GEVEKE-00011 | INSTRUMENT DATA SHEETS - PRESSURE CONTROL VALVE - MANUAL | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-IN-2105-009-GEVEKE-00012 | INSTRUMENT DATA SHEETS - PRESSURE CONTROL VALVE - AUTOMATED | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-IN-8880-009-GEVEKE-00001 | WIRING DIAGRAMS (JUNCTION BOXES) | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-IN-8880-009-GEVEKE-00002 | WIRING DIAGRAMS (MOTOR) | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-IN-8880-009-GEVEKE-00003 | WIRING DIAGRAMS FLOWLINE CORROSION INHIBITOR A-4280 | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-IN-8880-009-GEVEKE-00004 | WIRING DIAGRAMS HYDRATE INHIBITOR INJECTION A-4270A | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-IN-8880-009-GEVEKE-00005 | WIRING DIAGRAMS HYDRATE INHIBITOR INJECTION A-4270B | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-IN-8880-009-GEVEKE-00006 | BLOCK DIAGRAM CI AND MI - METHANOL PACKAGES A-4270A/B_ CORROSION PACKAGE A-4280 | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-JA-4372-009-GEVEKE-00001 | TECHNICAL DATA MANUAL | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-JA-4372-009-GEVEKE-00002 | CERTIFICATE OF COMPLIANCE | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-JA-6611-009-GEVEKE-00001 | (PRE-)FINAL ACCEPTANCE TEST (FAT) PROCEDURE FOR CORROSION INHIBITOR PACKAGE AND METHANOL INJECTION PACKAGE. | IT / IM | JA - IM | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-MR-2105-009-GEVEKE-00001 | MOTOR DATA SHEETS CORROSION INHIBITOR INJECTION SKID | MECHANICAL | MR - MECHANICAL ROTATING | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-MR-2105-009-GEVEKE-00002 | NOISE REPORT / DATASHEET METHANOL PUMPS P-4270A/B/C/D | MECHANICAL | MR - MECHANICAL ROTATING | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-MR-2105-009-GEVEKE-00003 | WEIGHT REPORT CORROSION INHIBITOR INJECTION SKID | MECHANICAL | MR - MECHANICAL ROTATING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-MR-2105-009-GEVEKE-00004 | EQUIPMENT DATA SHEETS - PUMP API 675 | MECHANICAL | MR - MECHANICAL ROTATING | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-MR-2105-009-GEVEKE-00005 | EQUIPMENT DATA SHEETS - METHANOL PUMP | MECHANICAL | MR - MECHANICAL ROTATING | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-MR-7180-009-GEVEKE-00001 | EQUIPMENT HAZ. AREA CERTIFICATE AND SCHEDULE | MECHANICAL | MR - MECHANICAL ROTATING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-MR-7180-009-GEVEKE-00002 | PERFORMANCE TEST RESULTS METHANOL PUMPS P-4270A/B/C/D | MECHANICAL | MR - MECHANICAL ROTATING | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-MR-7180-009-GEVEKE-00003 | PERFORMANCE TEST RESULTS METHANOL PUMPS P-4280A/B | MECHANICAL | MR - MECHANICAL ROTATING | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-MS-1379-009-GEVEKE-00001 | MECHANICAL FRAME CALCULATIONS CORROSION INHIBITOR INJECTION SKID | MECHANICAL | MS - MECHANICAL STATIC | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-MS-1379-009-GEVEKE-00002 | MECHANICAL FRAME CALCULATIONS METHANOL INJECTION SKID | MECHANICAL | MS - MECHANICAL STATIC | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-MS-7880-009-GEVEKE-00001 | NAME PLATE DRAWINGS CORROSION INHIBITOR SKID - A-4280 | MECHANICAL | MS - MECHANICAL STATIC | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-MS-7880-009-GEVEKE-00002 | NAME PLATE DRAWINGS HYDRATE INHIBITOR SKID - A-4270A | MECHANICAL | MS - MECHANICAL STATIC | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-MS-7880-009-GEVEKE-00003 | NAME PLATE DRAWINGS HYDRATE INHIBITOR SKID - A-4270B | MECHANICAL | MS - MECHANICAL STATIC | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-MS-7880-009-GEVEKE-00004 | NAME PLATE DRAWINGS CORROSION INHIBITOR PUMP - P-4280A/B & C/D | MECHANICAL | MS - MECHANICAL STATIC | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-MX-2321-009-GEVEKE-00001 | DETAIL DRAWINGS - IF ENCOUNTERED | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-MX-2321-009-GEVEKE-00002 | DETAILED FABRICATION DRAWING | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-MX-2321-009-GEVEKE-00003 | DETAIL DRAWING - DECK MOUNTING - A-4280 | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-MX-2321-009-GEVEKE-00004 | DETAIL DRAWING - DECK MOUNTING - A-4270A | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-MX-2321-009-GEVEKE-00005 | DETAIL DRAWING - DECK MOUNTING - A-4270B | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-MX-3328-009-GEVEKE-00001 | INSTALLATION MANUAL | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-MX-4018-009-GEVEKE-00001-001 | GENERAL ARRANGEMENT CORROSION INHIBITOR INJECTION SKID (A-4280) | MECHANICAL | MX - OVERAL MECHANICAL | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-MX-4018-009-GEVEKE-00002-001 | GENERAL ARRANGEMENT METHANOL INJECTION SKID (A-4270A) | MECHANICAL | MX - OVERAL MECHANICAL | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-MX-4018-009-GEVEKE-00003-001 | GENERAL ARRANGEMENT METHANOL INJECTION SKID (A-4240B) | MECHANICAL | MX - OVERAL MECHANICAL | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-MX-5507-009-GEVEKE-00001 | 3D MODEL - METHANOL SKID | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-MX-5507-009-GEVEKE-00002 | 3D MODEL - CORROSION INHIBITOR | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-MX-5507-009-GEVEKE-00003 | 3D MODEL METHANOL INJECTION SKID A-4270B | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-MX-6067-009-GEVEKE-00001 | HYDROSTATIC PROCEDURE | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-MX-6067-009-GEVEKE-00002 | NDE OPERATOR QUALIFICATIONS | MECHANICAL | MX - OVERAL MECHANICAL | R02 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-MX-6067-009-GEVEKE-00003 | NDE RECORDS | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-MX-7205-009-GEVEKE-00001 | PURCHASER'S RELEASE NOTE | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-MX-8611-009-GEVEKE-00001 | PRESSURE TEST CERTIFICATE INSTRUMENTS - CERTIFICATION DATA BOOK | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-NA-4354-009-GEVEKE-00001 | LIST OF RECOMMENDED SPARE PARTS FOR STARUP AND NORMAL MAINTENANCE PURPOSES | NA - MAINTENANCE | NA - MAINTENANCE | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-NA-4354-009-GEVEKE-00002 | RECOMMENDED SPARES FOR 2 YEARS OPERATION | NA - MAINTENANCE | NA - MAINTENANCE | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-NA-4810-009-GEVEKE-00001 | LIST OF SPECIAL TOOLS FURNISHED FOR MAINTENANCE | NA - MAINTENANCE | NA - MAINTENANCE | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-NA-4810-009-GEVEKE-00002 | UTILITY CONSUMPTION LIST | NA - MAINTENANCE | NA - MAINTENANCE | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-OA-4811-009-GEVEKE-00001 | OPERATING AND MAINTENANCE MANUAL | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-PX-2365-009-GEVEKE-00001 | P&ID FLOWLINE CORROSION INHIBITOR SKID | PROCESS | PX - PROCESS | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-PX-2365-009-GEVEKE-00002 | P&ID HYDRATE INHIBITOR INJECTION SKID A-4270A | PROCESS | PX - PROCESS | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-PX-2365-009-GEVEKE-00003 | P&ID HYDRATE INHIBITOR INJECTION SKID A-4270B | PROCESS | PX - PROCESS | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-PX-2908-009-GEVEKE-00001 | PRESSURE RELIEF VALVE CALCULATION | PROCESS | PX - PROCESS | A01 | NAO |  | Diretorio Vendor | ISSUED |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-QA-3880-009-GEVEKE-00001 | PAINTING INSPECTION REPORT | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-QA-3880-009-GEVEKE-00002 | MECHANICAL RUNNING TEST REPORT (4HR RUNTEST) CORROSION INHIBITOR PUMPS P-4280A/B | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-QA-3880-009-GEVEKE-00003 | MECHANICAL RUNNING TEST REPORT (4HR RUNTEST) METHANOL PUMPS P-4270A/B/C/D | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | ISSUED |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-QA-3880-009-GEVEKE-00004 | HYDROSTATIC TEST REPORT PIPING PARTS METHANOL INJECTION SKID | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-QA-5733-009-GEVEKE-00001 | INSPECTION & TEST PLAN CORROSION INHIBITOR INJECTION SKID | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-QA-5733-009-GEVEKE-00002 | INSPECTION & TEST PLAN METHANOL INJECTION SKID | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-QA-5880-009-GEVEKE-00001 | PROJECT QUALITY PLAN | QA - QUALITY | QA - QUALITY | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-QA-6050-009-GEVEKE-00001 | HYDRAULIC LEAK TEST COMPLETE ASSEMBLY CORROSION INHIBITOR INJECTION SKID | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-QA-6050-009-GEVEKE-00002 | HYDRAULIC LEAK TEST COMPLETE ASSEMBLY METHANOL INJECTION SKID | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-QA-6050-009-GEVEKE-00003 | HYDRAULIC LEAK TEST COMPLETE ASSEMBLY METHANOL INJECTION SKID | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-QA-6050-009-GEVEKE-00004 | QUALITY ASSURANCE BOOK | QA - QUALITY | QA - QUALITY | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-RA-1580-009-GEVEKE-00001 | MATERIAL TRACEABILITY RECORDS | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-RA-6068-009-GEVEKE-00001 | SURFACE PREPARATION & PAINTING PROCEDURE | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | ISSUED |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-RA-7180-009-GEVEKE-00001 | NON-DESTRUCTIVE EXAMINATION PROCEDURE (NDE) | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | ISSUED |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-RA-7180-009-GEVEKE-00002 | MATERIAL TEST CERTIFICATES | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-SA-1448-009-GEVEKE-00001 | WEIGHT DATA SHEET CORROSION INHIBITOR INJECTION SKID | SA - LOGISTICS | SA - LOGISTICS | C01 | NAO |  | Diretorio Vendor | ISSUED | NOT ISSUED |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-SA-1448-009-GEVEKE-00002 | WEIGHT DATA SHEET METHANOL INJECTION SKID | SA - LOGISTICS | SA - LOGISTICS | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-SA-1448-009-GEVEKE-00003 | WEIGHT DATA SHEET METHANOL INJECTION SKID | SA - LOGISTICS | SA - LOGISTICS | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-SA-6028-009-GEVEKE-00001 | PRESERVATION PACKAGING AND SHIPPING PROCEDURES | SA - LOGISTICS | SA - LOGISTICS | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-SA-6028-009-GEVEKE-00002 | SKID PACKING AND PRESERVATION PROCEDURE | SA - LOGISTICS | SA - LOGISTICS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-40000538-300-ZH-1449-009-GEVEKE-00001 | WELDER PERFORMANCE QUALIFICATION CERTIFICATES | ZH - HUMAN RESOURCES | ZH - HUMAN RESOURCES | R02 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / GEVEKE / PO_40000538-METHANOL_AND_CI_PUMPS
BNO-505151-300-AA-6944-040-SOTU-00001 | COMMON SITE ISSUES AND COMMISSIONING LESSONS LEARNED (PIL 249) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-AA-6944-040-SOTU-00101 | PROGRESS REPORTS | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-BA-2322-040-SOTU-00001 | CUSTOMER STATION GROUNDING REQUIREMENTS (ES 2648) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | CONSTRUCTION | BA - CONSTRUCTION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-BA-2404-040-SOTU-00001 | PKG LIFT ARRANGEMENT DRG | CONSTRUCTION | BA - CONSTRUCTION | R01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-BA-4802-040-SOTU-00001 | PACKAGE LIFTING GUIDELINES (PIL 183) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | CONSTRUCTION | BA - CONSTRUCTION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-BA-4802-040-SOTU-00002 | NEW EQUIPMENT INSTALLATION AND COMMISSIONING PROCESS (PIL 250) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | CONSTRUCTION | BA - CONSTRUCTION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-BA-4802-040-SOTU-00003 | TURBOMACHINARY PACKAGE INSTALLATION GUIDELINES (() - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | CONSTRUCTION | BA - CONSTRUCTION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  | 8/15/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-BA-4802-040-SOTU-00005 | PUMP COMMISSIONING SPARES LIST - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | CONSTRUCTION | BA - CONSTRUCTION | A01 | NAO |  | Diretorio Vendor | ISSUED |  |  | 5/23/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-BA-5736-040-SOTU-00001 | LEVELING AND INSTALLING OF PACKAGE BASES (ES 9-414) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | CONSTRUCTION | BA - CONSTRUCTION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-BA-6065-040-SOTU-00001 | WELD PROCEDURE SPECIFICATION (WPS) & PROCEDURE QUALIFICATION RECORD (PQR) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | CONSTRUCTION | BA - CONSTRUCTION | A04 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-BA-6065-040-SOTU-00002 | INSTALLATION INSTR FOR LUBE OIL TANK VENT & SEPARATOR (ES 1745) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | CONSTRUCTION | BA - CONSTRUCTION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-BC-4354-040-SOTU-00002 | SPECIAL & COMMSIONING TOOLS LIST / COMMISINING EQUIPMENT LIST / CONSUMERABLES LIST - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | CONSTRUCTION | BA - CONSTRUCTION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  | 12/5/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-CS-8180-040-SOTU-00001 | PKG LIFT KIT CALCS | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-EA-6067-040-SOTU-00001 | 120VDC POWER SUPPLY SYSTEM REQUIREMENTS FOR SOLAR PACKAGES - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-EA-6067-040-SOTU-00002 | DIRECT DRIVE A/C START SYSTEMS | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-EA-6067-040-SOTU-00003 | VARIABLE FREQUENCY DRIVES | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-EA-8251-040-SOTU-10001 | ANTI-SURGE DESIGN (SOLAR SURGE CONTROL) | ELECTRICAL | EA - ELECTRICAL | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-FA-5803-040-SOTU-00001 | PRODUCTION SCHEDULE - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | FA - COST AND PLANNING | FA - COST AND PLANNING | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-HS-2107-040-SOTU-00001 | MATERIAL SAFETY DATA SHEETS - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | TECHNICAL SAFETY | HX - HSE | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-HX-2110-040-SOTU-10001 | NOISE DATA SHEET | TECHNICAL SAFETY | HX - HSE | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-HX-2110-040-SOTU-10002 | PREDICTED NOISE LEVEL | TECHNICAL SAFETY | HX - HSE | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-IN-2105-040-SOTU-00001 | INSTRUMENT DATA SHEETS - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | NAO |  | Diretorio Vendor | ISSUED |  |  | 6/20/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-IN-2335-040-SOTU-00001-001 | SEAL SYSTEM INSTRUMENT HOOK UP DRAWING | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Diretorio Vendor | CANCELADO |  |  | 5/23/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-IN-3328-040-SOTU-00001 | INSTRUMENTATION LABEL DATASHEET - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-IN-4302-040-SOTU-10001 | INSTRUMENT LIST/DATA SHEETS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-IN-4306-040-SOTU-00002 | NEW EQUIPMENT CONNECTIVITY INSIGHT CONNECT - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-IN-4308-040-SOTU-00001 | PUMP CABLE LIST - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-IN-4308-040-SOTU-10001 | FIELD CABLE/WIRE REPORT - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | INSTRUMENTATION | IN - INSTRUMENTATION | R02 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-IN-4780-040-SOTU-00001-001 | PUMP LOGIC DIAGRAM - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Diretorio Vendor | CANCELADO |  |  | 6/20/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-IN-4780-040-SOTU-10001 | TURBOTRONIC SOFTWARE (SINGLE DISPLAY ONLY) | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-IN-4780-040-SOTU-10001-001 | REVIEW OF PLANT DCS CONTROLS IMPLEMENTATION | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-IN-5505-040-SOTU-00001 | PUMP CONTROL PHILOSOPHY - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | NOT ISSUED |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-IN-6604-040-SOTU-00001 | PUMP CAUSE & EFFECT - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-IN-6604-040-SOTU-00002 | F&G CONTROLLER C&E | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-IN-6612-040-SOTU-00001 | PUMP INSTRUMENT INDEX/ SCHEDULE - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  | 6/20/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-IN-6612-040-SOTU-10001-001 | ELECTRICAL LOOP SCHEMATIC - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | INSTRUMENTATION | IN - INSTRUMENTATION | R02 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-IN-7180-040-SOTU-10001 | 'LOCK' MODBUS TCP/IP (MODBUS OVER-ETHERNET) INTERFACE REPORT | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-IN-7770-040-SOTU-00001 | PUMP CONTROL PHILOSOPHY | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Diretorio Vendor | CANCELADO |  |  | 6/20/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-IN-7771-040-SOTU-00001 | PROJECT FUNCTIONAL SAFETY REPORT - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047). | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-IN-8880-040-SOTU-00001-001 | PUMP INSTRUMENT WIRING DIAGRAM - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | INSTRUMENTATION | IN - INSTRUMENTATION | C03 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  | 6/20/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-JA-4372-040-SOTU-00002 | SUPPLIER DOCUMENT REGISTER - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | IT / IM | JA - IM | A04 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-JA-4372-040-SOTU-10001 | DOCUMENT TRANSMITTAL RECORD (SDRL) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | IT / IM | JA - IM | R01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-JA-4372-040-SOTU-10002 | SUB-SUPPLIER - VENDOR LIST | IT / IM | JA - IM | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MP-2105-040-SOTU-10001 | RELIEF VALVE DATA SHEETS | PIPING | MP - PIPING | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MP-4018-040-SOTU-00005-001 | DOUBLE BLOCK AND BLEED VALVE GA DRAWING - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | PIPING | MP - PIPING | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MR-1580-040-SOTU-10002 | ISO CERTIFICATES | MECHANICAL | MR - MECHANICAL ROTATING | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MR-2105-040-SOTU-00001 | MOTOR DATA SHEETS - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MR - MECHANICAL ROTATING | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MR-2105-040-SOTU-10001 | UTILITY & CONSUMPTION LIST - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MR - MECHANICAL ROTATING | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MR-2105-040-SOTU-10002 | API 616 COMBUSTION GAS TURBINE DATA SHEETS - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MR - MECHANICAL ROTATING | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MR-2105-040-SOTU-10003 | API 617 CENTRIFUGAL COMPRESSOR DATA SHEETS (SOLAR PRIME) | MECHANICAL | MR - MECHANICAL ROTATING | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MR-2105-040-SOTU-10010 | API 692 DRY GAS SEAL DATA SHEET (AS REQUIRED) | MECHANICAL | MR - MECHANICAL ROTATING | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MR-2105-040-SOTU-10011 | GEARBOX DATA SHEET API 613 - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MR - MECHANICAL ROTATING | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MR-2105-040-SOTU-10012 | API 671 COUPLING DATA SHEET | MECHANICAL | MR - MECHANICAL ROTATING | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MR-2105-040-SOTU-10013 | API 614 LUBE OIL DATA SHEET - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MR - MECHANICAL ROTATING | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MR-2105-040-SOTU-10014 | API 661 LUBE OIL COOLER GT- PUMP DATA SHEET | MECHANICAL | MR - MECHANICAL ROTATING | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MR-4018-040-SOTU-00001-001 | GEARBOX OUTLINE DRAWING & 3D MODEL - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MR - MECHANICAL ROTATING | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MR-4018-040-SOTU-00002-001 | COUPLING DRAWING - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MR - MECHANICAL ROTATING | A01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  | 6/6/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MR-4018-040-SOTU-00004-001 | PUMP CROSS SECTION DRAWING - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MR - MECHANICAL ROTATING | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | 2/9/2026 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MR-4018-040-SOTU-00011-001 | GEARBOX CROSS SECTION DRAWING - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MR - MECHANICAL ROTATING | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | 6/20/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MR-4018-040-SOTU-10001 | GENERAL PACKAGE OUTLINE (REFERENCE ONLY) | MECHANICAL | MR - MECHANICAL ROTATING | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MR-4018-040-SOTU-10002 | LUBE OIL FUEL SEAL START TURBINE AND ENCLOSURE SYSTEMS | MECHANICAL | MR - MECHANICAL ROTATING | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MR-4018-040-SOTU-10002-001 | MECHANICAL INTERFACE DRAWING (MID) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MR - MECHANICAL ROTATING | A04 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MR-6180-040-SOTU-00001 | GEARBOX TEST PROCEDURE - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MR - MECHANICAL ROTATING | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MR-7180-040-SOTU-00001 | HYDROSTATIC TEST PROCEDURE - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MR - MECHANICAL ROTATING | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MR-7180-040-SOTU-00003 | TORSIONAL ANALYSIS REPORT - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MR - MECHANICAL ROTATING | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  | 7/18/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MR-7771-040-SOTU-00001 | PUMP PERFORMANCE CURVE - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MR - MECHANICAL ROTATING | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MR-7771-040-SOTU-00002 | PUMP SPEED/TORQUE CURVE - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MR - MECHANICAL ROTATING | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MR-7771-040-SOTU-10003 | GAS TURBINE PERFORMANCE CURVES - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MR - MECHANICAL ROTATING | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MR-7771-040-SOTU-10004 | GAS COMPRESSOR PERFORMANCE CURVES (SOLAR PRIME) | MECHANICAL | MR - MECHANICAL ROTATING | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MR-8226-040-SOTU-00001 | PUMP LATERAL ANALYSIS - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MR - MECHANICAL ROTATING | A03 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  | 8/15/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MR-8226-040-SOTU-10001 | PUMP TORSIONAL ANALYSIS - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MR - MECHANICAL ROTATING | A02 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MR-8226-040-SOTU-10004 | TORSIONAL ANALYSIS | MECHANICAL | MR - MECHANICAL ROTATING | R01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MS-2105-040-SOTU-10001 | GENERATOR DATA SHEET AND CURVES PER IEC/API (PRELIMINARY AT THE PROPOSAL STAGE) | MECHANICAL | MS - MECHANICAL STATIC | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-1580-040-SOTU-00001 | PUMP CERTIFICATION DATA BOOK INDEX - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MX - OVERAL MECHANICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-1580-040-SOTU-00002 | PUMP CERTIFICATION DATA BOOK | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  | 6/28/2026 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-2105-040-SOTU-00001 | PUMP DATA SHEET - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MX - OVERAL MECHANICAL | R03 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-2105-040-SOTU-00002 | PUMP NOISE LEVEL DATA SHEETS - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MX - OVERAL MECHANICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 2 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-2321-040-SOTU-00001 | SUPERVISORY CONTROL CONSOLE INSTRUCTIONS (AS REQUIRED) | MECHANICAL | MX - OVERAL MECHANICAL | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-2321-040-SOTU-00001-001 | MECHANICAL SEAL DRAWING - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL | 6/6/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-2321-040-SOTU-00002 | GT DRIVEN WATERFLOOD INJECTION PUMP | MECHANICAL | MX - OVERAL MECHANICAL | X | NAO |  | Diretorio Vendor | CANCELADO | NOT ISSUED |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-2321-040-SOTU-00003 | AUXILIARY AIR SERVICE (ES 2201) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-2321-040-SOTU-00004 | PRESERVATION TURBOMACHINERY AIR SIDE AND FUEL SYSTEMS (ES 9-249 ) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-2321-040-SOTU-00005 | BATTERY SUPPLY SYSTEMS FOR USE ON SOLAR PACKAGES (ES 2416) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-2321-040-SOTU-00006 | PACKAGE PRESERVATION AND PREPARATION FOR SHIPMENT (PIL 097) | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-2321-040-SOTU-00007 | PACKAGE TIE-DOWN OPTIONS - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-2321-040-SOTU-00008 | BLOCK AND BLEED VALVES - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-2321-040-SOTU-00009 | TURBINE EXHAUST SUPPORT RECOMMENDATIONS - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-2328-040-SOTU-00001 | FASTENER INSTALLATION AND TORQUE VALUES (ES 9-54) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-2580-040-SOTU-00001 | LUBRICATING OILS FOR USE IN SOLAR GAS TURBINE ENGINES (ES 9-224) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-2580-040-SOTU-00002 | FUEL AIR AND WATER (OR STEAM) FOR SOLAR GAS TURBINES (ES 9-98) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-2580-040-SOTU-00003 | OIL LUBRICATION SYSTEM DURABILITY CARE AND MAINTENANCE (PIL 278) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-4018-040-SOTU-00001 | SOURCING HANDLING STORAGE AND TREATMENT OF FUELS | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-4018-040-SOTU-00002 | ACOUSTIC ENCLOSURE GA DRAWING - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MX - OVERAL MECHANICAL | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-4018-040-SOTU-00003-001 | PUMP GENERAL ARRANGEMENT DRAWING - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 4 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-4024-040-SOTU-00002-001 | PUMP NAME/ DUTY PLATE DRAWING - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MX - OVERAL MECHANICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-4024-040-SOTU-00003-001 | GEARBOX NAMEPLATE DRAWING - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-4380-040-SOTU-00001 | PUMP UTILITY CONSUMPTION LIST - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MR - MECHANICAL ROTATING | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  | 6/6/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-5733-040-SOTU-00001 | GEARBOX INSPECTION AND TEST PLAN | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Diretorio Vendor | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-6067-040-SOTU-00001 | FUEL GAS PIPING SYSTEM CLEANING METHODS - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-6067-040-SOTU-00002 | PUMP PERFORMANCE TEST PROCEDURE - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  | 12/1/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-6067-040-SOTU-00003 | MARS 100-15000/16000 2-SHAFT ENGINE ACCEPTANCE TEST - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-6180-040-SOTU-00001 | PUMP WEIGHT CONTROL / WEIGHING PROCEDURE - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-6180-040-SOTU-00003 | COMMISSIONING PROCEDURE (PRE-COMMISSIONING) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-6612-040-SOTU-00001 | CORROSION-PREVENTIVE OIL FOR LONG-TERM PRESERVATION (ES 9-248) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-6612-040-SOTU-00010 | LIST OF EQUIPMENTS (EX-CERTIFIED) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MX - OVERAL MECHANICAL | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | 8/15/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-7180-040-SOTU-00001 | PUMP BASEPLATE ANALYSIS - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MR - MECHANICAL ROTATING | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  | 8/15/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-7180-040-SOTU-00010 | COMPRESSOR MECHANICAL RUN TEST REPORT | MECHANICAL | MX - OVERAL MECHANICAL | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-7180-040-SOTU-00011 | COMPRESSOR PERFORMANCE TEST REPORT | MECHANICAL | MX - OVERAL MECHANICAL | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-7180-040-SOTU-00012 | GENERATOR ROUTINE TEST REPORT | MECHANICAL | MX - OVERAL MECHANICAL | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-7180-040-SOTU-00013 | GENERATOR PERFORMANCE TEST REPORT | MECHANICAL | MX - OVERAL MECHANICAL | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-7180-040-SOTU-00014 | DRY GAS SEAL TEST REPORT | MECHANICAL | MX - OVERAL MECHANICAL | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-7180-040-SOTU-00015 | DRY GAS SEAL VENT STUDY (AS PER API-692 PART 1 ANNEX A) | MECHANICAL | MX - OVERAL MECHANICAL | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-7180-040-SOTU-00018 | COMPUTATION FLUID DYNAMICS REPORT - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-7180-040-SOTU-10001 | ENGINE TEST REPORT | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-7180-040-SOTU-10002 | PACKAGE TEST REPORT | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-7205-040-SOTU-00001 | PROCESS CONTROL SYSTEM OPERATING INSTRUCTIONS (AS REQUIRED) | MECHANICAL | MX - OVERAL MECHANICAL | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-7771-040-SOTU-00001 | PACKAGE SOUND LEVELS - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-MX-8611-040-SOTU-00010 | HYDROSTATIC TEST | MECHANICAL | MX - OVERAL MECHANICAL | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-NA-4354-040-SOTU-00001 | LIST OF RECOMMENDED SPARE PARTS FOR COMMISSSIONING STARTUP AND NORMAL MAINTENANCE PURPOSES | NA - MAINTENANCE | NA - MAINTENANCE | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  | 7/10/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-NA-4354-040-SOTU-10001 | RECOMMENDED SPARE PARTS LIST (E-SPIR REQUIREMENT TO BE DISCUSSED PROJECT SPECIFIC) | NA - MAINTENANCE | NA - MAINTENANCE | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-NA-4811-040-SOTU-00005 | PUMP LUBRICATION SCHEDULE - GT DRIVEN WATERFLOOD INJECTION PUMP | NA - MAINTENANCE | NA - MAINTENANCE | R01 | NAO |  | Diretorio Vendor | ISSUED | NOT ISSUED |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-OA-4811-040-SOTU-00001 | TURBOMACHINERY OPERATION & MAINTENANCE MANUALS | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-OA-4811-040-SOTU-00002 | COUPLING INSTALLATION OPERATION & MAINTENANCE MANUAL | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 |  | 6/20/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-OA-4811-040-SOTU-00003 | PUMP OPERATION & MAINTENANCE MANUAL - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | OA - OPERATIONS | OA - OPERATIONS | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | 6/28/2026 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-OA-4811-040-SOTU-00004 | SEAL SYSTEM OPERATION & MAINTENANCE MANUAL | OA - OPERATIONS | OA - OPERATIONS | X | NAO |  | Diretorio Vendor | CANCELADO |  |  | 6/28/2026 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-OA-4811-040-SOTU-00005 | MECHANICAL SEAL OPERATION & MAINTENANCE MANUAL | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  | 5/3/2026 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-OA-4811-040-SOTU-00006 | PUMP INSTALLATION OPERATION & MAINTENANCE MANUAL | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  | 6/20/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-OA-4811-040-SOTU-00007 | CLEANING AND FLUSHING OF HYDRAULIC SYS / COMPONENTS (ES 2184) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  | 6/28/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-OA-4811-040-SOTU-00008 | CORROSION-PREVENTIVE OIL FOR LONG-TERM - ADDENDUM | OA - OPERATIONS | OA - OPERATIONS | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-OA-4811-040-SOTU-00009 | INGESTIVE CLEANING OF SOLAR GAS TURBINES (ES 9-62) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-OA-4811-040-SOTU-00010 | OFFSHORE PRODUCT MOTION REQUIREMENTS FOR OIL & GAS PACKAGE DESIGN - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-OA-4811-040-SOTU-00011 | CUSTOMER DOCUMENTATION - OIL & GAS - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 |  | 11/11/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-OA-4811-040-SOTU-00012 | DURABILITY IN HARSH ENVIRONMENTS - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-OA-4811-040-SOTU-00013 | SERVICE PARTS PACKAGING STANDARDS AND PROCEDURES - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | OA - OPERATIONS | OA - OPERATIONS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-OA-4811-040-SOTU-00014 | GEARBOX OPERATION AND MAINTENANCE MANUAL - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | OA - OPERATIONS | OA - OPERATIONS | R01 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-OA-4811-040-SOTU-10001 | QUALITY ASSURANCE DATA BOOK | OA - OPERATIONS | OA - OPERATIONS | X | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-PX-2310-040-SOTU-10001 | PACKAGE (ALLEN BRADLEY) CONTROLLER CAUSE AND EFFECT | PROCESS | PX - PROCESS | R01 | NAO |  | Diretorio Vendor | ENGINEERING COMMENTS |  |  | 6/20/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-PX-2310-040-SOTU-10002 | FIRE & GAS (DET-TRONICS - EAGLE QUANTUM) CONTROLLER CAUSE & EFFECT | PROCESS | PX - PROCESS | R01 | NAO |  | Diretorio Vendor | ENGINEERING CONSOLIDATION |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-PX-2365-040-SOTU-00001-001 | PUMP P&I DIAGRAM - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | PROCESS | PX - PROCESS | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW | 6/12/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-PX-2365-040-SOTU-10001-001 | PROCESS & INSTRUMENTATION DIAGRAM (P&ID) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | PROCESS | PX - PROCESS | R02 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-PX-3342-040-SOTU-10001 | UNIT CONTROL BALANCE OF PLANT (BOP) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | PROCESS | PX - PROCESS | R01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-QA-5733-040-SOTU-00001 | PUMP INSPECTION & TEST PLAN (ITP) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | QA - QUALITY | QA - QUALITY | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-QA-5733-040-SOTU-00002 | SULZER INSPECTION & TEST PLAN (ITP) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | QA - QUALITY | QA - QUALITY | X | NAO |  | Diretorio Vendor | CANCELADO |  | IFR - ISSUED FOR REVIEW | 3/28/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-QA-5733-040-SOTU-00003 | STANDARD PAINT FOR TURBOMACHINERY (ES 9-58) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-QA-5733-040-SOTU-00004 | STANDARD PAINT FOR TURBOMACHINERY - ADDENDUM (ES 9-58-1) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-QA-5733-040-SOTU-00005 | GEARBOX INSPECTION & TEST PLAN (ITP) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-QA-5733-040-SOTU-10001 | SOLAR INSPECTION & TEST PLAN (ITP) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | QA - QUALITY | QA - QUALITY | R02 | NAO |  | Diretorio Vendor | ISSUED | IFR RETURNED AS CODE 3 |  | 6/30/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-QA-5798-040-SOTU-00001 | QUALITY ASSURANCE PLAN - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-QA-6050-040-SOTU-00001 | PACKAGE TEST REQUIREMENTS FOR CS/MDS (ES 2334) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-QA-6050-040-SOTU-00002 | FACTORY TESTING OF TURBOTRONIC CONTROL CONSOLES (PIL-185) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | QA - QUALITY | QA - QUALITY | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-RA-6038-040-SOTU-00001 | NON-DESTRUCTIVE TESTING - VISUAL EXAMINATION OF CASTINGS - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MATERIALS | RA - MATERIALS | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFI - ISSUED FOR INFORMATION | 3/28/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-RA-6038-040-SOTU-00002 | NON-DESTRUCTIVE TESTING - VISUAL EXAMINATION (VT) OF WELDED PIPEWORK - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFI - ISSUED FOR INFORMATION | 3/28/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-RA-6038-040-SOTU-00003 | NON-DESTRUCTIVE TESTING - VISUAL EXAMINATION (VT) OF MACHINED SURFACES - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFI - ISSUED FOR INFORMATION | 3/28/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-RA-6038-040-SOTU-00004 | NON-DESTRUCTIVE TESTING - VISUAL EXAMINATION (VT) OF STRUCTURAL FABRICATIONS - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFI - ISSUED FOR INFORMATION | 3/28/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-RA-6038-040-SOTU-00005 | NON-DESTRUCTIVE TESTING - LIQUID PENETRANT EXAMINATION (LP) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFI - ISSUED FOR INFORMATION | 3/28/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-RA-6038-040-SOTU-00006 | NON-DESTRUCTIVE TESTING - POSITIVE MATERIAL IDENTIFICATION - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-RA-6038-040-SOTU-00007 | NON-DESTRUCTIVE TESTING - MAGNETIC PARTICLE TESTING - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFI - ISSUED FOR INFORMATION | 3/28/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-RA-6038-040-SOTU-00008 | NON-DESTRUCTIVE TESTING - ULTRASONIC TESTING OF AUSTENITIC/AUSTENITIC - FERRITIC STAINLESS STEEL FORGINGS | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFI - ISSUED FOR INFORMATION | 3/28/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-RA-6038-040-SOTU-00009 | NON-DESTRUCTIVE TESTING - RADIOGRAPHIC EXAMINATION (RT) OF CASTINGS - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFI - ISSUED FOR INFORMATION | 3/28/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-RA-6038-040-SOTU-00010 | NON-DESTRUCTIVE TESTING - RADIOGRAPHIC EXAMINATION (RT) WELDED JOINTS - ASME) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MATERIALS | RA - MATERIALS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 2 | IFI - ISSUED FOR INFORMATION | 3/28/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-RA-6068-040-SOTU-00001 | PAINT SPECIFICATION TURBOMACHINERY (ES9-58) ADDENDUM 1 - APPROVED MATERIALS/SUPPLIERS LIST (ES9-58-1) - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-RA-6068-040-SOTU-00002 | SURFACE PREPARATION & PAINT PROCEDURE - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MATERIALS | RA - MATERIALS | A03 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-RA-6068-040-SOTU-00003 | PMI PROCEDURE | MATERIALS | RA - MATERIALS | X | NAO |  | Diretorio Vendor | CANCELADO |  |  | 3/28/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-RA-6068-040-SOTU-00004 | BARREL FORGING WELD PROCEDURE - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MATERIALS | RA - MATERIALS | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-RA-6068-040-SOTU-00005 | CASTING REPAIR PROCEDURE - IMPELLERS - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MATERIALS | RA - MATERIALS | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-RA-6068-040-SOTU-00006 | CASTING REPAIR PROCEDURE - SUCTION CASE - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MATERIALS | RA - MATERIALS | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-RA-6068-040-SOTU-00011 | GEARBOX SURFACE PROTECTION AND PAINT PROCEDURE - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MATERIALS | RA - MATERIALS | A03 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-RA-6068-040-SOTU-00012 | BASEPLATE WPS/PQR - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MATERIALS | RA - MATERIALS | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-RA-6068-040-SOTU-00013 | OUTSOURCE PIPEWORK WPS/PQR | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | NÃO SE APLICA |  |  |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-RA-7180-040-SOTU-00009 | PUMP PERFORMANCE TEST REPORT (INCLUDES VIBRATION ANALYSIS) | MATERIALS | RA - MATERIALS | R01 | NAO |  | Diretorio Vendor | ENGINEERING CONSOLIDATION |  |  | 1/16/2026 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-SA-6028-040-SOTU-00001 | PROTECTION & PRESERVATION FOR STORAGE - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | SA - LOGISTICS | SA - LOGISTICS | A01 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-SA-6028-040-SOTU-00005 | PACKING AND SHIPMENT LIST | SA - LOGISTICS | SA - LOGISTICS | R01 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  |  | 5/17/2026 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-505151-300-VA-4305-040-SOTU-00001 | LIST OF MAJOR SUB-MANUFACTURERS/SUB SUPPLIERS - GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | VA - PROCUREMENT | VA - PROCUREMENT | A02 | NAO |  | Diretorio Vendor | ISSUED |  | IFR - ISSUED FOR REVIEW | 6/12/2025 | BNO / 03-VENDOR / SOLAR / PO_505151-TURBINE (P-4047)
BNO-AOL-UTC-300-AA-0190_INC | BLOWDOWN PIPING AREA ACCESS 2 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.3-MABU_RFI
BNO-AOL-UTC-300-AA-0191_INC | BLOWDOWN PIPING AREA ACCESS 1 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.3-MABU_RFI
BNO-AOL-UTC-300-AA-0192_INC | STARBOARD SUBSEA LEVEL2 BLOWDOWN VALVE | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.3-MABU_RFI
BNO-AOL-UTC-300-AA-0193_INC | STARBOARD SUBSEA MODULE STRUCTURE-DECK EXTENSION (EL.108682) | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.3-MABU_RFI
BNO-AOL-UTC-300-AA-0194_INC | STRUCTURE HPU DECK EXTENSION | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.3-MABU_RFI
BNO-AOL-UTC-300-AA-0195_INC | STARBOARD SUBSEA STRUCTURE - DECK EXTENSION RELIEF VALVE (EL+114802)-DROP OBJECT PROTECTION | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.3-MABU_RFI
BNO-AOL-UTC-300-AA-0196_INC | DECK EXTENSION PIG LAUNCHER / RECEIVER (EL+109800) | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.3-MABU_RFI
BNO-AOL-UTC-300-AA-0197_INC | USE OF 25MM ROUND BAR S355+AR IN PLACE OF SPECIFIED S355+N | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.3-MABU_RFI
BNO-MABU-2025-TQ-000001 | DBR ORIGINATOR CODE | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000002 | DISCIPLINE & DOCUMENT TYPE ID | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000003 | PIPE SPEC | PIPING | MP - PIPING | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000004 | SPPID AND SPI VERSION | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000005 | METHANOL PUMPS SUPPLY ELECTRICAL PANEL | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000006 | LOAD SHEDDING SYSTEM | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000007 | ELECTRICAL PANELS DOCUMENTS | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000008 | ELECTRICAL CIRCUIT TAG | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000009 | SPPID AND SPI VERSION | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000010 | DBR DOCUMENT/DRAWING NUMBER - STAMP | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000011 | DOCUMENT REQUEST | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000012 | DBR STAMP FOR LIMITED RESPONSABILITY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000013 | DOCUMENT REQUEST | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000014 | DOCUMENT REQUEST | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000015 | SPEL DATABASE | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000016 | PIG LAUNCHER STANDARDS | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000017 | EXISTING INTERLOCK SYSTEM | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000018 | PROCEDURE FOR INTERLOCK SYSTEM | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000019 | INSTRUMENTS DATA SHEETS REQUEST | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000020 | SACS IMPUT FILES REQUEST | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000021 | PIG LAUNCHER DATA SHEET | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000022 | METHANOL PUMP MATERIAL SPECIFICATION | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000023 | ELECTRICAL LOADS FROM EPC2 AND EPC3 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000024 | 3D MODEL - TURBINE | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000025 | 3D MODEL - DARK BLUE ELEMENT | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000026 | 3D MODEL - DARK BLUE ELEMENT | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000027 | RESPOND TIME | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000028 | HYSYS SIMULATION | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000029 | DESPRESSURIZATION CRITERIA | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000030 | MATERIAL BALANCE CLARIFICATION | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000031 | REQUEST FOR SPI DATABASE UPDATED | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000032 | OIL FLOW LIMIT CONDITION | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000033 | FLOWSHEET LEGEND | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000034 | IAMS SERVER / CLIENT LOCATION | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000035 | MISSING PROCESS DATA IN SPPID AND SPI | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000036 | PVT REPORTS | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000037 | AUTOMATION STANDARDIZATION | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000038 | SPPID DATA | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000039 | SAND DETECTOR | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000040 | WELLS PRODUCTION PROFILE/FORECAST | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000041 | DEMOLITION DRAWINGS SPPID DATABASE | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000042 | TRANSFORMERS CTS | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000043 | ESSENTIAL AND EMERG. GENERATORS LOAD | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000044 | BACKWASH FILTERS LINE TO REMOVE | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000045 | CHANGE OF FAILURE MODE OF BDV | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000046 | ELECTRICAL STUDIES ETAP | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000047 | LAYDOWN ON THE TOP OF SSCB | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000048 | FILTER PRESSURE DROP | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000049 | FAILURE MODE OF MOVS AND SDVS | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000050 | DELETE SAND DETECTOR / EROSION PROBE | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000051 | ALARM AND SET POINT LIST | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000052 | CABLE SIZING | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000053 | LAYOUT WATERF. DECK EXTENSION LEVEL 1 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000054 | MPFM - POSSIBLE SOLUTION | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000055 | SPECIAL ITEMS SPECIFICATION | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000056 | BN SAFEGUARDING MEMORANDUM | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000057 | DATA SHEET SMALL AND LARGE BALL VALVE | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000058 | SPACE HEATERS FOR MOTORS | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000059 | SSCB ELECTRICAL ROOM DOORS X REMOVABLE | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000060 | POWELL PANELS IN SSCB ELECTRICAL ROOM | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000061 | STRESS ANALYSIS CALCULATION | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000062 | ADDITIONAL RECOMMENDATIONS FOR SPEC "J1" | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000063 | MATERIALS FOR WETTED PARTS IN WI VALVES | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000064 | CORROSION INHIBITOR PUMPS LOCATION | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000065 | NORMAL/ESSENTIAL/EMERG. - CLASSIF. SOCIETY | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000066 | TAG'S FOR EQUIPMENTS IN SSCB - REV1 | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000067 | DIESEL FUEL PUMP AND AIR COMPRESSOR | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000068 | STRUCTURE TO SUPPORT METHANOL PUMPS | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000069 | DATA SHEETS FOR GATE AND NEEDLE VALVES | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000070 | NEW SKID AND INSTRUMENT FOR P-4046A PUMP | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000071 | EXPLOSION OVERPRESSURE CRITERIA | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000072 | PIPING STRESS ANALYSIS - SLUVVVING CONSID. | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000073 | DEPRESSURIZATION STUDY | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000074 | DROPPED OBJECTS | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000075 | TRANSFORMER SUPPLIER | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000076 | CANCELADA | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000077 | CABLE ROUTE TO CONTROL ROOM | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000078 | CHANGE THE FLOWMETER TYPE (44-FIT-503) | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000079 | DOCUMENT SHARING (PT-4040A) | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000080 | METHANOL LINES | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000081 | HAZOP RECOMENDATION NUMBER 30 | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000082 | HAZOP RECOMENDATION NUMBER 23 | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000083 | SOUR SERVICE FOR CRA IN WET H2S COUNT.LINES | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000084 | FIRE SUPRESSION TO SSCB | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000085 | PIPING MATERIAL FOR METHANOL SERVICE | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000086 | SMART CHOKE VALVE PRESSURE DROP | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000087 | VENDOR DEFINITION FOR GRE (RTR) PIPING | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000088 | WATERFLOOD INJECTION PUMP SUCTION MATERIAL | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000089 | FIREWATER AND DELUGE P&IDS | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000090 | DR2 - PUNCH LIST ITEM 23 - PIPING ARRANGEMENT | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000091 | TEMPERATURE GAUGE TYPE (04-TG-468 AND 04-TG-469) | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000092 | CAUSE AND EFFECT REFERENCE DOCUMENTS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000093 | MABU 2026 TAM SCOPE | CONSTRUCTION | BA - CONSTRUCTION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000094 | PORT SUBSEA INDUCING VIBRATION IN SSCB | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000095 | CABLE SUPPLIER | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000096 | DROPPED OBJECTS OVER SSCB | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000097 | APPROVED VENDOR FOR THE ON/OFF VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000098 | APPROVED VENDOR FOR PRESSURE RELIEF VALVE | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000099 | METHANOL LINES - PUMP P-4270 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000100 | DELUGE WATER SPRAY NOZZLE | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000101 | WATERFLOOD DISCHARGE LINE 10.000PSI SSDD | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000102 | REQUEST OF EXISTING ELECTRICAL PANELS DRAWINGS | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000103 | MATERIALS FOR VALVES WI SERVICE - SPEC J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000104 | MARINE CERTIFICATION - PROCESS EQUIPMENT | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000105 | STRUCTURAL WELDING QUALIFICATION - AVEON | CONSTRUCTION | BA - CONSTRUCTION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000106 | REQUEST FOR THE USE OF BOLTED CONNECTION FOR SUPPORTS | CONSTRUCTION | BA - CONSTRUCTION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000107 | MARINE CERTIFICATION - PROCESS EQUIPMENT | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000108 | AIR LOCKS REMOVAL | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000109 | DESIGN ALLOWANCE TO HEAT DISSIPATION TO HVAC CALCULATION | MECHANICAL | MH - HVAC | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000110 | CABLE TRAYS AND LADDERS FOR INTERNAL CABLE CONTAINMENT | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000111 | TRANSFORMER BUNDING | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000112 | ALTERNATIVE MATERIAL - TANK OF TRANSFORMERS | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000113 | TOPSIDE PIGABLE PRODUCTION LINE THICKNESS | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000114 | ROOM PRESSURIZATION AFTER REMOVAL OF AIRLOCK | MECHANICAL | MH - HVAC | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000115 | SAFETY MARGIN PERCENTAGE FOR HVAC CALCULATION | MECHANICAL | MH - HVAC | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000116 | KAMOS GASKETS FOR LEAK TEST OF FLANGES | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000117 | DIESEL LINE CANCELLING | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000118 | GANGWAY LANDING PLATFORM | SA - LOGISTICS | SA - LOGISTICS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000119 | BN PIPING SPECIFICATION | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000120 | INSPECTION REPORT OF EXISTING BN PIPING TIE-INS | CONSTRUCTION | BA - CONSTRUCTION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000121 | PIG LAUNCHING / RECEIVING REFERENCE DOCUMENTS | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000122 | STRUCTURAL WELDING QUALIFICATION ON PLATE (BOP) TEST - AVEON | CONSTRUCTION | BA - CONSTRUCTION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000123 | VAPOR PRESSURE OF THE CORROSION INHIBITOR | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000124 | REQUEST FOR BONGA MAIN LINE LIST | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000125 | SPECIFICATION FOR GAS LIFT PIPE/TUBING FROM GAS LIFT MANIFOLD TO BGLU-17 | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000126 | REQUEST FOR HOOK-UP DOCUMENT FOR METHANOL SUPPLY | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000127 | METHANOL SOURCE TO BE ROUTED TO WHICH TUPA | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000128 | STRUCTURAL INFORMATION FOR MAIN RACK 4 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000129 | NATIVE FILES FOR BONGA MAIN FIREWATER PUMPS & NETWORK P&ID AND DELUGE DISTRIBUTION P&ID | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000130 | SAFETY DOCUMENTS AND DEPS | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000131 | COATING/ PAINTING STANDARDS FOR LABELING MATERIALS | CONSTRUCTION | BA - CONSTRUCTION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000132 | COMPANY SP-ITEM TAGGING | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000133 | PROPOSAL TO USE CS CLADDED INSTEAD OF SDSS | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000134 | PWHT REQUIREMENT FOR LINES | CONSTRUCTION | BA - CONSTRUCTION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000135 | ENSURING ESCAPE ROUTE AROUND EXISTING HPU | MECHANICAL | MH - HVAC | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000136 | METHANOL PUMPS TO BE DISMANTLED X UMBILICAL TERMINATION PANELS | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000137 | CABLE ENTRANCE IN HPU X WALKWAY | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000138 | REQUEST FOR DOCUMENT TO RAM STUDY | BC - COMMISSIONING | BC - COMMISSIONING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000139 | DESIGN PARAMETERS FOR DAMAGE CONDITION | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000140 | DROPPED OBJECT PROTECTION | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000141 | CORRELATION GAS LIFT MANIFOLD X BGLU-17 | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000142 | PROPOSAL TO USE CS CLADDED INSTEAD OF SDSS - 2 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000143 | ARRANGEMENT OF THE MAC GATEWAY CABINET | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000144 | PROPOSAL FOR EXTENDED BEAM AND SUPPORT POSITION | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000145 | DRAIN SEGREGATION | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000146 | ACQUISITION OF PIPE "SEAMED" SUPER DUPLEX STAINLESS STEEL. | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000147 | NPSH OF GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MR - MECHANICAL ROTATING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000148 | BONGA MAIN ASSUMPTION REGISTER SAFETY STUDIES AND MANNING DISTRIBUTION DATA | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000149 | FRED SOFTWARE INSTEAD OF PHAST DNV FOR FIRE AND EXPLOSION ANALYSIS | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000150 | BONGA MAIN EXHAUST DATA FOR TURBINE GENERATORS | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000151 | NOISE EXISTING WF PUMP AND LUBE OIL ON BONGA MAIN | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000152 | METHANOL PUMPS TO BE DISMANTLED X UMBILICAL TERMINATION | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000153 | BONGA MAIN FLARE STUDY - APPENDIX 3 FLARENET RUNS | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000154 | SSCB DROPPED OBJECT DIMENSIONS | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000155 | DROPPED OBJECT PROTECTION FOR THE NEW HPU | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000156 | COMPANY INSTRUMENT AIR DISTRIBUTION P&IDS | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000157 | ADDITIONAL CHECK VALVE AGAINST REVERSE FLOW FROM P-4046A | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000158 | NOT ISSUED | MECHANICAL | MR - MECHANICAL ROTATING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000159 | NOT ISSUED | MECHANICAL | MR - MECHANICAL ROTATING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000160 | NOT ISSUED | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000161 | BONGA MAIN TURBINE CONTROL REFERENCE DOCUMENTS | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000162 | COMPANY INSTRUMENT AIR DISTRIBUTION P&IDS | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000163 | CORRELATION GAS LIFT MANIFOLD X BGLU-17 | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000164 | REQUEST FOR BONGA NORTH PROJECT EPC-2 RISER AND PIPELINE DATA | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000165 | EXHAUST OUTLET SIZE AND EXHAUST OUTLET ELEVATION FOR EXISTING AND UPGRADED WATERFLOOD INJECTION PUMPS (P-4046A/B) ON BONGA MAIN | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000166 | CLARIFICATION ON THE EXHAUST DATA FOR THE UPGRADED WATERFLOOD INJECTION PUMP (P-4046A) ON BONGA MAIN | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000167 | CLARIFICATION AND CONFIRMATION ON EXHAUST DISCHARGE COMPOSITION TO BE USED IN GAS DISPERSION MODELLING STUDY | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000168 | EXISTING LAYDOWN AREAS & DOP IMPACT RESISTANCE & FREQUENCY | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000169 | METHANOL SOURCE TO BGLU-17 | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000170 | METHANOL PUMPS TO BE DISMANTLED X UMBILICAL TERMINATION PANELS | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000171 | LATEST REVISION OF THE WATER HAMMER STUDY | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000172 | PROPOSAL FOR STRUCTURE MATERIALS SUBSTITUTIONS | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000173 | COMPANY INSTRUMENT AIR DISTRIBUTION | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000174 | REQUEST FOR EXISTING BONGA MAIN SAFETY CASE REPORT. | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000175 | SPARE AND FUTURE LINES TO UMBILICAL UMB-08 AND UMB-09 | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000176 | USE STEEL MATERIALS WITH EN 10204 TYPE 3.1 CERTIFICATION | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000177 | REQUEST FOR APPROVED VENDOR LIST FOR SAFETY EQUIPMENT | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000178 | OPERATION WORKSTATION IN TAGGING PHILOSOPHY | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000179 | DED HAZOP CLOSEOUT - ADDITIONAL CHECK VALVE TO PROTECT P-4047 AGAINST POTENTIAL REVERSE FLOW FROM P-4046A | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000180 | EXHAUST DISCHARGE COMPOSITION OF NEW WATERFLOOD INJECTION PUMP TURBINE (PT-4047) | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000181 | SUCTION STRAINER FOR WFI PUMP (P-4047) PROTECTION: SP-080224 | MECHANICAL | MR - MECHANICAL ROTATING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000182 | BPCS GATEWAY CABINET AND THE BONGA MAIN EXISTING SERVER CABINET POWER REQUIREMENT | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000183 | USE OF REMOVABLE AND FIXED GUARDRAILS | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000184 | REQUEST FOR PORT AND DEVICE TAG NUMBERS | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000185 | CLARIFICATIONS ON BONGA NORTH PCD IT SECURITY AND PCD HANDOVER PLAN | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000186 | MPDS AND OTS DATA AND INPUT TO EPC-1 | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000187 | CONFIRMATION FOR CHARPY VALUE GRADE IN TERTIARY STEEL | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000188 | SSCB - STEEL MATERIAL GRADE PROPOSAL | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000189 | COMPANY - DATASHEET TZIT | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000190 | NOMENCLATURE FOR FIBER-OPTIC PATCH PANELS INSTALLED IN THE BPCS GATEWAY CABINET | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000191 | EXISTING MR2 LIGHTING DOCUMENTS | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000192 | GAS TURBINE FOR P-4047 EXHAUST STACK CLASH WITH AFT CRANE | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000193 | PRESSURE SETTINGS FOR METHANOL AND CORROSION INHIBITOR PUMPS | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000194 | BLAST LOAD APPLICATION FOR EXISTING HEADERS DURING STRESS ANALYSIS | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000195 | BOARDING PANEL - REQUEST FOR USE ALTERNATIVE CABLE CROSS-SECTIONS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000196 | CLARIFICATION OF FIREWATER COVERAGE FOR CORROSION INHIBITOR PUMPS | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000197 | POSTWELD HEATING TREATING | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000198 | SIL 2 TO SMOKE DETECTORS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000199 | SULZER CABLE REQUIREMENTS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000200 | REQUEST FOR EXISTING PDS FOR PROJECT UPDATE | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000201 | REFERENCE DOCUMENTS FROM BONGA MAIN - INTERCONNECTION WITH THE BONGA MAIN DCS/IP | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000202 | PROCESS TUBING MATERIAL TO 10000 PSI WATER INJECTION | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000203 | FINAL COLOUR TO INSTRUMENTES RELIEF AND MANUAL VALVES | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000204 | SCHEDULE SPOOL PIECE FOR ULTRASSONOC FLOWMETER 31-FIT-402 AND 31-FIT-412 | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000205 | HUB CODE OF THE VALVE 40-BLV-0225 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000209 | COMPANY - 24VDC FIELD POWER DISTRIBUTION | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000210 | REQUEST FOR PCD ASSET INFORMATION | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000211 | TUPA RETURN LINES | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000212 | REQUEST FOR WRIPS DOCUMENTS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000213 | INTERFACE BETWEEN MAC AND EPC3 | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000214 | CONFIRMATION OF NUMBER OF POB ON BONGA MAIN DURING BONGA NORTH OPERATE PHASE | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000215 | REQUEST FOR PORT AND DEVICE TAG NUMBERS | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000216 | SPARE AND FUTURE LINES TO UMBILICALS UMB-08 AND UMB-09 FROM HPU AND PUMPS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000217 | REQUEST FOR PORT AND DEVICE TAG NUMBERS | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000218 | THE USE OF INC625 60K FORGED BAR IN LIEU OF THE OVERLAY INCONEL625 PROCESS IN 14” API DBB VALVES | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000219 | UMBILICALS INJECTION LINES | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000220 | FLEXIBLE HOSE SPECIFICATION - EXISTING UMBILICALS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000221 | CORROSION INHIBITOR LINE FROM TANK TO HPU AND BOARDING VALVE PANEL | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000222 | MATERIAL CHANGE 40-BLV-926 (VBH-2502) | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000223 | NATIVE FORMAT OF THE BONGA MAIN PDS DOCUMENTS - SCHNEIDER REQUEST | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000224 | REQUEST FOR PORT AND DEVICE TAG NUMBERS | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000225 | CLARIFICATION ON FURNITURE FIRE CERTIFICATION REQUIREMENTS | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000226 | WATER INJECTION SYSTEM DYNAMIC SIMULATIONS STUDY GT | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000227 | CLARIFICATION ON OPERATION PROCEDURE AND PURPOSE FOR SPECIFIC WATER INJECTION AND DRAIN LINES | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000228 | FAILURE POSITION REQUIREMENTS FOR SDVS 04?SDV?709 AND 04?SDV?710 | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000229 | CONFIRMATION OF CONNECTION TO THE SSCB DRAIN (TRANSFORMER OIL) | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000230 | REPEATED TAG NUMBERS TO HVAC | MECHANICAL | MH - HVAC | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000231 | PIG LAUNCHER - RELOCATION OF SPEC BREAK (B31.8 AND B31.3) TO ENABLE INTRODUCTION OF FLANGES BETWEEN THE DBB 04-DBB-836 AND PIG LAUNCHER / RECEIVER | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000233 | MATERIAL ACCEPTANCE OF PROFILES WITHOUT NORMALIZATION EVIDENCE | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000234 | REQUEST FOR SAFETY EQUIPMENT (SPRAY NOZZLES AND FIRE EXTINGUISHERS) CATALOGUES | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000235 | REQUEST FOR INFORMATION REGARDING EXISTING STORAGE TANKS ON LACT MODULE | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000236 | P&IDS FOR THE 9 PRODUCERS WELLS AND 8 INJECTOR WELLS | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000237 | PRESSURE TEST FOR TUBINGS - INJECTION TUBINGS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000238 | INSTRUMENT AIR DISTRIBUTION P&IDS | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000239 | METHANOL LINES FROM 10000 PUMP SKID TO TUPA UMB-08 AND UMB-09 | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000240 | CORROSION INHIBITOR LINES FROM 10000 PUMP SKID TO TUPA UMB-08 AND UMB-09 | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000241 | POWELL TQ-0054 : 13A SOCKET OUTLET MAKER | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000242 | HYDRAULIC FLUID LINE FROM TANK TO HPU AND BOARDING VALVE PANEL | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000243 | DISTRIBUTION BOARD SCHEDULE PS LEVEL 1 - DB-7642-N-01 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000244 | INSTRUMENT AIR SUPPLY FROM BONGA MAIN | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000245 | LIGHTING AND SMALL POWER CIRCUIT TAGGING PHILOSOPHY | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000246 | CLARIFICATION ON EPC3/SOLAR FO CABLE | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000247 | REQUEST FOR TELECOM CABINET ACCESSORIES | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000248 | EQUIPMENT DOCUMENTATION FROM BONGA NORTH INSTALLATIONS FOR CLASH ANALYSIS CLASH REPORT AND DOCUMENT UPDATE | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000249 | H60 INSULATION IN SSCB - FIRE PROOFING | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000250 | CLARIFICATION ON TELECOM TAGGING PHILOSOPHY ALIGNMENT | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000251 | ACCEPTANCE OF MTC 3.1 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000252 | RESERVED TO CHRIS LUCE | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000253 | SSCB - ANTI-ACID FLOOR FOR BATTERY ROOM(POWELL TQ-0024R02) | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000254 | INJECTION TUBING MATERIAL SELECTION | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000255 | H60 INSULATION IN SSCB - FIRE PROOFING | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000256 | THE USE OF INC625 60K FORGED BAR IN LIEU OF THE OVERLAY INCONEL625 PROCESS IN 14” API DBB VALVES | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000257 | PORCENTAGE CONTINGENCY MATERIAL (ALLOWANCE) TO PIPING BULKING MATERIAL | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000258 | USE OF THE DEIONIZING UNIT - PT-4040A-T-02 ( EXISTING MOBILE UNIT ) TO FEED THE P-4047 GAS TURBINE WATER WASHING SYSTEM | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000259 | WATER TO FEED THE P4047 WATER MIST FIRE SUPPRESSION SYSTEM | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000260 | NATIVE FORMAT OF THE BONGA MAIN FIRE DAMPER PDS AND ESS WATCHDOG APPLICATION PDS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000261 | CLARIFICATION ON COATING REQUIREMENT FOR BVP ENCLOSURE | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000262 | REQUEST FOR BONGA MAIN ESS FROZEN PT2 FILES | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000263 | INJECTION TUBING MATERIAL SELECTION | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000264 | MOS KEY SWITCH | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000265 | POLYURETHANE JACKET THICKNESS FOR TUBINGS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000266 | LADDER DETAIL SUBSTITUTION | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000267 | FLOWRATE IN UMBILICAL LINES | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000268 | FAIL MODE OF THE CONTROL VALVE 40-FCV- 843 AND 40-FCV-602A - PUMPS | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000269 | FLEXIBLE HOSE SPECIFICATION - EXISTING UMBILICALS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000270 | HYDRAULIC RETURN LINE FROM TUPA UMB-08 AND UMB-09 TO HPU | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000271 | FC FOR 40-SDV-670 | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000272 | POWELL TQ-0055 : REQUESTING FOR APPROVAL - PAINTED ALUMINUM ALLOY AS PURGE CONTROL PANEL (PCP) ENCLOSURE MATERIAL | MECHANICAL | MH - HVAC | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2025-TQ-000273 | LLOYD’S CERTIFICATION REQUIREMENT FOR POLYURETHANE JACKETING ON TUBING | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TD-000001 | ACQUISITION OF PIPE “SEAMED” SUPER DUPLEX STAINLESS STEEL | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.2-MABU_TDV
BNO-MABU-2026-TD-000002 | ACQUISITION OF PIPE “SEAMED” SUPER DUPLEX STAINLESS STEEL | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.2-MABU_TDV
BNO-MABU-2026-TD-000003 | PROPOSED USE OF S355J0 STRUCTURAL BEAMS SUBJECT TO ADDITIONAL LOW-TEMPERATURE TESTING | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.2-MABU_TDV
BNO-MABU-2026-TD-000004 | PROPOSED USE PLATES WITH EN 10204 MTC 3.1 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.2-MABU_TDV
BNO-MABU-2026-TD-000005 | NON-IMPLEMENTATION OF PRESCRIBED NDT INSPECTION ON THE SPECIAL SUPPORT WELDING DURING TAM-26 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.2-MABU_TDV
BNO-MABU-2026-TD-000006 | ACCEPTANCE OF MTC 3.1 FOR VENDORS LISTED IN THE APPROVED VENDOR LIST (AVL)_ CANCELLED | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.2-MABU_TDV
BNO-MABU-2026-TD-000007 | USE OF 25MM ROUNDBAR S355+AR IN PLACE OF SPECIFIED S355+N | CONSTRUCTION | BA - CONSTRUCTION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.2-MABU_TDV
BNO-MABU-2026-TQ-000206 | TEMPERATURE INDICATING TRANSMITTER - DESIGN CLAMP-ON X DESIGN | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000207 | DESIGN IMPACT RESISTANCE OF EXISTING LAYDOWN AREAS & DROPPED OBJECT PROTECTION (DOP) | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000208 | REQUEST FOR APPROVAL OF CABLE CORE SIZE FOR INTERNAL ENCLOSURE OF BOARDING VALVE PANEL | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000209 | COMPANY - 24VDC FIELD POWER DISTRIBUTION | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000210 | REQUEST FOR PCD ASSET INFORMATION | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000211 | TUPA RETURN LINES | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000212 | REQUEST FOR WRIPS DOCUMENTS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000213 | INTERFACE BETWEEN MAC AND EPC3 | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000214 | CONFIRMATION OF NUMBER OF POB ON BONGA MAIN DURING BONGA NORTH OPERATE PHASE | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000215 | REQUEST FOR PORT AND DEVICE TAG NUMBERS | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000216 | SPARE AND FUTURE LINES TO UMBILICALS UMB-08 AND UMB-09 FROM HPU AND PUMPS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000217 | REQUEST FOR PORT AND DEVICE TAG NUMBERS | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000218 | THE USE OF INC625 60K FORGED BAR IN LIEU OF THE OVERLAY INCONEL625 PROCESS IN 14" API DBB VALVES | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000219 | UMBILICALS INJECTION LINES | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000220 | FLEXIBLE HOSE SPECIFICATION - EXISTING UMBILICALS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000221 | CORROSION INHIBITOR LINE FROM TANK TO HPU AND BOARDING VALVE PANEL | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000222 | MATERIAL CHANGE 40-BLV-926 (VBH-2502) | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000223 | NATIVE FORMAT OF THE BONGA MAIN PDS DOCUMENTS - SCHNEIDER REQUEST | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000224 | REQUEST FOR PORT AND DEVICE TAG NUMBERS | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000225 | CLARIFICATION ON FURNITURE FIRE CERTIFICATION REQUIREMENTS | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000226 | WATER INJECTION SYSTEM DYNAMIC SIMULATIONS STUDY GT | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000227 | CLARIFICATION ON OPERATION PROCEDURE AND PURPOSE FOR SPECIFIC WATER INJECTION AND DRAIN LINES | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000228 | FAILURE POSITION REQUIREMENTS FOR SDVS 04?SDV?709 AND 04?SDV?710 | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000229 | CONFIRMATION OF CONNECTION TO THE SSCB DRAIN (TRANSFORMER OIL) | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000230 | REPEATED TAG NUMBERS TO HVAC | MECHANICAL | MH - HVAC | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000231 | PIG LAUNCHER - RELOCATION OF SPEC BREAK (B31.8 AND B31.3) TO ENABLE INTRODUCTION OF FLANGES BETWEEN THE DBB 04-DBB-836 AND PIG LAUNCHER / RECEIVER | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000232 | MATERIAL ACCEPTANCE OF PROFILES WITHOUT NORMALIZATION EVIDENCE | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000233 | REQUEST FOR SAFETY EQUIPMENT (SPRAY NOZZLES AND FIRE EXTINGUISHERS) CATALOGUES | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000234 | REQUEST FOR INFORMATION REGARDING EXISTING STORAGE TANKS ON LACT MODULE | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000235 | P&IDS FOR THE 9 PRODUCERS WELLS AND 8 INJECTOR WELLS | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000236 | PRESSURE TEST FOR TUBINGS - INJECTION TUBINGS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000237 | INSTRUMENT AIR DISTRIBUTION P&IDS | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000238 | METHANOL LINES FROM 10000 PUMP SKID TO TUPA UMB-08 AND UMB-09 | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000239 | CORROSION INHIBITOR LINES FROM 10000 PUMP SKID TO TUPA UMB-08 AND UMB-09 | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000240 | POWELL TQ-0054 : 13A SOCKET OUTLET MAKER | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000241 | HYDRAULIC FLUID LINE FROM TANK TO HPU AND BOARDING VALVE PANEL | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000242 | DISTRIBUTION BOARD SCHEDULE PS LEVEL 1 - DB-7642-N-01 | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000243 | INSTRUMENT AIR SUPPLY FROM BONGA MAIN | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000244 | LIGHTING AND SMALL POWER CIRCUIT TAGGING PHILOSOPHY | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000245 | CLARIFICATION ON EPC3/SOLAR FO CABLE | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000246 | REQUEST FOR TELECOM CABINET ACCESSORIES | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000247 | EQUIPMENT DOCUMENTATION FROM BONGA NORTH INSTALLATIONS FOR CLASH ANALYSIS CLASH REPORT AND DOCUMENT UPDATE | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000248 | H60 INSULATION IN SSCB - FIRE PROOFING | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000249 | CLARIFICATION ON TELECOM TAGGING PHILOSOPHY ALIGNMENT | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000250 | ACCEPTANCE OF MTC 3.1 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000251 | RESERVED TO CHRIS LUCE | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000252 | SSCB - ANTI-ACID FLOOR FOR BATTERY ROOM(POWELL TQ-0024R02) | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000253 | INJECTION TUBING MATERIAL SELECTION | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000254 | H60 INSULATION IN SSCB - FIRE PROOFING | TECHNICAL SAFETY | HS - SAFETY | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000255 | THE USE OF INC625 60K FORGED BAR IN LIEU OF THE OVERLAY INCONEL625 PROCESS IN 14" API DBB VALVES | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000256 | PORCENTAGE CONTINGENCY MATERIAL (ALLOWANCE) TO PIPING BULKING MATERIAL | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000257 | USE OF THE DEIONIZING UNIT - PT-4040A-T-02 ( EXISTING MOBILE UNIT ) TO FEED THE P-4047 GAS TURBINE WATER WASHING SYSTEM | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000258 | WATER TO FEED THE P4047 WATER MIST FIRE SUPPRESSION SYSTEM | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000259 | NATIVE FORMAT OF THE BONGA MAIN FIRE DAMPER PDS AND ESS WATCHDOG APPLICATION PDS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000260 | CLARIFICATION ON COATING REQUIREMENT FOR BVP ENCLOSURE | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000261 | REQUEST FOR BONGA MAIN ESS FROZEN PT2 FILES | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000262 | INJECTION TUBING MATERIAL SELECTION | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000263 | MOS KEY SWITCH | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000264 | POLYURETHANE JACKET THICKNESS FOR TUBINGS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000265 | LADDER DETAIL SUBSTITUTION | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000266 | FLOWRATE IN UMBILICAL LINES | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000267 | FAIL MODE OF THE CONTROL VALVE 40-FCV- 843 AND 40-FCV-602A - PUMPS | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000268 | FLEXIBLE HOSE SPECIFICATION - EXISTING UMBILICALS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000269 | HYDRAULIC RETURN LINE FROM TUPA UMB-08 AND UMB-09 TO HPU | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000270 | FC FOR 40-SDV-670 | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000271 | POWELL TQ-0055 : REQUESTING FOR APPROVAL - PAINTED ALUMINUM ALLOY AS PURGE CONTROL PANEL (PCP) ENCLOSURE MATERIAL | MECHANICAL | MH - HVAC | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-2026-TQ-000272 | LLOYD'S CERTIFICATION REQUIREMENT FOR POLYURETHANE JACKETING ON TUBING | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
BNO-MABU-300-AA-0780-10001 | LNTP CLOSE-OUT REPORT | PMT | AA - PROJECT MANAGEMENT | A02 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.01-AA-PROJECT MANAGEMENT
BNO-MABU-300-AA-5760-10001 | PROJECT EXECUTION PLAN - DED PHASE | PMT | AA - PROJECT MANAGEMENT | A02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU - RELEASE |  | BNO / 02-DED / 02.01-AA-PROJECT MANAGEMENT
BNO-MABU-300-AA-5787-10002 | LEVEL 3 PROJECT SCHEDULE | PMT | AA - PROJECT MANAGEMENT | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.01-AA-PROJECT MANAGEMENT
BNO-MABU-300-AA-5800-10001 | EPC-1 DETAILED ENGINEERING DESIGN (DED) - INTERFACE MANAGEMENT PLAN | PMT | AA - PROJECT MANAGEMENT | A03 | SIM | IFR |  | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.01-AA-PROJECT MANAGEMENT
BNO-MABU-300-AA-6619-10001 | MONTHLY RISK/ OPPORTUNITY REGISTER - MAR.2025 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Titulo excluido por regra | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 02-DED / 02.01-AA-PROJECT MANAGEMENT
BNO-MABU-300-AA-6619-10002 | MONTHLY RISK/ OPPORTUNITY REGISTER - JUL.2025 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Titulo excluido por regra | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 02-DED / 02.01-AA-PROJECT MANAGEMENT
BNO-MABU-300-AA-6945-10001 | DED CLOSE-OUT REPORT | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.01-AA-PROJECT MANAGEMENT
BNO-MABU-300-AA-7180-10001 | SITE VISIT PLAN AND CHECKLIST | PMT | AA - PROJECT MANAGEMENT | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 2 | IFA - ISSUED FOR APPROVAL |  | BNO / 02-DED / 02.01-AA-PROJECT MANAGEMENT
BNO-MABU-300-AA-7180-10002 | SITE VISIT REPORT | PMT | AA - PROJECT MANAGEMENT | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.01-AA-PROJECT MANAGEMENT
BNO-MABU-300-AA-7180-10011 | WEEKLY PROGRESS REPORT DED WEEK 11 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10012 | WEEKLY PROGRESS REPORT DED WEEK 12 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10013 | WEEKLY PROGRESS REPORT - DED - WEEK 13 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10014 | WEEKLY PROGRESS REPORT DED WEEK 14 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10015 | WEEKLY PROGRESS REPORT DED - WEEK 15 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10016 | WEEKLY PROGRESS REPORT - DED - WEEK 16 | NÃO SE APLICA | NÃO SE APLICA | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10017 | WEEKLY PROGRESS REPORT_DED_WEEK 17 | NÃO SE APLICA | NÃO SE APLICA | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10018 | DED WEEKLY PROGRESS REPORT #018 FOR WEEK 19TH MAY TO 23RD MAY 2025 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10019 | WEEKLY PROGRESS REPORT - DED - WEEK 19 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10020 | DED WEEKLY PROGRESS REPORT # 20 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10021 | WEEKLY PROGRESS REPORT #21 FOR W/E 16-06-2025 | NÃO SE APLICA | NÃO SE APLICA | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10022 | DED WEEKLY PROGRESS REPORT FOR WEEK 22 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10023 | DED WEEKLY PROGRESS REPORT #23 FOR WEEK ENDING 27-JUNE-2025 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10024 | DED WEEKLY PROGRESS REPORT FOR WE 4-07-2025 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10025 | WEEKLY PROGRESS REPORT - DED - WEEK 25 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10026 | DED WEEKLY PROGRESS REPORT#26 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10027 | DED WEEKLY PROGRESS REPORT #27 FOR WEEK ENDED 25-JULY-2025 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10028 | DED WEEKLY PROGRESS REPORT#28 FOR WE 01-AUGUST-2025 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10029 | DED WEEKLY PROGRESS REPORT#29 FOR WE 08-AUGUST-2025 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10030 | DED WEEKLY PROGRESS REPORT FOR WEEK ENDED 15-08-2025 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10031 | DED WEEKLY PROGRESS REPORT #31 FOR WEEK ENDED 22-AUGUST-2025 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10032 | DED WEEKLY PROGRESS REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10033 | WEEKLY PROGRESS REPORT - DED - WEEK 33 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10034 | WEEKLY PROGRESS REPORT - DED - WEEK 34 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10035 | DED WEEKLY PROGRESS REPORT #35 FOR W/E 19-09-2025 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10036 | DED WEEKLY PROGRESS REPORT - WEEK 36 (19TH - 25TH SEPTEMBER 2025) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10037 | WEEKLY PROGRESS REPORT – WEEK 37 REPORT (26TH SEPT - 2ND OCT. 2025 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10038 | WEEKLY DED PROGRESS REPORT#38_(3RD OCT - 9TH OCT. 2025) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10039 | WEEKLY PROGRESS REPORT DED WEEK 39 (10 TO 16TH OCTOBER, 2025) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10040 | WEEKLY PROGRESS REPORT - WEEK 40 REPORT (17TH - 23RD OCT. 2025) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10041 | DED WEEKLY PROGRESS REPORT - WEEK 41 (24TH - 30TH OCT. 2025) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10042 | WEEKLY PROGRESS REPORT - DED - WEEK 42 (30TH OCT - 6TH NOV. 2025) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10043 | WEEKLY PROGRESS REPORT - DED - WEEK 43 (7TH - 13TH NOV. 2025) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10044 | WEEKLY PROGRESS REPORT - WEEK 44 (14TH-20TH NOV. 2025) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10046 | WEEKLY PROGRESS REPORT – WEEK 46 (28TH NOV-04TH DEC. 2025) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10047 | WEEKLY PROGRESS REPORT – WEEK 47 (05TH-11TH DEC. 2025) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10048 | WEEKLY PROGRESS REPORT - DED - WEEK 48 (12TH-18TH DEC. 2025) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10049 | BNO-MABU-300-AA-7180-10049_WEEKLY PROGRESS REPORT - DED - WEEK 49, 50 & 51 (19TH DEC 2025 - 8TH, JAN 2026) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10052 | WEEKLY PROGRESS REPORT – WEEK 52 (9TH JAN – 15TH JAN, 2026) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10053 | WEEKLY PROGRESS REPORT – WEEK 53 (16TH JAN – 22ND JAN,2026) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10054 | WEEKLY PROGRESS REPORT – WEEK 54 (23RD JAN – 29TH JAN,2026) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10055 | DED WEEKLY PROGRESS REPORT#55 (30JAN – 5FEB2026) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10056 | WEEK 56 REPORT (6TH FEB. - 12TH FEB. 2026) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10057 | WEEKLY PROGRESS REPORT – WEEK 57 (13TH FEB – 19TH FEB. 2026) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10058 | WEEKLY PROGRESS REPORT – WEEK 58 (20FEB – 26FEB 2026) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10059 | BNO-MABU-300-AA-7180-10059 WEEKLY PROGRESS REPORT – WEEK 59 (27TH FEB – 5TH MARCH 2026) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10060 | BNO-MABU-300-AA-7180-10060_WEEKLY PROGRESS REPORT – WEEK 60 (6TH – 12TH MARCH 2026) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10061 | WEEKLY PROGRESS REPORT – WEEK 61 (13TH – 19TH MARCH 2026) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10063 | WEEKLY PROGRESS REPORT#63 (27TH MARCH - 2ND APRIL 2026) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10064 | WEEKLY PROGRESS REPORT – WEEK 64 (9TH APRIL 2026) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10065 | WEEKLY PROGRESS REPORT – WEEK 65 (16TH APRIL 2026) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10066 | WEEKLY PROGRESS REPORT - WEEK 66 (23RD APRIL 2026) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10068 | WEEKLY PROGRESS REPORT – WEEK 68 (7TH MAY 2026) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10069 | WEEKLY PROGRESS REPORT – WEEK 69 (14TH MAY 2026) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10070 | WEEKLY PROGRESS REPORT – WEEK 70 (21ST MAY 2026) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.003-REPORTS
BNO-MABU-300-AA-7180-10100 | 2ND SITE SURVEY REPORT | PMT | AA - PROJECT MANAGEMENT | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.01-AA-PROJECT MANAGEMENT
BNO-MABU-300-AA-7403-10001 | MULTIDISCIPLINE DESIGN REVIEW TERMS OF REFERENCE | PMT | AA - PROJECT MANAGEMENT | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 02-DED / 02.01-AA-PROJECT MANAGEMENT
BNO-MABU-300-AA-7403-10002 | MULTIDISCIPLINARY DESIGN REVIEW REPORT | PMT | AA - PROJECT MANAGEMENT | A02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 02-DED / 02.01-AA-PROJECT MANAGEMENT
BNO-MABU-300-AA-7704-10001 | PROJECT BASIS OF DESIGN | PMT | AA - PROJECT MANAGEMENT | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 02-DED / 02.01-AA-PROJECT MANAGEMENT
BNO-MABU-300-AA-8502-10002 | REVIEW OF 2D-3D TEMPLATES | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 02-DED / 02.001-DAE_TQR
BNO-MABU-300-AA-8502-10004 | TQ_FOR_CERTIFIED_VENDOR_DATA | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | CANCELADO |  |  |  | BNO / 02-DED / 02.001-DAE_TQR
BNO-MABU-300-BA-5537-10002 | CONSTRUCTION SCOPE OF WORK | CONSTRUCTION | BA - CONSTRUCTION | A02 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.02-BA-CONSTRUCTION
BNO-MABU-300-BA-6065-10006 | METHANOL SKID ISOLATION MATERIALS - MATERIAL REQUISITION | CONSTRUCTION | BA - CONSTRUCTION | R01 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.02-BA-CONSTRUCTION
BNO-MABU-300-BA-7180-10001 | 1ST CONSTRUCTABILITY REVIEW REPORT | CONSTRUCTION | BA - CONSTRUCTION | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.02-BA-CONSTRUCTION
BNO-MABU-300-BA-7180-10002 | 60% CONSTRUCTABILITY REVIEW REPORT | CONSTRUCTION | BA - CONSTRUCTION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.02-BA-CONSTRUCTION
BNO-MABU-300-BA-7180-10003 | 90% CONSTRUCTABILITY REVIEW REPORT | CONSTRUCTION | BA - CONSTRUCTION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.02-BA-CONSTRUCTION
BNO-MABU-300-BA-7753-10001 | CONSTRUCTABILITY REVIEW TERMS OF REFERENCE | CONSTRUCTION | BA - CONSTRUCTION | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.02-BA-CONSTRUCTION
BNO-MABU-300-BA-7753-10002 | 2ND CONSTRUCTABILITY REVIEW TERMS OF REFERENCE | CONSTRUCTION | BA - CONSTRUCTION | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.02-BA-CONSTRUCTION
BNO-MABU-300-BA-7753-10003 | 90% CONSTRUCTABILITY REVIEW TERMS OF REFERENCE | CONSTRUCTION | BA - CONSTRUCTION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.02-BA-CONSTRUCTION
BNO-MABU-300-CS-0514-10001 | STRUCTURAL VERIFICATION REPORT - BONGA HULL PEDESTAL STRENGTH ASSESSMENT | STRUCTURAL | CS - STRUCTURAL | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-0514-10002 | CORROSION INHIBITOR PLATFORM IN PLACE ANALYSIS REPORT CORROSION INHIBITOR PLATFORM IN PLACE ANALYSIS REPORT | STRUCTURAL | CS - STRUCTURAL | A03 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-0514-10018 | STARBOARD SUBSEA MODULE STOOL VERIFICATION REPORT | STRUCTURAL | CS - STRUCTURAL | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-0514-10019 | WATERFLOOD MODULE STOOL VERIFICATION REPORT | STRUCTURAL | CS - STRUCTURAL | A03 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-0514-10020 | STARBOARD SUBSEA MODULE IN PLACE ANALYSIS VERIFICATION REPORT | STRUCTURAL | CS - STRUCTURAL | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-0514-10021 | WATERFLOOD MODULE DECK EXTENSIONS IN PLACE ANALYSIS VERIFICATION REPORT | STRUCTURAL | CS - STRUCTURAL | A02 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-0514-10022 | LACT MODULE STOOL VERIFICATION | STRUCTURAL | CS - STRUCTURAL | A03 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-0514-10023 | HPU DROPPED OBJECT PROTECTION LIFTING ANALYSIS REPORT | STRUCTURAL | CS - STRUCTURAL | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-0514-10024 | MAIN RACK 3 STRUTURAL VERIFICATION REPORT - IN PLACE ANALYSIS WITH HPU PACKAGE | STRUCTURAL | CS - STRUCTURAL | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-0514-10026 | LACT. WATERFLOOD & MR2 MODULE INPLACE ANALYSIS WI PACKAGE. WI HANDLING AREA & WF DECK EXTENSION | STRUCTURAL | CS - STRUCTURAL | A02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-0514-10027 | PORTSIDE SUBSEA MODULE AND MR3 MISCELLANEOUS CALCULATION REPORT | STRUCTURAL | CS - STRUCTURAL | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-0514-10028 | STARBOARD SUBSEA MODULE MISCELLANEOUS CALCULATION REPORT | STRUCTURAL | CS - STRUCTURAL | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-0514-10029 | PORTSIDE SUBSEA MODULE STOOL VERIFICATION REPORT | STRUCTURAL | CS - STRUCTURAL | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-0514-10030 | CORROSION INHIBITOR PLATFORM LIFTING ANALYSIS REPORT | STRUCTURAL | CS - STRUCTURAL | A03 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-0520-10002 | STARBOARD SUBSEA MODULE INPLACE ANALYSIS REPORT -BONGA NORTH MODIFICATIONS | STRUCTURAL | CS - STRUCTURAL | A05 | SIM | MABU UNDER REVIEW |  | TRANSMITTAL |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-1448-10001 | WEIGHT CONTROL REPORT - APRIL 2026 | STRUCTURAL | CS - STRUCTURAL | A02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-1448-10001-000 | WEIGHT CONTROL REPORT - MAY 2025 | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-1448-10001-002 | WEIGHT CONTROL REPORT - AUGUST 2025 | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-1448-10001-003 | WEIGHT CONTROL REPORT - SEPTEMBER 2025 | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-1448-10001-004 | WEIGHT CONTROL REPORT - OCTOBER 2025 | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-1448-10001-005 | WEIGHT CONTROL REPORT - FEBRUARY 2026 | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-1448-10002 | WATER INJECTION TURBINE SKID - STRUCTURAL CALCULATION REPORT - LIFTING ANALYSIS | STRUCTURAL | CS - STRUCTURAL | A03 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-2358-10001-001 | TUPA STRUCTURAL SUPPORT | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50008 | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-2358-10001-002 | TUPA STRUCTURAL SUPPORT | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50008 | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-2358-10001-003 | TUPA STRUCTURAL SUPPORT | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-2358-10002-001 | SSCB CONTROL BUILDING - STRUCTURE - FOUNDATION STOOLS PART 1 | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU - RELEASE |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-2358-10002-002 | SSCB CONTROL BUILDING - STRUCTURE - FOUNDATION STOOLS PART 2 | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU - RELEASE |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-2358-10003-001 | BOARDING VALVE PANEL STRUCTURAL SUPPORT | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-2358-10004-001 | MAIN RACK 4 STRUCTURE - BOARDING VALVE PANEL SUPPORT @ EL. +114802 | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE | FAB-MABU-AVEON-2026-TN-50008 | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-2358-10005-001 | DEMOLITION DRAWING FOR HANDRAIL OF MAIN RACK 4 STRUCTURE - BOARDING VALVE PANEL SUPPORT @ EL. +114802 | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50008 | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-2408-10001-001 | BGLU MANIFOLD ACCESS PLATFORM | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE | FAB-MABU-AVEON-2026-TN-50005 | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-2408-10001-002 | BGLU MANIFOLD ACCESS PLATFORM | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE | FAB-MABU-AVEON-2026-TN-50005 | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-3323-10001 | GENERAL NOTES | STRUCTURAL | CS - STRUCTURAL | X | NAO |  | Revisao X cancelada | CANCELADO |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-3323-10001-001 | GENERAL NOTES_ TYPICAL DETAILS - GRATING (STEEL)_ TYPICAL DETAILS - HANDRAIL_ AND TYPICAL JOINT DETAILS | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-3323-10001-002 | GENERAL NOTES - TYPICAL DETAILS - STEEL GRATING | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-3323-10001-003 | GENERAL NOTES - TYPICAL DETAILS - HANDRAIL | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-3323-10001-004 | GENERAL NOTES - TYPICAL DETAILS - JOINT | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 | IFA - ISSUED FOR APPROVAL |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10001-001 | WATERFLOOD MODULE DRAWINGS SHOWING PIPE SUPPORT STRINGERS @ ALL LEVELS | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10002-001 | STARBOARD SUBEA MODULE DRAWINGS SHOWING PIPE SUPPORT STRINGERS ALL LEVELS | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10004-001 | MAIN RACK 2 MODULE DRAWINGS SHOWING PIPE SUPPORT STRINGERS @ ALL LEVELS | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10006-001 | DEMOLITION WORKS FOR WATERFLOOD MODULE DECK EXTENSION @LEVEL 1 AND LEVEL 3 | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10006-002 | DEMOLITION WORKS FOR WATERFLOOD MODULE DECK EXTENSION @LEVEL 1 AND LEVEL 3 | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10008-001 | WATER INJECTION TURBINE SKID - STRUCTURE - LEVEL 1 | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10008-002 | WATER INJECTION TURBINE SKID - STRUCTURE - LEVEL 1 | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | IFR |  | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10008-003 | WATER INJECTION TURBINE SKID - STRUCTURE - LEVEL 1 | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10009-001 | WATER INJECTION TURBINE SKID - STRUCTURE - LEVEL 2 | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | IFR |  | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10009-002 | WATER INJECTION TURBINE SKID - STRUCTURE - LEVEL 2 | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | IFR |  | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10009-003 | WATER INJECTION TURBINE SKID - STRUCTURE - LEVEL 2 | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10009-004 | WATER INJECTION TURBINE SKID - STRUCTURE - LEVEL 2 | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10010-001 | WATER INJECTION TURBINE SKID - STRUCTURE - ELEVATION - NORTH & SOUTH TRUSS | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | IFR |  | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10011-001 | WATER INJECTION TURBINE SKID - STRUCTURE - TRANSVERSAL SECTION (E 940000) | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | IFR |  | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10012-001 | WATER INJECTION TURBINE SKID - STRUCTURE - TRANSVERSAL SECTION (E 945000) | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | IFR |  | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10013-001 | WATER INJECTION TURBINE SKID - STRUCTURE - TRANSVERSAL SECTION (E 950000) | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | IFR |  | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10014-001 | WATER INJECTION TURBINE SKID - STRUCTURE - DETAILS | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | IFR |  | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10015-001 | WATERFLOOD MODULE - DECK EXTENSION (LEVEL 1) MODIFICATIONS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10015-002 | WATERFLOOD MODULE - DECK EXTENSION (LEVEL 1) MODIFICATIONS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10016-001 | WATERFLOOD MODULE - DECK EXTENSION (LEVEL 3) MODIFICATIONS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | IFR |  | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10016-002 | WATERFLOOD MODULE - DECK EXTENSION (LEVEL 3) MODIFICATIONS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | IFR |  | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10016-003 | WATERFLOOD MODULE - DECK EXTENSION (LEVEL 3) MODIFICATIONS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | IFR |  | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10016-004 | WATERFLOOD MODULE DECK EXTENSION (LEVEL 3) MODIFICATIONS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10017-001 | STARBOARD SUBSEA MODULE - STRUCTURE - DECK EXTENSION - PIG LAUNCHER/RECIEVER (EL+109800) PART 1 | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50008 | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10017-002 | STARBOARD SUBSEA MODULE - STRUCTURE - DECK EXTENSION - PIG LAUNCHER/RECIEVER (EL+109800) PART 2 | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50008 | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10017-003 | STARBOARD SUBSEA MODULE - STRUCTURE - DECK EXTENSION - PIG LAUNCHER/RECIEVER (EL+109800) PART 3 | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50008 | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10018-001 | STARBOARD SUBSEA STRUCTURE - DECK EXTENSION RELIEF VALVE (EL+114802) DROP OBJECT PROTECTION | STRUCTURAL | CS - STRUCTURAL | C03 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10018-002 | STARBOARD SUBSEA STRUCTURE - DECK EXTENSION RELIEF VALVE (EL+114802) DROP OBJECT PROTECTION | STRUCTURAL | CS - STRUCTURAL | C03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10018-003 | STARBOARD SUBSEA STRUCTURE - DECK EXTENSION RELIEF VALVE (EL+114802) DROP OBJECT PROTECTION | STRUCTURAL | CS - STRUCTURAL | C03 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10018-004 | STARBOARD SUBSEA STRUCTURE - DECK EXTENSION RELIEF VALVE (EL+114802) DROP OBJECT PROTECTION. | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU - RELEASE |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10019-001 | STARBOARD SUBSEA MODULE - STRUCTURE - INJECTION METHANOL SKID SUPPORT | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU - RELEASE |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10019-002 | STARBOARD SUBSEA MODULE STRUCTURE - METHANOL INJECTION SKID SUPPORT | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU - RELEASE |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10020-001 | PORTSIDE SUBSEA MODULE -STRUCTURE - DECK EXTENSION - MEZZANINE LEVEL - (CORROSION INHIBITOR SKID)STRUCTURE - DECK EXTENSION - MEZZANINE LEVEL - (CORROSION INHIBITOR SKID) | STRUCTURAL | CS - STRUCTURAL | C03 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10020-002 | PORTSIDE SUBSEA MODULE -STRUCTURE - DECK EXTENSION - MEZZANINE LEVEL - (CORROSION INHIBITOR SKID) | STRUCTURAL | CS - STRUCTURAL | C03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW | FAB-MABU-AVEON-2026-TN-50005 | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10020-003 | PORTSIDE SUBSEA MODULE -STRUCTURE - DECK EXTENSION - MEZZANINE LEVEL - (CORROSION INHIBITOR SKID) | STRUCTURAL | CS - STRUCTURAL | C03 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10020-004 | PORTSIDE SUBSEA MODULE -STRUCTURE - DECK EXTENSION - MEZZANINE LEVEL - (CORROSION INHIBITOR SKID) | STRUCTURAL | CS - STRUCTURAL | C03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW | FAB-MABU-AVEON-2026-TN-50005 | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10020-005 | PORTSIDE SUBSBEA MODULE - STRUCTURE-DECK EXTENSION MEZZANINE LEVEL - (CORROSION INHIBITOR SKID) | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50005 | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10021-001 | STARBOARD SUBSEA MODULE - STRUCTURE - MONORAIL/EQP FOUNDATION/CONTAINMENT BASIN TO PIG LAUNCHER/RECIEVER SHEET 1 | STRUCTURAL | CS - STRUCTURAL | C03 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  | AFC/AFU - RELEASE |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10021-002 | STARBOARD SUBSEA MODULE - STRUCTURE - MONORAIL/EQP FOUNDATION/CONTAINMENT BASIN TO PIG LAUNCHER/RECIEVER SHEET 2 | STRUCTURAL | CS - STRUCTURAL | C03 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  | AFC/AFU - RELEASE |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10021-003 | STARBOARD SUBSEA MODULE - STRUCTURE MONORAIL/EQP FOUNDATION/CONTAIMENT BASIN TO PIG LAUNCHER/RECIEVER | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10021-005 | STARBOARD SUBSEA MODULE - STRUCTURE MONORAIL/EQP FOUNDATION/CONTAIMENT BASIN TO PIG LAUNCHER/RECIEVER (LOOSE ITEMS) | STRUCTURAL | CS - STRUCTURAL | C01.1 | SIM | AFC 3 |  | NÃO SE APLICA | FOE |  |  | BNO / 02.5-FOE / FOE.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10021-006 | STARBOARD SUBSEA MODULE - STRUCTURE MONORAIL/EQP FOUNDATION/CONTAIMENT BASIN TO PIG LAUNCHER/RECIEVER (LOOSE ITEMS) | STRUCTURAL | CS - STRUCTURAL | C01.1 | SIM | AFC 3 |  | NÃO SE APLICA | FOE |  |  | BNO / 02.5-FOE / FOE.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10022-001 | MAIN RACK 3 - STRUCTURE - HPU DECK EXTENSION | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW | FAB-MABU-AVEON-2026-TN-50008 | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10022-002 | MAIN RACK 3 - STRUCTURE - HPU DECK EXTENSION | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10022-003 | MAIN RACK 3 - STRUCTURE - HPU DECK EXTENSION | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10022-004 | MAIN RACK 3 - STRUCTURE - HPU DECK EXTENSION | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10022-005 | MAIN RACK 3 - STRUCTURE - HPU DECK EXTENSION | STRUCTURAL | CS - STRUCTURAL | C03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10022-006 | MAIN RACK 3 - STRUCTURE HPU DECK EXTENSION (LOOSE ITEMS) | STRUCTURAL | CS - STRUCTURAL | C02.1 | SIM | AFC 3 |  | NÃO SE APLICA | FOE |  |  | BNO / 02.5-FOE / FOE.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10023-001 | WATER INJECTION TURBINE SKID - STRUCTURE - WALKWAYS AND STAIRS - PART 1 | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10023-002 | WATER INJECTION TURBINE SKID - STRUCTURE - WALKWAYS AND STAIRS - PART 2 | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10023-003 | WATER INJECTION TURBINE SKID - STRUCTURE - WALKWAYS AND STAIRS - PART 3 | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10023-004 | WATER INJECTION TURBINE SKID - STRUCTURE - WALKWAYS AND STAIRS - PART 4 | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10023-005 | WATER INJECTION TURBINE SKID - STRUCTURE - WALKWAYS AND STAIRS - PART 5 | STRUCTURAL | CS - STRUCTURAL | X | NAO |  | Revisao X cancelada | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10024-001 | WATER INJECTION TURBINE SKID - STRUCTURE - WALKWAYS AND STAIRS | STRUCTURAL | CS - STRUCTURAL | X | NAO |  | Revisao X cancelada | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10024-002 | WATER INJECTION TURBINE SKID - STRUCTURE - WALKWAYS AND STAIRS | STRUCTURAL | CS - STRUCTURAL | X | NAO |  | Revisao X cancelada | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10025-001 | WATER INJECTION TURBINE SKID - STRUCTURE - TRANSVERSAL SECTION (E 935000) | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | IFR |  | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10026-001 | MAIN RACK 2 - STRUCTURE - WI PUMP HANDLING AREA | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10026-002 | MAIN RACK 2 - STRUCTURE - WI PUMP HANDLING AREA | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10026-003 | MAIN RACK 2 - STRUCTURE WI PUMP HANDLING AREA | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10027-001 | STARBOARD SUBSEA MODULE - STRUCTURE - DECK EXTENSION (EL.+108.719) | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10027-002 | STARBOARD SUBSEA MODULE - STRUCTURE - DECK EXTENSION (EL.+108.719) | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10027-003 | STARBOARD SUBSEA MODULE - STRUCTURE - DECK EXTENSION (EL.+108.719) | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10028-001 | WATER INJECTION TURBINE LIFTING ARRANGEMENT | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10028-002 | WATER INJECTION TURBINE LIFTING ARRANGEMENT | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10037-001 | MAIN RACK 3 - HPU ROOF STRUCTURE DRAWING | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10037-002 | MAIN RACK 3 - HPU ROOF STRUCTURE DRAWING | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10038-001 | WATER INJECTION TURBINE SKID - TYPICAL DETAILS | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | IFR |  | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10038-002 | WATER INJECTION TURBINE SKID - TYPICAL DETAILS | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | IFR |  | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10038-003 | WATER INJECTION TURBINE SKID - TYPICAL DETAILS | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | IFR |  | ENGINEERING DISTRIBUTION |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10038-004 | WATER INJECTION TURBINE SKID - TYPICAL DETAILS | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10038-005 | WATER INJECTION TURBINE SKID - TYPICAL DETAILS | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10042-001 | STARBOARD SUBSEA MODULE LEVEL 2 BLOWDOWN VALVE ASSEMBLY PLATFORM AND DOP DRAWING | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10042-002 | STARBOARD SUBSEA MODULE LEVEL 2 BLOWDOWN VALVE ASSEMBLY PLATFORM AND DOP DRAWING | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10042-003 | STARBOARD SUBSEA MODULE LEVEL 2 BLOWDOWN VALVE ASSEMBLY PLATFORM AND DOP DRAWING | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10042-004 | STARBOARD SUBSEA MODULE LEVEL 2 BLOWDOWN VALVE ASSEMBLY PLATFORM AND DOP DRAWING | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10042-005 | STARBOARD SUBSEA MODULE LEVEL 2 BLOWDOWN VALVE ASSEMBLY PLATFORM AND DOP DRAWING | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10042-006 | STARBOARD SUBSEA MODULE LEVEL 2 BLOWDOWN VALVE ASSEMBLY PLATFORM AND DOP DRAWING | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10043-001 | STARBOARD SUBSEA MODULE - STRUCTURE - BLOWDOWN PIPING AREA ACCESS 1 | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10043-002 | STARBOARD SUBSEA MODULE - STRUCTURE - BLOWDOWN PIPING AREA ACCESS 1 | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10044-001 | STARBOARD SUBSEA MODULE - STRUCTURE - BLOWDOWN PIPING AREA ACCESS 2 | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-001 | STARBOARD SUBSEA MODULE - SPS-BN-SS-1236 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-002 | STARBOARD SUBSEA MODULE - SPS-BN-SS-1238 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-003 | STARBOARD SUBSEA MODULE - SPS-BN-SS-1239 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-004 | STARBOARD SUBSEA MODULE - SPS-BN-SS-1365 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-005 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0001 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-006 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0002 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-007 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0004 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-008 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0005 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-009 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0020 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | X | NAO |  | Revisao X cancelada | TRANSMITTAL |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-010 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0021 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-011 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0022 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | MABU UNDER REVIEW |  | TRANSMITTAL |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-012 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0022 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | MABU UNDER REVIEW |  | TRANSMITTAL |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-013 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0023 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-014 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0046 - SPECIAL PIPE SUPPORTS -PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-015 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0025 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-016 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0026 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | X | NAO |  | Revisao X cancelada | TRANSMITTAL |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-017 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0028 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-018 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0027 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-019 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0029 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-020 | STARBOARD SUBSEA MODULE - SPS-BN-MRS-0031 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-021 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0003 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | X | NAO |  | Revisao X cancelada | TRANSMITTAL |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-022 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0008 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-023 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0031 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | X | NAO |  | Revisao X cancelada | TRANSMITTAL |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-024 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0035 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-025 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0036 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-026 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0040 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-027 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0041 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-028 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0044 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-029 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0045 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-030 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0006 & 0007 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-031 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0006 & 0007 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-032 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0032 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | MABU UNDER REVIEW |  | TRANSMITTAL |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-033 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0032 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | MABU UNDER REVIEW |  | TRANSMITTAL |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-034 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0038 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-035 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0049 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-036 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0024 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-037 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0050 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-038 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0034 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | X | NAO |  | Revisao X cancelada | TRANSMITTAL |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-039 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0056 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-040 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0062 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-041 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0057 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-042 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0057 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-043 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0055 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-044 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0058 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-045 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0060 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-046 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0059 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-048 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0084 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | MABU UNDER REVIEW |  | TRANSMITTAL |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-049 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0106 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | X | NAO |  | Revisao X cancelada | TRANSMITTAL |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-050 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0083 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-051 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0064 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-052 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0065 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-053 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0042 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-054 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0042 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-055 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0047 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-056 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0069 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | MABU UNDER REVIEW |  | TRANSMITTAL |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-057 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0070 - SPECIAL PIPE SUPPORT PLAN SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-058 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0071 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-059 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0068 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-060 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0089 - TEMPORARY PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | X | NAO |  | Revisao X cancelada | TRANSMITTAL |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-061 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0073 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-062 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0075 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-063 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0078 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-064 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0079 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-065 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0080 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-066 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0077 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-067 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0081 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-068 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0085 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-069 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0072 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | MABU UNDER REVIEW |  | TRANSMITTAL |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-070 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0074 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-071 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0117 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-072 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0118 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-073 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0119 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-074 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0136 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-075 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0125 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-076 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0137 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-077 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0138 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-078 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0112 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-079 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0037 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-080 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0126 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-081 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0066 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-082 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0143 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-083 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0127 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-084 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0067 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-085 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0140 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-086 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0039 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-087 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0141 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-088 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0152 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-089 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0145 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-090 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0148 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | MABU UNDER REVIEW |  | TRANSMITTAL |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-091 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0142 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-092 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0076 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-093 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0115 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-094 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0158 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-095 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0159 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-096 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0160 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-097 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0155 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-098 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0121 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-099 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0120 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-100 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0116 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | MABU UNDER REVIEW |  | TRANSMITTAL |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-101 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0109 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-102 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0154 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-103 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0166 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-104 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0167 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-105 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0168 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-106 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0169 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-107 | STARBOARD SUBSEA MODULE SPS-BN-SS-0171 - SPECIAL PIPE SUPPORT PLAN_ | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-108 | STARBOARD SUBSEA MODULE SPS-BN-SS-0172 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10051-109 | STARBOARD SUBSEA MODULE SPS-BN-SS-0173 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS_ AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-001 | WATERFLOOD MODULE - SPS-BN-MR2-0058 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-002 | WATERFLOOD MODULE - SPS-BN-MR2-0059 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-003 | WATERFLOOD MODULE - SPS-BN-MR2-0060 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-004 | WATERFLOOD MODULE - SPS-BN-SS-0013 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-005 | WATERFLOOD MODULE - SPS-BN-SS-0014 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-006 | WATERFLOOD MODULE - SPS-BN-SS-0015 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-007 | WATERFLOOD MODULE - SPS-BN-SS-0019 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | MABU UNDER REVIEW |  | TRANSMITTAL |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-008 | WATERFLOOD MODULE - SPS-BN-MR2-0027 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-009 | WATERFLOOD MODULE - SPS-BN-MR2-0028 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-010 | WATERFLOOD MODULE - SPS-BN-MR2-0029 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-011 | WATERFLOOD MODULE - SPS-BN-MR2-0030 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-012 | WATERFLOOD MODULE - SPS-BN-MR2-0054 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-013 | WATERFLOOD MODULE - SPS-BN-MR2-0038 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-014 | WATERFLOOD MODULE - SPS-BN-MR2-0039 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-015 | WATERFLOOD MODULE - SPS-BN-MR2-0040 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-016 | WATERFLOOD MODULE - SPS-BN-MR2-0041 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-017 | WATERFLOOD MODULE - SPS-BN-MR2-0006 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-018 | WATERFLOOD MODULE - SPS-BN-MR2-0025 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAIL | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-019 | WATERFLOOD MODULE - SPS-BN-MR2-0044 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-020 | WATERFLOOD MODULE - SPS-BN-SS-0012 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-021 | WATERFLOOD MODULE - SPS-BN-MR2-0046 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-022 | WATERFLOOD MODULE - SPS-BN-MR2-0050 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-023 | WATERFLOOD MODULE - SPS-BN-MR2-0051 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-024 | WATERFLOOD MODULE - SPS-BN-MR2-0051 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-025 | WATERFLOOD MODULE - SPS-BN-MR2-0052 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-026 | WATERFLOOD MODULE - SPS-BN-MR2-0052 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-027 | WATERFLOOD MODULE - SPS-BN-MR2-0053 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-028 | WATERFLOOD MODULE - SPS-BN-MR2-0053 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-029 | WATERFLOOD MODULE - SPS-BN-MR2-0024 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-030 | WATERFLOOD MODULE - SPS-BN-MR2-0037 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-031 | WATERFLOOD MODULE - SPS-BN-MR2-0061 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | MABU UNDER REVIEW |  | TRANSMITTAL |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-032 | WATERFLOOD MODULE - SPS-BN-MR2-0061 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | MABU UNDER REVIEW |  | TRANSMITTAL |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-033 | WATERFLOOD MODULE - SPS-BN-SS-0030 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-034 | WATERFLOOD MODULE - SPS-BN-SS-0048 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-035 | WATERFLOOD MODULE - SPS-BN-SS-0048 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-036 | WATERFLOOD MODULE - SPS-BN-SS-0011 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-037 | WATERFLOOD MODULE - SPS-BN-SS-0011 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-038 | WATERFLOOD MODULE - SPS-BN-WF-0001 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-039 | WATERFLOOD MODULE - SPS-BN-WF-0002 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-040 | WATERFLOOD MODULE - SPS-BN-WF-0003 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-041 | WATERFLOOD MODULE - SPS-BN-WF-0004 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-042 | WATERFLOOD MODULE SPS-BN-WF-0004 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-043 | WATERFLOOD MODULE - SPS-BN-WF-0017 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-044 | WATERFLOOD MODULE SPS-BN-WF-0017-SPECIAL PIPE SUPPORT PLAN_ SECTIONS_ AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-045 | WATERFLOOD MODULE SPS-BN-WF-0017 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-046 | WATERFLOOD MODULE SPS-BN-WF-0065 SPECIAL PIPE SUPPORT PLAN_ SECTIONS_ AND DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-047 | WATERFLOOD MODULE SPS-BN-WF-0073 SPECIAL PIPE SUPPORT PLAN_ SECTIONS_ AND DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-104 | WATERFLOOD MODULE - SPS-BN-SS-0013 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-105 | WATERFLOOD MODULE - SPS-BN-SS-0014 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-106 | WATERFLOOD MODULE - SPS-BN-SS-0015 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10052-107 | WATERFLOOD MODULE - SPS-BN-SS-0019 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10053-001 | STRUCTURAL PIPE SUPPORTS - DRAWING INDEX | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10054-001 | STRUCTURAL CABLE TRAY SUPPORTS LAYOUTS | STRUCTURAL | CS - STRUCTURAL | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10055-001 | MAINRACK 2 - SPS-BN-MR2-0013 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10055-002 | MAINRACK 2 - SPS-BN-MR2-0014 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10055-003 | MAINRACK 2 - SPS-BN-MR2-0015 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10055-004 | MAINRACK 2 - SPS-BN-MR2-0016 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10055-005 | MAINRACK 2 - SPS-BN-MR2-0035 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10055-006 | MAINRACK 2 - SPS-BN-MR2-0043 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10055-007 | MAINRACK 2 - SPS-BN-MR2-0042 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10055-008 | MAINRACK 2 - SPS-BN-MR2-0033 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10055-009 | MAINRACK 2 - SPS-BN-MR2-0018 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10055-010 | MAINRACK 2 - SPS-BN-MR2-0018 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10055-011 | MAINRACK 2 - SPS-BN-MR2-0023 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10055-012 | MAINRACK 2 - SPS-BN-MR2-0003 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10055-014 | MAINRACK 2 - SPS-BN-MR2-0021 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10055-015 | MAINRACK 2 - SPS-BN-MR2-0012 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10055-016 | MAINRACK 2 - SPS-BN-MR2-0012 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 2 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10055-017 | MAINRACK 2 SPS-BN-MR2-0001 - SPECIAL PIPE SUPPORT PLAN, SECTIONS, AND DETAILS | STRUCTURAL | CS - STRUCTURAL | X | NAO |  | Revisao X cancelada | TRANSMITTAL |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10055-018 | MAINRACK 2 - SPS-BN-MR2-0036 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10055-019 | MAINRACK 2 - SPS-BN-MR2-0066 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10055-020 | MAINRACK 2 - SPS-BN-MR2-0067 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10055-021 | MAINRACK 2 - SPS-BN-MR2-0068 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10055-022 | MAINRACK 2 - SPS-BN-MR2-0077 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10055-023 | MAINRACK 2 - SPS-BN-MR2-0088 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | MABU UNDER REVIEW |  | TRANSMITTAL |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10055-024 | MAINRACK 2 - SPS-BN-MR2-0089 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10055-026 | MAINRACK 2 SPS-BN-MR2-0078 SPECIAL PIPE SUPPORT PLAN_ SECTIONS_ AND DETAILS | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10056-001 | STRUCTURAL CABLE TRAY SUPPORTS - DRAWING INDEX | STRUCTURAL | CS - STRUCTURAL | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10057-001 | CABLE LADDER LAYOUT SUPPORTS - MR2 LEVEL 1 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10058-001 | CABLE LADDER LAYOUT SUPPORTS - MR3 LEVEL 1 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10059-001 | CABLE LADDER LAYOUT SUPPORTS - MR3 LEVEL 4 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10060-001 | CABLE LADDER LAYOUT SUPPORTS - PS LEVEL 1 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10061-001 | CABLE LADDER LAYOUT SUPPORTS - MR2 LEVEL 4 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10062-001 | CABLE LADDER LAYOUT SUPPORTS - SS LEVEL 1 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10063-001 | CABLE LADDER LAYOUT SUPPORTS - MR6 LEVEL 1 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10064-001 | CABLE LADDER LAYOUT SUPPORTS - SS LEVEL 2 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10065-001 | CABLE LADDER LAYOUT SUPPORTS - MR4 LEVEL 1 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10066-001 | CABLE LADDER LAYOUT SUPPORTS - MR1 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10067-001 | CABLE LADDER LAYOUT SUPPORTS - MR5 LEVEL 1 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10068-001 | CABLE LADDER LAYOUT SUPPORTS - VR MODULE LEVEL 1 | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10069-001 | DEMOLITION_DRAWING_WATER_INJECTION_TURBINE_SKID_STRUCTURE_EXTENSI | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10070-001 | DEMOLITION DRAWING FOR PS MODULE CORROSION INHIBITOR SKID DECK EXTENSION | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10071-001 | DEMOLITION DRAWING FOR SS MODULE E LAUNCHER RECEIVER DECK EXTENSION | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10072-001 | DEMOLITION DRAWING FOR MR3 HPU DECK EXTENSION | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10073-001 | DEMOLITION DRAWING_MR2 WI PUMP HANDLING AREA | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10074-001 | DEMOLITION DRAWING FOR SS MODULE RELIEF VALVE DECK EXTENTION (EL+114802) | STRUCTURAL | CS - STRUCTURAL | C03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE | FAB-MABU-AVEON-2026-TN-50005 | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10075-001 | MAIN RACK 3 - STRUCTURE HPU ROOF STRUCTURE LIFTING ARRANGEMENT | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10076-001 | WATERFLOOD-MODULE-INLINE-STRAINER-ACCESS-PLATFORM | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10076-002 | WATERFLOOD MODULE-INLINE-STRAINER-ACCESS-PLATFORM | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10081-001 | DEMOLITION DRAWING FOR PIPE SUPPORTS STRINGERS 001 | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10084-001 | DEMOLITION STARBOARD SUBSEA MODULE DROPPED OBJECT PROTECTION | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10086-001 | STARBOARD SUBSEA LEVEL2 VALVE ACCESS PLATFORM | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU - RELEASE |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10086-002 | STARBOARD SUBSEA LEVEL2 VALVE ACCESS PLATFORM | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE | FAB-MABU-AVEON-2026-TN-50005 | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10086-003 | STARBOARD SUBSEA LEVEL2 VALVE ACCESS PLATFORM | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU - RELEASE |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10086-004 | STARBOARD SUBSEA LEVEL2 VALVE ACCESS PLATFORM | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE | FAB-MABU-AVEON-2026-TN-50005 | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10088-001 | MAIN RACK 2 MODULE - WATER INJECTION TURBINE SKID LEVEL1 ACCESS PLATFORM | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10088-002 | MAIN RACK 2 MODULE - WATER INJECTION TURBINE SKID LEVEL1 ACCESS PLATFORM | STRUCTURAL | CS - STRUCTURAL | X | NAO |  | Revisao X cancelada | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10088-003 | MAIN RACK 2 MODULE - WATER INJECTION TURBINE SKID LEVEL1 ACCESS PLATFORM | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10088-004 | MAIN RACK 2 MODULE - WATER INJECTION TURBINE SKID LEVEL1 ACCESS PLATFORM | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10088-005 | MAIN RACK 2 MODULE - WATER INJECTION TURBINE SKID LEVEL1 ACCESS PLATFORM | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10088-006 | MAIN RACK 2 MODULE - WATER INJECTION TURBINE SKID LEVEL1 ACCESS PLATFORM | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10088-007 | MAIN RACK 2 MODULE - WATER INJECTION TURBINE SKID LEVEL1 ACCESS PLATFORM | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10089-001 | STARBOARD SUBSEA MODULE STRUCTURE - HANDRAIL DEMOLITION FOR DECK EXTENSION (EL. +108682) | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE | FAB-MABU-AVEON-2026-TN-50005 | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10090-001 | DEMOLITION DRAWING FOR HANDRAIL OF BLOWDOWN PIPING AREA ACCESS 1 - STRUCTURES | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10091-001 | PORTSIDE SUBEA MODULE - STRUCTURE-DECK EXTENSION LEVEL 1 - CORROSION INHIBITOR SKID LIFTING ARRANGEMENT | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10092-001 | BLOWDOWN PIPING AREA ACCESS 1 - STRUCTURAL INTEGRITY REPLACEMENT DRAWING | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE | FAB-MABU-AVEON-2026-TN-50005 | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10093-001 | BLOWDOWN PIPING AREA ACCESS 2 - STRUCTURAL INTEGRITY REPLACEMENT DRAWING | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE | FAB-MABU-AVEON-2026-TN-50005 | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10094-001 | STRUCTURAL INTEGRITY DEMOLITION DRAWING FOR BLOWDOWN PIPING AREA ACCESS 1 | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE | FAB-MABU-AVEON-2026-TN-50005 | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10095-001 | STRUCTURAL INTEGRITY DEMOLITION DRAWING FOR BLOWDOWN PIPING AREA ACCESS 2 | STRUCTURAL | CS - STRUCTURAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE | FAB-MABU-AVEON-2026-TN-50005 | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10096-001 | WATER FLOOD MODULE-DECK EXTENSION (LEVEL 1) STRENGTHENING LAYOUT AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10097-001 | HANDRAIL DEMOLITION FOR LACT MODULE LEVEL 2 - LADDER LANDING FOR MR2 | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10098-001 | WATER FLOOD MODULE-DECK EXTENSION (LEVEL 1) DEMOLITION SCOPE | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10099-001 | WATER FLOOD MODULE-DECK EXTENSION (LEVEL 1) BEAM REPLACEMENT LAYOUT AND DETAILS | STRUCTURAL | CS - STRUCTURAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-4018-10100-001 | DEMOLITION DRAWING FOR METHANOL SKID SUPPORT | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-5721-10001 | STRUCTURAL DESIGN PREMISE | STRUCTURAL | CS - STRUCTURAL | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-6063-10001 | WEIGHT CONTROL PROCEDURE | STRUCTURAL | CS - STRUCTURAL | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-7180-10001 | TBE FOR STRUCTURAL MATERIALS | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-7303-10001 | STRUCTURAL MATERIAL TAKE-OFF (MTO) | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-7303-10003 | WATER INJECTION TURBINE SKID - STRUCTURE - MATERIAL LIST (MTO) | STRUCTURAL | CS - STRUCTURAL | A02 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-7303-10004 | PORT SUBSEA MODULE - STRUCTURE DECK EXTENSIONS - MATERIAL LIST (MTO)PORTSIDE SUBSEA MODULE - STRUCTURE DECK EXTENSIONS - MATERIAL LIST (MTO) | STRUCTURAL | CS - STRUCTURAL | A02 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-7303-10006 | STARBOARD SUBSEA MODULE - STRUCTURE DUE TO BONGA NORTH MODIFICATIONS - MATERIAL LIST (MTO) | STRUCTURAL | CS - STRUCTURAL | A03 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-7303-10007 | MAIN RACK 3 - STRUCTURE - HPU DECK EXTENSION - MATERIAL LIST (MTO) | STRUCTURAL | CS - STRUCTURAL | A03 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-7303-10008 | MAIN RACK 2 - STRUCTURE - WI PUMP HANDLING AREA - MATERIAL LIST (MTO) | STRUCTURAL | CS - STRUCTURAL | A02 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-7303-10012 | STRUCTURAL PIPE SUPPORTS MTO | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-7303-10013 | STRUCTURAL CABLE TRAY SUPPORTS MTO | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-7303-10014 | REQUISITION FOR STRUCTURAL MATERIALS | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-7303-10017 | WATERFLOOD MODULE - STRUCTURE DUE TO BONGA NORTH MODIFICATIONS - MATERIAL LIST (MTO) | STRUCTURAL | CS - STRUCTURAL | A02 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-7303-10019 | REQUISITION FOR STRUCTURAL MATERIALS - SPECIAL PIPE SUPPORT | STRUCTURAL | CS - STRUCTURAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-8102-10001 | BONGA HULL PEDESTALS FATIGUE ASSESSMENT REPORT FOR WF. PS. LACT & SS MODULES | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-8102-10010 | WATER INJECTION TURBINE STRUCTURE CALCULATION MEMORY | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-8180-10003 | WATER INJECTION TURBINE SKID - STRUCTURAL VERIFICATION REPORT - IN PLACE ANALYSIS | STRUCTURAL | CS - STRUCTURAL | A02 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-8180-10005 | MAIN RACK 3 - STRUCTURAL CALCULATION REPORT - BONGA NORTH MODIFICATIONS | STRUCTURAL | CS - STRUCTURAL | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-8180-10006 | PORT SUBSEA MODULE - STRUCTURAL CALCULATION REPORT - BONGA NORTH MODIFICATIONSPORTSIDE SUBSEA MODULE - STRUCTURAL CALCULATION REPORT - BONGA NORTH MODIFICATIONS | STRUCTURAL | CS - STRUCTURAL | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-8180-10011 | STARBOARD SUBSEA MODULE - STRUCTURAL CALCULATION REPORT - BONGA NORTH MODIFICATIONS | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-8180-10012 | STRUCTURAL PIPE SUPPORTS CALCULATIONS REPORT | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-8180-10013 | STRUCTURAL CABLE TRAY SUPPORTS CALCULATIONS REPORT | STRUCTURAL | CS - STRUCTURAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-8180-10014 | WI TURBINE & WF MODULE DECK EXTENSIONS MISCELLANEOUS CALCULATION REPORT | STRUCTURAL | CS - STRUCTURAL | A02 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-8180-10015 | BONGA HULL PEDESTAL FATIGUE ASSESSMENT | STRUCTURAL | CS - STRUCTURAL | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-8180-10016 | MAIN RACK 4 BOARDING VALVE PANEL STRUCTURAL SUPPORT CALCULATION REPORT | STRUCTURAL | CS - STRUCTURAL | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.05-CS-STRUCTURAL
BNO-MABU-300-CS-8502-10001 | TQR-DAE-CS001 | STRUCTURAL | CS - STRUCTURAL | A01 | NAO |  | Numero do documento excluido por regra | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 02-DED / 02.001-DAE_TQR
BNO-MABU-300-CS-8502-10002 | AS-BUILT DRAWINGS FOR MR2, MR3, LACT, WATERFLOOD, PORT SUBSEA, STARBOARD SUBSEA MODULE | STRUCTURAL | CS - STRUCTURAL | A01 | NAO |  | Numero do documento excluido por regra | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 02-DED / 02.001-DAE_TQR
BNO-MABU-300-CS-8502-10003 | REQUEST FOR CENTER OF GRAVITY (COG) OF SSCB. | STRUCTURAL | CS - STRUCTURAL | A01 | NAO |  | Numero do documento excluido por regra | ISSUED |  |  |  | BNO / 02-DED / 02.001-DAE_TQR
BNO-MABU-300-CS-8502-10004 | RFI FOR VENDOR DATA OF WI TURBINE SKID | STRUCTURAL | CS - STRUCTURAL | A01 | NAO |  | Numero do documento excluido por regra | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 02-DED / 02.001-DAE_TQR
BNO-MABU-300-CS-8502-10006 | INFORMATION REQUIRED FOR HPU DOP DESIGN AND DETAILS | STRUCTURAL | CS - STRUCTURAL | A01 | NAO |  | Numero do documento excluido por regra | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 02-DED / 02.001-DAE_TQR
BNO-MABU-300-EA-0980-10001 | CONTROL SYSTEM BLOCK DIAGRAM (SHOWING INTERFACE BETWEEN ELECTRICAL AND INSTRUMENTATION & AUTOMATIONSYSTEMS.) | ELECTRICAL | EA - ELECTRICAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-0980-10002-001 | BLOCK DIAGRAM FOR HV MCC | ELECTRICAL | EA - ELECTRICAL | C04 | SIM | MABU UNDER REVIEW |  | TRANSMITTAL |  |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-0980-10003-001 | COMMISSIONING PLAN INPUT | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-0980-10004-001 | BLOCK DIAGRAM FOR SUBSEA SYSTEM PACKAGES. CHEMICAL INJECTION AND EVERY OTHER PACKAGE | ELECTRICAL | EA - ELECTRICAL | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-0980-10005-001 | BLOCK DIAGRAM FOR PACKAGES | ELECTRICAL | EA - ELECTRICAL | C03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-0980-10006-001 | BLOCK DIAGRAM FOR ALL THE UPS | ELECTRICAL | EA - ELECTRICAL | C03 | SIM | MABU UNDER REVIEW |  | TRANSMITTAL |  |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-1380-10001 | CALCULATION REPORT - LIGHTINING PROTECTION SYSTEM (LPS) | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-1380-10002 | CALCULATION REPORT - ELECTRICAL LOAD BALANCE SB-7401A/B-E-01 | ELECTRICAL | EA - ELECTRICAL | A05 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-1380-10003 | CALCULATION REPORT - LIGHTING SYSTEM | ELECTRICAL | EA - ELECTRICAL | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-2105-10001 | ELECTRICAL DATASHEET FOR MOTORS | ELECTRICAL | EA - ELECTRICAL | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-2105-10002 | ELECTRICAL DATASHEET - FLOODLIGHT LUMINARIES | ELECTRICAL | EA - ELECTRICAL | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-2105-10003 | ELECTRICAL DATASHEET - NORMAL & EMERGENCY ESCAPE LED LUMINARIES | ELECTRICAL | EA - ELECTRICAL | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-2105-10004 | ELECTRICAL DATASHEET - SOCKET OUTLETS & PLUGS | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-2105-10005 | ELECTRICAL DATASHEET - REMOTE CONTROL STATIONS | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-2105-10006 | ELECTRICAL DATASHEET - ISOLATORS | ELECTRICAL | EA - ELECTRICAL | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-2105-10007 | ELECTRICAL DATASHEET - ELECTRICA JUNCTION BOXES | ELECTRICAL | EA - ELECTRICAL | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-2335-10001-001 | ELECTRICAL JUNCTION BOX ( EJB) TO SPCU INTERFACE HOOKUP DRAWINGS | ELECTRICAL | EA - ELECTRICAL | C03 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-2341-10001-001 | INTERCONNECTION WIRING DIAGRAMS | ELECTRICAL | EA - ELECTRICAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-2341-10002-001 | HULL INTERFACE DIAGRAM UPDATE (BON-AME-3GN-E-25090-001) | ELECTRICAL | EA - ELECTRICAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-2384-10001-001 | BN KEY AC ONE LINE DIAG. SHT. 1 OF 2 | ELECTRICAL | EA - ELECTRICAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IDC - INTERNAL COMMENTS |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-2384-10001-002 | BN KEY AC ONE LINE DIAG. SHT. 2 OF 2 | ELECTRICAL | EA - ELECTRICAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IDC - INTERNAL COMMENTS |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-2384-10002-001 | BN KEY ONE LINE DIAGRAM | ELECTRICAL | EA - ELECTRICAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IDC - INTERNAL COMMENTS |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-2384-10003-001 | BN HV MCC-C (MCC-7355-D-01) ONE LINE DIAGRAM | ELECTRICAL | EA - ELECTRICAL | C03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-2384-10004-001 | BN LV (SB-7446) ONE LINE DIAGRAM | ELECTRICAL | EA - ELECTRICAL | C05 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-2384-10005-001 | BN EMERGENCY MCC (MCC-7457-E-01) SINGLE LINE DIAGRAM | ELECTRICAL | EA - ELECTRICAL | C05 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-2384-10006-001 | BN LV ESSENTIAL MCC (MCC-7456-E-01) SINGLE LINE DIAGRAM SHEET 2 OF 2 | ELECTRICAL | EA - ELECTRICAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-2384-10007-001 | KEY AC UPS SINGLE LINE DIAGRAM | ELECTRICAL | EA - ELECTRICAL | C03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-2384-10008-001 | KEY DC UPS SINGLE LINE DIAGRAM | ELECTRICAL | EA - ELECTRICAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-2398-10001-001 | INSTALLATION DETAILS: HEAT TRACING | ELECTRICAL | EA - ELECTRICAL | A01 | SIM | MABU UNDER REVIEW |  | ENGINEERING COMMENTS |  |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-2580-10001 | PROTECTION AND METERING DIAGRAMS FOR ALL SWITCHBOARDS | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-2901-10001 | AC AND DC UPS SIZING CALCULATIONS | ELECTRICAL | EA - ELECTRICAL | A03 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-2901-10002 | CABLE SELECTION AND SIZING CALCULATION | ELECTRICAL | EA - ELECTRICAL | A05 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-3323-10001 | TECHNICAL BID EVALUATION REPORT FOR LIGHTING LUMINARIES | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-3323-10002 | TECHNICAL BID EVALUATION REPORT FOR POWER CABLE | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-3323-10003 | TECHNICAL BID EVALUATION REPORT FOR SOCKET OUTLET & PLUGS | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-3323-10004 | TECHNICAL BID EVALUATION FOR EXISTING DRAWER (FEEDER) - POWELL | ELECTRICAL | EA - ELECTRICAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 4 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-3323-10005 | TECHNICAL BID EVALUATION REPORT FOR ISOLATORS | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-3323-10006 | TECHNICAL BID EVALUATION REPORT FOR ELECTRICAL JUNCTION BOXES | ELECTRICAL | EA - ELECTRICAL | R01 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-3323-10007 | TECHNICAL BID EVALUATION REPORT FOR CABLE RACKS_ GLANDS & FITTINGS | ELECTRICAL | EA - ELECTRICAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-3323-10008 | TECHNICAL BID EVALUATION REPORT FOR TERMINATION KIT AND TERMINALS | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-3323-10009 | TECHNICAL BID EVALUATION REPORT FOR MCT | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-3323-10010 | TECHNICAL BID EVALUATION REPORT FOR EARTHING MATERIALS | ELECTRICAL | EA - ELECTRICAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 2 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-3323-10011 | TECHNICAL BID EVALUATION REPORT FOR BLANKING PLUGS AND REDUCING BUSHING | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-3323-10012 | TECHNICAL BID EVALUATION REPORT FOR CABLE CLEATS AND CABLE TIES | ELECTRICAL | EA - ELECTRICAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-3323-10013 | TECHNICAL BID EVALUATION REPORT FOR CABLE LUGS | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-3323-10014 | TECHNICAL BID EVALUATION REPORT FOR REMOTE CONTROL STATIONS | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-3323-10015 | TECHNICAL BID EVALUATION REPORT FOR ELECTRICAL HEAT TRACING | ELECTRICAL | EA - ELECTRICAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4005-10008-001 | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - MR2 LEVEL 4 | ELECTRICAL | EA - ELECTRICAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4005-10009-001 | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - MR3 LEVEL 1 | ELECTRICAL | EA - ELECTRICAL | C03 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4005-10010-001 | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - MR5 LEVEL 1 | ELECTRICAL | EA - ELECTRICAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4005-10011-001 | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - MR6 LEVEL 1 | ELECTRICAL | EA - ELECTRICAL | C03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4005-10012-001 | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - SS LEVEL 1 | ELECTRICAL | EA - ELECTRICAL | C02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4005-10013-001 | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - SS LEVEL 2 | ELECTRICAL | EA - ELECTRICAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4005-10014-001 | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - VR MODULE LEVEL 1 | ELECTRICAL | EA - ELECTRICAL | C03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4005-10015-001 | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - MR1 | ELECTRICAL | EA - ELECTRICAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4005-10016-001 | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - MR2 LEVEL 1 | ELECTRICAL | EA - ELECTRICAL | C03 | SIM | IFR |  | TRANSMITTAL |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4005-10017-001 | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - PS LEVEL 1 | ELECTRICAL | EA - ELECTRICAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4005-10018-001 | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - MR3 LEVEL 4 | ELECTRICAL | EA - ELECTRICAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4005-10019-001 | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - MR4 LEVEL 1 | ELECTRICAL | EA - ELECTRICAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4005-10020-001 | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - CC ELECTRICAL ROOM | ELECTRICAL | EA - ELECTRICAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4005-10023-001 | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT-WATERFLOOD | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4005-10024-001 | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - PW ELECTRICAL ROOM | ELECTRICAL | EA - ELECTRICAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4005-10025-001 | CABLE LADDER LAYOUT SUPPORTS - MR2 LEVEL 1 | ELECTRICAL | EA - ELECTRICAL | C02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4005-10026-001 | CABLE LADDER LAYOUT SUPPORTS - MR3 LEVEL 1 | ELECTRICAL | EA - ELECTRICAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4005-10027-001 | CABLE LADDER LAYOUT SUPPORTS - MR3 LEVEL 4 | ELECTRICAL | EA - ELECTRICAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4005-10028-001 | CABLE LADDER LAYOUT SUPPORTS - PS LEVEL 1 | ELECTRICAL | EA - ELECTRICAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4005-10029-001 | CABLE LADDER LAYOUT SUPPORTS - MR2 LEVEL 4 | ELECTRICAL | EA - ELECTRICAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4005-10030-001 | CABLE LADDER LAYOUT SUPPORTS - SS LEVEL 1 | ELECTRICAL | EA - ELECTRICAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4005-10031-001 | CABLE LADDER LAYOUT SUPPORTS - WATERFLOOD | ELECTRICAL | EA - ELECTRICAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4005-10032-001 | CABLE LADDER LAYOUT SUPPORTS - MR 1 | ELECTRICAL | EA - ELECTRICAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4005-10033-001 | CABLE LADDER LAYOUT SUPPORTS - MR 4 | ELECTRICAL | EA - ELECTRICAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4005-10034-001 | CABLE LADDER LAYOUT SUPPORTS - PW AREA | ELECTRICAL | EA - ELECTRICAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4005-10035-001 | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - MR4 LEVEL 4. | ELECTRICAL | EA - ELECTRICAL | C02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4005-10036-001 | CABLE LADDER LAYOUT SUPPORTS - HULL | ELECTRICAL | EA - ELECTRICAL | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4018-10001-001 | BONGA MAIN HV SWITCHBOARD SB-7340-D-01 GENERAL ARRANGEMENT UPDATE | ELECTRICAL | EA - ELECTRICAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4018-10002-001 | BONGA MAIN COMPRESSION MODULE SWITCHBOARD SB-7451 GENERAL ARRANGENT UPDATE | ELECTRICAL | EA - ELECTRICAL | A02 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4024-10001-001 | INSTALLATION DRAWINGS - GROUNDING DISTRIBUTION | ELECTRICAL | EA - ELECTRICAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4024-10002-001 | INSTALLATION DRAWINGS - POWER DISTRIBUTION | ELECTRICAL | EA - ELECTRICAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4024-10003-001 | INSTALLATION DRAWINGS - LIGHTING DISTRIBUTION | ELECTRICAL | EA - ELECTRICAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4024-10006-001 | LIGHTING DISTRIBUTION PLAN - MR LEVELS | ELECTRICAL | EA - ELECTRICAL | C02 | SIM | MABU UNDER REVIEW |  | TRANSMITTAL |  |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4024-10008-001 | LIGHTING DISTRIBUTION PLAN - PS LEVEL 1 | ELECTRICAL | EA - ELECTRICAL | C03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4024-10009-001 | LIGHTING DISTRIBUTION PLAN - SSCB EXTERNAL | ELECTRICAL | EA - ELECTRICAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4024-10010-001 | BONGA MAIN ESSENTIAL SWITCHBOARD - SB-7401A/B-E-01 GENERAL ARRANGEMENT DRAWING UPDATE | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4024-10016-001 | GROUNDING DISTRIBUTION PLAN - MR LEVELS | ELECTRICAL | EA - ELECTRICAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4024-10017-001 | GROUNDING DISTRIBUTION PLAN - PS LEVEL 1 | ELECTRICAL | EA - ELECTRICAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4024-10018-001 | LIGHTING DISTRIBUTION PLAN FOR MR3 LEVEL 4_ HPU AREA | ELECTRICAL | EA - ELECTRICAL | C03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4024-10019-001 | LIGHTING & SMALL POWER LAYOUT STARBOARD SUBSEA MODULE | ELECTRICAL | EA - ELECTRICAL | C03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4024-10020-001 | GROUND DISTRIBUTION PLAN SSCB EXTERNAL. | ELECTRICAL | EA - ELECTRICAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4024-10021-001 | LIGHTING DISTRIBUTION PLAN MR4 LEVEL 4 BVP AREA | ELECTRICAL | EA - ELECTRICAL | C01 | SIM | MABU UNDER REVIEW |  | ENGINEERING COMMENTS |  |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4024-10022-001 | GROUNDING DISTRIBUTION PLAN MR4 LEVEL 4 BVP AREA | ELECTRICAL | EA - ELECTRICAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4024-10023-001 | GROUNDING DISTRIBUTION PLAN - MR3 LEVEL 4_ HPU AREA | ELECTRICAL | EA - ELECTRICAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4024-10024-001 | GROUNDING DISTRIBUTION PLAN METHANOL SKID AREA | ELECTRICAL | EA - ELECTRICAL | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4025-10001-001 | UPDATE OF EXISTING LIGHTING AND SMALL POWER LAYOUT | ELECTRICAL | EA - ELECTRICAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4180-10001-001 | CABLE TERMINATION DETAILS | ELECTRICAL | EA - ELECTRICAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4180-10002-001 | LV CABLE ROUTING LAYOUT HULL TO SSCB | ELECTRICAL | EA - ELECTRICAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4180-10003-001 | POWER LAYOUT (FOR OUTDOOR SOCKET) | ELECTRICAL | EA - ELECTRICAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4180-10004-001 | ELECTRICAL SYSTEM REPORT AUTOMATION ARCHITECTURE | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4306-10001 | ELECTRICAL MTO | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4306-10002 | BULK MATERIALS MTO | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4306-10003 | CABLE LADDER RACK ISOMETRICS AND MTO FOR ALL NEW BONGA NORTH CABLE TRAYS | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4306-10003-001 | CABLE LADDER RACK ISOMETRICS AND MTO ALL NEW BONGA NORTH CABLE TRAYS | ELECTRICAL | EA - ELECTRICAL | R02 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4306-10004 | SPARE PART LIST | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4308-10001 | ELECTRICAL CABLE LIST | ELECTRICAL | EA - ELECTRICAL | A06 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4308-10002 | LIST OF RECOMMENDED VENDORS (FOR COMPANY REVIEW) | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4308-10003 | CABLE CUTTING PLAN | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4329-10001 | ELECTRICAL LOAD LIST | ELECTRICAL | EA - ELECTRICAL | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4380-10004 | CABLE TRAY UTILISATION SCHEDULE | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4380-10006 | PENETRATION SCHEDULE | ELECTRICAL | EA - ELECTRICAL | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4380-10007 | PROTECTION SCHEME & RELAY SETTING SCHEDULES | ELECTRICAL | EA - ELECTRICAL | A01 | SIM | MABU UNDER REVIEW |  | ENGINEERING COMMENTS |  |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4380-10008 | DISTRIBUTION BOARD SCHEDULE FOR ALL THE DB | ELECTRICAL | EA - ELECTRICAL | C02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4380-10009 | LV SWITCHGEAR SCHEDULE UPDATE FOR BM | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4380-10010 | HV SWITCHGEAR SCHEDULE UPDATE FOR BM | ELECTRICAL | EA - ELECTRICAL | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4380-10011 | CABLE TRANSIT AND PENETRATION SCHEDULE | ELECTRICAL | EA - ELECTRICAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4380-10012 | CONTROL. ALARM AND MONITORING TABLE | ELECTRICAL | EA - ELECTRICAL | A04 | SIM | MABU UNDER REVIEW |  | TRANSMITTAL |  |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4380-10013 | EX REGISTER | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4380-10014 | DISTRIBUTION BOARD SCHEDULE FOR LIGHTING - NORMAL BOARD DB-7642-N-01 | ELECTRICAL | EA - ELECTRICAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-4380-10015 | DISTRIBUTION BOARD SCHEDULE FOR LIGHTING & SMALL POWER- EMERGENCY BOARD DB-7652-N-01 | ELECTRICAL | EA - ELECTRICAL | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-5680-10001 | ELECTRICAL SYSTEM MEMORANDUM | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-6067-10001 | GROUNDING AND EQUIPOTENTIAL BONDING PROCEDURE | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-6067-10002 | CAD WELDING PROCEDURE | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-7180-10003 | EQUIPMENT VENDOR DOSSIERS (INCLUDING FAT REPORTS) | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-7180-10005 | BN PROJECT SAFOP CLOSE OUT REPORT | ELECTRICAL | EA - ELECTRICAL | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-7180-10006 | ARC-FLASH HAZARD REPORT | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-7180-10009 | ESSENTIAL GENERATOR ADEQUACY CHECK REPORT | ELECTRICAL | EA - ELECTRICAL | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-7180-10011 | FAULT RECOVERY/SYSTEM DYNAMIC STABILITY UNDER 3-PHASE FAULT CONDITIONS REPORT | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-7180-10012 | ELECTRICAL SITE VISIT REPORT | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-7303-10001 | MATERIAL REQUISITION FOR POWER CABLE | ELECTRICAL | EA - ELECTRICAL | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-7303-10002 | REQUISITION FOR CABLES GLANDS | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-7303-10003 | REQUISITION FOR ELECTRICAL BULK MATERIALS | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-7303-10004 | REQUISITION FOR CABLE RACK AND FITTINGS | ELECTRICAL | EA - ELECTRICAL | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-7303-10005 | MATERIAL REQUISITION FOR ELECTRICAL HEAT TRACING | ELECTRICAL | EA - ELECTRICAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 2 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-7770-10001 | SPECIFICATION FOR ELECTRICAL EQUIPMENT SIZING REVALIDATION | ELECTRICAL | EA - ELECTRICAL | A06 | SIM | IFR |  | TRANSMITTAL |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-7771-10001 | SPECIFICATION FOR POWER DISTRIBUTION AND SYSTEM OPERATION PHILOSOPHY | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-7771-10002 | SPECIFICATION FOR ELECTRICAL POWER CABLE | ELECTRICAL | EA - ELECTRICAL | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-7771-10003 | SPECIFICATION FOR ELECTRIC MOTOR | ELECTRICAL | EA - ELECTRICAL | A04 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-7771-10004 | SPECIFICATION FOR ELECTRICAL EQUIPMENT-PACKAGED | ELECTRICAL | EA - ELECTRICAL | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-7771-10005 | SPECIFICATION FOR ELECTRICAL DESIGN PHILOSOPHY | ELECTRICAL | EA - ELECTRICAL | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-7771-10006 | CONSTRUCTION AND INSTALLATION SPECIFICATION | ELECTRICAL | EA - ELECTRICAL | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-7771-10007 | SPECIFICATION FOR LV SWITCHGEAR | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-7771-10008 | SPECIFICATION FOR HV SWITCHGEAR | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-7771-10009 | SPECIFICATION FOR AC UPS | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-7771-10010 | SPECIFICATION FOR DC UPS | ELECTRICAL | EA - ELECTRICAL | A03 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-7771-10011 | SPECIFICATION FOR TRANSFORMER | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-7771-10012 | SPECIFICATION FOR LV DISTRIBUTION BOARD PANELS | ELECTRICAL | EA - ELECTRICAL | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-8251-10001 | SAFOP TERMS OF REFERENCE | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-8260-10001 | ELECTRICAL STUDIES REPORT - LOAD FLOW | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-8260-10002 | ELECTRICAL STUDIES REPORT - HARMONIC DISTORTION | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-8260-10003 | ELECTRICAL STUDIES REPORT - SHORT-CIRCUIT CURRENTS | ELECTRICAL | EA - ELECTRICAL | A03 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-8260-10004 | ELECTRICAL STUDIES REPORT - PROTECTION COORDINATION | ELECTRICAL | EA - ELECTRICAL | A03 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-8260-10006 | ELECTRICAL STUDIES REPORT - ARC FLASH | ELECTRICAL | EA - ELECTRICAL | A02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.06-EA-ELECTRICAL
BNO-MABU-300-EA-8502-10001 | DED LIGHTNING PROTECTION CALCULATIONS | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Numero do documento excluido por regra | ISSUED |  |  |  | BNO / 02-DED / 02.001-DAE_TQR
BNO-MABU-300-EA-8502-10002 | DED UPS UTILITY CONSUMPTION LIST | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Numero do documento excluido por regra | ISSUED |  |  |  | BNO / 02-DED / 02.001-DAE_TQR
BNO-MABU-300-EA-8502-10003 | DED LIGHTNING PROTECTION CALCULATIONS | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Numero do documento excluido por regra | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 02-DED / 02.001-DAE_TQR
BNO-MABU-300-EA-8502-10004 | DED LIGHTING DISTRIBUTION PLAN PS LEVEL 1 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Numero do documento excluido por regra | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 02-DED / 02.001-DAE_TQR
BNO-MABU-300-EA-8502-10015 | DED REQUEST FOR SERIAL NUMBERS | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Numero do documento excluido por regra | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.001-DAE_TQR
BNO-MABU-300-HS-7411-10001 | DROPPED OBJECT STUDY REPORT | TECHNICAL SAFETY | HS - SAFETY | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.11-HS-SAFETY
BNO-MABU-300-HS-7411-10002 | BOWTIE REVIEW TERMS OF REFERENCE | TECHNICAL SAFETY | HS - SAFETY | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 02-DED / 02.11-HS-SAFETY
BNO-MABU-300-HS-7411-10003 | BOWTIE REVIEW REPORT | TECHNICAL SAFETY | HS - SAFETY | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.11-HS-SAFETY
BNO-MABU-300-HX-0580-10001 | NOISE STUDY REPORT | TECHNICAL SAFETY | HX - HSE | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-0704-10002 | FIRE AND EXPLOSION ANALYSIS (FEA) REPORT | TECHNICAL SAFETY | HX - HSE | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-0709-10003 | QUANTITATIVE RISK ANALYSIS (QRA) REPORT - UPDATE DETAIL PHASE | TECHNICAL SAFETY | HX - HSE | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-0780-10005 | SIMOPS REPORT | TECHNICAL SAFETY | HX - HSE | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-1212-10001 | FIRE WATER DEMAND VERIFICATION - CALCULATION NOTES | TECHNICAL SAFETY | HX - HSE | A05 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-1222-10001 | DELUGE SYSTEM HYDRAULIC CALCULATION NOTES | TECHNICAL SAFETY | HX - HSE | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-1415-10001 | HAZARDOUS AREA CLASSIFICATION (HAC) PROCEDURE | TECHNICAL SAFETY | HX - HSE | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-1601-10005 | HAZARDOUS AREA CLASSIFICATION SCHEDULE | TECHNICAL SAFETY | HX - HSE | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-2318-10001 | EMERGENCY EVACUATION RESCUE ANALYSIS (EERA) REPORT | TECHNICAL SAFETY | HX - HSE | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-2334-10003-001 | HAZARDOUS AREA CLASSIFICATION UPPER DECK - AFT | TECHNICAL SAFETY | HX - HSE | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-2334-10004-001 | HAZARDOUS AREA CLASSIFICATION UPPER DECK - MID AFT | TECHNICAL SAFETY | HX - HSE | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-2334-10004-002 | HAZARDOUS AREA CLASSIFICATION UPPER DECK - MID AFT | TECHNICAL SAFETY | HX - HSE | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-2334-10006-001 | HAZARDOUS AREA CLASSIFICATION MAIN DECK - MID AFT | TECHNICAL SAFETY | HX - HSE | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-2334-10006-002 | HAZARDOUS AREA CLASSIFICATION MAIN DECK - MID AFT | TECHNICAL SAFETY | HX - HSE | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-3323-10001 | TBE FOR SAFETY ITEMS | TECHNICAL SAFETY | HX - HSE | A01 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-4180-10006-001 | ESCAPE ROUTE & SAFETY EQUIPMENT LAYOUT - CARGO DECK (EL.100000) AFT | TECHNICAL SAFETY | HX - HSE | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-4180-10008-001 | ESCAPE ROUTE & SAFETY EQUIPMENT LAYOUT- MAIN DECK (EL.105182) AFT | TECHNICAL SAFETY | HX - HSE | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-4180-10010-001 | ESCAPE ROUTE & SAFETY EQUIPMENT LAYOUT- UPPER DECK (EL. 112802) AFT | TECHNICAL SAFETY | HX - HSE | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-4301-10001 | ASSUMPTION REGISTER | TECHNICAL SAFETY | HX - HSE | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-5798-10001 | HAZARD EVALUATION AND RISK MANAGEMENT PLAN | TECHNICAL SAFETY | HX - HSE | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-5880-10001 | HEALTH SAFETY SECURITY ENVIRONMENT PLAN | TECHNICAL SAFETY | HX - HSE | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-5880-10002 | HUMAN FACTORS ENGINEERING INTEGRATION PLAN | TECHNICAL SAFETY | HX - HSE | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-6019-10001 | EMERGENCY SYSTEMS SURVIVABILITY ASSESSMENT | TECHNICAL SAFETY | HX - HSE | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-6180-10003 | PACKAGED EQUIPMENT REVIEW- WATER INJECTION SYSTEM | TECHNICAL SAFETY | HX - HSE | R01 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-6180-10004 | PACKAGED EQUIPMENT REVIEW- METHANOL INJECTION SYSTEM | TECHNICAL SAFETY | HX - HSE | R01 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-6613-10002 | ACTION TRACKING REGISTER | TECHNICAL SAFETY | HX - HSE | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-6873-10001 | PACKAGED EQUIPMENT REVIEW- CORROSION INHIBITION SYSTEM | TECHNICAL SAFETY | HX - HSE | R01 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-6873-10003 | HAZID REPORT (DED) | TECHNICAL SAFETY | HX - HSE | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-6873-10004 | HAZID CLOSE OUT REPORT | TECHNICAL SAFETY | HX - HSE | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-6873-10005 | CONSTRUCTION HAZID REPORT | TECHNICAL SAFETY | HX - HSE | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-6873-10006 | CONSTRUCTION HAZID CLOSE-OUT REPORT | TECHNICAL SAFETY | HX - HSE | A02 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-6874-10001 | GAS DISPERSION MODELLING STUDY REPORT | TECHNICAL SAFETY | HX - HSE | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-6875-10001 | SAFOP CLOSE-OUT REPORT | TECHNICAL SAFETY | HX - HSE | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-6875-10005 | INTEGRATED HAZOP CLOSEOUT REPORT - UPDATE | TECHNICAL SAFETY | HX - HSE | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-6875-10006 | HAZOP - TERMS OF REFERENCE | TECHNICAL SAFETY | HX - HSE | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-6875-10007 | HAZOP REPORT (DED) | TECHNICAL SAFETY | HX - HSE | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-6875-10008 | HAZOP CLOSEOUT REPORT (DED) | TECHNICAL SAFETY | HX - HSE | A02 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-6881-10001 | SPECIFICATIONS FOR SAFETY SYSTEM DESCRIPTION | TECHNICAL SAFETY | HX - HSE | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-6881-10002 | DESIGN SAFETY CASE REPORT | TECHNICAL SAFETY | HX - HSE | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-6881-10003 | HFE 60% 3D MODEL REVIEW AND VALVE CRITICALITY ASSESSMENT REPORT | TECHNICAL SAFETY | HX - HSE | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-7180-10001 | HUMAN FACTORS ENGINEERING REVIEW OF ALARM RATIONALISATION REPORT | TECHNICAL SAFETY | HX - HSE | A01 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-7303-10001 | PASSIVE FIRE PROTECTION LIST | TECHNICAL SAFETY | HX - HSE | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-7303-10002 | MATERIAL REQUISITION FOR SAFETY ITEMS | TECHNICAL SAFETY | HX - HSE | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-7303-10003 | BILL OF MATERIALS (FIRE & SAFETY) | TECHNICAL SAFETY | HX - HSE | A02 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-7739-10001 | SAFETY CONCEPT & PHILOSOPHIES | TECHNICAL SAFETY | HX - HSE | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-7739-10002 | SAFETY SIGNS LAYOUT | TECHNICAL SAFETY | HX - HSE | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-7739-10002-001 | SAFETY SIGNS LAYOUT | TECHNICAL SAFETY | HX - HSE | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-7739-10003 | SAFETY EQUIPMENT SPECIFICATION | TECHNICAL SAFETY | HX - HSE | A05 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-7739-10004 | SAFETY EQUIPMENT MTO | TECHNICAL SAFETY | HX - HSE | A02 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-7739-10005 | SAFETY EQUIPMENT DATASHEET | TECHNICAL SAFETY | HX - HSE | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-7753-10003 | HAZID - TERMS OF REFERENCE | TECHNICAL SAFETY | HX - HSE | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-7753-10005 | SIMOPS TERMS OF REFERENCE | TECHNICAL SAFETY | HX - HSE | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-7753-10006 | DESIGN SAFETY CASE TERMS OF REFERENCE | TECHNICAL SAFETY | HX - HSE | A02 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-7753-10007 | CONSTRUCTION HAZID TERMS OF REFERENCE | TECHNICAL SAFETY | HS - SAFETY | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-7876-10001 | SAFETY EQUIPMENT LIST | TECHNICAL SAFETY | HX - HSE | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-7880-10002 | SPECIFICATIONS FOR SUB-CONTRACTED SAFETY STUDIES REQUIREMENTS | TECHNICAL SAFETY | HX - HSE | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-7880-10003 | SPECIFICATIONS FOR SAFETY SHOWER SPECIFICATION | TECHNICAL SAFETY | HX - HSE | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-7880-10004 | SPECIFICATIONS FOR PASSIVE FIRE PROTECTION (PFP) FLEXIBLE JACKET | TECHNICAL SAFETY | HX - HSE | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.12-HX-HSE
BNO-MABU-300-HX-8502-10017 | REQUEST FOR APPROVED VENDOR LIST FOR SAFETY EQUIPMENT | TECHNICAL SAFETY | HX - HSE | A01 | NAO |  | Numero do documento excluido por regra | CANCELADO |  |  |  | BNO / 02-DED / 02.001-DAE_TQR
BNO-MABU-300-HX-8502-10023 | REQUEST FOR APPROVED VENDORS SAFETY EQUIPMENT CATALOGUES | TECHNICAL SAFETY | HX - HSE | A01 | NAO |  | Numero do documento excluido por regra | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.001-DAE_TQR
BNO-MABU-300-IN-0780-10001 | SIL DETERMINATION REPORT | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 2 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-0780-10002 | OSI PI PROCESS HISTORIAN POINT CONFIGURATION REPORT. | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-0780-10004 | SIF DESIGN VERIFICATION (AS PER IEC 61511) | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-0780-10005 | FUNCTIONAL SAFETY ASSESSMENT - STAGE 2 TOR | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 2 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-0780-10006 | FUNCTIONAL SAFETY ASSESSMENT - STAGE 2 REPORT | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-0780-10009 | ALARM RATIONALISATION WORKSHOP - TOR | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-0980-10001-001 | VIBRATION MONITORING SYSTEMS BLOCK DIAGRAMS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-0980-10001-002 | VIBRATION_MONITORING_SYSTEMS_BLOCK_DIAGRAMS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-0980-10002-001 | HYDRAULIC AND CHEMICAL SYSTEMS BLOCK DIAGRAM BOARDING VALVE HYDRAULIC DISTRIBUTION | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-0980-10007-001 | CABLE BLOCK DIAGRAM | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | BNO-DED-MABU-AVEON-2026-TN-10016 | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-0980-10008-001 | CHEMICAL INJECTION HYDRAULIC TUBING BLOCK DIAGRAM | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-0980-10008-002 | CHEMICAL INJECTION HYDRAULIC TUBING BLOCK DIAGRAM | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-1979-10002 | MASTER ALARM DATABASE (VARIABLE TABLE) | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-1979-10003 | ESD TRIP SCHEDULE (INPUT ONLY) | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2105-10001 | INSTRUMENTATION & AUTOMATION DATASHEET FOR PIG SIGNALER | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2105-10002 | INSTRUMENTATION & AUTOMATION DATASHEET FOR SAND DETECTOR | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2105-10003 | INSTRUMENTATION & AUTOMATION DATASHEET FOR SMART CHOKE VALVE | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2105-10004 | INSTRUMENTATION & AUTOMATION DATASHEET FOR HYDRAULIC MOTOR OPERATED VALVE | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2105-10005 | INSTRUMENTATION & AUTOMATION DATASHEET FOR PNEUMATIC ACTUATED ON-OFF_ BLOWDOWN AND SHUTDOWN VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2105-10006 | INSTRUMENTATION & AUTOMATION DATASHEET FOR CORIOLIS FLOWMETER | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2105-10007 | INSTRUMENTATION & AUTOMATION DATASHEET FOR CORROSION DETECTOR | INSTRUMENTATION | IN - INSTRUMENTATION | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2105-10008 | INSTRUMENTATION & AUTOMATION DATASHEET FOR DIFFERENTIAL PRESSURE INDICATING TRANSMITTER | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2105-10009 | INSTRUMENTATION & AUTOMATION DATASHEET FOR RESTRICTION ORIFICE | INSTRUMENTATION | IN - INSTRUMENTATION | A04 | SIM | AFC 3 |  | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2105-10010 | INSTRUMENTATION & AUTOMATION DATASHEET FOR TEMPERATURE INDICATING TRANSMITTER | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2105-10011 | INSTRUMENTATION & AUTOMATION DATASHEET FOR ULTRASONIC FLOWMETER | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 2 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2105-10012 | INSTRUMENTATION & AUTOMATION DATASHEET FOR PRESSURE GAUGE | INSTRUMENTATION | IN - INSTRUMENTATION | A04 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2105-10013 | INSTRUMENTATION & AUTOMATION DATASHEET FOR PRESSURE INDICATING TRANSMITTER | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2105-10014 | INSTRUMENTATION & AUTOMATION DATASHEET FOR TEMPERATURE GAUGE | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2105-10015 | INSTRUMENTATION & AUTOMATION DATASHEET FOR PRESSURE RELIEF VALVE | INSTRUMENTATION | IN - INSTRUMENTATION | A05 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2105-10016 | INSTRUMENTATION & AUTOMATION DATASHEET FOR CONTROL VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 2 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2105-10018 | INSTRUMENTATION & AUTOMATION DATASHEET FOR HYDRAULIC HAND VALVE AND SHUTDOWN VALVE | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2105-10019 | INSTRUMENTATION & AUTOMATION DATASHEET FOR HYDRAULIC BOARDING SHUTDOWN VALVE | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 2 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2105-10020 | INSTRUMENTATION & AUTOMATION DATASHEET FOR POINT TYPE GAS DETECTOR | INSTRUMENTATION | IN - INSTRUMENTATION | A05 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2105-10021 | INSTRUMENTATION & AUTOMATION DATASHEET FOR OPEN PATH GAS DETECTOR | INSTRUMENTATION | IN - INSTRUMENTATION | A05 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2105-10022 | INSTRUMENTATION & AUTOMATION DATASHEET FOR IR FLAME DETECTOR | INSTRUMENTATION | IN - INSTRUMENTATION | A05 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2105-10025 | INSTRUMENTATION & AUTOMATION DATASHEET FOR JUNCTION BOXES | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2312-10001-001 | SUBSEA CONTROL SYSTEM TOPSIDE INTERFACE SCHEMATIC | INSTRUMENTATION | IN - INSTRUMENTATION | C03 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2335-10001-001 | PROCESS HOOK UP DRAWING | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2335-10002-001 | SUPPORT HOOK UP DRAWING | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | SIM | IFR |  | ENGINEERING COMMENTS |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2335-10003-001 | ELECTRICAL HOOK UP DRAWING | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2335-10004-001 | PNEUMATIC/HYDRALIC HOOK UP DRAWING | INSTRUMENTATION | IN - INSTRUMENTATION | C03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2335-10006-001 | PNEUMATIC/HYDRAULIC HOOK-UP DRAWINGS | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2341-10003-001 | HPU/HCU INTERFACE HOOKUP DRAWINGS | INSTRUMENTATION | IN - INSTRUMENTATION | C03 | SIM | MABU UNDER REVIEW |  | ENGINEERING COMMENTS |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2341-10004-001 | PRODUCTION UMBILICAL INTERFACE HOOKUP DRAWINGS | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING COMMENTS |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2341-10005-001 | GASLIFT UMBILICAL HOOKUP DRAWING | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING COMMENTS |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2341-10007-001 | CORROSION INHIBITOR & METHANOL SYSTEM TO TUPA INTERFACE HOOKUP DRAWINGS | INSTRUMENTATION | IN - INSTRUMENTATION | C03 | SIM | MABU UNDER REVIEW |  | ENGINEERING COMMENTS |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2341-10008-001 | BUNDLE GASLIFT UMBILICAL (BGLU) TO GASLIFT TUPA HOOKUP DRAWINGS | INSTRUMENTATION | IN - INSTRUMENTATION | C03 | SIM | MABU UNDER REVIEW |  | ENGINEERING COMMENTS |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2341-10012-001 | CONTROL SYSTEMS INTERFACE HOOKUP DRAWINGS | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2347-10001-001 | INSTRUMENT LOOP DIAGRAMS | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2373-10001-001 | CHEMICAL INJECTION HYDRAULIC TUBING ROUTING DRAWINGS | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2389-10001 | RIO TERMINATION DRAWINGS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-2389-10002-001 | RIO PANEL TERMINATION DRAWINGS | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-3323-10004 | TBE FOR TUBING & BULK MATERIAL MTO | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-3323-10005 | TBE FOR SUPPORT | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-3323-10007 | TBE FOR CABLE TRAYS AND ACCESSORIES | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-3323-10008 | TBE FOR CHANNELS AND ACCESSORIES | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-3323-10011 | TBE FOR CABLE GLANDS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-3323-10012 | TBE FOR CABLES AND MULTICABLES | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-3323-10015 | TBE FOR JUNCTION BOXES | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-3323-10016 | TBE FOR MISCELLANEOUS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-3323-10017 | TBE FOR PIPING AND PIPING CONNECTIONS | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-3323-10030 | MATERIAL REQUISITION FOR INSTRUMENTATION CABLE TRAY (TAM 26) | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-3323-10031 | MATERIAL REQUISITION FOR INSTRUMENTATION SUPPORT (TAM 26) | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-3323-10032 | MATERIAL REQUISITION - CLAMPS FOR TUBING (TAM 26) | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4018-10001-001 | INSTRUMENT CABLES ROUTING DRAWINGS | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4018-10002-001 | INSTRUMENT TUBING ROUTING DRAWINGS | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | SIM | MABU UNDER REVIEW |  | TRANSMITTAL |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4018-10003-001 | PCD NETWORK ARCHITECTURE DRAWING (PHYSICAL LOGICAL) | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4018-10004-001 | PCD PI NETWORK ARCHITECTURE DRAWING | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4018-10005-001 | PCD NETWORK CABLE (BLOCK DIAGRAM) | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4018-10006-001 | CABLE TRAY AND TUBING TRAY SUPPORTS LOCATION LAYOUT COVER SHEET | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10002-001 | FIRE AND GAS LOCATION LAYOUT AND LOCATION PLAN - SSCB CONTROL ROOM SHT 1 | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10002-002 | FIRE AND GAS LOCATION LAYOUT AND LOCATION PLAN - SSCB CONTROL ROOM SHT 2 | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10003-001 | F&G LOCATION LAYOUT & PLAN SSCB (BATTERY ROOM) | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10004-001 | F&G LOCATION LAYOUT & PLAN FLOWLINE CORROSION INHIBITOR SKID | INSTRUMENTATION | IN - INSTRUMENTATION | C03 | SIM | IFA |  | TRANSMITTAL |  | IFA - ISSUED FOR APPROVAL |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10005-001 | F&G LOCATION LAYOUT & PLAN SUBSEA WELL LAUNCHER AND RECEIVER | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10005-002 | FIRE AND GAS LOCATION LAYOUT & PLAN SUBSEA WELL LAUNCHE AND RECEIVER | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10006-001 | F&G LOCATION LAYOUT & PLAN METHANOL INJECTION PACKAGE | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10007-001 | F&G LOCATION LAYOUT & PLAN WATERFLOOD INJECTION PACKAGE | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10007-002 | FIRE & GAS LOCATION LAYOUT WATERFLOOD INJECTION PUMP TURBINE PLAN AT LEVEL 2 SHT 2 | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10008-001 | PNEUMATIC & HYDRAULIC INSTRUMENTATION PLAN & LOCATION WATERFLOOD INJECTION PACKAGE | INSTRUMENTATION | IN - INSTRUMENTATION | C02 | SIM | IFA |  | ENGINEERING CONSOLIDATION |  | IFA - ISSUED FOR APPROVAL |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10009-001 | F&G LOCATION LAYOUT & PLAN BOARDING VALVE PANEL AND TERMINATION UNBILICAL PANEL | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10010-001 | PNEUMATIC & HYDRAULIC INSTRUMENTATION PLAN & LOCATION LAYOUT SUBSEA WELL LAUNCHER AND RECEIVER AND GAS LIFT | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  | IFA - ISSUED FOR APPROVAL |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10011-001 | PNEUMATIC & HYDRAULIC INSTRUMENTATION PLAN & LOCATION PRODUCTION MANIFOLD | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO | IFA RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10012-001 | PNEUMATIC & HYDRAULIC INSTRUMENTATION PLAN & LOCATION GAS RISER LIFT METERS | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10013-001 | PNEUMATIC & HYDRAULIC INSTRUMENTATION PLAN & LOCATION FLOWLINE CORROSION INHIBITOR SYSTEM PACKAGE | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10014-001 | PNEUMATIC & HYDRAULIC INSTRUMENTATION PLAN & LOCATION METHANOL INJECTION PACKAGE | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO | AFC/AFU RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10020-001 | ELECTRICAL & I NSTRUMENTATION PLAN & LOCATION PRODUCTION MANIFOLD | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10021-001 | ELECTRICAL & INSTRUMENTATION PLAN & LOCATION BOARDING VALVE PANEL-HPU (CANCELLED) | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10022-001 | ELECTRICAL INSTRUMENTATION PLAN & SSCB - BATTERY ROOM | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10023-001 | F&G LOCATION LAYOUT COVER SHEET | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10024-001 | F&G LOCATION LAYOUT INDEX SHEET | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10025-001 | F&G LOCATION LAYOUT LEGEND SHEET | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10028-001 | F&G LOCATION LAYOUT SSCB (OUTDOOR) | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10029-001 | F&G DEVICES AND JUNCTION BOX LOCATION LAYOUT - SSCB | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10031-001 | F&G DEVICES AND JUNCTION BOX LOCATION LAYOUT - FLOWLINE CORROSION INHIBITOR SKID | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10033-001 | PNEUMATIC & HYDRAULIC INSTRUMENTATION & AUTOMATION LOCATION LAYOUT - WATERFLOOD INJECTION PACKAGE | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10034-001 | PNEUMATIC & HYDRAULIC INSTRUMENTATION & AUTOMATION LOCATION LAYOUT SUBSEA WELL LAUNCHER AND RECEIVER | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10035-001 | PNEUMATIC & HYDRAULIC INSTRUMENTATION & AUTOMATION LOCATION LAYOUT - PRODUCTION MANIFOLD | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10036-001 | PNEUMATIC & HYDRAULIC INSTRUMENTATION & AUTOMATION LOCATION LAYOUT - WI TURBINE DIESEL DAY TANK SYSTEM | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10037-001 | PNEUMATIC & HYDRAULIC INSTRUMENTATION & AUTOMATION LOCATION LAYOUT - GAS RISER LIFT METERS | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10038-001 | PNEUMATIC & HYDRAULIC INSTRUMENTATION & AUTOMATION LOCATION LAYOUT - FLOWLINE CORROSION INHIBITOR SYSTEM PACKAGE | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10042-001 | INSTRUMENT AND JUNCTION BOX / LOCAL CONTROL PANELS LOCATION PLAN | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10056-001 | ELECTRICAL & INSTRUMENTATION PLAN & LOCATION SSCB | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10057-001 | ELECTRICAL & INSTRUMENTATION PLAN & LOCATION METHANOL LAYOUT INJECTION PACKAGE | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10060-001 | JUNCTION BOX TERMINATION LAYOUT | INSTRUMENTATION | IN - INSTRUMENTATION | C03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10070-001 | F&G DETECTION SYSTEM - FIRE ZONE COVER SHEET | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10071-001 | F&G DETECTION SYSTEM - FIRE ZONE LEGEND SHEET | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10072-001 | F&G DETECTION SYSTEM - FIRE ZONE WATERFLOOD INJECTION PUMP TURBINE | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10072-002 | FIRE AND GAS LOCATION LAYOUT WATERFLOOD INJECTION PUMP TURBINE PLAN AT LEVEL 2 | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10073-001 | F&G DETECTION SYSTEM - FIRE ZONE METHANOL INJECTION PACKAGE | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10074-001 | F&G DETECTION SYSTEM - FIRE ZONE FLOWLINE CORROSION INHIBITOR SKID | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10075-001 | F&G DETECTION SYSTEM - FIRE ZONE SWITCHGEAR & SUBSEA CONTROL BUILDING | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10076-001 | F&G DETECTION SYSTEM - FIRE ZONE SSCB (BATTERY ROOM) | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10077-001 | F&G DETECTION SYSTEM - FIRE ZONE SUBSEA WELL LAUNCHER AND RECEIVER | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10077-002 | FIRE AND GAS LOCATION LAYOUT & PLAN SUBSEA WELL LAUNCHER AND RECEIVER | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10078-001 | F&G DETECTION SYSTEM - FIRE ZONE BOARDING VALVE PANEL AND TUPA | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10078-002 | FIRE AND GAS LOCATION LAYOUT & PLAN BOARDING VALV PANEL & TERMINATION UMBLICAL PANEL ASSEMBLY SHT 2 | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10079-001 | FIRE AND GAS DETECTION SYSTEM FIRE ZONE INDEX SHEET | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10080-001 | FIRE AND GAS DETECTION SYSTEM FIRE ZONE - WATERFLOOD INJECTION PUMP STACK LEVEL | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10083-001 | FIRE AND GAS DETECTION SYSTEM FIRE ZONE - PRODUCTION MANIFLOD | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10101-001 | PNEUMATIC & HYDRAULIC INSTRUMENTATION LOCATION PLAN | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10102-001 | PNEUMATIC & HYDRAULIC TUBING TRAY INSTRUMENTATION ROUTE PLAN | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10103-001 | PNEUMATIC & HYDRAULIC TUBING TRAY INSTRUMENTATION SUPPORT PLAN | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10104-001 | ELECTRICAL & INSTRUMENTATION LOCATION PLAN | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10105-001 | ELECTRICAL & INSTRUMENTATION CABLE TRAY ROUTE PLAN | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10106-001 | ELECTRICAL & INSTRUMENTATION CABLE TRAY SUPPORT PLAN | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10107-001 | FIRE AND GAS INSTRUMENTATION LOCATION PLAN | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10108-001 | FIRE AND GAS INSTRUMENTATION CABLE TRAY ROUTE PLAN | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4024-10109-001 | FIRE AND GAS INSTRUMENTATION CABLE TRAY SUPPORT PLAN | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4180-10003-001 | STANDARD INSTALLATION DRAWINGS (INSTRUMENT_ JB_ CABLE TRAY SUPPORT DRAWINGS_ EARTHING DRAWINGS ETC.) | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4180-10004-001 | INSTRUMENT AND JUNCTION BOXES INSTALLATION DRAWING | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4180-10005 | ALARM & TRIP SCHEDULE | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4180-10006 | INSTRUMENT JUNCTION BOX SCHEDULE | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO | NOT ISSUED |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4180-10006-001 | INSTRUMENT JUNCTION BOX SCHEDULE | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4306-10002 | MATERIAL LIST FOR PNEUMATIC & HYDRAULIC L INSTRUMENTATION PLAN | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4306-10005 | MATERIAL LIST FOR PNEUMATIC & HYDRALIC HOOK UP DRAWING | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4306-10006 | MATERIAL LIST FOR INSTRUMENT & JUNCTION BOX SUPPORT HOOK UP ITEMS | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | SIM | MABU UNDER REVIEW |  | ENGINEERING COMMENTS |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4306-10009 | INSTRUMENTATION MTO - MISCELLANEOUS | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4306-10010 | MATERIAL LIST FOR INSTRUMENT & JUNCTION BOX SUPPORT ITEMS | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4306-10012 | INSTRUMENT TUBING & BULK MATERIAL MTO | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4306-10015 | MATERIAL LIST FOR ELECTRICAL INSTRUMENTATION PLAN | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4306-10016 | MATERIAL LIST FOR PROCESS HOOK UP DRAWING | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | SIM | MABU UNDER REVIEW |  | ENGINEERING COMMENTS |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4306-10017 | MATERIAL LIST FOR ELECTRICAL HOOK UP DRAWING | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | SIM | MABU UNDER REVIEW |  | ENGINEERING COMMENTS |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4306-10018 | CHEMICAL INJECTION HYDRAULIC TUBING MTO | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4308-10001 | INSTRUMENTATION CABLE SCHEDULE | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4327-10001 | I/O LIST | INSTRUMENTATION | IN - INSTRUMENTATION | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | BNO-DED-MABU-AVEON-2026-TN-10016 | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4380-10001 | MASTER CONTROL PANEL LIST | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 2 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4380-10002 | ALARM AND SET POINT LIST | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-4380-10003 | INSTRUMENT LIST | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-5505-10001 | CONTROL NARRATIVES | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 2 |  | BNO-DED-MABU-AVEON-2026-TN-10016 | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-5505-10002-001 | CONTROL SYSTEM BLOCK DIAGRAM | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-5680-10001 | IP(F) NARRATIVES | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | MABU UNDER REVIEW |  | TRANSMITTAL |  |  | BNO-DED-MABU-AVEON-2026-TN-10016 | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-5880-10002 | FUNCTIONAL SAFETY MANAGEMENT PLAN | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-6067-10005 | THIRD PARTY PACKAGE INTEGRATED FAT TESTING PROCEDURES | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO | NOT ISSUED |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-6180-10005 | FINAL SIF TEST PROCEDURES | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO | NOT ISSUED |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-6604-10001-001 | PROCESS AND ESS CAUSE AND EFFECT DIAGRAMS | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | BNO-DED-MABU-AVEON-2026-TN-10016 | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-6604-10003-001 | F&G CAUSE AND EFFECT DIAGRAMS - DETAIL PHASE | INSTRUMENTATION | IN - INSTRUMENTATION | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | BNO-DED-MABU-AVEON-2026-TN-10016 | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7180-10003 | ALARM RATIONALISATION WORKSHOP - REPORT | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7180-10005 | CONTROL VALVES SIZING CALCULATION | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7180-10006 | INSTRUMENT AIR CONSUMPTION CALCULATION | INSTRUMENTATION | IN - INSTRUMENTATION | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7180-10007 | INSTRUMENT POWER CONSUMPTION CALCULATION | INSTRUMENTATION | IN - INSTRUMENTATION | A05 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7180-10010 | PRESSURE RELIEF VALVES SIZING CALCULATION | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7180-10011 | RESTRICTION ORIFICE SIZING CALCULATION | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7180-10012 | SIL CALCULATION NOTES (DED) EPC-1 | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 2 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7180-10013 | THERMOWELLS SIZING CALCULATION | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10001 | MATERIAL REQUISITION FOR PIG SIGNALER | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10002 | MATERIAL REQUISITION SAND DETECTOR | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10004 | MATERIAL REQUISITION MAIN AUTOMATION CONTRACTOR | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10006 | MATERIAL REQUISITION BOARDING VALVES PANEL | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10007 | MATERIAL REQUISITION FOR HYDRAULIC MOTOR OPERATED VALVE | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10008 | MATERIAL REQUISITION FOR ULTRASONIC FLOWMETER | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10009 | MATERIAL REQUISITION FOR PNEUMATIC ACTUATED ON-OFF_ BLOWDOWN AND SHUTDOWN VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10010 | MATERIAL REQUISITION FOR PRESSURE INDICATING TRANSMITTER AND DIFFERENTIAL PRESSURE INDICATING TRANSMITTER | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10011 | MATERIAL REQUISITION FOR CONTROL VALVE | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10012 | MATERIAL REQUISITION FOR PRESSURE RELIEF VALVE | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10013 | MATERIAL REQUISITION TEMPERATURE INDICATING TRANSMITTER | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10014 | MATERIAL REQUISITION FOR CORROSION DETECTOR | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10015 | MATERIAL REQUISITION FOR PRESSURE GAUGE | INSTRUMENTATION | IN - INSTRUMENTATION | A06 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10016 | MATERIAL REQUISITION FOR TEMPERATURE GAUGE | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10017 | MATERIAL REQUISITION FOR RESTRICTION ORIFICE | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10018 | MATERIAL REQUISITION FOR CORIOLIS FLOWMETER | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10019 | MATERIAL REQUISITION FOR HYDRAULIC HAND VALVE AND SHUTDOWN VALVE | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10020 | MATERIAL REQUISITION FOR HYDRAULIC BOARDING SHUTDOWN VALVE | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10021 | MATERIAL REQUISITION FOR POINT TYPE GAS DETECTOR | INSTRUMENTATION | IN - INSTRUMENTATION | A06 | SIM | MABU UNDER REVIEW |  | ENGINEERING COMMENTS |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10022 | MATERIAL REQUISITION FOR OPEN PATH GAS DETECTOR | INSTRUMENTATION | IN - INSTRUMENTATION | A06 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10023 | MATERIAL REQUISITION FOR IR FLAME DETECTOR | INSTRUMENTATION | IN - INSTRUMENTATION | A06 | SIM | MABU UNDER REVIEW |  | ENGINEERING COMMENTS |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10024 | MATERIAL REQUISITION FOR MANUAL ALARM CALL POINT | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 2 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10026 | MATERIAL REQUISITION FOR INSTRUMENTATION CABLES | INSTRUMENTATION | IN - INSTRUMENTATION | A04 | SIM | MABU UNDER REVIEW |  | ENGINEERING COMMENTS |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10027 | MATERIAL REQUISITION FOR SUPPORT | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10028 | MATERIAL REQUISITION FOR TUBINGS AND COMPRESSION CONNSECTIONS | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | SIM | MABU UNDER REVIEW |  | ENGINEERING COMMENTS |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10030 | MATERIAL REQUISITION FOR CABLE GLANDS | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | SIM | AFC 3 |  | ENGINEERING COMMENTS | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10031 | MATERIAL REQUISITION FOR CABLES AND MULTICABLES | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10033 | MATERIAL REQUISITION FOR TUBING & BULK MATERIAL MTO | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10034 | MATERIAL REQUISITION FOR CABLE TRAYS AND ACCESSORIES | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10035 | MATERIAL REQUISITION FOR CABLE TRAYS. CHANNELS AND ACCESSORIES | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10038 | MATERIAL REQUISITION FOR JUNCTION BOXES | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10039 | MATERIAL REQUISITION FOR BULK & MISCELLANEOUS MATERIALS (TUBES_ FITTINGS_ AIR MANIFOLDS) | INSTRUMENTATION | IN - INSTRUMENTATION | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10040 | MATERIAL REQUISITION FOR SMART CHOKE VALVE | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7303-10041 | MATERIAL REQUISITION FOR CHEMICAL INJECTION HYDRAULIC TUBING | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7709-10001 | DESIGN SPECIFICATION FOR CONTROL_ AUTOMATION AND SAFETY SYSTEM | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7770-10001 | F&G DESIGN SPECIFICATION | INSTRUMENTATION | IN - INSTRUMENTATION | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7770-10002 | DESIGN SPECIFICATION FOR FIELD INSTRUMENTATION | INSTRUMENTATION | IN - INSTRUMENTATION | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7770-10003 | BOARDING VALVES PANEL SPECIFICATION | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7770-10004 | VENDOR SUPPLIED PACKAGES INTEGRATION DESIGN SPECIFICATION | INSTRUMENTATION | IN - INSTRUMENTATION | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IDC - INTERNAL COMMENTS |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7770-10005 | SPECIFICATIONS FOR SIL ASSESSMENT TERMS OF REFERENCE - DETAIL PHASE | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7770-10009 | SIF REQUIREMENT SPECIFICATION (SRS) | INSTRUMENTATION | IN - INSTRUMENTATION | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-7770-10010 | ALARM SYSTEM REQUIREMENTS SPECIFICATION | INSTRUMENTATION | IN - INSTRUMENTATION | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-8380-10001 | PANEL THERMAL DISPERSION (INTERNAL DOCUMENT) | INSTRUMENTATION | IN - INSTRUMENTATION | X | NAO |  | Revisao X cancelada | CANCELADO | NOT ISSUED |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-IN-8880-10001-001 | INSTRUMENT WIRING DIAGRAMS | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.13-IN-INSTRUMENTATION
BNO-MABU-300-JA-3375-10002-001 | 3D MODEL REVIEW FILE | IT / IM | JA - IM | R01 | NAO |  | Titulo excluido por regra | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 02-DED / 02.14-JA-INFORMATION MNGM
BNO-MABU-300-JA-5798-10001 | E3D MODELING EXECUTION PLAN | IT / IM | JA - IM | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.14-JA-INFORMATION MNGM
BNO-MABU-300-JA-5798-10002 | SMARTPLANT P&ID DESIGN EXECUTION PLAN | IT / IM | JA - IM | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.14-JA-INFORMATION MNGM
BNO-MABU-300-JA-5798-10003 | SMARTPLANT INSTRUMENTATION DESIGN EXECUTION PLAN | IT / IM | JA - IM | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.14-JA-INFORMATION MNGM
BNO-MABU-300-JA-6017-10001 | INFORMATION QUALITY MANAGEMENT SYSTEM (IQMS) | IT / IM | JA - IM | X | NAO |  | Revisao X cancelada | CANCELADO | NOT ISSUED |  |  | BNO / 02-DED / 02.14-JA-INFORMATION MNGM
BNO-MABU-300-JA-6611-10002 | DAE MASTER DOCUMENT REGISTER | IT / IM | JA - IM | A03 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 4 | IFA - ISSUED FOR APPROVAL |  | BNO / 02-DED / 02.14-JA-INFORMATION MNGM
BNO-MABU-300-KA-5798-10002-001 | PCD NETWORK ARCHITECTURE DRAWING (PHYSICAL & LOGICAL) | IT / IM | KA - IT | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.15-KA-IT
BNO-MABU-300-KA-5798-10004 | INFORMATION TECHNOLOGY (IT) PLAN | IT / IM | KA - IT | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.15-KA-IT
BNO-MABU-300-KA-5980-10001 | PCD ASSET REGISTER | IT / IM | KA - IT | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.15-KA-IT
BNO-MABU-300-KA-7739-10003 | BONGA NORTH PCD NETWORK DESIGN SPECIFICATION | IT / IM | KA - IT | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.15-KA-IT
BNO-MABU-300-KA-7739-10004 | BONGA NORTH PCD - IT SECURITY DESIGN SPECIFICATION - FINAL | IT / IM | KA - IT | A02 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.15-KA-IT
BNO-MABU-300-KA-7739-10005 | PCD 3RD PARTY NETWORK INTEGRATION DESIGN SPECIFICATION | IT / IM | KA - IT | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.15-KA-IT
BNO-MABU-300-KA-7739-10006 | PCD NETWORK MANAGEMENT DESIGN SPECIFICATION | IT / IM | KA - IT | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.15-KA-IT
BNO-MABU-300-KA-7739-10007 | PCD DMZ (SECURE PCD) INTEGRATION AND CONFIGURATION DETAILS | IT / IM | KA - IT | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.15-KA-IT
BNO-MABU-300-KA-7880-10001 | PCD HANDOVER PLAN | IT / IM | KA - IT | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.15-KA-IT
BNO-MABU-300-MP-1206-10001 | SUPPORT LOADS FOR STRUCTURE - PUMPS P-4046AB AND P-4047 | PIPING | MP - PIPING | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-1206-10002 | SUPPORT LOADS FOR STRUCTURE-LAUNCHER AND RECEIVER A-0820J | PIPING | MP - PIPING | A03 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-1206-10003 | SUPPORT LOADS FOR STRUCTURE-LAUNCHER AND RECEIVER A-0820K | PIPING | MP - PIPING | A02 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-1206-10004 | API 10000 PRESSURE RATING WALL THICKNESS CALCULATION REPORT | PIPING | MP - PIPING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-1206-10005 | SPRING SUPPORTS SCHEDULE | PIPING | MP - PIPING | A02 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-1206-10006 | SUPPORT LOADS FOR STRUCTURE-CORROSION INHIBITOR TANK T-4282 | PIPING | MP - PIPING | A03 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-1206-10007 | SUPPORT LOADS FOR STRUCTURE - GAS RISER LIFT METER LINES | PIPING | MP - PIPING | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-1206-10008 | SUPPORT LOADS FOR STRUCTURE- LEVEL-2 CRITICAL & FUTURE LINES | PIPING | MP - PIPING | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2105-10001 | PIPING DATASHEETS FOR LARGE BORE BALL VALVES | PIPING | MP - PIPING | A03 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2105-10002 | PIPING DATASHEETS FOR DOUBLE BLOCK AND BLEED VALVES | PIPING | MP - PIPING | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2105-10003 | PIPING DATASHEETS FOR QUICK CONNECT - DISCONNECT COUPLING | PIPING | MP - PIPING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2105-10004 | PIPING DATASHEETS FOR LARGE BORE CHECK VALVES | PIPING | MP - PIPING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2105-10005 | PIPING DATASODHEETS FOR GLOBE VALVES | PIPING | MP - PIPING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2105-10006 | PIPING DATASHEETS FOR SMALL BORE BALL VALVES | PIPING | MP - PIPING | A03 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2105-10007 | PIPING DATASHEETS FOR BUTTERFLY VALVES | PIPING | MP - PIPING | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2105-10008 | PIPING DATASHEETS FOR SMALL BORE CHECK VALVE | PIPING | MP - PIPING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2105-10009 | PIPING DATASHEETS FOR INSULATING GASKET SET | PIPING | MP - PIPING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2105-10010 | PIPING DATASHEETS FOR BARRED TEE | PIPING | MP - PIPING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2105-10011 | PIPING DATASHEETS FOR GATE VALVES | PIPING | MP - PIPING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2105-10012 | PIPING DATASHEETS FOR NEEDLE VALVES | PIPING | MP - PIPING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2105-10013 | PIPING DATASHEET FOR VALVE & DOOR INTERLOCK SYSTEM FOR PIG LAUNCHING AND RECEIVING | PIPING | MP - PIPING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2105-10015 | PIPING DATA SHEET FOR SLIPSTREAM SAND SAMPLING SYSTEM | PIPING | MP - PIPING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2105-10016 | DATASHEET FOR STRAINERS | PIPING | MP - PIPING | A02 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2105-10017 | DATASHEET FOR AIR RELEASE VALVE (AIR ELIMINATOR) | PIPING | MP - PIPING | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2105-10018 | DATASHEET FOR CORROSION MONITOR (ACCESS FITTING ASSEMBLIES) | PIPING | MP - PIPING | A02 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2105-10019 | DATASHEET FOR FLAME ARRESTOR | PIPING | MP - PIPING | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2105-10020 | DATASHEET FOR BIRD SCREEN | PIPING | MP - PIPING | A02 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2105-10021 | DATA SHEET FOR IN-LINE SIGHT GLASS. | PIPING | MP - PIPING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10001 | PIPING_CONSTRUCT_ISOMETRIC_DRAWING-14-PM-033030-100-CC | PIPING | MP - PIPING | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10001-001 | PIPING_ISOMETRIC_DRAWING: 14-PM-033030-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10001-002 | PIPING_ISOMETRIC_DRAWING: 14-PM-033030-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10001-003 | PIPING_ISOMETRIC_DRAWING: 14-PM-033030-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10001-004 | PIPING_ISOMETRIC_DRAWING: 14-PM-033030-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10001-005 | PIPING_ISOMETRIC_DRAWING: 14-PM-033030-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10001-006 | PIPING_ISOMETRIC_DRAWING: 14-PM-033030-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10002 | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-PM-033031-100-CC | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10002-001 | PIPING_ISOMETRIC_DRAWING: 14-PM-033031-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10002-002 | PIPING_ISOMETRIC_DRAWING: 14-PM-033031-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10002-003 | PIPING_ISOMETRIC_DRAWING: 14-PM-033031-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10002-004 | PIPING_ISOMETRIC_DRAWING: 14-PM-033031-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10002-005 | PIPING_ISOMETRIC_DRAWING: 14-PM-033031-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10003 | PIPING CONSTRUCT ISOMETRIC DRAWING: 12-PM-043090-1800-JJ | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50006 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10004 | PIPING CONSTRUCT ISOMETRIC DRAWING: 12-PM-043091-100-IFJ | PIPING | MP - PIPING | C02 | SIM | AFC 3A |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  | BNO-DED-MABU-AVEON-2026-TN-10019 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10004-002 | PIPING_ISOMETRIC_DRAWING: 12-PM-043091-100-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10004-003 | PIPING_ISOMETRIC_DRAWING: 12-PM-043091-100-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10004-004 | PIPING_ISOMETRIC_DRAWING: 12-PM-043091-100-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10004-005 | PIPING_ISOMETRIC_DRAWING: 12-PM-043091-100-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10004-006 | PIPING_ISOMETRIC_DRAWING: 12-PM-043091-100-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10005 | PIPING CONSTRUCT ISOMETRIC DRAWING: 3/4-PM-033030-100-CC | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10005-002 | PIPING_ISOMETRIC_DRAWING: 14-PM-043092-100-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10005-003 | PIPING_ISOMETRIC_DRAWING: 14-PM-043092-100-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10006 | PIPING CONSTRUCT ISOMETRIC DRAWING: 6-PM-043093-1125-JJ | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50004 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10006-001 | PIPING_ISOMETRIC_DRAWING: 6-PM-043093-1125-JJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10006-002 | PIPING_ISOMETRIC_DRAWING: 6-PM-043093-1125-JJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10006-003 | PIPING_ISOMETRIC_DRAWING: 6-PM-043093-1125-JJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10006-004 | PIPING_ISOMETRIC_DRAWING: 6-PM-043093-1125-JJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10006-005 | PIPING_ISOMETRIC_DRAWING: 6-PM-043093-1125-JJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10006-006 | PIPING_ISOMETRIC_DRAWING: 6-PM-043093-1125-JJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10006-007 | PIPING_ISOMETRIC_DRAWING: 6-PM-043093-1125-JJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10006-008 | PIPING_ISOMETRIC_DRAWING: 6-PM-043093-1125-JJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10006-009 | PIPING_ISOMETRIC_DRAWING: 6-PM-043093-1125-JJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10007 | PIPING CONSTRUCT ISOMETRIC DRAWING: 6-PM-043094-120-IFJ | PIPING | MP - PIPING | C02 | SIM | AFC 3A |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  | BNO-DED-MABU-AVEON-2026-TN-10019 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10007-001 | PIPING_ISOMETRIC_DRAWING: 6"-PM-043094-120-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10008 | PIPING CONSTRUCT ISOMETRIC DRAWING: 12-PM-043095-1800-IFJ | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | BNO-DED-MABU-AVEON-2026-TN-10018 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10008-001 | PIPING_ISOMETRIC_DRAWING: 12-PM-043095-1800-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10008-002 | PIPING_ISOMETRIC_DRAWING: 12-PM-043095-1800-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10008-003 | PIPING_ISOMETRIC_DRAWING: 12-PM-043095-1800-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10008-004 | PIPING_ISOMETRIC_DRAWING: 12-PM-043095-1800-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10008-005 | PIPING_ISOMETRIC_DRAWING: 12-PM-043095-1800-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10008-006 | PIPING_ISOMETRIC_DRAWING: 12-PM-043095-1800-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10009 | PIPING CONSTRUCT ISOMETRIC DRAWING: 10"-PM-043096-120-IFJ | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10009-001 | PIPING_ISOMETRIC_DRAWING: 10-PM-043096-120-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10009-002 | PIPING_ISOMETRIC_DRAWING: 10-PM-043096-120-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10009-003 | PIPING_ISOMETRIC_DRAWING: 10-PM-043096-120-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10009-004 | PIPING_ISOMETRIC_DRAWING: 10-PM-043096-120-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10010 | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-PM-043095-1800-IFJ | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  | FAB-MABU-AVEON-2026-TN-50001 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10010-001 | PIPING_ISOMETRIC_DRAWING: 12-PM-043095-1800-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10010-002 | PIPING_ISOMETRIC_DRAWING: 12-PM-043095-1800-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10010-003 | PIPING_ISOMETRIC_DRAWING: 12-PM-043095-1800-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10010-004 | PIPING_ISOMETRIC_DRAWING: 12-PM-043095-1800-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10010-005 | PIPING_ISOMETRIC_DRAWING: 12-PM-043095-1800-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10010-006 | PIPING_ISOMETRIC_DRAWING: 12-PM-043095-1800-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10010-007 | PIPING_ISOMETRIC_DRAWING: 12-PM-043095-1800-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10010-008 | PIPING_ISOMETRIC_DRAWING: 12-PM-043095-1800-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10011 | PIPING CONSTRUCT ISOMETRIC DRAWING: 12-PM-043098-100-CC | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10011-002 | PIPING_ISOMETRIC_DRAWING: 12-PM-043098-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10012 | PIPING CONSTRUCT ISOMETRIC DRAWING: 14-PM-043099-100-CC | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10012-001 | PIPING_ISOMETRIC_DRAWING: 14-PM-043099-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10012-002 | PIPING_ISOMETRIC_DRAWING: 14-PM-043099-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10012-003 | PIPING_ISOMETRIC_DRAWING: 14-PM-043099-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10012-004 | PIPING_ISOMETRIC_DRAWING: 14-PM-043099-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10012-005 | PIPING_ISOMETRIC_DRAWING: 14-PM-043099-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10012-006 | PIPING_ISOMETRIC_DRAWING: 14-PM-043099-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10012-007 | PIPING_ISOMETRIC_DRAWING: 14-PM-043099-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10012-008 | PIPING_ISOMETRIC_DRAWING: 14-PM-043099-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10012-009 | PIPING_ISOMETRIC_DRAWING: 14-PM-043099-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10012-010 | PIPING_ISOMETRIC_DRAWING: 14-PM-043099-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10012-011 | PIPING_ISOMETRIC_DRAWING: 14-PM-043099-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10012-012 | PIPING_ISOMETRIC_DRAWING: 14-PM-043099-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10012-013 | PIPING_ISOMETRIC_DRAWING: 14-PM-043099-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10013 | PIPING CONSTRUCT ISOMETRIC DRAWING: 10"-PM-043100-1562-IFJ | PIPING | MP - PIPING | C02 | SIM | AFC 3A |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  | BNO-DED-MABU-AVEON-2026-TN-10018 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10013-001 | PIPING_ISOMETRIC_DRAWING: 10-PM-043100-1562-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10013-002 | PIPING_ISOMETRIC_DRAWING: 10-PM-043100-1562-IFJ | PIPING | MP - PIPING | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10014 | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-PM-043101-120-IFJ | PIPING | MP - PIPING | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10014-002 | PIPING_ISOMETRIC_DRAWING: 8"-PM-043101-120-IFJ | PIPING | MP - PIPING | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10015 | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-PM-043102-1800-JJ | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | BNO-DED-MABU-AVEON-2026-TN-10018 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10016 | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-PM-043103-1125-IFJ | PIPING | MP - PIPING | C03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50006 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10016-001 | PIPING_ISOMETRIC_DRAWING: 12-PM-043103-1125-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10016-002 | PIPING_ISOMETRIC_DRAWING: 12-PM-043103-1125-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10016-003 | PIPING_ISOMETRIC_DRAWING: 12-PM-043103-1125-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10016-004 | PIPING_ISOMETRIC_DRAWING: 12-PM-043103-1125-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10016-005 | PIPING_ISOMETRIC_DRAWING: 12-PM-043103-1125-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10016-006 | PIPING_ISOMETRIC_DRAWING: 12-PM-043103-1125-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10017 | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-PM-043111-100-CC | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  | FAB-MABU-AVEON-2026-TN-50001 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10017-001 | PIPING_ISOMETRIC_DRAWING: 14-PM-043111-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10017-002 | PIPING_ISOMETRIC_DRAWING: 14-PM-043111-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10017-003 | PIPING_ISOMETRIC_DRAWING: 14-PM-043111-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10017-004 | PIPING_ISOMETRIC_DRAWING: 14-PM-043111-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10017-005 | PIPING_ISOMETRIC_DRAWING: 14-PM-043111-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10017-006 | PIPING_ISOMETRIC_DRAWING: 14-PM-043111-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10017-007 | PIPING_ISOMETRIC_DRAWING: 14-PM-043111-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10017-008 | PIPING_ISOMETRIC_DRAWING: 14-PM-043111-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10018 | PIPING CONSTRUCT ISOMETRIC DRAWING: 3/4"-PM-043117-80-B | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10018-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 3/4"-PM-043117-80-B | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10019 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-083090-XXS-IFJ | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10019-001 | PIPING_ISOMETRIC_DRAWING: 2-PM-083090-XXS-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10019-002 | PIPING_ISOMETRIC_DRAWING: 2-PM-083090-XXS-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10019-003 | PIPING_ISOMETRIC_DRAWING: 2-PM-083090-XXS-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10020 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-083091-XXS-IFJ | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10020-001 | PIPING_ISOMETRIC_DRAWING: 2-PM-083091-XXS-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10020-002 | PIPING_ISOMETRIC_DRAWING: 2-PM-083091-XXS-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10020-003 | PIPING_ISOMETRIC_DRAWING: 2-PM-083091-XXS-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10021 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-083094-XXS-IFJ | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | BNO-DED-MABU-AVEON-2026-TN-10018 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10021-001 | PIPING_ISOMETRIC_DRAWING: 2-PM-083094-XXS-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10021-002 | PIPING_ISOMETRIC_DRAWING: 2-PM-083094-XXS-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10021-003 | PIPING_ISOMETRIC_DRAWING: 2-PM-083094-XXS-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10021-004 | PIPING_ISOMETRIC_DRAWING: 2-PM-083094-XXS-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10022 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-083095-XXS-IFJ | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10022-001 | PIPING ISOMETRIC DRAWING: 2"-PM-083095-XXS-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10023 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-083097-XXS-IFJ | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10023-001 | PIPING ISOMETRIC DRAWING: 2"-PM-083097-XXS-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10024 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-1/2"-PM-083098-XXS-CC | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | BNO-DED-MABU-AVEON-2026-TN-10018 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10024-001 | PIPING ISOMETRIC DRAWING: 1-1/2"-PM-083098-XXS-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10024-002 | PIPING ISOMETRIC DRAWING: 1-1/2"-PM-083098-XXS-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10025 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-083099-XXS-IFJ | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10025-001 | PIPING_ISOMETRIC_DRAWING: 2-PM-083099-XXS-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10025-002 | PIPING_ISOMETRIC_DRAWING: 2-PM-083099-XXS-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10025-003 | PIPING_ISOMETRIC_DRAWING: 2-PM-083099-XXS-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10026 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-083100-XXS-IFJ | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10026-001 | PIPING_ISOMETRIC_DRAWING: 2-PM-083100-XXS-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10026-002 | PIPING_ISOMETRIC_DRAWING: 2-PM-083100-XXS-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10026-003 | PIPING_ISOMETRIC_DRAWING: 2-PM-083100-XXS-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10026-004 | PIPING_ISOMETRIC_DRAWING: 2-PM-083100-XXS-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10027 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-PM-083101-120-IFJ | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10027-001 | PIPING_ISOMETRIC_DRAWING: 4-PM-083101-120-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10027-002 | PIPING_ISOMETRIC_DRAWING: 4-PM-083101-120-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10027-003 | PIPING_ISOMETRIC_DRAWING: 4-PM-083101-120-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10028 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-083102-XXS-IFJ | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10028-001 | PIPING ISOMETRIC DRAWING: 2"-PM-083102-XXS-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10029 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-083103-XXS-IFJ | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | BNO-DED-MABU-AVEON-2026-TN-10019 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10029-001 | PIPING_ISOMETRIC_DRAWING: 2-PM-083103-XXS-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10029-002 | PIPING_ISOMETRIC_DRAWING: 2-PM-083103-XXS-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10030 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PL-233050-80-B | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10030-001 | PIPING ISOMETRIC DRAWING: 2"-PL-233148-80-B | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10031 | PIPING CONSTRUCT ISOMETRIC DRAWING: 24"-WI-403225-10S-13841 | PIPING | MP - PIPING | C02 | SIM | AFC 3A |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  | FAB-MABU-AVEON-2026-TN-50001 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10031-001 | PIPING_ISOMETRIC_DRAWING: 24-WI-403225-10S-13840 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10031-002 | PIPING_ISOMETRIC_DRAWING: 24-WI-403225-10S-13841 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10031-003 | PIPING_ISOMETRIC_DRAWING: 24-WI-403225-10S-13841 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10032 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-1/2"-VA-403232-80-AV | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  | FAB-MABU-AVEON-2026-TN-50001 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10032-002 | PIPING_ISOMETRIC_DRAWING: 1-1-2-VA-403232-80-AV | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10032-003 | PIPING_ISOMETRIC_DRAWING: 1-1-2-VA-403232-80-AV | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10033 | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-VA-403233-20-AV | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  | FAB-MABU-AVEON-2026-TN-50001 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10034 | PIPING_ISOMETRIC_DRAWING: 8-VA-403234-40S-SS | PIPING | MP - PIPING | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10034-002 | PIPING_ISOMETRIC_DRAWING: 8-VA-403234-40S-SS | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10035 | PIPING_ISOMETRIC_DRAWING: 4-LO-403235-40S-SS | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10035-002 | PIPING_ISOMETRIC_DRAWING: 4-LO-403235-40S-SS | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10035-003 | PIPING_ISOMETRIC_DRAWING: 4-LO-403235-40S-SS | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10035-004 | PIPING_ISOMETRIC_DRAWING: 4-LO-403235-40S-SS | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10036-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-DN-483211-40-AW | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10037-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 10"-DN-473801-40-AW | PIPING | MP - PIPING | R02 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10038 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473813-40-AW | PIPING | MP - PIPING | C02 | SIM | AFC 3A |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  | BNO-DED-MABU-AVEON-2026-TN-10018 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10038-002 | PIPING ISOMETRIC DRAWING 2-DN-473803-80-AW | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10038-003 | PIPING ISOMETRIC DRAWING 2-DN-473803-80-AW | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10039 | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-DN-473804-STD-H | PIPING | MP - PIPING | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10039-001 | PIPING ISOMETRIC DRAWING: 12"-DN-483204-STD-H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10040 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-DN-473805-80-AW | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | TRANSMITTAL |  |  | FAB-MABU-AVEON-2026-TN-50001 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10041 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-WI-403238-10S-13841 | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50001 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10041-001 | PIPING ISOMETRIC DRAWING: 2"-WI-403238-10S-13841 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10042 | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-DN-473806-40-AW | PIPING | MP - PIPING | C02 | SIM | AFC 3A |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  | BNO-DED-MABU-AVEON-2026-TN-10018 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10042-002 | PIPING ISOMETRIC DRAWING-8-DN-473806-40-AW | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10042-003 | PIPING ISOMETRIC DRAWING-8-DN-473806-40-AW | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10043-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-DN-483207-10S-13841 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10043-002 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-DN-483207-10S-13841 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10043-003 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-DN-483207-10S-13841 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10043-004 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-DN-483207-10S-13841 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10044-001 | PIPING_ISOMETRIC_DRAWING: 2-LO-403260-40S-SS | PIPING | MP - PIPING | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10045-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-CC-423005-40S-SS | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10046 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-CC-423040-40S-SS | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50006 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10046-002 | PIPING_ISOMETRIC_DRAWING: 2-CC-423040-40S-SS | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10046-003 | PIPING_ISOMETRIC_DRAWING: 2-CC-423040-40S-SS | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10046-004 | PIPING_ISOMETRIC_DRAWING: 2-CC-423040-40S-SS | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10046-005 | PIPING_ISOMETRIC_DRAWING: 2-CC-423040-40S-SS | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10047 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-CC-423041-40S-SS | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | BNO-DED-MABU-AVEON-2026-TN-10018 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10047-001 | PIPING_ISOMETRIC_DRAWING: 1-CC-423041-40S-SS | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10047-002 | PIPING_ISOMETRIC_DRAWING: 1-CC-423041-40S-SS | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10047-003 | PIPING_ISOMETRIC_DRAWING: 1-CC-423041-40S-SS | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10047-004 | PIPING_ISOMETRIC_DRAWING: 1-CC-423041-40S-SS | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10048 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-BH-463371-80-ALT | PIPING | MP - PIPING | C03 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  | BNO-DED-MABU-AVEON-2026-TN-10018 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10048-001 | PIPING ISOMETRIC DRAWING: 2"-BH-463371-80-ALT | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | NOT ISSUED |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10049 | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-BH-463372-80-A | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  | FAB-MABU-AVEON-2026-TN-50001 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10050 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-BH-463373-80-ALT | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | BNO-DED-MABU-AVEON-2026-TN-10018 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10050-001 | PIPING ISOMETRIC DRAWING: 2"-BH-463373-80-ALT | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10051 | PIPING CONSTRUCT ISOMETRIC DRAWING: 10"-BH-463374-40-ALT | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50006 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10051-001 | PIPING ISOMETRIC DRAWING: 10"-BH-463374-40-ALT | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10052 | PIPING CONSTRUCT ISOMETRIC DRAWING: 10"-BH-463374-40-ALT | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | BNO-DED-MABU-AVEON-2026-TN-10019 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10052-002 | PIPING_ISOMETRIC_DRAWING: 8-BH-463375-40-ALT | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10053 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-BH-463377-80-ALT | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | BNO-DED-MABU-AVEON-2026-TN-10018 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10053-001 | PIPING ISOMETRIC DRAWING: 2"-BH-463377-80-ALT | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10054 | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-BH-463378-80-A | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50006 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10054-001 | PIPING ISOMETRIC DRAWING: 3"-BH-463378-80-A | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10055 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-BH-463379-80-ALT | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10055-001 | PIPING ISOMETRIC DRAWING: 2"-BH-463379-80-ALT | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10056 | PIPING CONSTRUCT ISOMETRIC DRAWING: 10"-BH-463380-40-ALT | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50006 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10056-002 | PIPING_ISOMETRIC_DRAWING: 10-BH-463380-40-ALT | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10056-003 | PIPING_ISOMETRIC_DRAWING: 10-BH-463380-40-ALT | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10057 | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-BH-463381-40-ALT | PIPING | MP - PIPING | C02 | SIM | AFC 3A |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  | FAB-MABU-AVEON-2026-TN-50001 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10057-001 | PIPING_ISOMETRIC_DRAWING: 8-BH-463381-40-ALT | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10057-002 | PIPING_ISOMETRIC_DRAWING: 8-BH-463381-40-ALT | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10057-003 | PIPING_ISOMETRIC_DRAWING: 8-BH-463381-40-ALT | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10058 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-BH-463383-40S-SS | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10058-001 | PIPING ISOMETRIC DRAWING: 4"-BH-463383-40S-SS | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10059 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-BH-463384-40-ALT | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50006 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10059-001 | PIPING ISOMETRIC DRAWING: 4"-BH-463384-40-ALT | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10060 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-BH-463386-40S-SS | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50007 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10060-001 | PIPING ISOMETRIC DRAWING: 4"-BH-463386-40S-SS | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10061 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-BH-463387-40-ALT | PIPING | MP - PIPING | C02 | SIM | AFC 3A |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  | BNO-DED-MABU-AVEON-2026-TN-10018 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10061-001 | PIPING ISOMETRIC DRAWING: 4"-BH-463387-40-ALT | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10062 | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-BH-463392-STD-ALT | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | BNO-DED-MABU-AVEON-2026-TN-10019 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10062-001 | PIPING ISOMETRIC DRAWING: 14"-BH-463392-STD-ALT | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10062-002 | PIPING ISOMETRIC DRAWING: 14"-BH-463392-STD-ALT | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10063 | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-BH-463393-STD-ALT | PIPING | MP - PIPING | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10063-001 | PIPING_ISOMETRIC_DRAWING: 8-BH-463393-STD-ALT | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10063-002 | PIPING_ISOMETRIC_DRAWING: 8-BH-463393-STD-ALT | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10063-003 | PIPING_ISOMETRIC_DRAWING: 8-BH-463393-STD-ALT | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10064 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-BH-463394-40-ALT | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50001 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10064-001 | PIPING_ISOMETRIC_DRAWING: 4-BH-463394-40-ALT | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10064-002 | PIPING_ISOMETRIC_DRAWING: 4-BH-463394-40-ALT | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10065 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473605-STD-H | PIPING | MP - PIPING | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10065-001 | PIPING ISOMETRIC DRAWING: 4"-DN-473605-STD-H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10066 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473606-STD-H | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10066-001 | PIPING_ISOMETRIC_DRAWING: 4-DN-473606-STD-H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10067 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473607-STD-H | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10067-001 | PIPING_ISOMETRIC_DRAWING: 4-DN-473607-STD-H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10068 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473608-STD-H | PIPING | MP - PIPING | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10068-001 | PIPING_ISOMETRIC_DRAWING: 4-DN-473608-STD-H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10069 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473609-STD-H | PIPING | MP - PIPING | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10069-001 | PIPING_ISOMETRIC_DRAWING: 4-DN-473609-STD-H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10070 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473610-STD-H | PIPING | MP - PIPING | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10070-001 | PIPING_ISOMETRIC_DRAWING: 4-DN-473610-STD-H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10071 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473611-STD-G | PIPING | MP - PIPING | C02 | SIM | AFC 3A |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  | FAB-MABU-AVEON-2026-TN-50001 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10071-001 | PIPING_ISOMETRIC_DRAWING: 4-DN-473611-STD-G | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10072 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473612-STD-G | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10072-001 | PIPING_ISOMETRIC_DRAWING: 4-DN-473612-STD-G | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10073 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473613-STD-G | PIPING | MP - PIPING | C02 | SIM | AFC 3A |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  | FAB-MABU-AVEON-2026-TN-50001 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10073-001 | PIPING ISOMETRIC DRAWING: 4"-DN-473613-STD-G | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10074 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473614-STD-G | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10074-001 | PIPING_ISOMETRIC_DRAWING: 4-DN-473614-STD-G | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10075 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473615-STD-H | PIPING | MP - PIPING | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10075-001 | PIPING_ISOMETRIC_DRAWING: 4-DN-473615-STD-H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10075-002 | PIPING_ISOMETRIC_DRAWING: 4-DN-473615-STD-H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10075-003 | PIPING_ISOMETRIC_DRAWING: 4-DN-473615-STD-H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10076 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473616-STD-H | PIPING | MP - PIPING | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10077 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-DN-473617-80-G | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10077-002 | PIPING_ISOMETRIC_DRAWING: 2-DN-473617-80-G | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10077-003 | PIPING_ISOMETRIC_DRAWING: 2-DN-473617-80-G | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10077-004 | PIPING_ISOMETRIC_DRAWING: 2-DN-473617-80-G | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10077-005 | PIPING_ISOMETRIC_DRAWING: 2-DN-473617-80-G | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10077-006 | PIPING_ISOMETRIC_DRAWING: 2-DN-473617-80-G | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10078 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-DN-473618-STD-H | PIPING | MP - PIPING | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10078-002 | PIPING_ISOMETRIC_DRAWING: 2-DN-473618-STD-H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10078-003 | PIPING_ISOMETRIC_DRAWING: 2-DN-473618-STD-H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10079 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473620-STD-H | PIPING | MP - PIPING | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10079-001 | PIPING_ISOMETRIC_DRAWING: 4-DN-473620-STD-H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10079-002 | PIPING_ISOMETRIC_DRAWING: 4-DN-473620-STD-H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10080 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-DN-473621-80-G | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  | FAB-MABU-AVEON-2026-TN-50001 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10080-002 | PIPING_ISOMETRIC_DRAWING: 1-DN-473621-80-G | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10080-003 | PIPING_ISOMETRIC_DRAWING: 1-DN-473621-80-G | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10080-004 | PIPING_ISOMETRIC_DRAWING: 1-DN-473621-80-G | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10081-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-DN-473622-80-G | PIPING | MP - PIPING | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10081-002 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-DN-473622-80-G | PIPING | MP - PIPING | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10081-003 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-DN-473622-80-G | PIPING | MP - PIPING | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10082-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-DN-473622-80-G | PIPING | MP - PIPING | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10082-002 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-DN-473622-80-G | PIPING | MP - PIPING | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10082-003 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-DN-473622-80-G | PIPING | MP - PIPING | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10083 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-DN-473624-80-G | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  | FAB-MABU-AVEON-2026-TN-50001 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10083-002 | PIPING_ISOMETRIC_DRAWING: 1-DN-473624-80-G | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10083-003 | PIPING_ISOMETRIC_DRAWING: 1-DN-473624-80-G | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10084 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-DN-473625-80-G | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  | FAB-MABU-AVEON-2026-TN-50001 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10084-001 | PIPING_ISOMETRIC_DRAWING: 2-DN-473625-80-G | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10085 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-DN-473626-80-G | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  | FAB-MABU-AVEON-2026-TN-50001 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10086 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473633-STD-H | PIPING | MP - PIPING | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10086-001 | PIPING_ISOMETRIC_DRAWING: 4-DN-473633-STD-H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10086-002 | PIPING_ISOMETRIC_DRAWING: 4-DN-473633-STD-H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10086-003 | PIPING_ISOMETRIC_DRAWING: 4-DN-473633-STD-H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10087 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-DC-483015-80-A | PIPING | MP - PIPING | C01 | SIM | AFC 3A |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  | FAB-MABU-AVEON-2026-TN-50002 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10088 | PIPING CONSTRUCT ISOMETRIC DRAWING: 16"-WI-403226-30-63860 | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50007 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10088-002 | PIPING_ISOMETRIC_DRAWING: 16-WI-403226-30-63861 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10089 | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-DN-473800-40-AW | PIPING | MP - PIPING | C02 | SIM | AFC 3A |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  | BNO-DED-MABU-AVEON-2026-TN-10018 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10089-001 | PIPING_ISOMETRIC_DRAWING: 8-DN-473800-40-AW | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10089-002 | PIPING_ISOMETRIC_DRAWING: 8-DN-473800-40-AW | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10089-003 | PIPING_ISOMETRIC_DRAWING: 8-DN-473800-40-AW | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10090 | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-WI-403249-30-63861 | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50007 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10091 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-DN-473807-10S-13841 | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10091-002 | PIPING_ISOMETRIC_DRAWING: 2-FG-443100-40S-SSB-T | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10091-003 | PIPING_ISOMETRIC_DRAWING: 2-FG-443100-40S-SSB-T | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10091-004 | PIPING_ISOMETRIC_DRAWING: 2-FG-443100-40S-SSB-T | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10092-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-DN-473806-40-AW | PIPING | MP - PIPING | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10092-002 | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-DN-473806-40-AW | PIPING | MP - PIPING | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10092-003 | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-DN-473806-40-AW | PIPING | MP - PIPING | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10093 | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-DN-473808-40-AW | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  | FAB-MABU-AVEON-2026-TN-50002 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10093-001 | PIPING ISOMETRIC DRAWING 8-DN-473808-40-AW | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10093-002 | PIPING ISOMETRIC DRAWING 8-DN-473808-40-AW | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10093-003 | PIPING ISOMETRIC DRAWING 8-DN-473808-40-AW | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10094 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473809-40-AW | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  | FAB-MABU-AVEON-2026-TN-50002 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10095 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473810-40-AW | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  | FAB-MABU-AVEON-2026-TN-50002 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10096 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-IA-503286-80-G | PIPING | MP - PIPING | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10096-002 | PIPING_ISOMETRIC_DRAWING: 2-IA-503286-80-G | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10096-003 | PIPING_ISOMETRIC_DRAWING: 2-IA-503286-80-G | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10096-004 | PIPING_ISOMETRIC_DRAWING: 2-IA-503286-80-G | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10096-005 | PIPING_ISOMETRIC_DRAWING: 2-IA-503286-80-G | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10096-006 | PIPING_ISOMETRIC_DRAWING: 2-IA-503286-80-G | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10097 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-IA-503287-80-G | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10098 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-IA-503288-80-G | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10098-002 | PIPING_ISOMETRIC_DRAWING: 2-IA-503288-80-G | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10098-003 | PIPING_ISOMETRIC_DRAWING: 2-IA-503288-80-G | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10099 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-PM-083101-120-IFJ | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  | FAB-MABU-AVEON-2026-TN-50002 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10099-002 | PIPING_ISOMETRIC_DRAWING: 4-PM-083101-120-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10099-003 | PIPING_ISOMETRIC_DRAWING: 4-PM-083101-120-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10099-004 | PIPING_ISOMETRIC_DRAWING: 4-PM-083101-120-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10099-005 | PIPING_ISOMETRIC_DRAWING: 4-PM-083101-120-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10100 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-UW-513772-80-G | PIPING | MP - PIPING | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10101 | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-DN-473811-40-AW | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  | FAB-MABU-AVEON-2026-TN-50002 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10101-001 | PIPING ISOMETRIC DRAWING: 8-DN-473811-40-AW | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10101-002 | PIPING ISOMETRIC DRAWING: 8-DN-473811-40-AW | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10101-003 | PIPING ISOMETRIC DRAWING: 8-DN-473811-40-AW | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10101-004 | PIPING ISOMETRIC DRAWING: 8-DN-473811-40-AW | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10101-005 | PIPING ISOMETRIC DRAWING: 8-DN-473811-40-AW | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10102 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473812-40-AW | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10102-001 | PIPING ISOMETRIC DRAWING-4-DN-473812-40-AW | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10103 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-1/2"-CM-423045-160S-J3 | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10103-002 | PIPING_ISOMETRIC_DRAWING: 1-1/2-CM-423045-160S-J3 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10103-003 | PIPING_ISOMETRIC_DRAWING: 1-1/2-CM-423045-160S-J4 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10104 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473813-40-AW | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10104-001 | PIPING ISOMETRIC DRAWING-4-DN-473813-40-AW | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10105 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-PG-313045-750-F1-1H | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10105-001 | PIPING_ISOMETRIC_DRAWING: 4-PG-313045-750-F1-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10105-002 | PIPING_ISOMETRIC_DRAWING: 4-PG-313045-750-F1-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10105-003 | PIPING_ISOMETRIC_DRAWING: 4-PG-313045-750-F1-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10105-004 | PIPING_ISOMETRIC_DRAWING: 4-PG-313045-750-F1-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10106 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-CM-423046-160S-J3 | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10107 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-PG-313046-750-FLT-1H | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10107-001 | PIPING_ISOMETRIC_DRAWING: 4-PG-313046-750-FLT-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10107-002 | PIPING_ISOMETRIC_DRAWING: 4-PG-313046-750-FLT-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10107-003 | PIPING_ISOMETRIC_DRAWING: 4-PG-313046-750-FLT-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10107-004 | PIPING_ISOMETRIC_DRAWING: 4-PG-313046-750-FLT-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10108 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-CM-423047-160S-J3 | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10109 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-PG-313047-750-FFLT-1H | PIPING | MP - PIPING | C02 | SIM | AFC 3A |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  | FAB-MABU-AVEON-2026-TN-50002 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10109-001 | PIPING_ISOMETRIC_DRAWING: 4-PG-313047-750-FFLT-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10109-002 | PIPING_ISOMETRIC_DRAWING: 4-PG-313047-750-FFLT-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10109-003 | PIPING_ISOMETRIC_DRAWING: 4-PG-313047-750-FFLT-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10109-004 | PIPING_ISOMETRIC_DRAWING: 4-PG-313047-750-FFLT-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10109-005 | PIPING_ISOMETRIC_DRAWING: 4-PG-313047-750-FFLT-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10109-006 | PIPING_ISOMETRIC_DRAWING: 4-PG-313047-750-FFLT-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10109-007 | PIPING_ISOMETRIC_DRAWING: 4-PG-313047-750-FFLT-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10109-008 | PIPING_ISOMETRIC_DRAWING: 4-PG-313047-750-FFLT-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10109-009 | PIPING_ISOMETRIC_DRAWING: 4-PG-313047-750-FFLT-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10109-010 | PIPING_ISOMETRIC_DRAWING: 4-PG-313047-750-FFLT-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10110 | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-PG-313048-"750"-F1-1H | PIPING | MP - PIPING | C01 | SIM | AFC 3A |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  | FAB-MABU-AVEON-2026-TN-50002 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10110-001 | PIPING ISOMETRIC DRAWING: 3"-PG-313048-"750"-F1-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10111 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-PG-313048-750-F1-1H | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10111-001 | PIPING_ISOMETRIC_DRAWING: 4-PG-313048-750-F1-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10111-002 | PIPING_ISOMETRIC_DRAWING: 4-PG-313048-750-F1-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10111-003 | PIPING_ISOMETRIC_DRAWING: 4-PG-313048-750-F1-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10111-004 | PIPING_ISOMETRIC_DRAWING: 4-PG-313048-750-F1-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10112 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-PG-313049-750-FLT-1H | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10112-001 | PIPING_ISOMETRIC_DRAWING: 4-PG-313049-750-FLT-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10112-002 | PIPING_ISOMETRIC_DRAWING: 4-PG-313049-750-FLT-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10112-003 | PIPING_ISOMETRIC_DRAWING: 4-PG-313049-750-FLT-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10112-004 | PIPING_ISOMETRIC_DRAWING: 4-PG-313049-750-FLT-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10112-005 | PIPING_ISOMETRIC_DRAWING: 4-PG-313049-750-FLT-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10113 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-PG-313050-750-FFLT-1H | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10113-001 | PIPING_ISOMETRIC_DRAWING: 4-PG-313050-750-FFLT-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10113-002 | PIPING_ISOMETRIC_DRAWING: 4-PG-313050-750-FFLT-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10113-003 | PIPING_ISOMETRIC_DRAWING: 4-PG-313050-750-FFLT-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10113-004 | PIPING_ISOMETRIC_DRAWING: 4-PG-313050-750-FFLT-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10113-005 | PIPING_ISOMETRIC_DRAWING: 4-PG-313050-750-FFLT-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10113-006 | PIPING_ISOMETRIC_DRAWING: 4-PG-313050-750-FFLT-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10113-007 | PIPING_ISOMETRIC_DRAWING: 4-PG-313050-750-FFLT-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10113-008 | PIPING_ISOMETRIC_DRAWING: 4-PG-313050-750-FFLT-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10113-009 | PIPING_ISOMETRIC_DRAWING: 4-PG-313050-750-FFLT-1H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10114 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-083093-XXS-IFJ | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10114-001 | PIPING_ISOMETRIC_DRAWING: 2"-PM-083093-XXS-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10115-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 6"-FG-443083-40S-SSB | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10116-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-PM-043092-100-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10117 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-1/2"-PM-083096-XXS-CC | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | BNO-DED-MABU-AVEON-2026-TN-10018 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10117-001 | PIPING_ISOMETRIC_DRAWING: 1-1/2-PM-083096-XXS-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10117-002 | PIPING_ISOMETRIC_DRAWING: 1-1/2-PM-083096-XXS-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10117-003 | PIPING_ISOMETRIC_DRAWING: 1-1/2-PM-083096-XXS-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10118 | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-WI-403103-30-63861 | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10118-001 | PIPING ISOMETRIC DRAWING-12-WI-403103-30-63862 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10119 | PIPING CONSTRUCT ISOMETRIC DRAWING: 24"-BH-463001-STD-ALT | PIPING | MP - PIPING | C02 | SIM | AFC 3A |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  | BNO-DED-MABU-AVEON-2026-TN-10019 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10120-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-PM-043099-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10121-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-FG-443100-40S-SSB-ET | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10122-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-FG-443100-40S-SSB-ET | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10123 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-FG-443100-40S-SSB-ET | PIPING | MP - PIPING | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10123-002 | PIPING_ISOMETRIC_DRAWING: 4-FG-443100-40S-SSB-ET | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10123-003 | PIPING_ISOMETRIC_DRAWING: 4-FG-443100-40S-SSB-ET | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10123-004 | PIPING_ISOMETRIC_DRAWING: 4-FG-443100-40S-SSB-ET | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10123-005 | PIPING_ISOMETRIC_DRAWING: 4-FG-443100-40S-SSB-ET | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10124 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-FG-443101-80-B-P | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  | FAB-MABU-AVEON-2026-TN-50002 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10125-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-PM-083103-XXS-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10126-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-043103-"1125"-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10127 | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-DN-483104-STD-H | PIPING | MP - PIPING | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10127-001 | PIPING_ISOMETRIC_DRAWING: 12-DN-483104-STD-H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10127-002 | PIPING_ISOMETRIC_DRAWING: 12-DN-483104-STD-H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10128 | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-PM-043104-100-IFJ | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10128-002 | PIPING_ISOMETRIC_DRAWING: 14-PM-043104-100-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10128-003 | PIPING_ISOMETRIC_DRAWING: 14-PM-043104-100-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10129-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-DN-83105-STD-H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10130 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-1/2"-PM-083105-XXS-CC | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50002 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10130-002 | PIPING ISOMETRIC DRAWING-1-1-2-PM-083105-XXS-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10130-003 | PIPING ISOMETRIC DRAWING-1-1-2-PM-083105-XXS-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10130-004 | PIPING ISOMETRIC DRAWING-1-1-2-PM-083105-XXS-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10131 | PIPING CONSTRUCT ISOMETRIC DRAWING: 6"-PM-043105-1125-JJ | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50006 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10131-001 | PIPING_ISOMETRIC_DRAWING: 6-PM-043105-1125-JJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10131-002 | PIPING_ISOMETRIC_DRAWING: 6-PM-043105-1125-JJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10131-003 | PIPING_ISOMETRIC_DRAWING: 6-PM-043105-1125-JJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10131-004 | PIPING_ISOMETRIC_DRAWING: 6-PM-043105-1125-JJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10131-005 | PIPING_ISOMETRIC_DRAWING: 6-PM-043105-1125-JJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10132 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-083106-XXS-CC | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10132-001 | PIPING ISOMETRIC DRAWING: 2"-PM-083106-XXS-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10133 | PIPING CONSTRUCT ISOMETRIC DRAWING: 6"-PM-043106-120-IFJ | PIPING | MP - PIPING | C02 | SIM | AFC 3A |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  | BNO-DED-MABU-AVEON-2026-TN-10019 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10133-001 | PIPING_ISOMETRIC_DRAWING: 6-PM-043106-1125-JJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10134 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-1/2"-PM-083107-XXS-CC | PIPING | MP - PIPING | C02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10134-001 | PIPING_ISOMETRIC_DRAWING: 1-1/2-PM-083107-XXS-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10134-002 | PIPING_ISOMETRIC_DRAWING: 1-1/2-PM-083107-XXS-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10135 | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-PM-043107-1800-IFJ | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | BNO-DED-MABU-AVEON-2026-TN-10019 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10135-001 | PIPING_ISOMETRIC_DRAWING: 12-PM-043107-1800-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10135-002 | PIPING_ISOMETRIC_DRAWING: 12-PM-043107-1800-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10135-003 | PIPING_ISOMETRIC_DRAWING: 12-PM-043107-1800-IF | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10135-004 | PIPING_ISOMETRIC_DRAWING: 12-PM-043107-1800-IF | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10135-005 | PIPING_ISOMETRIC_DRAWING: 12-PM-043107-1800-IF | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10135-006 | PIPING_ISOMETRIC_DRAWING: 12-PM-043107-1800-IF | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10135-007 | PIPING_ISOMETRIC_DRAWING: 12-PM-043107-1800-IF | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10136 | PIPING CONSTRUCT ISOMETRIC DRAWING: 10"-PM-043108-120-CC | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | BNO-DED-MABU-AVEON-2026-TN-10019 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10136-001 | PIPING_ISOMETRIC_DRAWING: 10-PM-043108-120-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10136-002 | PIPING_ISOMETRIC_DRAWING: 10-PM-043108-120-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10136-003 | PIPING_ISOMETRIC_DRAWING: 10-PM-043108-120-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10137 | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-PM-043109-100-CC | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10137-001 | PIPING_ISOMETRIC_DRAWING: 14-PM-043109-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10137-002 | PIPING_ISOMETRIC_DRAWING: 14-PM-043109-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10137-003 | PIPING_ISOMETRIC_DRAWING: 14-PM-043109-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10137-004 | PIPING_ISOMETRIC_DRAWING: 14-PM-043109-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10137-005 | PIPING_ISOMETRIC_DRAWING: 14-PM-043109-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10137-006 | PIPING_ISOMETRIC_DRAWING: 14-PM-043109-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10137-007 | PIPING_ISOMETRIC_DRAWING: 14-PM-043109-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10138 | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-PM-043110-100-CC | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10138-001 | PIPING_ISOMETRIC_DRAWING: 12-PM-043110-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10138-002 | PIPING_ISOMETRIC_DRAWING: 12-PM-043110-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10138-003 | PIPING_ISOMETRIC_DRAWING: 12-PM-043110-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10138-004 | PIPING_ISOMETRIC_DRAWING: 12-PM-043110-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10139 | PIPING CONSTRUCT ISOMETRIC DRAWING: 10"-PM-043112-"1562"-IF | PIPING | MP - PIPING | C02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10139-001 | PIPING ISOMETRIC DRAWING: 12"-PM-043112-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10140 | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-PM-043113-120-IFJ | PIPING | MP - PIPING | C02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10140-002 | PIPING_ISOMETRIC_DRAWING: 8"-PM-043113-120-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10141 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1/2"-PM-043111-100-CC | PIPING | MP - PIPING | C02 | SIM | AFC 3A |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  | FAB-MABU-AVEON-2026-TN-50002 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10141-001 | PIPING_ISOMETRIC_DRAWING: 1/2-PM-043111-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10141-002 | PIPING_ISOMETRIC_DRAWING: 1/2-PM-043111-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10141-003 | PIPING_ISOMETRIC_DRAWING: 1/2-PM-043111-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10142 | PIPING CONSTRUCT ISOMETRIC DRAWING: 3/4"-PM-043115-80-B | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50006 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10143 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1/2"-PM-043116-0.31-CC | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50002 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10143-002 | PIPING_ISOMETRIC_DRAWING: 1/2"-PM-043116-0.31-CC | PIPING | MP - PIPING | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10143-003 | PIPING_ISOMETRIC_DRAWING: 1/2"-PM-043116-0.31-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10144-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1/2"-PM-038674-0.31-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10145-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 3/4"-PM-038675-80-B | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10146-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 10"-PL-43118-80-C-H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10147-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 10"-PL-43119-80-C-H | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10148-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-WI-403139-"1125"-F | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10149-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-WI-403139-"1125"-F | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10150-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 3/4"-DN-483205-80-AW | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10151-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-BH-463205-80-A | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10152-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 6"-DN-483206-40-AW | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10153-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-483210-40-AW | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10154-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-483211-40-AW | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10155-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 16"-WI-403225-10S-13841 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10156-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-WI-403226-30-63861 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10157 | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-WI-403227-2000-J1 | PIPING | MP - PIPING | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10157-002 | PIPING_ISOMETRIC_DRAWING: 14-WI-403227-2000-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10157-003 | PIPING_ISOMETRIC_DRAWING: 14-WI-403227-2000-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10157-004 | PIPING_ISOMETRIC_DRAWING: 14-WI-403227-2000-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10157-005 | PIPING_ISOMETRIC_DRAWING: 14-WI-403227-2000-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10157-006 | PIPING_ISOMETRIC_DRAWING: 14-WI-403227-2000-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10157-007 | PIPING_ISOMETRIC_DRAWING: 14-WI-403227-2000-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10157-008 | PIPING_ISOMETRIC_DRAWING: 14-WI-403227-2000-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10157-009 | PIPING_ISOMETRIC_DRAWING: 14-WI-403227-2000-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10157-010 | PIPING_ISOMETRIC_DRAWING: 14-WI-403227-2000-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10157-011 | PIPING_ISOMETRIC_DRAWING: 14-WI-403227-2000-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10157-012 | PIPING_ISOMETRIC_DRAWING: 14-WI-403227-2000-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10157-013 | PIPING_ISOMETRIC_DRAWING: 14-WI-403227-2000-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10157-014 | PIPING_ISOMETRIC_DRAWING: 14-WI-403227-2000-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10158 | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-WI-403229-2205-251432 | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | TRANSMITTAL |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10158-002 | PIPING_ISOMETRIC_DRAWING: 12-WI-403229-2205-251432 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10158-003 | PIPING_ISOMETRIC_DRAWING: 12-WI-403229-2205-251432 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10159 | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-WI-403230-2000-J1 | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50004 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10159-002 | PIPING_ISOMETRIC_DRAWING: 14-WI-403230-2000-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10159-003 | PIPING_ISOMETRIC_DRAWING: 14-WI-403230-2000-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10159-004 | PIPING_ISOMETRIC_DRAWING: 14-WI-403230-2000-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10159-005 | PIPING_ISOMETRIC_DRAWING: 14-WI-403230-2000-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10159-006 | PIPING_ISOMETRIC_DRAWING: 14-WI-403230-2000-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10159-007 | PIPING_ISOMETRIC_DRAWING: 14-WI-403230-2000-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10160 | PIPING CONSTRUCT ISOMETRIC DRAWING: 6"-WI-403231-"1000"-J1 | PIPING | MP - PIPING | C02 | SIM | AFC 3A |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  | FAB-MABU-AVEON-2026-TN-50004 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10160-002 | PIPING_ISOMETRIC_DRAWING: 6-WI-403231-"1000"-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10160-003 | PIPING_ISOMETRIC_DRAWING: 6-WI-403231-"1000"-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10161-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-VA-403232-80-AV | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10162 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-LO-403236-40S-SS-P | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10162-002 | PIPING_ISOMETRIC_DRAWING: 4-LO-403236-40S-SS-P | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10162-003 | PIPING_ISOMETRIC_DRAWING: 4-LO-403236-40S-SS-P | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10162-004 | PIPING_ISOMETRIC_DRAWING: 4-LO-403236-40S-SS-P | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10163-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1/2"-VA-403237-40S-SS-P | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10164 | PIPING CONSTRUCT ISOMETRIC DRAWING: 3/4"-VA-403237-40S-SS-P | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  | FAB-MABU-AVEON-2026-TN-50002 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10164-002 | PIPING_ISOMETRIC_DRAWING: 3/4-VA-403237-40S-SS-P | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10164-003 | PIPING_ISOMETRIC_DRAWING: 3/4-VA-403237-40S-SS-P | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10165 | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-WI-403239-2000-J1 | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50007 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10166 | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-WI-403240-1771-J1 | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10166-002 | PIPING_ISOMETRIC_DRAWING: 14-WI-403240-1771-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10166-003 | PIPING_ISOMETRIC_DRAWING: 14-WI-403240-1771-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10166-004 | PIPING_ISOMETRIC_DRAWING: 14-WI-403240-1771-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10166-005 | PIPING_ISOMETRIC_DRAWING: 14-WI-403240-1771-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10166-006 | PIPING_ISOMETRIC_DRAWING: 14-WI-403240-1771-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10167 | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-WI-403241-2000-J1 | PIPING | MP - PIPING | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10167-002 | PIPING_ISOMETRIC_DRAWING: 14-WI-403241-2000-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10167-003 | PIPING_ISOMETRIC_DRAWING: 14-WI-403241-2000-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10167-004 | PIPING_ISOMETRIC_DRAWING: 14-WI-403241-2000-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10167-005 | PIPING_ISOMETRIC_DRAWING: 14-WI-403241-2000-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10167-006 | PIPING_ISOMETRIC_DRAWING: 14-WI-403241-2000-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10167-007 | PIPING_ISOMETRIC_DRAWING: 14-WI-403241-2000-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10167-008 | PIPING_ISOMETRIC_DRAWING: 14-WI-403241-2000-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10167-009 | PIPING_ISOMETRIC_DRAWING: 14-WI-403241-2000-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10167-010 | PIPING_ISOMETRIC_DRAWING: 14-WI-403241-2000-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10167-011 | PIPING_ISOMETRIC_DRAWING: 14-WI-403241-2000-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10167-012 | PIPING_ISOMETRIC_DRAWING: 14-WI-403241-2000-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10167-013 | PIPING_ISOMETRIC_DRAWING: 14-WI-403241-2000-J1 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10168 | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-WI-403244-2205-251432 | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  | FAB-MABU-AVEON-2026-TN-50002 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10168-002 | PIPING_ISOMETRIC_DRAWING: 12-WI-403244-2205-251432 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10169 | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-WI-403246-140-253841A | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50007 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10170 | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-WI-403248-140-253841A | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10170-001 | PIPING ISOMETRIC DRAWING: 12"-WI-403248-"2000"-253841A | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10171-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-WI-403251-"1890"-251432 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10172 | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-WI-403251-1890-251432 | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10172-002 | PIPING_ISOMETRIC_DRAWING: 8-WI-403251-1890-251433 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10172-003 | PIPING_ISOMETRIC_DRAWING: 8-WI-403251-1890-251434 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10173 | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-WI-403252-1890-251432 | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | TRANSMITTAL |  |  | FAB-MABU-AVEON-2026-TN-50002 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10173-002 | PIPING_ISOMETRIC_DRAWING: 8-WI-403252-1890-251432 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10174 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-WI-403254-866-251432 | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50007 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10175 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-WI-403255-866-251432 | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50007 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10176 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-WI-403256-866-251432 | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10176-001 | PIPING ISOMETRIC DRAWING: 4"-WI-403256-"866"-251432 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10177 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-WI-403257-866-251432 | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10177-001 | PIPING ISOMETRIC DRAWING: 4"-WI-403257-"866"-251432 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10178 | PIPING CONSTRUCT ISOMETRIC DRAWING: 16"-WI-403259-1900-F | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10178-002 | PIPING_ISOMETRIC_DRAWING: 16-WI-403259-1900-F | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10179-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 3/4"-IA-503287-80-G | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10180-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-IA-503288-80-G | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10181 | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-BH-463370-STD-ALT | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50006 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10181-001 | PIPING_ISOMETRIC_DRAWING: 14-BH-463370-STD-ALT | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10181-002 | PIPING_ISOMETRIC_DRAWING: 14-BH-463370-STD-ALT | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10181-003 | PIPING_ISOMETRIC_DRAWING: 14-BH-463370-STD-ALT | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10182-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-BH-463372-80-A | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10183 | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-BH-463376-STD-ALT | PIPING | MP - PIPING | C01 | SIM | AFC 3A |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  | FAB-MABU-AVEON-2026-TN-50002 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10183-001 | PIPING ISOMETRIC DRAWING: 14"-BH-463376-STD-ALT | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10184 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-BH-463382-750-FFLT-P | PIPING | MP - PIPING | C02 | SIM | AFC 3A |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  | FAB-MABU-AVEON-2026-TN-50002 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10184-001 | PIPING_ISOMETRIC_DRAWING: 4-BH-463382-750-FFLT-P | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10184-002 | PIPING_ISOMETRIC_DRAWING: 4-BH-463382-750-FFLT-P | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10184-003 | PIPING_ISOMETRIC_DRAWING: 4-BH-463382-750-FFLT-P | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10184-004 | PIPING_ISOMETRIC_DRAWING: 4-BH-463382-750-FFLT-P | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10185 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-BH-463385-750-FFLT-P | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10185-002 | PIPING_ISOMETRIC_DRAWING: 4-BH-463385-750-FFLT-P | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10185-003 | PIPING_ISOMETRIC_DRAWING: 4-BH-463385-750-FFLT-P | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10185-004 | PIPING_ISOMETRIC_DRAWING: 4-BH-463385-750-FFLT-P | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10185-005 | PIPING_ISOMETRIC_DRAWING: 4-BH-463385-750-FFLT-P | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10186 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-BH-463389-80-A-P | PIPING | MP - PIPING | C02 | SIM | AFC 3A |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  | FAB-MABU-AVEON-2026-TN-50002 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10186-001 | PIPING_ISOMETRIC_DRAWING: 2-BH-463389-80-A-P | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10186-002 | PIPING_ISOMETRIC_DRAWING: 2-BH-463389-80-A-P | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10186-003 | PIPING_ISOMETRIC_DRAWING: 2-BH-463389-80-A-P | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10186-004 | PIPING_ISOMETRIC_DRAWING: 2-BH-463389-80-A-P | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10187-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-BH-463389-80-A-P | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10188 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473619-40-G | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10189 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473628-40-G | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10190-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 3/4"-UW-513771-80-G | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10191-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 24"-PM-038674-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10192-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: 16"-PM-038675-100-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10193 | PIPING CONSTRUCT ISOMETRIC DRAWING: TAM26-TP-01 16"-PM-038675-100-CC | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10194-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: TP-02 14"-PM-033031-100-CC | PIPING | MP - PIPING | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10195-001 | PIPING CONSTRUCT ISOMETRIC DRAWING: TP-03 14"-PM-033030-100-CC | PIPING | MP - PIPING | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10196 | PIPING CONSTRUCT ISOMETRIC DRAWING: TAM26-TP-04 24"-PM-038674-100-CC | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10197 | PIPING CONSTRUCT ISOMETRIC DRAWING: TAM26-TP-05 12"-PL-043002-80-C-1-1-2H | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10198 | PIPING CONSTRUCT ISOMETRIC DRAWING: TAM26-TP-06 10"-PL-043005-80-C-1-1- | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10199 | PIPING CONSTRUCT ISOMETRIC DRAWING: TAM26-TP-07 4"-PG-313045-750-F1-1H. | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10200 | PIPING CONSTRUCT ISOMETRIC DRAWING: TAM26-TP-08 4"-PG-313048-750-F1-1H | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10201 | PIPING CONSTRUCT ISOMETRIC DRAWING: TAM26-TP25-26-56 3"-CC-423005-40S-S | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10202 | PIPING CONSTRUCT ISOMETRIC DRAWING: TAM26-TP-28A-28B 2"-WI-403065-STD-A | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10203 | PIPING CONSTRUCT ISOMETRIC DRAWING: TAM26_TP-49 AND 50 2"-BH-463389-80-A-P. | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10204 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-PM-083092-120-IFJ | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10204-002 | PIPING_ISOMETRIC_DRAWING: 4-PM-083092-120-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10205 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-083104-XXS-IFJ | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10205-001 | PIPING_ISOMETRIC_DRAWING: 2-PM-083104-XXS-IFJ | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10206 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-PM-A-0820J-N7 | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10207 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-PM-A-0820K-N7 | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10208 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-A-0820J_K1 | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10209 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-A-0820J_K2 | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10210 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-A-0820K_K1 | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10211 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-A-0820K_K2 | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10212 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-UW-513033-80-G | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10213 | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-DN-473034-STD-H | PIPING | MP - PIPING | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10214 | PIPING CONSTRUCT ISOMETRIC DRAWING: 6"-FG-443007-40S-SSB-ET | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10215 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1/2"-PM-043118-0.31-CC | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10215-002 | PIPING ISOMETRIC DRAWING: 1/2-PM-043118-0.31-CC | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10216 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1/2"-PM-043119-0.31-CC | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10217 | PIPING CONSTRUCT ISOMETRIC DRAWING: 10"-DN-473801-40-AW | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10218 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-BH-443102-80-B-P | PIPING | MP - PIPING | C02 | SIM | AFC 3A |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  | FAB-MABU-AVEON-2026-TN-50002 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10219 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-WF-613800-200-MV | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10220 | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-WF-613079-200-MVB | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10221 | PIPING CONSTRUCT ISOMETRIC DRAWING: 24"-WI-403065-STD-AW | PIPING | MP - PIPING | C02 | SIM | AFC 3A |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  | FAB-MABU-AVEON-2026-TN-50002 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10222 | PIPING CONSTRUCT ISOMETRIC DRAWING: 6"-CM-423002-40S-SS | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10223 | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-CM-423021-40S-SS | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10224 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-DN-473372-STD-H | PIPING | MP - PIPING | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10225 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-IA-503501-80-G | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50007 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10226 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-IA-503502-80-G | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  | FAB-MABU-AVEON-2026-TN-50002 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10227 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-IA-503503-80-G | PIPING | MP - PIPING | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10228 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-IA-503504-80-G | PIPING | MP - PIPING | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10229 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-IA-503505-80-G | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50003 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10230 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-IA-503506-80-G | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10231 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-IA-503507-80-G | PIPING | MP - PIPING | C03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50007 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10232 | PIPING CONSTRUCT ISOMETRIC DRAWING: 6"-CM-423048-40S-SS | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50007 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10233 | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-CM-423049-40S-S | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50007 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10234 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-1/2"-CM-423050-"281"-J | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  | FAB-MABU-AVEON-2026-TN-50007 | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10235 | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-DN-473373-STD-H | PIPING | MP - PIPING | C01 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10236 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-IA-503508-80-G | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10237 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-IA-503509-80-G | PIPING | MP - PIPING | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10246 | PIPING CONSTRUCT ISOMETRIC DRAWING 6"-DN-473139-STD-H | PIPING | MP - PIPING | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10247 | PIPING CONSTRUCT ISOMETRIC DRAWING 6"-DN-473048-STD-H | PIPING | MP - PIPING | A01 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10248 | PIPING CONSTRUCT ISOMETRIC DRAWING 2"-DN-473634-80-G | PIPING | MP - PIPING | A01 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10249 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-1/2-DN-488837-160S-253841A | PIPING | MP - PIPING | A01 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10250 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-1/2-DN-483817-160S-253841A | PIPING | MP - PIPING | A01 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10251 | PIPING CONSTRUCT ISOMETRIC DRAWING-2"-CM-423014-XXS-J | PIPING | MP - PIPING | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10252 | PIPING CONSTRUCT ISOMETRIC DRAWING-1"-UW-513779-80-G | PIPING | MP - PIPING | A01 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10253 | PIPING CONSTRUCT ISOMETRIC DRAWING 6"-VA-403235-40S-SS | PIPING | MP - PIPING | A01 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10254 | PIPING CONSTRUCT ISOMETRIC DRAWING 3"-CM-423051-40S-SS | PIPING | MP - PIPING | A01 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10255 | PIPING CONSTRUCT ISOMETRIC DRAWING-2-IA- 503082-80-G | PIPING | MP - PIPING | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10256 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2-DN-473635-80-G | PIPING | MP - PIPING | A01 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10257 | PIPING CONSTRUCT ISOMETRIC DRAWING 2"-DN-473379-80-G | PIPING | MP - PIPING | A01 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10258 | PIPING CONSTRUCT ISOMETRIC DRAWING 2"-DN-473377-STD-H | PIPING | MP - PIPING | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10259 | PIPING CONSTRUCT ISOMETRIC DRAWING 2"-DN-473380-80-G | PIPING | MP - PIPING | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10260 | PIPING CONSTRUCT ISOMETRIC DRAWING-2-DN-473378-STD-H | PIPING | MP - PIPING | A01 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10261 | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313051-750-FFLT-1H | PIPING | MP - PIPING | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10262 | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313055-750-FFLT-1H | PIPING | MP - PIPING | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10263 | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313058-750-FFLT-1H | PIPING | MP - PIPING | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10264 | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313054-750-FFLT-1H | PIPING | MP - PIPING | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10265 | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313057-750-FFLT-1H | PIPING | MP - PIPING | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10266 | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313053-750-FFLT-1H | PIPING | MP - PIPING | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10267 | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313052-750-FFLT-1H | PIPING | MP - PIPING | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10268 | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313056-750-FFLT-1H | PIPING | MP - PIPING | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10269 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-DN-483103-80-AW | PIPING | MP - PIPING | A01 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10270 | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1/2"-DN-433637-80-G | PIPING | MP - PIPING | A01 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2343-10272 | PIPING CONSTRUCT ISOMETRIC DRAWING-1"-IA-503289-80-G | PIPING | MP - PIPING | A01 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2358-10001-001 | PRODUCTION FLOWLINE INTERFACE HOOKUP DRAWINGS | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2358-10002-001 | WATER INJECTION FLOWLINE INTERFACE HOOKUP DRAWINGS | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2358-10002-002 | WATER INJECTION FLOWLINE INTERFACE HOOKUP DRAWINGS | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2358-10003-001 | TOPSIDE GAS LIFT INTERFACE HOOKUP DRAWINGS | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2358-10004 | PIPING SPECIALTY ITEM LIST | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2358-10004-001 | WATERFLOOD SYSTEM INTERFACE HOOKUP DRAWINGS | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2358-10004-002 | WATERFLOOD SYSTEM INTERFACE HOOKUP DRAWINGS | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2358-10005-001 | DIESEL AND FUEL GAS SYSTEM HOOKUP DRAWING | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-2358-10015-001 | PIPING SUPPORT DRAWINGS | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-3323-10001 | TBE FOR STUD BOLTS AND NUTS | PIPING | MP - PIPING | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-3323-10002 | TBE FOR FITTINGS | PIPING | MP - PIPING | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 | IDC - INTERNAL COMMENTS |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-3323-10003 | TBE FOR FLANGES | PIPING | MP - PIPING | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-3323-10004 | TECHNICAL BID EVALUATION FOR GASKETS | PIPING | MP - PIPING | R01 | SIM | IFR |  | ISSUED |  | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-3323-10005 | TBE FOR PIPES | PIPING | MP - PIPING | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-3323-10006 | TBE FOR VA LVES | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-3323-10007 | TBE FOR SPRING SUPPORTS | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-3323-10008 | TBE FOR PRODUCTION & GAS LIFT HEAVY WALL PIPING | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-3323-10009 | TBE FOR PIPING SPECIAL ITEMS | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-3323-10010 | TBE FOR WI HEAVY WALL INCONEL CLAD PIPING & FITTINGS | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-3323-10011 | TBE FOR PIPING SUPPORT MATERIALS | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-3323-10012 | TBE FOR SPECIAL VALVES | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-3323-10013 | TBE FOR HUB CONNECTOR (GRAYLOC) | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-3323-10014 | TBE FOR BARRED TEES | PIPING | MP - PIPING | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-3323-10015 | TECHNICAL BID EVALUATION FOR STRAINER | PIPING | MP - PIPING | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-3323-10016 | TBE FOR VALVE & DOOR INTERLOCKING SYSTEM FOR PIG LAUNCHING & RECEIVING | PIPING | MP - PIPING | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4018-10001-001 | PIPE SUPPORT STANDARD COMPONENTS DETAILS | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4018-10002-001 | PIPING PLAN (STARBOARD SUBSEA MODULE) PLAN @ LEVEL 2 (T.O.S EL.+114.802M) METHANOL INJECTION PUMP | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4018-10003-001 | PIPING PLAN & ELEVATION (STARBOARD SUBSEA MODULE) ELEVATION LOOKING NORTH - HYDRAULIC POWER / METHANOL INJECTION PUMP / PIGS L-R | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4018-10004-001 | PIPING PLAN & ELEVATION (PORT SUBSEA MODULE) ELEVATION LOOKING SOUTH - SWITCH GEAR AND SUBSEA CONTROL BUILDING | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4018-10005-001 | PIPING PLAN & ELEVATION (PORT SUBSEA MODULE) ELEVATION LOOKING EAST - SWITCH GEAR AND SUBSEA CONTROL BUILDING / CORROSION INHIBITOR INJECTION PUMP SKID | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4018-10006-001 | PIPING PLAN & ELEVATION (STARBOARD SUBSEA MODULE) PLAN @ LEVEL 1 (T.O.S EL.+105.182M) - PIG LAUCHER AND RECEIVER | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4018-10007-001 | PIPING PLAN & ELEVATION (STARBOARD SUBSEA MODULE) PLAN @ LEVEL 2 (T.O.S EL.+114.802M) - METHANOL INJECTION PUMP | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4018-10007-002 | PIPING PLAN & ELEVATION (STARBOARD SUBSEA MODULE) PLAN @ LEVEL 3 (T.O.S. EL.+119.300M) METHANOL INJECTION PUMP | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4018-10008-001 | PIPING PLAN & ELEVATION (STARBOARD SUBSEA MODULE) PLAN @ MAIN DECK (T.O.S EL.+99.059M) - RISER AREA | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4018-10008-002 | PIPING PLAN & ELEVATION (STARBOARD SUBSEA MODULE) PLAN @ MAIN DECK (T.O.S EL.+99.059M) - RISER AREA | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4018-10009-001 | PIPING PLAN & ELEVATION (PORT SUBSEA MODULE) PLAN @ LEVEL 2 (T.O.S EL.+114.802M) - SWITCH GEAR AND SUBSEA CONTROL BUILDING | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4018-10010-001 | PIPING PLAN & ELEVATION (PORT SUBSEA MODULE) PLAN @ MEZZANINE (T.O.S EL.+109.800M) - CORROSIN INHIBITOR INJECTION PUMP SKID | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4018-10011-001 | PIPING PLAN & ELEVATION (MAIN RACK 2) ELEVATION LOOKING SOUTH - WATERFLOOD INJECTION PUMP / TURBINE SYSTEM | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4018-10012-001 | PIPING PLAN & ELEVATION (MAIN RACK 2) PLAN AT LEVEL 2 - WATERFLOOD INJECTION PUMP / TURBINE SYSTEM | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4018-10013-001 | PIPING PLAN & ELEVATION (PORT SUBSEA MODULE) MEZZANINE DECK | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4018-10014-001 | PIPING PLAN & ELEVATION (STARBOARD MODULE) MEZZANINE DECK | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4018-10015-001 | PIPING PLAN & ELEVATION (MAIN RACK 2) PLAN AT LEVEL-3 WATERFLOOD | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4018-10016-001 | PIPING PLAN & ELEVATION (STARBOARD SUBSEA MODULE) PLAN @ LEVEL 1 (T.O.S EL.+105.182M) - PRODUCTION MANIFOLD | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4024-10001-001 | PLOT PLAN LAYOUT (OVERALL) | PIPING | MP - PIPING | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4033-10001-001 | EQUIPMENT LAYOUT (STARBOARD SUBSEA MODULE) ELEVATION LOOKING EAST - HYDRAULIC POWER / METHANOL INJECTION PUMP / PIGS L-R | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4033-10002-001 | EQUIPMENT LAYOUT (STARBOARD SUBSEA MODULE) ELEVATION LOOKING NORTH - HYDRAULIC POWER / METHANOL INJECTION PUMP / PIGS L-R | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4033-10003-001 | EQUIPMENT LAYOUT (PORT SUBSEA MODULE) ELEVATION LOOKING SOUTH - SWITCH GEAR AND SUBSEA CONTROL BUILDING | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4033-10004-001 | EQUIPMENT LAYOUT (PORT SUBSEA MODULE) ELEVATION LOOKING EAST - SWITCH GEAR AND SUBSEA CONTROL BUILDING / CORROSION INHIBITOR INJECTION PUMP SKID | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4033-10005-001 | EQUIPMENT LAYOUT (STARBOARD SUBSEA MODULE) PLAN @ LEVEL 1 (T.O.S EL.+105.182M) - PIG LAUCHER AND RECEIVER | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4033-10006-001 | EQUIPMENT LAYOUT (STARBOARD SUBSEA MODULE) PLAN @ LEVEL 2 (T.O.S EL.+114.802M) - METHANOL INJECTION PUMP | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4033-10007-001 | EQUIPMENT LAYOUT (STARBOARD SUBSEA MODULE) PLAN @ MAIN DECK (T.O.S EL.+99.059M) - RISER AREA | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4033-10008-001 | EQUIPMENT LAYOUT (PORT SUBSEA MODULE) PLAN @ LEVEL 2 (T.O.S EL.+114.802M) - SWITCH GEAR AND SUBSEA CONTROL BUILDING | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4033-10009-001 | EQUIPMENT LAYOUT (PORT SUBSEA MODULE) PLAN @ MEZZANINE (T.O.S EL.+109.800M) - CORROSIN INHIBITOR INJECTION PUMP SKID | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4033-10010-001 | EQUIPMENT LAYOUT (MAIN RACK 2) ELEVATION LOOKING SOUTH - WATERFLOOD INJECTION PUMP / TURBINE SYSTEM | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4033-10011-001 | EQUIPMENT LAYOUT (MAIN RACK 2) PLAN AT LEVEL 2 - WATERFLOOD INJECTION PUMP / TURBINE SYSTEM | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4033-10012-001 | EQUIPMENT LAYOUT (STARBOARD SUBSEA MODULE) PLAN @ LEVEL 1 | PIPING | MP - PIPING | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4306-10001 | PIPE SUPPORT MTO | PIPING | MP - PIPING | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4306-10002 | TOPSIDE PIPING BULK MTO | PIPING | MP - PIPING | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4306-10003 | WI HEAVY WALL INCONEL CLAD PIPING & FITTINGS - MTO | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4306-10004 | PRODUCTION & GAS LIFT HEAVY WALL PIPING - MTO | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4306-10005 | TOPSIDES PIPING INSULATION MTO | PIPING | MP - PIPING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4337-10001 | PIPE SUPPORT LIST | PIPING | MP - PIPING | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4338-10001 | ISOMETRIC LIST | PIPING | MP - PIPING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4338-10002 | CRITICAL LINE LIST | PIPING | MP - PIPING | A02 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4338-10003 | PIPING SPECIALTY ITEM LIST | PIPING | MP - PIPING | A03 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4363-10001 | PIPING TIE-IN LIST | PIPING | MP - PIPING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-4368-10001 | VALVE LIST | PIPING | MP - PIPING | A03 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7205-10002 | ACQUISITION OF PIPE “SEAMED” SUPER DUPLEX STAINLESS STEEL. | PIPING | MP - PIPING | R01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.001-DAE_TQR
BNO-MABU-300-MP-7303-10001 | MATERIAL REQUISITION FOR BOLTS | PIPING | MP - PIPING | A03 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7303-10002 | MATERIAL REQUISITION FOR BALL VALVES | PIPING | MP - PIPING | A02 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7303-10003 | MATERIAL REQUISITION FOR FLANGES | PIPING | MP - PIPING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7303-10004 | MATERIAL REQUISITION FOR PIPES | PIPING | MP - PIPING | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7303-10005 | MATERIAL REQUISITION FOR FITTINGS | PIPING | MP - PIPING | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7303-10006 | MATERIAL REQUISITION FOR GASKETS | PIPING | MP - PIPING | A04 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7303-10007 | MATERIAL REQUISITION FOR GRAYLOCK CONNECTORS (HUBS, CLAMPS & SEAL RINGS) | PIPING | MP - PIPING | A02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7303-10008 | MATERIAL REQUISITION FOR DOUBLE BLOCK & BLEED VALVES | PIPING | MP - PIPING | A02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7303-10009 | MATERIAL REQUISITION FOR GLOBE VALVES | PIPING | MP - PIPING | A02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7303-10010 | MATERIAL REQUISITION FOR CHECK VALVES | PIPING | MP - PIPING | A02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7303-10011 | MATERIAL REQUISITION FOR GATE VALVES | PIPING | MP - PIPING | A02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7303-10012 | MATERIAL REQUISITION FOR NEEDLE VALVES | PIPING | MP - PIPING | A02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7303-10013 | MATERIAL REQUISITION FOR SPECTACLE BLANK AND PADDLE BLANK | PIPING | MP - PIPING | A03 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7303-10014 | MATERIAL REQUISITION FOR STRAINER | PIPING | MP - PIPING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7303-10015 | MATERIAL REQUISITION FOR WI HEAVY WALL INCONEL CLAD PIPING & FITTINGS | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7303-10016 | MATERIAL REQUISITION FOR SPRING SUPPORTS | PIPING | MP - PIPING | A01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7303-10017 | MATERIAL REQUISITION FOR PRODUCTION & GAS LIFT HEAVY WALL PIPING | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7303-10018 | MATERIAL REQUISITION FOR PIPING SPECIAL ITEMS | PIPING | MP - PIPING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7303-10019 | MATERIAL REQUISITION FOR PIPING SUPPORT MATERIALS | PIPING | MP - PIPING | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7303-10020 | MATERIAL REQUISITION FOR SPECIAL TYPE VA LVES | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7303-10021 | MATERIAL REQUISITION FOR BARRED TEE | PIPING | MP - PIPING | A02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7303-10022 | MATERIAL REQUISITION FOR BUTTERFLY VALVES | PIPING | MP - PIPING | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7303-10023 | MATERIAL REQUISITION FOR TOPSIDES PIPING INSULATION | PIPING | MP - PIPING | A01 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7402-10001 | 60% MODEL REVIEW REPORT | PIPING | MP - PIPING | A02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7402-10002 | 90% MODEL REVIEW REPORT (P0 & P1) | PIPING | MP - PIPING | A02 | SIM | AFC 3 |  | ISSUED | AFC/AFU RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7402-10003 | 90% MODEL REVIEW REPORT (P2+) | PIPING | MP - PIPING | A02 | SIM | MABU UNDER REVIEW |  | ENGINEERING CONSOLIDATION |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7737-10001 | SPECIFICATION FOR TOPSIDE PIPING SYSTEMS | PIPING | MP - PIPING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7737-10002 | SPECIFICATION FOR VALVES | PIPING | MP - PIPING | A03 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7737-10003 | SPECIFICATION FOR SPECIAL PIPING ITEMS | PIPING | MP - PIPING | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7737-10004 | SPECIFICATIONS FOR PIPING STRESS ANALYSIS PHILOSOPHY | PIPING | MP - PIPING | A03 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7737-10005 | TECHNICAL SPECIFICATION - INTERLOCK & DOOR INTERLOCK SYSTEM TO PIG LAUNCHING/RECEIVING | PIPING | MP - PIPING | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7737-10006 | STANDARD SPECIFICATION FOR INSULATION | PIPING | MP - PIPING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7737-10008 | SPECIFICATION FOR PIPING SUPPORT MATERIALS | PIPING | MP - PIPING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7737-10009 | SPECIFICATION FOR VARIABLE AND CONSTANT LOAD SPRING SUPPORTS | PIPING | MP - PIPING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7753-10001 | 60% MODEL REVIEW TERMS OF REFERENCE | PIPING | MP - PIPING | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7753-10002 | 90% MODEL REVIEW TERMS OF REFERENCE | PIPING | MP - PIPING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-7880-10002-001 | SPECIAL PIPING SUPPORT DRAWINGS | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-8005-10001 | PIPING STRESS ANALYSIS REPORT - PUMPS S-4046-A/B E P-4047 | PIPING | MP - PIPING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-8005-10002 | PIPING STRESS ANALYSIS REPORT - SYSTEMS 300-PP-S07 AND 300-PP-S17 | PIPING | MP - PIPING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-8005-10003 | PIPING STRESS ANALYSIS REPORT - SYSTEMS 300-PP-S04_ 300-PP-S05_ 300-PP-S06 AND 300-PP-S16 | PIPING | MP - PIPING | A02 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-8005-10004 | PIPING STRESS ANALYSIS REPORT - SYSTEMS S-14/S-15 | PIPING | MP - PIPING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-8005-10005 | PIPING STRESS ANALYSIS REPORT - SYSTEMS S-03/S-07 | PIPING | MP - PIPING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-8005-10006 | PIPING STRESS ANALYSIS REPORT - SYSTEMS 300-PP-S11_ 300-PP-S12_300-PP-S13 AND 300-PP-S15 | PIPING | MP - PIPING | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-8005-10007 | PIPING STRESS ANALYSIS REPORT - SYSTEMS 300-PP-S19 | PIPING | MP - PIPING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.17-MP-PIPING
BNO-MABU-300-MP-8502-10004 | DAE REQUEST MABU TO REVIEW THE ATTACHED CALCULATION SHEETS COMPARING DED RECOMMENDED PIPE WALL THICKNESSES | PIPING | MP - PIPING | R01 | NAO |  | Numero do documento excluido por regra | ISSUED | IFR RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.001-DAE_TQR
BNO-MABU-300-MR-2105-10001 | MECHANICAL DATASHEET FOR GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MR - MECHANICAL ROTATING | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING
BNO-MABU-300-MR-2105-10002 | MECHANICAL DATASHEET FOR METHANOL INJECTION PUMPS (P-4270A/B/C/D) | MECHANICAL | MR - MECHANICAL ROTATING | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING
BNO-MABU-300-MR-2105-10003 | MECHANICAL DATASHEET FOR CORROSION INHIBITOR INJECTION PUMPS (P-4280A/B/C/D) | MECHANICAL | MR - MECHANICAL ROTATING | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING
BNO-MABU-300-MR-2105-10004 | MECHANICAL DATASHEET FOR UPGRADED WATERFLOOD INJECTION PUMP (P-4046A) | MECHANICAL | MR - MECHANICAL ROTATING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING
BNO-MABU-300-MR-2105-10005 | MECHANICAL DATASHEET FOR MONORAIL PNEUMATIC TROLLEY HOIST | MECHANICAL | MR - MECHANICAL ROTATING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING
BNO-MABU-300-MR-2105-10006 | MECHANICAL DATASHEET FOR CHAIN PULLEY BLOCKS | NÃO SE APLICA | NÃO SE APLICA | A02 | NAO |  | Disciplina fora do monitoramento | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING
BNO-MABU-300-MR-2105-10007 | MECHANICAL DATASHEET FOR MANUAL BEAM TROLLEY | MECHANICAL | MR - MECHANICAL ROTATING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING
BNO-MABU-300-MR-2105-10008 | MECHANICAL DATASHEET FOR BEAM CLAMPS | MECHANICAL | MR - MECHANICAL ROTATING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING
BNO-MABU-300-MR-2105-10009 | MECHANICAL DATASHEET FOR MANUAL AND POWERED TROLLIES | MECHANICAL | MR - MECHANICAL ROTATING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING
BNO-MABU-300-MR-7303-10001 | MATERIAL REQUISITION FOR GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MR - MECHANICAL ROTATING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING
BNO-MABU-300-MR-7303-10002 | MATERIAL REQUISITION FOR METHANOL INJECTION PUMPS (P-4270A/B/C/D) | MECHANICAL | MR - MECHANICAL ROTATING | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING
BNO-MABU-300-MR-7303-10003 | MATERIAL REQUISITION FOR CORROSION INHIBITOR INJECTION PUMPS (P-4280A/B/C/D) | MECHANICAL | MR - MECHANICAL ROTATING | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING
BNO-MABU-300-MR-7303-10004 | MATERIAL REQUISITION FOR THE UPGRADED WATERFLOOD INJECTION PUMP (P-4046A) | MECHANICAL | MR - MECHANICAL ROTATING | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING
BNO-MABU-300-MR-7303-10005 | WATERFLOOD INJECTION PUMP SIZING CALCULATION AND REPORT (POWER REQUIREMENT) | MECHANICAL | MR - MECHANICAL ROTATING | A03 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING
BNO-MABU-300-MR-7303-10006 | MATERIAL REQUISITION FOR HANDLING EQUIPMENT | MECHANICAL | MR - MECHANICAL ROTATING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING
BNO-MABU-300-MR-7771-10001 | SPECIFICATION FOR THE GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MR - MECHANICAL ROTATING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING
BNO-MABU-300-MR-7771-10002 | SPECIFICATION FOR METHANOL INJECTION PUMPS P-4280A/B/C/D | MECHANICAL | MR - MECHANICAL ROTATING | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING
BNO-MABU-300-MR-7771-10003 | SPECIFICATION FOR CORROSION INHIBITOR INJECTION PUMPS (P-4270A/B/C/D) | MECHANICAL | MR - MECHANICAL ROTATING | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING
BNO-MABU-300-MR-7771-10004 | SPECIFICATION FOR THE UPGRADED WATERFLOOD INJECTION PUMP (P-4046A) | MECHANICAL | MR - MECHANICAL ROTATING | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING
BNO-MABU-300-MR-7771-10005 | SPECIFICATION FOR HANDLING EQUIPMENT | MECHANICAL | MR - MECHANICAL ROTATING | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING
BNO-MABU-300-MS-1208-10001 | PIG LAUNCHER DESIGN CALCULATION FOR PRODUCTION FLOWLINE AND REPORT | MECHANICAL | MS - MECHANICAL STATIC | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.19-MS-MECHANICAL_STATIC
BNO-MABU-300-MS-2105-10001 | MECHANICAL DATASHEET FOR PIG LAUNCHER/RECEIVER (A-0820J/K) | MECHANICAL | MS - MECHANICAL STATIC | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.19-MS-MECHANICAL_STATIC
BNO-MABU-300-MS-4322-10001 | MTO FOR PIG LAUNCHER AND RECEIVER (A-0820J /K) | MECHANICAL | MS - MECHANICAL STATIC | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.19-MS-MECHANICAL_STATIC
BNO-MABU-300-MS-7303-10001 | MATERIAL REQUISITION FOR QUICK OPENING END CLOSURES FOR PIG LAUNCHER AND RECEIVER (QOE-A-0820J /K) | MECHANICAL | MS - MECHANICAL STATIC | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.19-MS-MECHANICAL_STATIC
BNO-MABU-300-MS-7771-10001 | SPECIFICATIONS FOR PIG LAUNCHER/RECEIVER (A-0820J /K) | MECHANICAL | MS - MECHANICAL STATIC | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.19-MS-MECHANICAL_STATIC
BNO-MABU-300-MX-4018-10001-001 | GA DRAWING FOR SUBSEA WELLS PIG LAUNCHER AND RECEIVER | MECHANICAL | MX - OVERAL MECHANICAL | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.20-MX-MECHANICAL
BNO-MABU-300-MX-6612-10001 | MECHANICAL EQUIPMENT LIST | MECHANICAL | MX - OVERAL MECHANICAL | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.20-MX-MECHANICAL
BNO-MABU-300-MX-7180-10001 | MECHANICAL HANDLING PHILOSOPHY | MECHANICAL | MX - OVERAL MECHANICAL | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.20-MX-MECHANICAL
BNO-MABU-300-MX-7180-10002 | MECHANICAL HANDLING STUDY REPORT - WATERFLOOD INJECTION PUMPS | MECHANICAL | MX - OVERAL MECHANICAL | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.20-MX-MECHANICAL
BNO-MABU-300-MX-7180-10003 | MECHANICAL HANDLING STUDY REPORT | MECHANICAL | MX - OVERAL MECHANICAL | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.20-MX-MECHANICAL
BNO-MABU-300-MX-7180-10004 | RAM STUDY REPORT | MECHANICAL | MX - OVERAL MECHANICAL | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 4 |  |  | BNO / 02-DED / 02.20-MX-MECHANICAL
BNO-MABU-300-MX-8502-10001 | RAM STUDY ASSUMPTIONS ALIGNMENT AND CONFIRMATION | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Numero do documento excluido por regra | CANCELADO |  |  |  | BNO / 02-DED / 02.001-DAE_TQR
BNO-MABU-300-MX-8502-10003 | PT-4047 EXHAUST GAS DATA AND COMPOSITION | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Numero do documento excluido por regra | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 02-DED / 02.001-DAE_TQR
BNO-MABU-300-MX-8502-10005 | INSTRUMENTATION AIR CONSUMPTION FOR METHANOL INJECTION PUMPS AND CORROSION INHIBITOR PUMPS | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Numero do documento excluido por regra | CANCELADO |  |  |  | BNO / 02-DED / 02.001-DAE_TQR
BNO-MABU-300-PX-0580-10001 | UTILITY CONSUMPTION SUMMARY | PROCESS | PX - PROCESS | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-0580-10002 | BN SYSTEM PRESSURE SETTING REPORT | PROCESS | PX - PROCESS | A05 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-0580-10003 | EQUIPMENT & LINE SIZING VALIDATION REPORT | PROCESS | PX - PROCESS | A03 | SIM | MABU UNDER REVIEW |  | ENGINEERING COMMENTS |  |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-0580-10004 | PROCESS SIMULATION REPORT | PROCESS | PX - PROCESS | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-1216-10001 | HEAT AND MASS BALANCE REPORT | PROCESS | PX - PROCESS | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-1380-10001 | WATERFLOOD INJECTION SIZING CALCULATION REPORT P-4047 | PROCESS | PX - PROCESS | A09 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-1380-10002 | DRAINAGE SYSTEM CALCULATION NOTES | PROCESS | PX - PROCESS | A03 | SIM | MABU UNDER REVIEW |  | ENGINEERING COMMENTS |  |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-1380-10003 | METHANOL PUMP PROCESS CALCULATION NOTES | PROCESS | PX - PROCESS | A04 | SIM | AFC 1 |  | ENGINEERING COMMENTS | APPROVED FOR USE (AFU) |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-1380-10004 | CORROSION INHIBITOR PUMP PROCESS CALCULATION NOTES | PROCESS | PX - PROCESS | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-1380-10005 | WATERFLOOD INJECTION PUMPS SIZING CALCULATION REPORT P-4046 A | PROCESS | PX - PROCESS | A07 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-1380-10008 | CONTROL VALVES CALCULATION NOTES | PROCESS | PX - PROCESS | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-1380-10009 | FLOW INSTRUMENTS CALCULATION NOTES | PROCESS | PX - PROCESS | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-1380-10010 | PRESSURE INSTRUMENTS CALCULATION NOTES | PROCESS | PX - PROCESS | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-1380-10011 | TEMPERATURE INSTRUMENTS CALCULATION NOTES | PROCESS | PX - PROCESS | A05 | SIM | MABU UNDER REVIEW |  | ENGINEERING COMMENTS |  |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-1380-10012 | FLARE SYSTEM CALCULATION NOTES | PROCESS | PX - PROCESS | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-1380-10013 | DESPRESSURIZATION SYSTEM CALCULATION NOTES | PROCESS | PX - PROCESS | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-1380-10015 | PROCESS SAFETY TIME CALCULATIONS | PROCESS | PX - PROCESS | A03 | SIM | MABU UNDER REVIEW |  | ENGINEERING COMMENTS |  |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2105-10001 | PROCESS DATASHEETS FOR SAND DETECTOR | PROCESS | PX - PROCESS | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2105-10002 | PROCESS DATASHEETS FOR CHOKE VALVES | PROCESS | PX - PROCESS | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2105-10003 | PROCESS DATASHEET FOR WATERFLOOD INJECTION PUMP UPGRADE (P-4046A) | PROCESS | PX - PROCESS | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2105-10004 | PROCESS DATASHEET FOR CORROSION INHIBITOR PUMP | PROCESS | PX - PROCESS | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2105-10006 | PROCESS DATASHEETS FOR CONTROL VALVES | PROCESS | PX - PROCESS | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2105-10007 | PROCESS DATASHEETS FOR ON/OFF VALVES | PROCESS | PX - PROCESS | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2105-10008 | PROCESS DATASHEETS FOR SHUTDOWN VALVES | PROCESS | PX - PROCESS | A05 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2105-10009 | PROCESS DATASHEET FOR TEMPERATURE INSTRUMENTS | PROCESS | PX - PROCESS | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2105-10010 | PROCESS DATASHEET FOR FLOW INSTRUMENTS | PROCESS | PX - PROCESS | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2105-10011 | PROCESS DATASHEET FOR PRESSURE INSTRUMENTS | PROCESS | PX - PROCESS | A06 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2105-10012 | PROCESS DATASHEET FOR WATERFLOOD INJECTION PUMP NEW (P-4047) | PROCESS | PX - PROCESS | A04 | SIM | IFA |  | ISSUED | IFA RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2105-10013 | PROCESS DATASHEET FOR HAND VALVES | PROCESS | PX - PROCESS | A05 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2105-10014 | PROCESS DATASHEETS FOR RELIEF VALVES | PROCESS | PX - PROCESS | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2105-10015 | PROCESS DATASHEET FOR METHANOL INJECTION PUMP | PROCESS | PX - PROCESS | A06 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10005-001 | P&ID- PRODUCTION SYSTEM-SUBSEA WELLS LAUNCHERS / RECEIVERS-MODIFICATION | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IDC - INTERNAL COMMENTS |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10006-001 | P&ID- PRODUCTION SYSTEM -OIL/ OIL HEAT EXCHANGER-MODIFICATION | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IDC - INTERNAL COMMENTS |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10007-001 | P&ID- PRODUCTION SYSTEMS GAS LIFT COMPRESSOR-MODIFICATION | PROCESS | PX - PROCESS | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IDC - INTERNAL COMMENTS |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10008-001 | P&ID- PRODUCTION SYSTEMS GAS RISER LIFT METERS-MODIFICATION | PROCESS | PX - PROCESS | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IDC - INTERNAL COMMENTS |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10009-001 | P&ID - BN PRODUCTION SYSTEMS GAS RISER LIFT METER | PROCESS | PX - PROCESS | C04 | SIM | MABU UNDER REVIEW |  | ENGINEERING COMMENTS |  | AFC/AFU - RELEASE |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10010-001 | P&ID - BN PRODUCTION SYSTEM PIG LAUNCHER /RECEIVER (A-0820J) | PROCESS | PX - PROCESS | C04 | SIM | MABU UNDER REVIEW |  | ENGINEERING COMMENTS |  | IDC - INTERNAL COMMENTS |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10011-001 | P&ID - BN PRODUCTION SYSTEM PIG LAUNCHER /RECEIVER (A-0820K) | PROCESS | PX - PROCESS | C04 | SIM | MABU UNDER REVIEW |  | ENGINEERING COMMENTS |  | IDC - INTERNAL COMMENTS |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10012-001 | P&ID PRODUCTION SYSTEMS - PRODUCTION MANIFOLD - MODIFICATION | PROCESS | PX - PROCESS | C05 | SIM | MABU UNDER REVIEW |  | ENGINEERING COMMENTS |  | IDC - INTERNAL COMMENTS |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10013-001 | P&ID - PRODUCTION SYSTEMS- PRODUCTION FLOWLINES & INSTRUMENT - MODIFICATION | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IDC - INTERNAL COMMENTS |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10017-001 | P&ID - UTILITY SYSTEMS WATERFLOOD SYSTEM INJECTION WATER TANK & CHARGE PUMPS-MODIFICATION | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IDC - INTERNAL COMMENTS |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10018-001 | P&ID - UTILITY SYSTEMS WATERFLOOD SYSTEM WATERFLOOD INJECTION PUMP SHT. 1 OF 2-MODIFICATION | PROCESS | PX - PROCESS | C04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IDC - INTERNAL COMMENTS |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10019-001 | P&ID - UTILITY SYSTEMS WATERFLOOD INJECTION - LAUNCHER/RECEIVERS-MODIFICATION | PROCESS | PX - PROCESS | C03 | SIM | MABU UNDER REVIEW |  | ENGINEERING COMMENTS |  | IDC - INTERNAL COMMENTS |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10020-001 | P&ID - UTILITY SYSTEMS -WATERFLOOD INJECTION PUMP NO. 1 TURBINE UTILITIES-MODIFICATION | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IDC - INTERNAL COMMENTS |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10021-001 | P&ID - BN WATERFLOOD SYSTEM - WATERFLOOD INJECTION PUMP | PROCESS | PX - PROCESS | C04 | SIM | MABU UNDER REVIEW |  | ENGINEERING COMMENTS |  | IDC - INTERNAL COMMENTS |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10022-001 | P&ID - BN UTILITY SYSTEMS - WATERFLOOD INJECTION PUMP TURBINE PACKAGE | PROCESS | PX - PROCESS | C03 | SIM | AFC 1 |  | ENGINEERING COMMENTS | APPROVED FOR USE (AFU) | IDC - INTERNAL COMMENTS |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10024-001 | P&ID- UTILITY SYSTEMS FUEL GAS DISTRIBUTION-MODIFICATION | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IDC - INTERNAL COMMENTS |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10027-001 | P&ID- UTILITY SYSTEMS FLOWLINE CORROSION INHIBITOR PUMPS -MODIFICATION | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IDC - INTERNAL COMMENTS |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10029-001 | P&ID - UTILITY SYSTEM HYDRATE INHIBITOR SYSTEM MODIFICATION | PROCESS | PX - PROCESS | C04 | SIM | MABU UNDER REVIEW |  | ENGINEERING COMMENTS |  | IDC - INTERNAL COMMENTS |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10030-001 | P&ID - BN UTILITY SYSTEMS - CORROSION INHIBITOR SYSTEM PACKAGE - MODIFICATION | PROCESS | PX - PROCESS | C03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IDC - INTERNAL COMMENTS |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10033-001 | P&ID - PRODUCTION SYSTEM- SUBSEA / BLOWDOWN RELIEF HEADER-MODIFICATION | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IDC - INTERNAL COMMENTS |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10034-001 | P&ID - PRODUCTION SYSTEM- COMPRESSION RELIEF HEADER - MODIFICATION | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IDC - INTERNAL COMMENTS |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10035-001 | P&ID - PRODUCTION SYSTEMS OPEN DRAIN SYSTEM | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IDC - INTERNAL COMMENTS |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10037-001 | P&ID - BN UTILITY SYSTEMS - WATER HEADER DISTRIBUTION SYSTEM MODIFICATION | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IDC - INTERNAL COMMENTS |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10039-001 | P&ID - DIESEL DAY TANK SYSTEM- MODIFICATION | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 | IDC - INTERNAL COMMENTS |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10041-001 | P&ID - FIREWATER SYSTEM FIREWATER & FOAM SYSTEM RINGMAIN | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10045-001 | DEMOLITION P&ID - PRODUCTION SYSTEMS PRODUCTION MANIFOLD | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10046-001 | DEMOLITION P&ID - PRODUCTION SYSTEM-SUBSEA WELLSLAUNCHERS / RECEIVERS | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10047-001 | DEMOLITION P&ID - PRODUCTION SYSTEM -OIL/ OIL HEAT EXCHANGER | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10048-001 | DEMOLITION P&ID - PRODUCTION SYSTEMS GAS RISER LIFT METERS | PROCESS | PX - PROCESS | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10050-001 | DEMOLITION P&ID - UTILITY SYSTEMS FUEL GAS DISTRIBUTION | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IDC - INTERNAL COMMENTS |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10051-001 | DEMOLITION P&ID - UTILITY SYSTEMS - WATERFLOOD SYSTEM INJECTION WATER TANK & CHARGE PUMPS | PROCESS | PX - PROCESS | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10052-001 | DEMOLITION P&ID - UTILITY SYSTEMS - WATERFLOOD INJECTION LAUNCHER/RECEIVERS (CANCELLED) | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10053-001 | DEMOLITION P&ID - UTILITY SYSTEMS - WATERFLOOD INJECTION PUMP NO. 1 TURBINE UTILITIES | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10054-001 | DEMOLITION P&ID - UTILITY SYSTEMS - WATERFLOOD SYSTEM WATERFLOOD INJECTION PUMP SHT. 1 OF 2 | PROCESS | PX - PROCESS | C03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10055-001 | DEMOLITION P&ID - UTILITY SYSTEMS FLOWLINE CORROSION INHIBITOR PUMPS | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10056-001 | DEMOLITION P&ID - UTILITY SYSTEMS HYDRATE INHIBITOR SYSTEM | PROCESS | PX - PROCESS | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10057-001 | DEMOLITION P&ID - PRODUCTION SYSTEM - SUBSEA/BLOWDOWN RELIEF HEADER | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10058-001 | DEMOLITION P&ID - PRODUCTION SYSTEM - COMPRESSION RELIEF HEADER | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10059-001 | DEMOLITION P&ID - UTILITY SYSTEMS - WATER HEADER DISTRIBUTION SYSTEM | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10060-001 | DEMOLITION P&ID - DIESEL DAY TANK SYSTEM | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 | IDC - INTERNAL COMMENTS |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10061-001 | TIE-IN P&ID PRODUCTION SYSTEMS PRODUCTION MANIFOLD TP 01-TP 06 | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10062-001 | TIE-IN P&D PRODUCTION SYSTEMS GAS RISER LIFT METERS TP 07 & TP 08. | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10063-001 | TIE-IN P&ID UTILITY SYSTEMS FLOWLINE CORROSION INHIBITOR PUMPS TP 025, 026 & 056. | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10064-001 | TIE-IN P&ID UTILITY SYSTEMS WATERFLOOD SYSTEM INJECTION WATER TANK & CHARGE PUMPS TP 028A. | PROCESS | PX - PROCESS | C03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10065-001 | TIE-IN P&ID UTILITY SYSTEMS WEATERFLOOD INJECTION PUMP NO. 1 TURBINE UTILITIES TP 049 & 050. | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10066-001 | MODIFICATION_P&ID FIREWATER SYSTEM FIREWATER & FOAM SYSTEM RINGMAIN | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10067-001 | DEMOLITION_P&ID FIREWATER SYSTEM FIREWATER & FOAM SYSTEM RINGMAIN | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10068-001 | P&ID - UTILITY SYSTEMS SUBSEA CHEMICAL SYSTEM MODIFICATION | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10069-001 | DEMOLITION P&ID - UTILITY SYSTEMS SUBSEA CHEMICAL SYSTEM | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10070-001 | P&ID PRODUCTION SYSTEMS OPEN DRAIN SYSTEM DEMOLITION | NÃO SE APLICA | NÃO SE APLICA | C01 | NAO |  | Disciplina fora do monitoramento | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10071-001 | P&ID PRODUCTION SYSTEMS OPEN DRAIN SYSTEM MODIFICATION. | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10072-001 | P&ID PRODUCTION SYSTEMS INDUCED GAS FLOTATION SEPARATOR DEMOLITION. | PROCESS | PX - PROCESS | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10073-001 | P&ID PRODUCTION SYSTEMS INDUCED GAS FLOTATION SEPARATOR MODIFICATION. | PROCESS | PX - PROCESS | X | NAO |  | Revisao X cancelada | CANCELADO |  |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10074-001 | P&ID UTILITY SYSTEMS HYDRATE INHIBITOR INJECTION PUMPS MODIFICATION | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10075-001 | P&ID UTILITY SYSTEMS HYDRATE INHIBITOR INJECTION PUMPS DEMOLITION | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10076-001 | P&ID UTILITY SYSTEMS AIR SERVICE HEADER DISTRIBUTION MODIFICATION | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2365-10077-001 | P&ID UTILITY SYSTEMS AIR SERVICE HEADER DISTRIBUTION DEMOLITION | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2366-10001-001 | FLOWSHEET LEGEND SHT 1 | PROCESS | PX - PROCESS | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2366-10002-001 | FLOWSHEET LEGEND SHT 2 | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2366-10003-001 | FLOWSHEET LEGEND SHT 3 | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2366-10004-001 | FLOWSHEET LEGEND SHT 4 | PROCESS | PX - PROCESS | C03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2366-10005-001 | FLOWSHEET LEGEND SHT 5 | PROCESS | PX - PROCESS | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2366-10006-001 | PFS - BONGA NORTH WELLS FLOWLINES LAUNCHER RECEIVERS | PROCESS | PX - PROCESS | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING COMMENTS |  |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2366-10007-001 | PFS - WELL/FLOWLINES/PRODUCTION /RECEIVER TEST -MODIFICATION | PROCESS | PX - PROCESS | C03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2366-10008-001 | PFS - PRODUCTION MANIFOLD_ TEST SEPARATOR - MODIFICATION | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2366-10009-001 | PFS - HEATING AND TREATING OIL - MODIFICATION | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2366-10010-001 | PFS - GAS SALES AND RISER LIFT - MODIFICATION | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2366-10011-001 | PFS - WATERFLOOD SRS AND INJECTION - MODIFICATION | PROCESS | PX - PROCESS | C02 | SIM | MABU UNDER REVIEW |  | ENGINEERING COMMENTS |  |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2366-10012-001 | PFS - FUEL GAS-MODIFICATION | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2366-10013-001 | PFS - BONGA NORTH WATERFLOOD INJECTION PUMP | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2366-10014-001 | PFS - CHEMICAL INJECTION - MODIFICATION | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2366-10015-001 | PFS - BONGA NORTH CHEMICAL INJECTION: CORROSION INHIBITOR SYSTEM | PROCESS | PX - PROCESS | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2366-10016-001 | PFS - VENTS AND FLARE BOOM - MODIFICATION | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2366-10017-001 | PFS - DIESEL SUPPLY SYSTEM- MODIFICATION | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2366-10018-001 | PFS - MISCELLANEOUS SYSTEMS - MODIFICATION | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2368-10001-001 | PSFS - BONGA NORTH WELLS FLOWLINES LAUNCHER RECEIVERS | PROCESS | PX - PROCESS | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2368-10002-001 | PSFS-WELL/FLOWLINES/PRODUCTION /RECEIVER TEST-MODIFICATION | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2368-10003-001 | PSFS - PRODUCTION MANIFOLD_ TEST SEPARATOR - MODIFICATION | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2368-10004-001 | PSFS - HEATING & TREATING OIL | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2368-10005-001 | PSFS - GAS SALES -RISER LIFT | PROCESS | PX - PROCESS | C03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2368-10006-001 | PSFS - WATERFLOOD SRS AND INJECTION | PROCESS | PX - PROCESS | C02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2368-10007-001 | PSFS - FUEL GAS | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2368-10008-001 | PSFS - BONGA NORTH WATERFLOOD INJECTION PUMP | PROCESS | PX - PROCESS | C03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2368-10009-001 | PSFS - CHEMICAL INJECTION | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2368-10010-001 | PSFS - BONGA NORTH CHEMICAL INJECTION: CORROSION INHIBITOR SYSTEM | PROCESS | PX - PROCESS | C05 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2368-10011-001 | PSFS - VENTS AND FLARE BOOM - MODIFICATION | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2368-10012-001 | PSFS - MISCELLANEOUS SYSTEMS | PROCESS | PX - PROCESS | C01 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-2908-10001 | RELIEF VALVES CALCULATION NOTES | PROCESS | PX - PROCESS | A04 | SIM | AFC 1 |  | ENGINEERING COMMENTS | APPROVED FOR USE (AFU) |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-3363-10001 | PROCESS SAFEGUARDING MEMORANDUM | PROCESS | PX - PROCESS | A05 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-4322-10001 | PROCESS LINE LIST | PROCESS | PX - PROCESS | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-5517-10001 | ISOLATION PHILOSOPHY | PROCESS | PX - PROCESS | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-5527-10001 | RELIEF & BLOW DOWN PHILOSOPHY | PROCESS | PX - PROCESS | A03 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-5527-10002 | DRAINAGE & VENTING PHILOSOPHY | PROCESS | PX - PROCESS | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-7180-10001 | PROCESS AND MECHANICAL ISOLATION REVIEW REPORT | PROCESS | PX - PROCESS | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-7180-10002 | WATER INJECTION DYNAMIC SIMULATION REPORT | PROCESS | PX - PROCESS | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-7180-10003 | WATER INJECTION SURGE STUDY REPORT - 2 | PROCESS | PX - PROCESS | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-7753-10002 | TERMS OF REFERENCE FOR PROCESS AND MECHANICAL ISOLATION REVIEW | PROCESS | PX - PROCESS | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.23-PX-PROCESS
BNO-MABU-300-PX-8502-10001 | TQ FOR GAS LIFT HEATER BYPASS | PROCESS | PX - PROCESS | A01 | NAO |  | Numero do documento excluido por regra | CANCELADO |  |  |  | BNO / 02-DED / 02.001-DAE_TQR
BNO-MABU-300-PX-8502-10005 | PIG LAUNCHING / RECEIVING OPERATING PROCEDURE | PROCESS | PX - PROCESS | R01 | NAO |  | Numero do documento excluido por regra | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.001-DAE_TQR
BNO-MABU-300-PX-8502-10006 | LABORATORY REPORT FOR VAPOR PRESSURE OF THE CORROSION INHIBITOR CORRTREAT DF 16946 | PROCESS | PX - PROCESS | R01 | NAO |  | Numero do documento excluido por regra | ISSUED | ISSUED FOR INFORMATION | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.001-DAE_TQR
BNO-MABU-300-PX-8502-10008 | BNO MAIN FIREWATER PUMPS & NETWORK P&ID AND DELUGE DISTRIBUTION P&ID | PROCESS | PX - PROCESS | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.001-DAE_TQR
BNO-MABU-300-PX-8502-10016 | INSTRUMENT AIR HEADER DISTRIBUTION P&IDS | PROCESS | PX - PROCESS | A01 | NAO |  | Numero do documento excluido por regra | ISSUED | ISSUED FOR INFORMATION |  |  | BNO / 02-DED / 02.001-DAE_TQR
BNO-MABU-300-QA-5798-10001 | QUALITY PLAN | QA - QUALITY | QA - QUALITY | A03 | NAO |  | Disciplina fora do monitoramento | ISSUED | AFC/AFU RETURNED AS CODE 2 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.24-QA-QUALITY
BNO-MABU-300-RA-3375-10001 | TOPSIDES PAINTING AND COATING SPECIFICATION | MATERIALS | RA - MATERIALS | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-3375-10002 | SPECIFICATIONS AND PROCEDURES FOR TOPSIDES WELDING | MATERIALS | RA - MATERIALS | A02 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-6919-10001 | CORROSION MANAGEMENT FRAMEWORK AND INSPECTION PLAN | MATERIALS | RA - MATERIALS | A02 | SIM | MABU UNDER REVIEW |  | ENGINEERING DISTRIBUTION |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7180-00001 | METHANOL SKID ISOLATION MATERIALS - MATERIAL REQUISITION | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10001-001 | CORROSION MANAGEMENT DRAWINGS | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10002-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-B) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10002-002 | CORROSION MANAGEMENT DRAWING - 0.75-PM-043117-80-B | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10002-003 | CORROSION MANAGEMENT DRAWING - 2-PL-233050-80-B | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10003-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-C) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10003-002 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-C) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10003-003 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-C) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10003-004 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-C) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10003-005 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-C) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10003-006 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-C) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10004-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-D) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10004-002 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-D) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10004-003 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-D) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 2 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10005-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-E) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 2 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10005-002 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-E) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10005-003 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-E) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10005-004 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-E) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10005-005 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-E) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10006-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-F) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10006-002 | CORROSION MANAGEMENT DRAWING - 4-PG-313045-750-F1-1H | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10006-003 | CORROSION MANAGEMENT DRAWING - 4-PG-313045-750-F1-1H | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10006-004 | CORROSION MANAGEMENT DRAWING - 4-PG-313045-750-F1-1H | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10006-005 | CORROSION MANAGEMENT DRAWING - 4-PG-313045-750-F1-1H | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10006-006 | CORROSION MANAGEMENT DRAWING - 4-PG-313048-750-F1-1H | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10006-007 | CORROSION MANAGEMENT DRAWING - 4-PG-313048-750-F1-1H | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10006-008 | CORROSION MANAGEMENT DRAWING - 4-PG-313048-750-F1-1H | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10006-009 | CORROSION MANAGEMENT DRAWING - 4-PG-313048-750-F1-1H | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10006-010 | CORROSION MANAGEMENT DRAWING - 4-PG-313048-750-F1-1H | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10006-011 | CORROSION MANAGEMENT DRAWING - 4-PG-313048-750-F1-1H | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10006-012 | CORROSION MANAGEMENT DRAWING - TAM26-TP-07-4-PG-313045-750-F1-1H | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10006-013 | CORROSION MANAGEMENT DRAWING - TAM26-TP-08-4-PG-313048-750-F1-1H | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10007-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-G) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10007-002 | CORROSION MANAGEMENT DRAWING - 4-PG-313046-750-FLT-1H | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10007-003 | CORROSION MANAGEMENT DRAWING - 4-PG-313046-750-FLT-1H | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10007-004 | CORROSION MANAGEMENT DRAWING - 4-PG-313046-750-FLT-1H | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10007-005 | CORROSION MANAGEMENT DRAWING - 4-PG-313046-750-FLT-1H | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10007-006 | CORROSION MANAGEMENT DRAWING - 4-PG-313049-750-FLT-1H | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10007-007 | CORROSION MANAGEMENT DRAWING - 4-PG-313049-750-FLT-1H | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10007-008 | CORROSION MANAGEMENT DRAWING - 4-PG-313049-750-FLT-1H | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10007-009 | CORROSION MANAGEMENT DRAWING - 4-PG-313049-750-FLT-1H | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10008-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-H) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10008-002 | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10008-003 | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10008-004 | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10008-005 | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10008-006 | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10008-007 | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10008-008 | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & FLARE SYSTEM | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10008-009 | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10008-010 | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10008-011 | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10008-012 | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10008-013 | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & FLARE SYSTEM | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10008-014 | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & FLARE SYSTEM | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10008-015 | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & SLARE SYSTEM | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10008-016 | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & FLARE SYSTEM | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10008-017 | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10008-018 | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10008-019 | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10008-020 | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10008-021 | BONGA NORTH CORROSION MANAGEMENT DRAWING GAS LIFT SYSTEM | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10008-022 | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10008-023 | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10008-024 | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10008-025 | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10008-026 | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10008-027 | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10008-028 | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & FLARE SYSTEM | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10008-029 | BONGA NORTH CORROSION MANAGEMENT DRAWING RELIEF & FLARE SYSTEM | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10008-030 | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & FLARE SYSTEM | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10008-031 | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & FLARE SYSTEM | MATERIALS | RA - MATERIALS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10009-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-I) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10010-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-J) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10011-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-K) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10012-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-L) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10012-002 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-L) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10012-003 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-L) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10012-004 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-L) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10013-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-M) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10014-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-N) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10014-002 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-N) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10014-003 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-N) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10014-004 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-N) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10014-005 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-N) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10015-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-O) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10016-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-P) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10017-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-Q) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10018-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-R) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10019-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-S) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10020-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-T) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10021-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-U) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10022-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-V) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10023-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL01-W) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10024-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL02-A) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10025-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL02-B) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10026-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL02-C) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10027-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL02-D) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10027-002 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL02-D) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10028-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL02-E) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10028-002 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL02-E) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10029-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL04-A) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10030-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL05-A) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10031-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL07-A). | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10032-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL08-A). | NÃO SE APLICA | NÃO SE APLICA | R01 | NAO |  | Disciplina fora do monitoramento | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10032-002 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL08-A). | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10033-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL08-B). | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10033-002 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL08-B). | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10034-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL08-C). | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10034-002 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL08-C). | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10035-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL08-D). | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 1 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10036-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL08-E). | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10037-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON_CL15-A). | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10038-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL15-B). | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10038-002 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL15-B) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10038-003 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL15-B) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10038-004 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL15-B) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10039-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL15-C). | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10040-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON_CL15-D). | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10041-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL15-E). | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10042-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL15-F). | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10042-002 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL15-F) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10042-003 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL15-F). | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10043-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL15-G). | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10044-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL15-H). | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10044-002 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL15-H). | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10045-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL15-I) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10045-002 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL15-I). | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10046-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL16-A) | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10046-002 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL16-A). | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10047-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON_CL17-A). | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10048-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON_CL17-B). | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10049-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON_CL20-A). | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10050-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON_CL20-B). | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10051-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL20-C). | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-7769-10052-001 | CORROSION MANAGEMENT DRAWING - CORROSION LOOP (BON-CL21-A). | MATERIALS | RA - MATERIALS | R01 | SIM | IFR |  | ISSUED | IFR RETURNED AS CODE 3 |  |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-MABU-300-RA-8241-10001 | MATERIALS SELECTION REPORT | MATERIALS | RA - MATERIALS | A04 | SIM | AFC 1 |  | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFR - ISSUED FOR REVIEW |  | BNO / 02-DED / 02.25-RA-MATERIALS
BNO-RACIRT-300-AA-5798-10001 | MTC PROJECT EXECUTION PLAN | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Diretorio Vendor | ISSUED |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-0902-10001 | TELECOMMUNICATIONS - PUBLIC ADDRESS AND GENERAL ALARM (PAGA) - BLOCK DIAGRAM | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED |  | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-0902-10002 | TELECOMMUNICATIONS - DATA NETWORKS (LAN/WAN) - BLOCK DIAGRAM | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED |  | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-0902-10005 | TELECOMMUNICATIONS - CLOSED CIRCUIT TV SYSTEM (CCTV) - PROCESS MONITORING / DIGITAL VIDEO SURVEILLANCE - BLOCK DIAGRAM | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED |  | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-0902-10006 | TELECOMMUNICATIONS - WIRELESS LAN - BLOCK DIAGRAM | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED |  | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-0902-10009 | TELECOMMUNICATIONS - STRUCTURED CABLING NETWORK - BLOCK DIAGRAM | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-0902-10010 | TELECOMMUNICATIONS - TELEPHONE SYSTEM - BLOCK DIAGRAM | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED |  | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-0980-10001 | EARTHING & LIGHTNING BONDING BLOCK DIAGRAM | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED |  | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-0980-10002 | EARTHING & LIGHTNING BONDING WIRING/TERMINATION DRAWING | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED |  | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-0980-10003 | TELECOMMUNICATIONS - FIBRE OPTIC SYSTEM - BLOCK DIAGRAM | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED |  | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-0980-10004 | CABINET AND POWER ANCILLARIES SPECIFICATION | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A05 | NAO |  | Diretorio Vendor | ISSUED |  | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-0980-10005 | CABINET POWER BLOCK DIAGRAM | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-0980-10007 | ITP FOR TELECOMS SYSTEMS | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R03 | NAO |  | Diretorio Vendor | ISSUED |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-2105-10001 | EQUIPMENT DATASHEETS FOR CABLING SYSTEMS | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-2105-10002 | EQUIPMENT DATASHEET FOR CCTV SYSTEMS | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-2105-10003 | EQUIPMENT DATASHEETS FOR DATA NETWORKS (LAN/WAN) | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A03 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-2105-10006 | EQUIPMENT DATASHEETS FOR PAGA SYSTEMS | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A03 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-2105-10007 | EQUIPMENT DATASHEETS FOR TELEPHONE SYSTEMS | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A03 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-2105-10010 | EQUIPMENT DATASHEETS FOR WIRELESS LAN | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-2105-10011 | EQUIPMENT DATASHEET FOR CABINET & POWER ANCILLARIES | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A02 | NAO |  | Diretorio Vendor | ISSUED |  | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-2341-10001 | GENERAL TELECOMMUNICATION SYSTEMS ARCHITECTURE DIAGRAM | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C02 | NAO |  | Diretorio Vendor | ENGINEERING DISTRIBUTION |  | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-3309-10001 | MTO FOR DATA NETWORKS (LAN/WAN) SYSTEMS | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-3309-10002 | MTO FOR STRUCTURED CABLING (SOC/FOC) NETWORK SYSTEMS | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A03 | NAO |  | Diretorio Vendor | ISSUED |  | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-3309-10003 | MTO FOR CLOSED CIRCUIT TELEVISION (CCTV) SYSTEMS | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-3309-10004 | MTO FOR PUBLIC ADDRESS AND GENERAL ALARM (PAGA) SYSTEMS | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A03 | NAO |  | Diretorio Vendor | ISSUED |  | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-3309-10005 | MTO FOR WIRELESS LAN SYSTEMS | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-3309-10006 | MTO FOR TELEPHONE SYSTEM | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-3309-10007 | MTO FOR CABINET AND POWER ANCILLARIES | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A03 | NAO |  | Diretorio Vendor | TRANSMITTAL |  | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-4018-10001 | TELECOMMUNICATIONS - GENERAL ARRANGEMENT AND SUPPORT PLANT - BONGA NORTH INTEGRATION | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED |  | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-4018-10002 | TELECOMMUNICATIONS - GENERAL ARRANGEMENT AND SUPPORT PLANT - BONGA NORTH SWITCHGEAR & CONTROL ROOM | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED |  | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-4180-10001 | CLOSED CIRCUIT TELEVISION (CCTV) LAYOUT DRAWING | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED |  | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-4180-10002 | PUBLIC ADDRESS & GENERAL ALARM (PAGA) LAYOUT DRAWING | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED |  | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-4180-10003 | TELEPHONE SYSTEMS LAYOUT DRAWING | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED |  | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-4180-10004 | TELECOMS EQUIPMENT CABINET PANEL LAYOUT DRAWING | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-4180-10005 | DATA & VOICE AND WIRELESS LAN EQUIPMENT LAYOUT SHT 2 | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED |  | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-4180-10006-001 | TELECOMMUNICATIONS - PAGA TYPICAL DETAIL DIAGRAMS | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED |  | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-4180-10006-002 | TELECOMMUNICATIONS - TYPICAL DETAILS - CABLE ARRANGEMENT | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED |  | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-4308-10001 | TELECOMMUNICATIONS - CABLE SCHEDULE | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A03 | NAO |  | Diretorio Vendor | ENGINEERING CONSOLIDATION |  | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-4380-10006 | TELECOMMUNICATIONS POWER LOADS LIST | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A04 | NAO |  | Diretorio Vendor | ISSUED |  | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-5507-10001 | BONGA NORTH TELECOMMUNICATION DESIGN PHILOSOPHY | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C03 | NAO |  | Diretorio Vendor | ISSUED |  | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-6612-10001 | EX EQUIPMENT REGISTER | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A01 | NAO |  | Diretorio Vendor | TRANSMITTAL |  | IFR - ISSUED FOR REVIEW |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-7180-10001 | TELECOMMUNICATIONS - PUBLIC ADDRESS AND GENERAL ALARM (PAGA) - COVERAGE CALCULATION REPORT | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A05 | NAO |  | Diretorio Vendor | ISSUED |  | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-7180-10002 | TELECOMMUNICATIONS - WIRELESS LAN - COVERAGE CALCULATION REPORT | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-7180-10003 | BONGA NORTH SITE SURVEY REPORT | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A01 | NAO |  | Diretorio Vendor | ISSUED |  | IFI - ISSUED FOR INFORMATION |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-7180-10004 | TELECOMMUNICATIONS - CLOSED CIRCUIT TELEVISION (CCTV) - COVERAGE REPORT | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A04 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-7303-10001 | MATERIAL REQUISITION FOR TELECOM EQUIPMENT | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | R01 | NAO |  | Diretorio Vendor | CANCELADO |  |  |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-7303-10002 | SPECIFICATIONS FOR CLOSED CIRCUIT TV SYSTEM (CCTV) - MONITORING / DIGITAL VIDEO SURVEILLANCE | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A03 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-7303-10003 | SPECIFICATION FOR DATA NETWORKS (LAN-WAN) | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 3 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-7303-10004 | SPECIFICATIONS FOR STRUCTURED CABLING NETWORK | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A04 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-7303-10005 | SPECIFICATIONS FOR PUBLIC ADDRESS AND GENERAL ALARM (PAGA) | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A03 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-7303-10006 | SPECIFICATIONS FOR WIRELESS LAN | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A03 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-7303-10007 | SPECIFICATIONS FOR TELEPHONE SYSTEM | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A02 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-7303-10011 | MATERIAL REQUISITION FOR TELECOMS EQUIPMENT- CCTV | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A03 | NAO |  | Diretorio Vendor | ISSUED |  | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-7303-10012 | MATERIAL REQUISITION FOR TELECOMS EQUIPMENT- PAGA | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A04 | NAO |  | Diretorio Vendor | ISSUED |  | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-7303-10013 | MATERIAL REQUISITION FOR TELECOMS EQUIPMENT- TELEPHONE | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-7303-10014 | MATERIAL REQUISITION FOR TELECOMS EQUIPMENT- WIRELESS LAN | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A05 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-7303-10015 | MATERIAL REQUISITION FOR DATA NETWORKS | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A02 | NAO |  | Diretorio Vendor | ISSUED | IFA RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-7303-10016 | MATERIAL REQUISITION FOR STRUCTURED CABLING | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A02 | NAO |  | Diretorio Vendor | ISSUED |  | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-7303-10017 | MATERIAL REQUISITION FOR TELECOMS EQUIMENT- CABINET POWER AND ANCILLARIES | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A03 | NAO |  | Diretorio Vendor | ISSUED |  | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-7770-10001 | BONGA NORTH TELECOMMUNICATION FUNCTIONAL DESIGN SPECIFICATION | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED |  | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-8804-10001 | TELECOMMUNICATIONS - WIRELESS LAN - WIRING/TERMINATION DRAWING | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-8804-10002 | TELECOMMUNICATIONS - TELEPHONE SYSTEM - WIRING/TERMINATION DRAWING | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-8804-10003 | TELECOMMUNICATIONS - STRUCTURED CABLING NETWORK - WIRING/TERMINATION DRAWING | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-8804-10006 | TELECOMMUNICATIONS - DATA NETWORKS (LAN/WAN) - WIRING/TERMINATION DRAWING | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-8804-10007 | TELECOMMUNICATIONS - CLOSED CIRCUIT TV SYSTEM (CCTV) - MONITORING / DIGITAL VIDEO SURVEILLANCE - WIRING/TERMINATION DRAWING | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-8804-10008 | TELECOMMUNICATIONS - EQUIPMENT CABINET - WIRING/TERMINATION DRAWING | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-8804-10009 | TELECOMMUNICATIONS - FIBRE OPTIC SYSTEM - WIRING/TERMINATION DRAWING | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED |  | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-8804-10010 | CABINET POWER WIRING/TERMINATION DRAWING | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED |  | AFC/AFU - RELEASE |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-8804-10012 | TELECOMMUNICATIONS - PUBLIC ADDRESS AND GENERAL ALARM (PAGA) - WIRING/TERMINATION DRAWING | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | C01 | NAO |  | Diretorio Vendor | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU - APPROVED |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-RACIRT-300-TA-8804-10014 | TELECOMS CABLE ROUTING DRAWING | TA - TELECOMMUNICATIONS | TA - TELECOMMUNICATIONS | A01 | NAO |  | Diretorio Vendor | ISSUED |  | IFA - ISSUED FOR APPROVAL |  | BNO / 03-VENDOR / RADIAL_CIRCLE / RACIRT-(MTC)
BNO-WESTPAQ-DAE-2025-LT-10008 | 3D MODEL PROGRESS | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
BNO_APPROVAL STAMP | ENGINEERING APPROVAL STAMP TEMPLATE | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 00-TEMPLATES
BNO_COMMENT RESPONSE SHEET (CRS) - TEMPLATE_05-25 | CRS TEMPLATE | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 00-TEMPLATES
BNO_DOCUMENT TEMPLATE-UPDATED_05-25 - PMT | EXCEL TEMPLATE | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 00-TEMPLATES
BNO_DOCUMENT_TEMPLATE-UPDATED_05-25 - PMT | WORD TEMPLATE | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 00-TEMPLATES
BNO_DWG_A1_TEMPLATE_05-25 | DWG TEMPLATE | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 00-TEMPLATES
BNO_MINUTES OF MEETING_TEMPLATE-05-25 | MOM TEMPLATE | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 00-TEMPLATES
BNO_TRANSMITTAL NOTIFICATION_TEMPLATE_05-25A | TRANSMITTAL LETTER | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 00-TEMPLATES
BNO_VENDOR DOCUMENT REGISTER_TEMPLATE_05-25 | VENDOR DOCUMENT REGISTER TEMPLATE | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 00-TEMPLATES
BON-DAE-WESTPAQ-2025-LT-10006 | RE-REQUEST FOR ACCELERATION IN DED | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
BON-DAE-WESTPAQ-2025-LT-10007 | RE-MOBILIZATION OF ADDITIONAL PERSONNEL | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
BON-DAE-WESTPAQ-2025-LT-10008 | RE-PERFORMANCE AND PROGRESS REPORTING | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
BON-DAE-WESTPAQ-2025-LT-10009 | RE-3D MODEL PERFORMANCE AND PROGRESS | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
BON-DAE-WESTPAQ-2025-LT-10010 | PIPING SPECIFICATION AND PIPE WALL THICKNESS CALCULATION | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
BON-DAE-WESTPAQ-2025-LT-10013 | RE CRS _ BNO-MABU-300-JA-6611-10002 R05 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
BON-DAE-WESTPAQ-2025-LT-10014 | DELAY IN 60% E3D MODEL WORKSHOP DUE TO LACK OF CRITICAL VENDOR DATA | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
BON-DAE-WESTPAQ-2025-LT-10015 | BONGA NORTH COLLABORATION SITE (DED) RECORDS ALTERATION BY CONTRACTOR | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
BON-DAE-WESTPAQ-2025-LT-10021 | OVERDUE PIDS COMMENT FROM CONTRACTOR AND CONSEQUENT PROGRESS DELAY | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
BON-DAE-WESTPAQ-2025-LT-10022 | NOTICE OF WITHDRAWAL AND REPLACEMENT OF LEAD MECHANICAL ENGINEER | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
BON-DAE-WESTPAQ-2025-LT-10023 | NOTICE OF WITHDRAWAL AND REPLACEMENT OF SENIOR INTERFACE ENGINEER | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
BON-DAE-WESTPAQ-2025-LT-10024 | RE-OUTSTANDING PVNS | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
BON-DAE-WESTPAQ-2025-LT-10025 | NOTICE OF WITHDRAWAL AND REPLACEMENT OF SENIOR INTERFACE ENGINEER | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
BON-DAE-WESTPAQ-2025-LT-10026 | ADJUSTMENT OF THE SUBCONTRACT PRICE AND SCHEDULE OF KEY DATES | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
BON-DAE-WESTPAQ-2025-LT-10027 | VARIATION REQUEST TO ADJUST THE SCHEDULE OF KEY DATES | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
BON-DAE-WESTPAQ-2025-LT-10028 | ADJUSTMENT OF THE CONTRACT PRICE AND SCHEDULE OF KEY DATES | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
BON-DAE-WESTPAQ-2025-LT-10030 | NOTICE OF WITHDRAWAL AND REPLACEMENT OF LEAD MATERIALS AND CORROSION ENGINEER | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
BON-DAE-WESTPAQ-2026-LT-10003 | NOTICE OF WITHDRAWAL AND REPLACEMENT OF LEAD PROCESS ENGINEER | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
BON-DAE-WESTPAQ-2026-LT-10004 | IMMEDIATE MOBILISATION REQUIRED_AFC STRUCTURAL DRAWINGS | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
BON-DAE-WESTPAQ-2026-LT-10005 | NOTICE OF CONTRACTOR DEFAULT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
BONGA NORTH HAZOP P&IDS – MODIFICATIONS | BONGA NORTH HAZOP P&IDS – MODIFICATIONS | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
BONGA NORTH PMS - 2025-05-02 | DETAIL DESIGN - PROJECT MANAGEMENT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.000-PMS
BONGA NORTH PMS - 2025-05-09 | DETAIL DESIGN - PROJECT MANAGEMENT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.000-PMS
BONGA NORTH PMS - 2025-05-15 | DETAIL DESIGN - PROJECT MANAGEMENT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.000-PMS
BONGA NORTH PMS - 2025-06-07 | DETAIL DESIGN - PROJECT MANAGEMENT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.000-PMS
BONGA NORTH PMS - 2025-06-13 | DETAIL DESIGN - PROJECT MANAGEMENT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.000-PMS
BONGA NORTH PMS - 2025-06-27 | DETAIL DESIGN - PROJECT MANAGEMENT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.000-PMS
BONGA NORTH PMS - 2025-09-03 | DETAIL DESIGN - PROJECT MANAGEMENT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.000-PMS
BONGA NORTH PMS - 2025-09-11 | DETAIL DESIGN - PROJECT MANAGEMENT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.000-PMS
BONGA NORTH PMS - 2025-09-19 | DETAIL DESIGN - PROJECT MANAGEMENT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.000-PMS
BONGA NORTH PMS - 2025-09-30 | DETAIL DESIGN - PROJECT MANAGEMENT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.000-PMS
BONGA NORTH PMS - 2025-10-17 | DETAIL DESIGN - PROJECT MANAGEMENT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.000-PMS
BONGA NORTH PMS - 2025-11-07 | DETAIL DESIGN - PROJECT MANAGEMENT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.000-PMS
BONGA NORTH PMS - 2025-11-14 | DETAIL DESIGN - PROJECT MANAGEMENT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.000-PMS
BONGA NORTH PMS - 2025-11-21 | DETAIL DESIGN - PROJECT MANAGEMENT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.000-PMS
BONGA NORTH PMS - 2025-12-02 | DETAIL DESIGN - PROJECT MANAGEMENT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.000-PMS
BONGA NORTH PMS - 2025-12-05 | DETAIL DESIGN - PROJECT MANAGEMENT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.000-PMS
BONGA NORTH PMS - 2025-12-19 | DETAIL DESIGN - PROJECT MANAGEMENT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.000-PMS
BONGA NORTH PMS - 2026-01-16 | DETAIL DESIGN - PROJECT MANAGEMENT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.000-PMS
BONGA NORTH PMS - 2026-01-23 | DETAIL DESIGN - PROJECT MANAGEMENT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.000-PMS
BONGA NORTH PMS - 2026-02-06 | DETAIL DESIGN - PROJECT MANAGEMENT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.000-PMS
BONGA NORTH PMS - 2026-02-13 | DETAIL DESIGN - PROJECT MANAGEMENT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.000-PMS
BONGA NORTH PMS - 2026-02-20 | DETAIL DESIGN - PROJECT MANAGEMENT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.000-PMS
BONGA NORTH PMS - 2026-02-27 | DETAIL DESIGN - PROJECT MANAGEMENT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.000-PMS
BONGA NORTH PMS - 2026-03-01 | DETAIL DESIGN - PROJECT MANAGEMENT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.000-PMS
BONGA NORTH PMS - 2026-03-06 | DETAIL DESIGN - PROJECT MANAGEMENT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.000-PMS
BONGA NORTH PMS - 2026-03-13 | DETAIL DESIGN - PROJECT MANAGEMENT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.000-PMS
BONGA NORTH PMS - 2026-03-20 | DETAIL DESIGN - PROJECT MANAGEMENT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.000-PMS
BONGA NORTH PMS - 2026-04-03 | DETAIL DESIGN - PROJECT MANAGEMENT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.000-PMS
BONGA NORTH PMS - 2026-04-10 | DETAIL DESIGN - PROJECT MANAGEMENT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.000-PMS
BONGA NORTH PMS - 2026-04-17 | DETAIL DESIGN - PROJECT MANAGEMENT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.000-PMS
BONGA NORTH PMS - 2026-04-24 | DETAIL DESIGN - PROJECT MANAGEMENT SCHEDULE | FA - COST AND PLANNING | FA - COST AND PLANNING | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.000-PMS
BONGA NORTH PROJECT (EPC1 ) DED - MDR CHANGE NOTICE FORM - INSTRUMENTATION NO. 29 |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1 ) DED - MDR CHANGE_NOTICE_STRUCTURAL_ VALVE DECK EXTENSION |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1 ) DED - MDR CHANGE_NOTICE_STRUCTURAL_SPS |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1 ) DED - MDR CHANGE_NOTICE_STRUCTURAL_STRUCTURAL |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR 05 CHANGE NOTICE - DELETED DELIVERABLES |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR 05 CHANGE NOTICE - MODIFIED DELIVERABLES |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR 05 CHANGE NOTICE - PMT-2 |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE - 01X_STRUCTURAL |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE - 10-11-2025 PIPING |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE - CORROSSION INHIBITOR DRAWING |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE - DEMOLITION DRAWING FOR SS MODULE |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE - INSTRUMENTATION F&G DETECTION SYSTEM |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE - PROCESS & INSTRUMENTATION |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE - RM FOR SPECIAL PIPE SUPPORT |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE - STRUCTURAL |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE - STRUCTURAL HPU_DECK_EXTENSION |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE - STRUCTURAL SPECIAL PIPE SUPPORT |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE - WI PUMP HANDLING AREA |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - 09 APR 2026 |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - 21 APR 2026_ELECTRICAL |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - 22 APR 2026 |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - 07042026_-_STRUCTURAL |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - 09 APR 2026 ELECTRICAL |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - 29-04-26 |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - 7-04-26 - STRUCTURES |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - CONSTRUCTABILITY REVIEW |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - HANDLING EQUIPMENT_STRUCTURAL |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - INSTRUMENTATION NO. 13 |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - INSTRUMENTATION NO. 22 |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - INSTRUMENTATION NO. 26 |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - INSTRUMENTATION NO. 4 |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - INSTRUMENTATION NO. 6 |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - INSTRUMENTATION NO.10 |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - INSTRUMENTATION NO5. |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - PMT |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - PMT - 90%MR |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - PMT - 90%MR P2 |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - PMT 90% CONSTRUCTABILITY REVIEW REPORT |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - PROCESS AIR SERVICE HEADER DISTRIBUTION |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - PROCESS P&ID - UTILITY SYSTEMS HYDRATE INHIBITOR INJECTION PUMPS |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - SPS STRUCTURAL |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - STRUCTURES (SSCB-CONTROL-BUILDING-FOUNDATION STOOLS) |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - STRUCTURES GENERAL NOTES |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - STRUCTURES HPU ROOF |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - STRUCTURES PIG LAUNCHER RECIEVER |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - STRUCTURES-WFW |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - STRUCTURES_18022026 |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - STRUCTURES_HPU-005 |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - STRUCTURES_MR4 |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - TERMS OF REFERENCE FOR MECHANICAL HANDLIN |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM - WALKWAY AND STAIRS |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM PROCESS AIR SERVICE HEADER DISTRIBUTION |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM-SMART CHOKE_STRUCTURAL |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM_01192026 - STRUCTURES |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM_01232026 (4018-10042) - STRUCTURES |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM_07 JAN_ELECTRICAL |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM_24 FEB 2026 |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM_25 MAR 2026_ELECTRICAL |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM_MECHANICAL |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM_WATER INJECTION TURBINE SKID - STRUCTURE.PD |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE FORM_WI TURBINE - WALKWAYS AND STAIRS |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE_03112026 - STRUCTURAL |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE_12032026 - STRUCTURAL |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE_DATASHEET FOR INTERLOCKS |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE_STRUCTURAL |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE_STRUCTURAL (4018-10042) |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
BONGA NORTH PROJECT (EPC1) DED - MDR CHANGE NOTICE_STRUCTURES_MONORAIL |  | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.007-MDR_CHANGE NOTICE
CERTIFIED VENDOR FOR INLINE MANUAL VALVES AND SPS | CERTIFIED VENDOR FOR INLINE MANUAL VALVES AND SPS | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
KICK-OFF MEETING PRESENTATION_DOC. CTRL | DCC KOM PRESENTATION | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 00-TEMPLATES
MABU - EPC1- MOC REQUEST FORM TEMPLATE | TEMPLATE FORM FOR MOC | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 00-TEMPLATES
MABU - KICK-OFF (DOCUMENT CONTROL) | PACKAGE TO BE ISSUED TO VENDORS | IT / IM | JA - IM | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 00-TEMPLATES
MILESTONE 4.6_NOTIFICATION OF COMPLETION_ELECTRICAL | NOTIFICATION OF COMPLETION_4.6_ELECTRICAL DELIVERABLES CRITICAL FOR ENGINEERING REVIEWS AS IDENTIFIED IN MDR - ISSUE FOR REVIEW (IFR-2) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
MILESTONE 5.1 | NOTIFICATION OF COMPLETION ENGINEERING REVIEWS - INTEGRATED DESIGN REVIEW, DETAILED DESIGN HAZOP(S) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
MONTHLY BACKUP FILES FOR THE E3D, SPPID, AND SPI PROJECT DATA FOR JULY 2025 |  | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
NOTIFICATION OF COMPLETION - 11413-PVN-DAE-BONGA-00018 P0 - P1 90_ MODEL REVIEW WORKSHOP REV1 | NOTIFICATION OF COMPLETION - 11413-PVN-DAE-BONGA-00018 P0 - P1 90_ MODEL REVIEW WORKSHOP REV1=A01 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
NOTIFICATION OF COMPLETION 4.3 | NOTIFICATION OF COMPLETION 4.3 - MECHANICAL DELIVERABLES CRITICAL FOR ENGINEERING REVIEWS AS IDENTIFIED | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
NOTIFICATION OF COMPLETION 4.4 | NOTIFICATION OF COMPLETION FOR PIPING DELIVERABLES CRITICAL FOR ENGINEERING REVIEWS AS IDENTIFIED IN MDR - ISSUE FOR REVIEW (IFR-2)_4.4 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
NOTIFICATION OF COMPLETION 4.5 | NOTIFICATION OF COMPLETION 4.5 - STRUCTURAL DELIVERABLES CRITICAL FOR ENGINEERING REVIEWS AS IDENTIFIED | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
NOTIFICATION OF COMPLETION 4.7 | NOTIFICATION OF COMPLETION 4.7 - INSTRUMENTATION AND AUTOMATION DELIVERABLES CRITICAL FOR ENGINEERING. | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
NOTIFICATION OF COMPLETION 4.8 | NOTIFICATION OF COMPLETION 4.8 - TECHNICAL SAFETY DELIVERABLES CRITICAL FOR ENGINEERING REVIEWS AS IDENTIFIED | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
NOTIFICATION OF COMPLETION 5.2 | NOTIFICATION OF COMPLETION FOR ENGINEERING REVIEWS - SIL, 60% MODEL REVIEW, CONSTRUCTABILITY REVIEW AND ISSUE REPORTS (IFR)_5.2 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
NOTIFICATION OF COMPLETION FOR 11413-PVN-DAE-BONGA-00010 | NOTIFICATION OF COMPLETION FOR 11413-PVN-DAE-BONGA-00010=A01 - - EXPENSES FOR 1ST AND PRIORITY 0 &1 MODEL REVIEW WORKSHOPS.DOCX | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Numero do documento excluido por regra | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
NOTIFICATION OF COMPLETION_3.1 | NOTIFICATION OF COMPLETION DETAILED DESIGN PHILOSOPHIES, PROJECT DESIGN BASIS AND ISSUE IFR .DOCX | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
NOTIFICATION OF COMPLETION_3.2 | NOTIFICATION OF COMPLETION PROCESS SIMULATIONS AND HMB.DOCX | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
NOTIFICATION OF COMPLETION_4.2 | NOTIFICATION_OF_COMPLETION_PROCESS_DELIVERABLES_CRITICAL_FOR_ENGINEERING_REVIEWS_AS_IDENTIFIED_IN_MDR | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
NOTIFICATION OF COMPLETION_6.2 | MECHANICAL ENGINEERING DESIGN PACKAGE | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
NOTIFICATION OF COMPLETION_MILESTON 6.1 | NOTIFICATION OF COMPLETION FOR PROCESS ENGINEERING DESIGN PACKAGE - APPROVED FOR CONSTRUCTION | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
NOTIFICATION OF COMPLETION_MILESTONE 5.2 | NOTIFICATION OF COMPLETION - ENGINEERING REVIEWS - SIL, 60% MODEL REVIEW, CONSTRUCTABILITY REVIEW AND ISSUE REPORTS (IFR) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
NOTIFICATION OF COMPLETION_MILESTONE 5.3 | NOTIFICATION OF COMPLETION FOR ENGINEERING REVIEWS - ENGINEERING REVIEWS - SIMOPS, ALARM RATIONALIZATION; SAFETY AND OPERABILITY STUDY (SAFOP) AND ISSUE REPORTS (IFR) | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
NOTIFICATION OF COMPLETION_MILESTONE 5.4 | NOTIFICATION OF COMPLETION_MILESTONE 5.4_ FOR ENGINEERG REVIEWS - DESIGN SAFETY CASE; 90% 3D MODEL REVIEWS; 2ND CONSTRUCTABILITY REV & ISSUE REPORT | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
PPF-173 | SINGLE TENDER JUSTIFICATION FORM PPF-173_BONGA NORTH_SIL & ALARM RATIONALIZATION.DOC._A01 | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER
TBE BN-070.001_VO_MAT REQ TO QUICK CONNECT COUPLING P-S | TBE BN-070.001_VO_MAT REQ TO QUICK CONNECT COUPLING P-S | NÃO SE APLICA | NÃO SE APLICA | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.300-DAE_PROCUREMENT / 02.301-DAE_TBE
TQR-MABU-ENG-004 | SPPID AND SPI VERSION | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-005 | METHANOL PUMPS SUPPLY ELECTRICAL PANEL | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-006 | LOAD SHEDDING SYSTEM | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-007 | ELECTRICAL PANELS DOCUMENTS | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-008 | ELECTRICAL CIRCUIT TAG | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-009 | SPPID AND SPI VERSION | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-010 | DBR DOCUMENT/DRAWING NUMBER - STAMP | PMT | AA - PROJECT MANAGEMENT | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-011 | DOCUMENT REQUEST | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-012 | DBR STAMP FOR LIMITED RESPONSABILITY | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-013 | DOCUMENT REQUEST | PIPING | MP - PIPING | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-014 | DOCUMENT REQUEST | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-015 | SPEL DATABASE | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-016 | PIG LAUNCHER STANDARDS | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-017 | EXISTING INTERLOCK SYSTEM | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-018 | PROCEDURE FOR INTERLOCK SYSTEM | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-019 | INSTRUMENTS DATA SHEETS REQUEST | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-020 | SACS IMPUT FILES REQUEST | STRUCTURAL | CS - STRUCTURAL | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-021 | PIG LAUNCHER DATA SHEET | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-022 | METHANOL PUMP MATERIAL SPECIFICATION | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-023 | ELECTRICAL LOADS FROM EPC2 AND EPC3 | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-024 | 3D MODEL - TURBINE | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-025 | 3D MODEL - DARK BLUE ELEMENT | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-026 | 3D MODEL - DARK BLUE ELEMENT | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-027 | RESPOND TIME | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-028 | HYSYS SIMULATION | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-029 | DESPRESSURIZATION CRITERIA | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-030 | MATERIAL BALANCE CLARIFICATION | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-031 | REQUEST FOR SPI DATABASE UPDATED | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-032 | OIL FLOW LIMIT CONDITION | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-033 | FLOWSHEET LEGEND | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-034 | IAMS SERVER / CLIENT LOCATION | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-035 | MISSING PROCESS DATA IN SPPID AND SPI | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-036 | PVT REPORTS | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-037 | AUTOMATION STANDARDIZATION | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-038 | SPPID DATA | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-039 | SAND DETECTOR | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-040 | WELLS PRODUCTION PROFILE/FORECAST | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-041 | DEMOLITION DRAWINGS SPPID DATABASE | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-042 | TRANSFORMERS CTS | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-043 | ESSENTIAL AND EMERG. GENERATORS LOAD | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-044 | BACKWASH FILTERS LINE TO REMOVE | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-045 | CHANGE OF FAILURE MODE OF BDV | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-046 | ELECTRICAL STUDIES ETAP | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-047 | LAYDOWN ON THE TOP OF SSCB | STRUCTURAL | CS - STRUCTURAL | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-048 | FILTER PRESSURE DROP | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-049 | FAILURE MODE OF MOVS AND SDVS | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-050 | DELETE SAND DETECTOR / EROSION PROBE | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-051 | ALARM AND SET POINT LIST | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-052 | CABLE SIZING | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-053 | LAYOUT WATERF. DECK EXTENSION LEVEL 1 | STRUCTURAL | CS - STRUCTURAL | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-054 | MPFM - POSSIBLE SOLUTION | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-055 | SPECIAL ITEMS SPECIFICATION | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-056 | BN SAFEGUARDING MEMORANDUM | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-057 | DATA SHEET SMALL AND LARGE BALL VALVE | PIPING | MP - PIPING | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-058 | SPACE HEATERS FOR MOTORS | ELECTRICAL | EA - ELECTRICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-059 | SSCB ELECTRICAL ROOM DOORS X REMOVABLE | STRUCTURAL | CS - STRUCTURAL | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-060 | POWELL PANELS IN SSCB ELECTRICAL ROOM | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-061 | STRESS ANALYSIS CALCULATION | PIPING | MP - PIPING | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-062 | ADDITIONAL RECOMMENDATIONS FOR SPEC "J1" | PIPING | MP - PIPING | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-063 | MATERIALS FOR WETTED PARTS IN WI VALVES | MATERIALS | RA - MATERIALS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-064 | CORROSION INHIBITOR PUMPS LOCATION | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-065 | NORMAL/ESSENTIAL/EMERG. - CLASSIF. SOCIETY | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-066 | TAG'S FOR EQUIPMENTS IN SSCB - REV1 | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-067 | DIESEL FUEL PUMP AND AIR COMPRESSOR | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-068 | STRUCTURE TO SUPPORT METHANOL PUMPS | STRUCTURAL | CS - STRUCTURAL | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-069 | DATA SHEETS FOR GATE AND NEEDLE VALVES | PIPING | MP - PIPING | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-070 | NEW SKID AND INSTRUMENT FOR P-4046A PUMP | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-071 | EXPLOSION OVERPRESSURE CRITERIA | TECHNICAL SAFETY | HS - SAFETY | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-072 | PIPING STRESS ANALYSIS - SLUVVVING CONSID. | PIPING | MP - PIPING | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-073 | DEPRESSURIZATION STUDY | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-074 | DROPPED OBJECTS | TECHNICAL SAFETY | HS - SAFETY | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-075 | TRANSFORMER SUPPLIER | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-076 | CANCELADA | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-077 | CABLE ROUTE TO CONTROL ROOM | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-078 | CHANGE THE FLOWMETER TYPE (44-FIT-503) | INSTRUMENTATION | IN - INSTRUMENTATION | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-079 | DOCUMENT SHARING (PT-4040A) | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-080 | METHANOL LINES | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-081 | HAZOP RECOMENDATION NUMBER 30 | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-082 | HAZOP RECOMENDATION NUMBER 23 | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-083 | SOUR SERVICE FOR CRA IN WET H2S COUNT.LINES | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-084 | FIRE SUPRESSION TO SSCB | TECHNICAL SAFETY | HS - SAFETY | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-085 | PIPING MATERIAL FOR METHANOL SERVICE | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-086 | SMART CHOKE VALVE PRESSURE DROP | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-087 | VENDOR DEFINITION FOR GRE (RTR) PIPING | PIPING | MP - PIPING | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-088 | WATERFLOOD INJECTION PUMP SUCTION MATERIAL | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-089 | FIREWATER AND DELUGE P&IDS | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-090 | DR2 - PUNCH LIST ITEM 23 - PIPING ARRANGEMENT | PIPING | MP - PIPING | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-091 | TEMPERATURE GAUGE TYPE (04-TG-468 AND 04-TG-469) | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-092 | CAUSE AND EFFECT REFERENCE DOCUMENTS | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-093 | MABU 2026 TAM SCOPE | CONSTRUCTION | BA - CONSTRUCTION | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-094 | PORT SUBSEA INDUCING VIBRATION IN SSCB | STRUCTURAL | CS - STRUCTURAL | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-095 | CABLE SUPPLIER | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-096 | DROPPED OBJECTS OVER SSCB | TECHNICAL SAFETY | HS - SAFETY | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-097 | APPROVED VENDOR FOR THE ON/OFF VALVES | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-098 | APPROVED VENDOR FOR PRESSURE RELIEF VALVE | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-099 | METHANOL LINES - PUMP P-4270 | PIPING | MP - PIPING | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-100 | DELUGE WATER SPRAY NOZZLE | TECHNICAL SAFETY | HS - SAFETY | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-101 | WATERFLOOD DISCHARGE LINE 10.000PSI SSDD | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-102 | REQUEST OF EXISTING ELECTRICAL PANELS DRAWINGS | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-103 | MATERIALS FOR VALVES WI SERVICE - SPEC J1 | PIPING | MP - PIPING | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-104 | MARINE CERTIFICATION - PROCESS EQUIPMENT | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-105 | STRUCTURAL WELDING QUALIFICATION - AVEON | CONSTRUCTION | BA - CONSTRUCTION | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-106 | REQUEST FOR THE USE OF BOLTED CONNECTION FOR SUPPORTS | CONSTRUCTION | BA - CONSTRUCTION | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-107 | MARINE CERTIFICATION - PROCESS EQUIPMENT | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-108 | AIR LOCKS REMOVAL | STRUCTURAL | CS - STRUCTURAL | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-109 | DESIGN ALLOWANCE TO HEAT DISSIPATION TO HVAC CALCULATION | MECHANICAL | MH - HVAC | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-110 | CABLE TRAYS AND LADDERS FOR INTERNAL CABLE CONTAINMENT | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-111 | TRANSFORMER BUNDING | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-112 | ALTERNATIVE MATERIAL - TANK OF TRANSFORMERS | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-113 | TOPSIDE PIGABLE PRODUCTION LINE THICKNESS | PIPING | MP - PIPING | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-114 | ROOM PRESSURIZATION AFTER REMOVAL OF AIRLOCK | MECHANICAL | MH - HVAC | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-115 | SAFETY MARGIN PERCENTAGE FOR HVAC CALCULATION | MECHANICAL | MH - HVAC | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-116 | KAMOS GASKETS FOR LEAK TEST OF FLANGES | PIPING | MP - PIPING | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-117 | DIESEL LINE CANCELLING | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-118 | GANGWAY LANDING PLATFORM | SA - LOGISTICS | SA - LOGISTICS | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-119 | BN PIPING SPECIFICATION | PIPING | MP - PIPING | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-120 | INSPECTION REPORT OF EXISTING BN PIPING TIE-INS | CONSTRUCTION | BA - CONSTRUCTION | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-121 | PIG LAUNCHING / RECEIVING REFERENCE DOCUMENTS | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-122 | STRUCTURAL WELDING QUALIFICATION ON PLATE (BOP) TEST - AVEON | CONSTRUCTION | BA - CONSTRUCTION | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-123 | VAPOR PRESSURE OF THE CORROSION INHIBITOR | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-124 | REQUEST FOR BONGA MAIN LINE LIST | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-125 | SPECIFICATION FOR GAS LIFT PIPE/TUBING FROM GAS LIFT MANIFOLD TO BGLU-17 | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-126 | REQUEST FOR HOOK-UP DOCUMENT FOR METHANOL SUPPLY | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-127 | METHANOL SOURCE TO BE ROUTED TO WHICH TUPA | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-128 | STRUCTURAL INFORMATION FOR MAIN RACK 4 | STRUCTURAL | CS - STRUCTURAL | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-129 | NATIVE FILES FOR BONGA MAIN FIREWATER PUMPS & NETWORK P&ID AND DELUGE DISTRIBUTION P&ID | TECHNICAL SAFETY | HS - SAFETY | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-130 | SAFETY DOCUMENTS AND DEPS | TECHNICAL SAFETY | HS - SAFETY | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-131 | COATING/ PAINTING STANDARDS FOR LABELING MATERIALS | CONSTRUCTION | BA - CONSTRUCTION | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-132 | COMPANY SP-ITEM TAGGING | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-133 | PROPOSAL TO USE CS CLADDED INSTEAD OF SDSS | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-134 | PWHT REQUIREMENT FOR LINES | CONSTRUCTION | BA - CONSTRUCTION | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-135 | ENSURING ESCAPE ROUTE AROUND EXISTING HPU | MECHANICAL | MH - HVAC | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-136 | METHANOL PUMPS TO BE DISMANTLED X UMBILICAL TERMINATION PANELS | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-137 | CABLE ENTRANCE IN HPU X WALKWAY | ELECTRICAL | EA - ELECTRICAL | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-138 | REQUEST FOR DOCUMENT TO RAM STUDY | BC - COMMISSIONING | BC - COMMISSIONING | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-139 | DESIGN PARAMETERS FOR DAMAGE CONDITION | STRUCTURAL | CS - STRUCTURAL | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-140 | DROPPED OBJECT PROTECTION | STRUCTURAL | CS - STRUCTURAL | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-141 | CORRELATION GAS LIFT MANIFOLD X BGLU-17 | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-142 | PROPOSAL TO USE CS CLADDED INSTEAD OF SDSS - 2 | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-143 | ARRANGMENT OF THE MAC GATWAY CABINET | INSTRUMENTATION | IN - INSTRUMENTATION | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-144 | PROPOSAL FOR EXTENDED BEAM AND SUPPORT POSITION | STRUCTURAL | CS - STRUCTURAL | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-145 | DRAIN SEGREGATION | PROCESS | PX - PROCESS | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-146 | ACQUISITION OF PIPE "SEAMED" SUPER DUPLEX STAINLESS STEEL. | PIPING | MP - PIPING | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-147 | NPSH OF GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MECHANICAL | MX - OVERAL MECHANICAL | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-148 | BONGA MAIN ASSUMPTION REGISTER SAFETY STUDIES AND MANNING DISTRIBUTION DATA | TECHNICAL SAFETY | HS - SAFETY | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-149 | FRED SOFTWARE INSTEAD OF PHAST DNV FOR FIRE AND EXPLOSION ANALYSIS | TECHNICAL SAFETY | HS - SAFETY | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-150 | BONGA MAIN EXHAUST DATA FOR TURBINE GENERATORS | TECHNICAL SAFETY | HS - SAFETY | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-151 | NOISE EXISTING WF PUMP AND LUBE OIL ON BONGA MAIN | TECHNICAL SAFETY | HS - SAFETY | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-152 | METHANOL PUMPS TO BE DISMANTLED X UMBILICAL TERMINATION PANELS | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-153 | BONGA MAIN FLARE STUDY - APPENDIX 3 FLARENET RUNS | PROCESS | PX - PROCESS | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-154 | SSCB DROPPED OBJECT DIMENSIONS | STRUCTURAL | CS - STRUCTURAL | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-155 | DROPPED OBJECT PROTECTION FOR THE NEW HPU | STRUCTURAL | CS - STRUCTURAL | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-156 | COMPANY INSTRUMENT AIR DISTRIBUTION P&IDS. | TECHNICAL SAFETY | HS - SAFETY | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-157 | ADDITIONAL CHECK VALVE AGAINST REVERSE FLOW FROM P-4046A | TECHNICAL SAFETY | HS - SAFETY | A01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-158 | TBD | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-159 | TBD | MECHANICAL | MX - OVERAL MECHANICAL | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TQR-MABU-ENG-160 | TBD | PIPING | MP - PIPING | R01 | NAO |  | Nao aplicavel/cancelado | CANCELADO |  |  |  | BNO / 01.1-MABU_TQR
TUBINGS FOR QUOTATION - PARKER OFFER TBE | TUBINGS FOR QUOTATION - PARKER OFFER TBE | NÃO SE APLICA | NÃO SE APLICA | A01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.300-DAE_PROCUREMENT / 02.301-DAE_TBE
WPQ-DAE-DED-0001 | NOTIFICATION OF COMPLETION FOR ENGINEERING REVIEWS - BOWTIE AND HAZID_MILESTONE 4.1& 5.5 | PMT | AA - PROJECT MANAGEMENT | R01 | NAO |  | Nao aplicavel/cancelado | NÃO SE APLICA |  |  |  | BNO / 02-DED / 02.004-OTHER

## Resumo
Base AOL editavel
Edite Contabilizar e Status AOL. Depois importe este arquivo novamente para tornar a base oficial.
Item | Valor
Importacao AOL | #9 - 2026-05-27_07-31-35_381.xlsx
Linhas brutas | 4750
Contabilizadas | 1264
Desconsideradas | 2827
Aba para editar | Base AOL