## Summary
Engineering x EDROBO Difference
Comparison between active Engineering Base and EDROBO REPORT DED 27-05-26.xlsx
Metric | Value | Comment
Engineering active import | #3 - DED Status 22-05-26c.xlsx | Current dashboard engineering base
EDROBO report | EDROBO REPORT DED 27-05-26.xlsx | External/export file supplied for this comparison
Engineering documents | 1349 | Documents counted in active EngineeringStatusImport
EDROBO documents | 1347 | Rows counted in EDROBO Sheet1
Common documents | 1332 | Document Number exists in both bases
Only in Engineering Base | 17 | Needs to be added to EDROBO to match Engineering, or removed from Engineering if EDROBO is master
Only in EDROBO | 15 | Needs to be removed from EDROBO to match Engineering, or added to Engineering if EDROBO is master
Status differences | 319 | Same document but different final/status bucket
Status differences - source changed | 246 | Issue Status, Document Status or Revision changed between sources
Status differences - classification only | 73 | Same source fields but different status mapping
Revision differences | 88 | Same document with different revision
Document Status differences | 189 | Raw source field differs
Issue Status differences | 331 | Raw source field differs
Title differences | 11 | Usually wording/update only
Discipline differences | 0 | IM / IT normalized to IT / IM before comparing
Conclusion
The bases are not equal. Most status differences come from changed source fields, not only from calculation/classification.
If the target is to match the active Engineering Base exactly, apply the actions in the detail sheets: add/remove presence gaps, change 319 statuses and review 88 revisions.
If EDROBO is the current source-of-truth, the active Engineering Base looks stale because it is based on DED Status 22-05-26c.xlsx while the EDROBO report is dated 27-05-26.

## Status Summary
Status Summary
Delta = EDROBO minus Engineering Base
Status | Engineering Base | EDROBO | Delta | Action to match Engineering Base
AFC 1 | 626 | 617 | -9 | EDROBO has fewer; add/reclassify to match Engineering
AFC 3 | 234 | 157 | -77 | EDROBO has fewer; add/reclassify to match Engineering
AFC 3A | 0 | 23 | 23 | EDROBO has more; reduce/reclassify to match Engineering
IFA | 84 | 203 | 119 | EDROBO has more; reduce/reclassify to match Engineering
IFR | 171 | 206 | 35 | EDROBO has more; reduce/reclassify to match Engineering
NI | 65 | 35 | -30 | EDROBO has fewer; add/reclassify to match Engineering
UNDER REVIEW | 169 | 106 | -63 | EDROBO has fewer; add/reclassify to match Engineering

## Discipline Summary
Discipline Summary
Delta = EDROBO minus Engineering Base
Discipline | Engineering Base | EDROBO | Delta | Action
CONSTRUCTION | 7 | 7 | 0 | OK
ELECTRICAL | 133 | 134 | 1 | Presence differs; review Only in sheets
INSTRUMENTATION | 144 | 143 | -1 | Presence differs; review Only in sheets
IT / IM | 12 | 12 | 0 | OK
MATERIALS | 139 | 140 | 1 | Presence differs; review Only in sheets
MECHANICAL | 31 | 31 | 0 | OK
PIPING | 347 | 353 | 6 | Presence differs; review Only in sheets
PMT | 10 | 11 | 1 | Presence differs; review Only in sheets
PROCESS | 121 | 122 | 1 | Presence differs; review Only in sheets
STRUCTURAL | 348 | 334 | -14 | Presence differs; review Only in sheets
TECHNICAL SAFETY | 57 | 60 | 3 | Presence differs; review Only in sheets

## Only in Engineering
Only in Engineering Base
Documents counted in Engineering Base and absent from EDROBO Sheet1
Document Number | Base Document Number | Discipline | Revision | Engineering Status | Document Status | Issue Status | Title | Required Action
BNO-MABU-300-CS-1448-10001-004 | BNO-MABU-300-CS-1448-10001 | STRUCTURAL | R01 | IFA | ISSUED | IFA RETURNED AS CODE 3 | WEIGHT CONTROL REPORT - OCTOBER 2025 | Add/include this document in EDROBO to match Engineering Base. If EDROBO is master, validate whether Engineering Base should remove it.
BNO-MABU-300-CS-4018-10023-005 | BNO-MABU-300-CS-4018-10023 | STRUCTURAL | A01 | IFA | ISSUED | IFA RETURNED AS CODE 3 | WATER INJECTION TURBINE SKID - STRUCTURE - WALKWAYS AND STAIRS - PART 5 | Add/include this document in EDROBO to match Engineering Base. If EDROBO is master, validate whether Engineering Base should remove it.
BNO-MABU-300-CS-4018-10024-001 | BNO-MABU-300-CS-4018-10024 | STRUCTURAL | R01 | IFR | ISSUED | IFR RETURNED AS CODE 2 | WATER INJECTION TURBINE SKID - STRUCTURE - WALKWAYS AND STAIRS | Add/include this document in EDROBO to match Engineering Base. If EDROBO is master, validate whether Engineering Base should remove it.
BNO-MABU-300-CS-4018-10024-002 | BNO-MABU-300-CS-4018-10024 | STRUCTURAL | R01 | IFR | ISSUED | IFR RETURNED AS CODE 2 | WATER INJECTION TURBINE SKID - STRUCTURE - WALKWAYS AND STAIRS | Add/include this document in EDROBO to match Engineering Base. If EDROBO is master, validate whether Engineering Base should remove it.
BNO-MABU-300-CS-4018-10051-009 | BNO-MABU-300-CS-4018-10051 | STRUCTURAL | R01 | IFR | ISSUED | IFR RETURNED AS CODE 3 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0020 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | Add/include this document in EDROBO to match Engineering Base. If EDROBO is master, validate whether Engineering Base should remove it.
BNO-MABU-300-CS-4018-10051-016 | BNO-MABU-300-CS-4018-10051 | STRUCTURAL | R01 | IFR | ISSUED | IFR RETURNED AS CODE 3 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0026 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | Add/include this document in EDROBO to match Engineering Base. If EDROBO is master, validate whether Engineering Base should remove it.
BNO-MABU-300-CS-4018-10051-021 | BNO-MABU-300-CS-4018-10051 | STRUCTURAL | R01 | IFR | ISSUED | IFR RETURNED AS CODE 3 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0003 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | Add/include this document in EDROBO to match Engineering Base. If EDROBO is master, validate whether Engineering Base should remove it.
BNO-MABU-300-CS-4018-10051-023 | BNO-MABU-300-CS-4018-10051 | STRUCTURAL | R01 | IFR | ISSUED | IFR RETURNED AS CODE 3 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0031 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | Add/include this document in EDROBO to match Engineering Base. If EDROBO is master, validate whether Engineering Base should remove it.
BNO-MABU-300-CS-4018-10051-038 | BNO-MABU-300-CS-4018-10051 | STRUCTURAL | R01 | IFR | ISSUED | IFR RETURNED AS CODE 3 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0034 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | Add/include this document in EDROBO to match Engineering Base. If EDROBO is master, validate whether Engineering Base should remove it.
BNO-MABU-300-CS-4018-10051-049 | BNO-MABU-300-CS-4018-10051 | STRUCTURAL | R01 | IFR | ISSUED | IFR RETURNED AS CODE 3 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0106 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | Add/include this document in EDROBO to match Engineering Base. If EDROBO is master, validate whether Engineering Base should remove it.
BNO-MABU-300-CS-4018-10051-060 | BNO-MABU-300-CS-4018-10051 | STRUCTURAL | C01 | AFC 1 | ISSUED | AFC/AFU RETURNED AS CODE 1 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0089 - TEMPORARY PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | Add/include this document in EDROBO to match Engineering Base. If EDROBO is master, validate whether Engineering Base should remove it.
BNO-MABU-300-CS-4018-10088-002 | BNO-MABU-300-CS-4018-10088 | STRUCTURAL | A01 | IFA | ISSUED | IFA RETURNED AS CODE 3 | MAIN RACK 2 MODULE - WATER INJECTION TURBINE SKID LEVEL1 ACCESS PLATFORM | Add/include this document in EDROBO to match Engineering Base. If EDROBO is master, validate whether Engineering Base should remove it.
BNO-MABU-300-CS-8102-10010 | BNO-MABU-300-CS-8102-10010 | STRUCTURAL | R01 | NI | NÃO SE APLICA | - | WATER INJECTION TURBINE STRUCTURE CALCULATION MEMORY | Add/include this document in EDROBO to match Engineering Base. If EDROBO is master, validate whether Engineering Base should remove it.
BNO-MABU-300-CS-8180-10011 | BNO-MABU-300-CS-8180-10011 | STRUCTURAL | R01 | NI | NÃO SE APLICA | - | STARBOARD SUBSEA MODULE - STRUCTURAL CALCULATION REPORT - BONGA NORTH MODIFICATIONS | Add/include this document in EDROBO to match Engineering Base. If EDROBO is master, validate whether Engineering Base should remove it.
BNO-MABU-300-IN-7303-10035 | BNO-MABU-300-IN-7303-10035 | INSTRUMENTATION | R01 | NI | NÃO SE APLICA | - | MATERIAL REQUISITION FOR CABLE TRAYS. CHANNELS AND ACCESSORIES | Add/include this document in EDROBO to match Engineering Base. If EDROBO is master, validate whether Engineering Base should remove it.
BNO-MABU-300-MP-3323-10008 | BNO-MABU-300-MP-3323-10008 | PIPING | A01 | AFC 3 | ISSUED | - | TBE FOR PRODUCTION & GAS LIFT HEAVY WALL PIPING | Add/include this document in EDROBO to match Engineering Base. If EDROBO is master, validate whether Engineering Base should remove it.
BNO-MABU-300-MP-3323-10010 | BNO-MABU-300-MP-3323-10010 | PIPING | A01 | AFC 3 | ISSUED | - | TBE FOR WI HEAVY WALL INCONEL CLAD PIPING & FITTINGS | Add/include this document in EDROBO to match Engineering Base. If EDROBO is master, validate whether Engineering Base should remove it.

## Only in EDROBO
Only in EDROBO
Documents counted in EDROBO Sheet1 and absent from Engineering Base
Document Number | Base Document Number | Discipline | Revision | EDROBO Status | Document Status | Issue Status | Title | Required Action
BNO-MABU-300-AA-7180-10100 | BNO-MABU-300-AA-7180-10100 | PMT | R01 | IFR | ISSUED | IFR RETURNED AS CODE 3 | 2ND SITE SURVEY REPORT | Remove from EDROBO to match Engineering Base. If EDROBO is master/current, add/update this document in Engineering Base.
BNO-MABU-300-EA-3323-10006 | BNO-MABU-300-EA-3323-10006 | ELECTRICAL | R01 | IFR | ENGINEERING DISTRIBUTION |  | TECHNICAL BID EVALUATION REPORT FOR ELECTRICAL JUNCTION BOXES | Remove from EDROBO to match Engineering Base. If EDROBO is master/current, add/update this document in Engineering Base.
BNO-MABU-300-HX-1415-10001 | BNO-MABU-300-HX-1415-10001 | TECHNICAL SAFETY | R01 | NI | NÃO SE APLICA |  | HAZARDOUS AREA CLASSIFICATION (HAC) PROCEDURE | Remove from EDROBO to match Engineering Base. If EDROBO is master/current, add/update this document in Engineering Base.
BNO-MABU-300-HX-6613-10002 | BNO-MABU-300-HX-6613-10002 | TECHNICAL SAFETY | R01 | NI | NÃO SE APLICA |  | ACTION TRACKING REGISTER | Remove from EDROBO to match Engineering Base. If EDROBO is master/current, add/update this document in Engineering Base.
BNO-MABU-300-HX-7739-10002 | BNO-MABU-300-HX-7739-10002 | TECHNICAL SAFETY | R01 | NI | NÃO SE APLICA |  | SAFETY SIGNS LAYOUT | Remove from EDROBO to match Engineering Base. If EDROBO is master/current, add/update this document in Engineering Base.
BNO-MABU-300-MP-2343-10092-001 | BNO-MABU-300-MP-2343-10092 | PIPING | R01 | IFR | ISSUED | IFR RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-DN-473806-40-AW | Remove from EDROBO to match Engineering Base. If EDROBO is master/current, add/update this document in Engineering Base.
BNO-MABU-300-MP-2343-10092-002 | BNO-MABU-300-MP-2343-10092 | PIPING | R01 | IFR | ISSUED | IFR RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-DN-473806-40-AW | Remove from EDROBO to match Engineering Base. If EDROBO is master/current, add/update this document in Engineering Base.
BNO-MABU-300-MP-2343-10092-003 | BNO-MABU-300-MP-2343-10092 | PIPING | R01 | IFR | ISSUED | IFR RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-DN-473806-40-AW | Remove from EDROBO to match Engineering Base. If EDROBO is master/current, add/update this document in Engineering Base.
BNO-MABU-300-MP-2358-10015-001 | BNO-MABU-300-MP-2358-10015 | PIPING | R01 | NI | NÃO SE APLICA |  | PIPING SUPPORT DRAWINGS | Remove from EDROBO to match Engineering Base. If EDROBO is master/current, add/update this document in Engineering Base.
BNO-MABU-300-MP-4018-10014-001 | BNO-MABU-300-MP-4018-10014 | PIPING | R01 | NI | NÃO SE APLICA |  | PIPING PLAN & ELEVATION (STARBOARD MODULE) MEZZANINE DECK | Remove from EDROBO to match Engineering Base. If EDROBO is master/current, add/update this document in Engineering Base.
BNO-MABU-300-MP-4306-10003 | BNO-MABU-300-MP-4306-10003 | PIPING | R01 | NI | NÃO SE APLICA |  | WI HEAVY WALL INCONEL CLAD PIPING & FITTINGS - MTO | Remove from EDROBO to match Engineering Base. If EDROBO is master/current, add/update this document in Engineering Base.
BNO-MABU-300-MP-4306-10004 | BNO-MABU-300-MP-4306-10004 | PIPING | R01 | NI | NÃO SE APLICA |  | PRODUCTION & GAS LIFT HEAVY WALL PIPING - MTO | Remove from EDROBO to match Engineering Base. If EDROBO is master/current, add/update this document in Engineering Base.
BNO-MABU-300-MP-7880-10002-001 | BNO-MABU-300-MP-7880-10002 | PIPING | R01 | NI | NÃO SE APLICA |  | SPECIAL PIPING SUPPORT DRAWINGS | Remove from EDROBO to match Engineering Base. If EDROBO is master/current, add/update this document in Engineering Base.
BNO-MABU-300-PX-2365-10019-001 | BNO-MABU-300-PX-2365-10019 | PROCESS | C03 | UNDER REVIEW | ENGINEERING COMMENTS |  | P&ID - UTILITY SYSTEMS WATERFLOOD INJECTION - LAUNCHER/RECEIVERS-MODIFICATION | Remove from EDROBO to match Engineering Base. If EDROBO is master/current, add/update this document in Engineering Base.
BNO-MABU-300-RA-7180-00001 | BNO-MABU-300-RA-7180-00001 | MATERIALS | R01 | NI | NÃO SE APLICA |  | METHANOL SKID ISOLATION MATERIALS - MATERIAL REQUISITION | Remove from EDROBO to match Engineering Base. If EDROBO is master/current, add/update this document in Engineering Base.

## Status Differences
Status Differences
Same document exists in both bases but status differs
Document Number | Discipline | Eng Revision | EDROBO Revision | Engineering Status | EDROBO Status | Eng Document Status | EDROBO Document Status | Eng Issue Status | EDROBO Issue Status | Reason | Required Action | Title
BNO-MABU-300-AA-5787-10002 | PMT | R01 | R01 | AFC 1 | IFR | ISSUED | ISSUED | IFR RETURNED AS CODE 4 | IFR RETURNED AS CODE 4 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | LEVEL 3 PROJECT SCHEDULE
BNO-MABU-300-AA-5800-10001 | PMT | A02 | A03 | AFC 3 | IFA | ISSUED | ENGINEERING DISTRIBUTION | AFC/AFU RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | EPC-1 DETAILED ENGINEERING DESIGN (DED) - INTERFACE MANAGEMENT PLAN
BNO-MABU-300-BA-7753-10001 | CONSTRUCTION | A01 | A01 | AFC 3 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | CONSTRUCTABILITY REVIEW TERMS OF REFERENCE
BNO-MABU-300-CS-0514-10002 | STRUCTURAL | A03 | A03 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | CORROSION INHIBITOR PLATFORM IN PLACE ANALYSIS REPORT CORROSION INHIBITOR PLATFORM IN PLACE ANALYSIS REPORT
BNO-MABU-300-CS-0514-10019 | STRUCTURAL | A03 | A03 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | WATERFLOOD MODULE STOOL VERIFICATION REPORT
BNO-MABU-300-CS-0514-10021 | STRUCTURAL | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | WATERFLOOD MODULE DECK EXTENSIONS IN PLACE ANALYSIS VERIFICATION REPORT
BNO-MABU-300-CS-0514-10022 | STRUCTURAL | A03 | A03 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | LACT MODULE STOOL VERIFICATION
BNO-MABU-300-CS-0520-10002 | STRUCTURAL | A04 | A05 | AFC 3 | IFA | ISSUED | TRANSMITTAL | AFC/AFU RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | STARBOARD SUBSEA MODULE INPLACE ANALYSIS REPORT -BONGA NORTH MODIFICATIONS
BNO-MABU-300-CS-1448-10001 | STRUCTURAL | A02 | A02 | UNDER REVIEW | AFC 3 | ENGINEERING DISTRIBUTION | ISSUED | - | AFC/AFU RETURNED AS CODE 4 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | WEIGHT CONTROL REPORT - APRIL 2026
BNO-MABU-300-CS-1448-10002 | STRUCTURAL | A03 | A03 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | WATER INJECTION TURBINE SKID - STRUCTURAL CALCULATION REPORT - LIFTING ANALYSIS
BNO-MABU-300-CS-4018-10016-004 | STRUCTURAL | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | WATERFLOOD MODULE DECK EXTENSION (LEVEL 3) MODIFICATIONS
BNO-MABU-300-CS-4018-10021-001 | STRUCTURAL | C02 | C03 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING DISTRIBUTION | AFC/AFU RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | STARBOARD SUBSEA MODULE - STRUCTURE - MONORAIL/EQP FOUNDATION/CONTAINMENT BASIN TO PIG LAUNCHER/RECIEVER SHEET 1
BNO-MABU-300-CS-4018-10021-002 | STRUCTURAL | C02 | C03 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING DISTRIBUTION | AFC/AFU RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | STARBOARD SUBSEA MODULE - STRUCTURE - MONORAIL/EQP FOUNDATION/CONTAINMENT BASIN TO PIG LAUNCHER/RECIEVER SHEET 2
BNO-MABU-300-CS-4018-10043-001 | STRUCTURAL | C01 | C02 | AFC 3 | AFC 1 | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 1 | Source data changed: Revision, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | STARBOARD SUBSEA MODULE - STRUCTURE - BLOWDOWN PIPING AREA ACCESS 1
BNO-MABU-300-CS-4018-10043-002 | STRUCTURAL | C01 | C02 | AFC 3 | AFC 1 | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 1 | Source data changed: Revision, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | STARBOARD SUBSEA MODULE - STRUCTURE - BLOWDOWN PIPING AREA ACCESS 1
BNO-MABU-300-CS-4018-10044-001 | STRUCTURAL | C02 | C02 | UNDER REVIEW | AFC 3 | ENGINEERING DISTRIBUTION | ISSUED | - | AFC/AFU RETURNED AS CODE 3 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | STARBOARD SUBSEA MODULE - STRUCTURE - BLOWDOWN PIPING AREA ACCESS 2
BNO-MABU-300-CS-4018-10051-011 | STRUCTURAL | A01 | C01 | IFA | UNDER REVIEW | ISSUED | TRANSMITTAL | IFA RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | STARBOARD SUBSEA MODULE - SPS-BN-SS-0022 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-012 | STRUCTURAL | A01 | C01 | IFA | UNDER REVIEW | ISSUED | TRANSMITTAL | IFA RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | STARBOARD SUBSEA MODULE - SPS-BN-SS-0022 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-032 | STRUCTURAL | A01 | C01 | IFA | UNDER REVIEW | ISSUED | TRANSMITTAL | IFA RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | STARBOARD SUBSEA MODULE - SPS-BN-SS-0032 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-033 | STRUCTURAL | A01 | C01 | IFA | UNDER REVIEW | ISSUED | TRANSMITTAL | IFA RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | STARBOARD SUBSEA MODULE - SPS-BN-SS-0032 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-043 | STRUCTURAL | A01 | C01 | IFA | AFC 1 | ISSUED | ISSUED | IFA RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 1 | Source data changed: Revision, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | STARBOARD SUBSEA MODULE - SPS-BN-SS-0055 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-044 | STRUCTURAL | A01 | C01 | IFA | AFC 3 | ISSUED | ISSUED | IFA RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | Source data changed: Revision, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | STARBOARD SUBSEA MODULE - SPS-BN-SS-0058 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-045 | STRUCTURAL | C01 | C01 | UNDER REVIEW | AFC 3 | ENGINEERING DISTRIBUTION | ISSUED | - | AFC/AFU RETURNED AS CODE 3 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | STARBOARD SUBSEA MODULE - SPS-BN-SS-0060 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-048 | STRUCTURAL | A01 | C01 | IFA | UNDER REVIEW | ISSUED | TRANSMITTAL | IFA RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | STARBOARD SUBSEA MODULE - SPS-BN-SS-0084 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-056 | STRUCTURAL | A01 | C01 | IFA | UNDER REVIEW | ISSUED | TRANSMITTAL | IFA RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | STARBOARD SUBSEA MODULE - SPS-BN-SS-0069 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-069 | STRUCTURAL | A01 | C01 | IFA | UNDER REVIEW | ISSUED | TRANSMITTAL | IFA RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | STARBOARD SUBSEA MODULE - SPS-BN-SS-0072 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-075 | STRUCTURAL | A01 | C01 | IFA | AFC 1 | ISSUED | ISSUED | IFA RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 1 | Source data changed: Revision, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | STARBOARD SUBSEA MODULE - SPS-BN-SS-0125 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-076 | STRUCTURAL | A01 | C01 | IFA | AFC 1 | ISSUED | ISSUED | IFA RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 1 | Source data changed: Revision, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | STARBOARD SUBSEA MODULE - SPS-BN-SS-0137 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-090 | STRUCTURAL | R01 | A01 | IFR | IFA | ISSUED | TRANSMITTAL | IFR RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | STARBOARD SUBSEA MODULE - SPS-BN-SS-0148 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-100 | STRUCTURAL | R01 | A01 | IFR | IFA | ISSUED | TRANSMITTAL | IFR RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | STARBOARD SUBSEA MODULE - SPS-BN-SS-0116 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-108 | STRUCTURAL | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | STARBOARD SUBSEA MODULE SPS-BN-SS-0172 - SPECIAL PIPE SUPPORT PLAN, SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-109 | STRUCTURAL | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | STARBOARD SUBSEA MODULE SPS-BN-SS-0173 - SPECIAL PIPE SUPPORT PLAN, SECTIONS, AND DETAILS
BNO-MABU-300-CS-4018-10052-007 | STRUCTURAL | A01 | C01 | IFA | UNDER REVIEW | ISSUED | TRANSMITTAL | IFA RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | WATERFLOOD MODULE - SPS-BN-SS-0019 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10052-017 | STRUCTURAL | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | WATERFLOOD MODULE - SPS-BN-MR2-0006 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10052-021 | STRUCTURAL | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | WATERFLOOD MODULE - SPS-BN-MR2-0046 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10052-031 | STRUCTURAL | A01 | C01 | IFA | UNDER REVIEW | ISSUED | TRANSMITTAL | IFA RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | WATERFLOOD MODULE - SPS-BN-MR2-0061 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10052-032 | STRUCTURAL | A01 | C01 | IFA | UNDER REVIEW | ISSUED | TRANSMITTAL | IFA RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | WATERFLOOD MODULE - SPS-BN-MR2-0061 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10052-036 | STRUCTURAL | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | WATERFLOOD MODULE - SPS-BN-SS-0011 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10052-037 | STRUCTURAL | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | WATERFLOOD MODULE - SPS-BN-SS-0011 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10052-041 | STRUCTURAL | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | WATERFLOOD MODULE - SPS-BN-WF-0004 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10052-042 | STRUCTURAL | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | WATERFLOOD MODULE SPS-BN-WF-0004 - SPECIAL PIPE SUPPORT PLAN, SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10052-043 | STRUCTURAL | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | WATERFLOOD MODULE - SPS-BN-WF-0017 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10052-044 | STRUCTURAL | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | WATERFLOOD MODULE SPS-BN-WF-0017—SPECIAL PIPE SUPPORT PLAN, SECTIONS, AND DETAILS
BNO-MABU-300-CS-4018-10052-045 | STRUCTURAL | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | WATERFLOOD MODULE SPS-BN-WF-0017 - SPECIAL PIPE SUPPORT PLAN, SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10055-009 | STRUCTURAL | A01 | C01 | IFA | AFC 1 | ISSUED | ISSUED | IFA RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 1 | Source data changed: Revision, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | MAINRACK 2 - SPS-BN-MR2-0018 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10055-010 | STRUCTURAL | A01 | C01 | IFA | AFC 1 | ISSUED | ISSUED | IFA RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 1 | Source data changed: Revision, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | MAINRACK 2 - SPS-BN-MR2-0018 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10055-011 | STRUCTURAL | A01 | C01 | IFA | AFC 3 | ISSUED | ISSUED | IFA RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | Source data changed: Revision, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | MAINRACK 2 - SPS-BN-MR2-0023 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10055-023 | STRUCTURAL | R01 | A01 | IFR | IFA | ISSUED | TRANSMITTAL | IFR RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | MAINRACK 2 - SPS-BN-MR2-0088 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10084-001 | STRUCTURAL | C02 | C02 | AFC 3 | AFC 1 | TRANSMITTAL | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | DEMOLITION STARBOARD SUBSEA MODULE DROPPED OBJECT PROTECTION
BNO-MABU-300-CS-4018-10097-001 | STRUCTURAL | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | HANDRAIL DEMOLITION FOR LACT MODULE LEVEL 2 - LADDER LANDING FOR MR2
BNO-MABU-300-CS-7180-10001 | STRUCTURAL | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | TBE FOR STRUCTURAL MATERIALS
BNO-MABU-300-CS-7303-10003 | STRUCTURAL | A02 | A02 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | WATER INJECTION TURBINE SKID - STRUCTURE - MATERIAL LIST (MTO)
BNO-MABU-300-CS-7303-10004 | STRUCTURAL | A02 | A02 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PORT SUBSEA MODULE - STRUCTURE DECK EXTENSIONS - MATERIAL LIST (MTO)PORTSIDE SUBSEA MODULE - STRUCTURE DECK EXTENSIONS - MATERIAL LIST (MTO)
BNO-MABU-300-CS-7303-10006 | STRUCTURAL | A03 | A03 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | STARBOARD SUBSEA MODULE - STRUCTURE DUE TO BONGA NORTH MODIFICATIONS - MATERIAL LIST (MTO)
BNO-MABU-300-CS-7303-10008 | STRUCTURAL | A02 | A02 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | MAIN RACK 2 - STRUCTURE - WI PUMP HANDLING AREA - MATERIAL LIST (MTO)
BNO-MABU-300-CS-7303-10012 | STRUCTURAL | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | STRUCTURAL PIPE SUPPORTS MTO
BNO-MABU-300-CS-7303-10017 | STRUCTURAL | A02 | A02 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | WATERFLOOD MODULE - STRUCTURE DUE TO BONGA NORTH MODIFICATIONS - MATERIAL LIST (MTO)
BNO-MABU-300-CS-8180-10003 | STRUCTURAL | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | WATER INJECTION TURBINE SKID - STRUCTURAL VERIFICATION REPORT - IN PLACE ANALYSIS
BNO-MABU-300-CS-8180-10013 | STRUCTURAL | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ISSUED | - | IFA RETURNED AS CODE 3 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | STRUCTURAL CABLE TRAY SUPPORTS CALCULATIONS REPORT
BNO-MABU-300-CS-8180-10014 | STRUCTURAL | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | WI TURBINE & WF MODULE DECK EXTENSIONS MISCELLANEOUS CALCULATION REPORT
BNO-MABU-300-EA-0980-10006-001 | ELECTRICAL | C02 | C03 | AFC 3 | UNDER REVIEW | ISSUED | TRANSMITTAL | AFC/AFU RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BLOCK DIAGRAM FOR ALL THE UPS
BNO-MABU-300-EA-1380-10002 | ELECTRICAL | A05 | A05 | UNDER REVIEW | AFC 1 | ENGINEERING DISTRIBUTION | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CALCULATION REPORT - ELECTRICAL LOAD BALANCE SB-7401A/B-E-01
BNO-MABU-300-EA-2335-10001-001 | ELECTRICAL | C03 | C03 | UNDER REVIEW | AFC 3 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 3 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | ELECTRICAL JUNCTION BOX ( EJB) TO SPCU INTERFACE HOOKUP DRAWINGS
BNO-MABU-300-EA-2384-10007-001 | ELECTRICAL | C03 | C03 | UNDER REVIEW | AFC 1 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | KEY AC UPS SINGLE LINE DIAGRAM
BNO-MABU-300-EA-2384-10008-001 | ELECTRICAL | C02 | C02 | UNDER REVIEW | AFC 1 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | KEY DC UPS SINGLE LINE DIAGRAM
BNO-MABU-300-EA-2398-10001-001 | ELECTRICAL | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING COMMENTS | - |  | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | INSTALLATION DETAILS: HEAT TRACING
BNO-MABU-300-EA-2901-10001 | ELECTRICAL | A03 | A03 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | AC AND DC UPS SIZING CALCULATIONS
BNO-MABU-300-EA-2901-10002 | ELECTRICAL | A05 | A05 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | CABLE SELECTION AND SIZING CALCULATION
BNO-MABU-300-EA-3323-10010 | ELECTRICAL | A01 | A01 | AFC 3 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 2 | IFA RETURNED AS CODE 2 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | TECHNICAL BID EVALUATION REPORT FOR EARTHING MATERIALS
BNO-MABU-300-EA-3323-10011 | ELECTRICAL | A02 | A02 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ISSUED | - | IFA RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | TECHNICAL BID EVALUATION REPORT FOR BLANKING PLUGS AND REDUCING BUSHING
BNO-MABU-300-EA-3323-10013 | ELECTRICAL | A02 | A02 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ISSUED | - | IFA RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | TECHNICAL BID EVALUATION REPORT FOR CABLE LUGS
BNO-MABU-300-EA-3323-10014 | ELECTRICAL | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | TECHNICAL BID EVALUATION REPORT FOR REMOTE CONTROL STATIONS
BNO-MABU-300-EA-4005-10009-001 | ELECTRICAL | C03 | C03 | UNDER REVIEW | AFC 3 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 3 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - MR3 LEVEL 1
BNO-MABU-300-EA-4005-10016-001 | ELECTRICAL | C02 | C03 | AFC 3 | UNDER REVIEW | ISSUED | TRANSMITTAL | AFC/AFU RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - MR2 LEVEL 1
BNO-MABU-300-EA-4005-10025-001 | ELECTRICAL | C02 | C02 | UNDER REVIEW | AFC 3 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 3 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CABLE LADDER LAYOUT SUPPORTS - MR2 LEVEL 1
BNO-MABU-300-EA-4005-10026-001 | ELECTRICAL | C01 | C01 | UNDER REVIEW | AFC 1 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CABLE LADDER LAYOUT SUPPORTS - MR3 LEVEL 1
BNO-MABU-300-EA-4005-10027-001 | ELECTRICAL | C02 | C02 | UNDER REVIEW | AFC 1 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CABLE LADDER LAYOUT SUPPORTS - MR3 LEVEL 4
BNO-MABU-300-EA-4005-10028-001 | ELECTRICAL | C01 | C01 | UNDER REVIEW | AFC 1 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CABLE LADDER LAYOUT SUPPORTS - PS LEVEL 1
BNO-MABU-300-EA-4005-10029-001 | ELECTRICAL | C01 | C01 | UNDER REVIEW | AFC 3 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 3 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CABLE LADDER LAYOUT SUPPORTS - MR2 LEVEL 4
BNO-MABU-300-EA-4005-10030-001 | ELECTRICAL | C01 | C01 | UNDER REVIEW | AFC 1 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CABLE LADDER LAYOUT SUPPORTS - SS LEVEL 1
BNO-MABU-300-EA-4005-10036-001 | ELECTRICAL | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ISSUED | - | IFA RETURNED AS CODE 3 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CABLE LADDER LAYOUT SUPPORTS - HULL
BNO-MABU-300-EA-4024-10018-001 | ELECTRICAL | C03 | C03 | UNDER REVIEW | AFC 1 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | LIGHTING DISTRIBUTION PLAN FOR MR3 LEVEL 4_ HPU AREA
BNO-MABU-300-EA-4024-10019-001 | ELECTRICAL | C03 | C03 | UNDER REVIEW | AFC 1 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | LIGHTING & SMALL POWER LAYOUT STARBOARD SUBSEA MODULE
BNO-MABU-300-EA-4024-10022-001 | ELECTRICAL | C02 | C02 | UNDER REVIEW | AFC 1 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | GROUNDING DISTRIBUTION PLAN MR4 LEVEL 4 BVP AREA
BNO-MABU-300-EA-4024-10023-001 | ELECTRICAL | C02 | C02 | UNDER REVIEW | AFC 1 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | GROUNDING DISTRIBUTION PLAN - MR3 LEVEL 4_ HPU AREA
BNO-MABU-300-EA-4025-10001-001 | ELECTRICAL | C02 | C02 | UNDER REVIEW | AFC 1 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | UPDATE OF EXISTING LIGHTING AND SMALL POWER LAYOUT
BNO-MABU-300-EA-4308-10001 | ELECTRICAL | A06 | A06 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | ELECTRICAL CABLE LIST
BNO-MABU-300-EA-4329-10001 | ELECTRICAL | A04 | A04 | UNDER REVIEW | AFC 1 | ENGINEERING DISTRIBUTION | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | ELECTRICAL LOAD LIST
BNO-MABU-300-EA-4380-10007 | ELECTRICAL | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ENGINEERING COMMENTS | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PROTECTION SCHEME & RELAY SETTING SCHEDULES
BNO-MABU-300-EA-4380-10008 | ELECTRICAL | C02 | C02 | UNDER REVIEW | AFC 3 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 3 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | DISTRIBUTION BOARD SCHEDULE FOR ALL THE DB
BNO-MABU-300-EA-4380-10009 | ELECTRICAL | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | LV SWITCHGEAR SCHEDULE UPDATE FOR BM
BNO-MABU-300-EA-4380-10012 | ELECTRICAL | A04 | A04 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | TRANSMITTAL | - |  | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CONTROL. ALARM AND MONITORING TABLE
BNO-MABU-300-EA-7180-10005 | ELECTRICAL | A03 | A03 | UNDER REVIEW | AFC 1 | ENGINEERING DISTRIBUTION | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BN PROJECT SAFOP CLOSE OUT REPORT
BNO-MABU-300-EA-7180-10012 | ELECTRICAL | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | ELECTRICAL SITE VISIT REPORT
BNO-MABU-300-EA-7770-10001 | ELECTRICAL | A06 | A06 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | TRANSMITTAL | - |  | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | SPECIFICATION FOR ELECTRICAL EQUIPMENT SIZING REVALIDATION
BNO-MABU-300-EA-7771-10003 | ELECTRICAL | A04 | A04 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | SPECIFICATION FOR ELECTRIC MOTOR
BNO-MABU-300-EA-7771-10010 | ELECTRICAL | A03 | A03 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | SPECIFICATION FOR DC UPS
BNO-MABU-300-EA-8260-10003 | ELECTRICAL | A03 | A03 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ISSUED | - | IFA RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | ELECTRICAL STUDIES REPORT - SHORT-CIRCUIT CURRENTS
BNO-MABU-300-EA-8260-10004 | ELECTRICAL | A02 | A03 | AFC 3 | IFA | ISSUED | ENGINEERING DISTRIBUTION | AFC/AFU RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | ELECTRICAL STUDIES REPORT - PROTECTION COORDINATION
BNO-MABU-300-EA-8260-10006 | ELECTRICAL | A02 | A02 | UNDER REVIEW | AFC 3 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 3 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | ELECTRICAL STUDIES REPORT - ARC FLASH
BNO-MABU-300-HX-1212-10001 | TECHNICAL SAFETY | A05 | A05 | UNDER REVIEW | AFC 1 | ENGINEERING CONSOLIDATION | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | FIRE WATER DEMAND VERIFICATION - CALCULATION NOTES
BNO-MABU-300-HX-3323-10001 | TECHNICAL SAFETY | R01 | A01 | IFR | IFA | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | Source data changed: Revision, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | TBE FOR SAFETY ITEMS
BNO-MABU-300-HX-6019-10001 | TECHNICAL SAFETY | A02 | A02 | UNDER REVIEW | AFC 1 | ENGINEERING CONSOLIDATION | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | EMERGENCY SYSTEMS SURVIVABILITY ASSESSMENT
BNO-MABU-300-HX-6873-10006 | TECHNICAL SAFETY | A02 | A02 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CONSTRUCTION HAZID CLOSE-OUT REPORT
BNO-MABU-300-HX-6875-10008 | TECHNICAL SAFETY | A02 | A02 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | HAZOP CLOSEOUT REPORT (DED)
BNO-MABU-300-HX-6881-10002 | TECHNICAL SAFETY | A02 | A02 | UNDER REVIEW | AFC 1 | ENGINEERING CONSOLIDATION | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | DESIGN SAFETY CASE REPORT
BNO-MABU-300-HX-6881-10003 | TECHNICAL SAFETY | A01 | A01 | AFC 3 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | HFE 60% 3D MODEL REVIEW AND VALVE CRITICALITY ASSESSMENT REPORT
BNO-MABU-300-HX-7180-10001 | TECHNICAL SAFETY | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | HUMAN FACTORS ENGINEERING REVIEW OF ALARM RATIONALISATION REPORT
BNO-MABU-300-HX-7303-10003 | TECHNICAL SAFETY | A02 | A02 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ISSUED | - | IFA RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BILL OF MATERIALS (FIRE & SAFETY)
BNO-MABU-300-HX-7739-10003 | TECHNICAL SAFETY | A05 | A05 | UNDER REVIEW | AFC 1 | ENGINEERING CONSOLIDATION | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | SAFETY EQUIPMENT SPECIFICATION
BNO-MABU-300-HX-7739-10004 | TECHNICAL SAFETY | A02 | A02 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ISSUED | - | IFA RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | SAFETY EQUIPMENT MTO
BNO-MABU-300-HX-7753-10006 | TECHNICAL SAFETY | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | DESIGN SAFETY CASE TERMS OF REFERENCE
BNO-MABU-300-IN-0780-10001 | INSTRUMENTATION | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 2 | IFA RETURNED AS CODE 2 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | SIL DETERMINATION REPORT
BNO-MABU-300-IN-0780-10009 | INSTRUMENTATION | A03 | A03 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ENGINEERING CONSOLIDATION | - |  | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | ALARM RATIONALISATION WORKSHOP - TOR
BNO-MABU-300-IN-1979-10002 | INSTRUMENTATION | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | MASTER ALARM DATABASE (VARIABLE TABLE)
BNO-MABU-300-IN-1979-10003 | INSTRUMENTATION | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | ESD TRIP SCHEDULE (INPUT ONLY)
BNO-MABU-300-IN-2105-10009 | INSTRUMENTATION | A04 | A04 | UNDER REVIEW | AFC 3 | ENGINEERING DISTRIBUTION | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | Source data changed: Document Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | INSTRUMENTATION & AUTOMATION DATASHEET FOR RESTRICTION ORIFICE
BNO-MABU-300-IN-2105-10012 | INSTRUMENTATION | A04 | A04 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | INSTRUMENTATION & AUTOMATION DATASHEET FOR PRESSURE GAUGE
BNO-MABU-300-IN-2105-10015 | INSTRUMENTATION | A05 | A05 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | INSTRUMENTATION & AUTOMATION DATASHEET FOR PRESSURE RELIEF VALVE
BNO-MABU-300-IN-2105-10018 | INSTRUMENTATION | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | INSTRUMENTATION & AUTOMATION DATASHEET FOR HYDRAULIC HAND VALVE AND SHUTDOWN VALVE
BNO-MABU-300-IN-2105-10021 | INSTRUMENTATION | A05 | A05 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | INSTRUMENTATION & AUTOMATION DATASHEET FOR OPEN PATH GAS DETECTOR
BNO-MABU-300-IN-2335-10002-001 | INSTRUMENTATION | C01 | C02 | AFC 1 | UNDER REVIEW | ISSUED | ENGINEERING COMMENTS | AFC/AFU RETURNED AS CODE 1 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | SUPPORT HOOK UP DRAWING
BNO-MABU-300-IN-2341-10003-001 | INSTRUMENTATION | C02 | C03 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING COMMENTS | AFC/AFU RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | HPU/HCU INTERFACE HOOKUP DRAWINGS
BNO-MABU-300-IN-2341-10004-001 | INSTRUMENTATION | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING COMMENTS | AFC/AFU RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PRODUCTION UMBILICAL INTERFACE HOOKUP DRAWINGS
BNO-MABU-300-IN-2341-10005-001 | INSTRUMENTATION | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING COMMENTS | AFC/AFU RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | GASLIFT UMBILICAL HOOKUP DRAWING
BNO-MABU-300-IN-2341-10007-001 | INSTRUMENTATION | C02 | C03 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING COMMENTS | AFC/AFU RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CORROSION INHIBITOR & METHANOL SYSTEM TO TUPA INTERFACE HOOKUP DRAWINGS
BNO-MABU-300-IN-2341-10008-001 | INSTRUMENTATION | C02 | C03 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING COMMENTS | AFC/AFU RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BUNDLE GASLIFT UMBILICAL (BGLU) TO GASLIFT TUPA HOOKUP DRAWINGS
BNO-MABU-300-IN-2347-10001-001 | INSTRUMENTATION | A01 | A01 | AFC 3 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | INSTRUMENT LOOP DIAGRAMS
BNO-MABU-300-IN-2389-10002-001 | INSTRUMENTATION | A01 | A01 | AFC 3 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | RIO PANEL TERMINATION DRAWINGS
BNO-MABU-300-IN-3323-10004 | INSTRUMENTATION | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | TBE FOR TUBING & BULK MATERIAL MTO
BNO-MABU-300-IN-3323-10005 | INSTRUMENTATION | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | TBE FOR SUPPORT
BNO-MABU-300-IN-3323-10007 | INSTRUMENTATION | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | TBE FOR CABLE TRAYS AND ACCESSORIES
BNO-MABU-300-IN-3323-10008 | INSTRUMENTATION | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | TBE FOR CHANNELS AND ACCESSORIES
BNO-MABU-300-IN-3323-10011 | INSTRUMENTATION | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | TBE FOR CABLE GLANDS
BNO-MABU-300-IN-3323-10012 | INSTRUMENTATION | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | TBE FOR CABLES AND MULTICABLES
BNO-MABU-300-IN-3323-10015 | INSTRUMENTATION | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | TBE FOR JUNCTION BOXES
BNO-MABU-300-IN-3323-10016 | INSTRUMENTATION | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | TBE FOR MISCELLANEOUS
BNO-MABU-300-IN-3323-10017 | INSTRUMENTATION | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | TBE FOR PIPING AND PIPING CONNECTIONS
BNO-MABU-300-IN-4018-10002-001 | INSTRUMENTATION | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | TRANSMITTAL | - |  | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | INSTRUMENT TUBING ROUTING DRAWINGS
BNO-MABU-300-IN-4306-10006 | INSTRUMENTATION | A02 | A03 | AFC 3 | IFA | ISSUED | ENGINEERING COMMENTS | AFC/AFU RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | MATERIAL LIST FOR INSTRUMENT & JUNCTION BOX SUPPORT HOOK UP ITEMS
BNO-MABU-300-IN-4306-10016 | INSTRUMENTATION | A03 | A03 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ENGINEERING COMMENTS | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | MATERIAL LIST FOR PROCESS HOOK UP DRAWING
BNO-MABU-300-IN-4306-10017 | INSTRUMENTATION | A03 | A03 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ENGINEERING COMMENTS | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | MATERIAL LIST FOR ELECTRICAL HOOK UP DRAWING
BNO-MABU-300-IN-4308-10001 | INSTRUMENTATION | A02 | A02 | UNDER REVIEW | IFA | ENGINEERING CONSOLIDATION | ISSUED | NOT ISSUED | IFA RETURNED AS CODE 3 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | INSTRUMENT CABLE SCHEDULE
BNO-MABU-300-IN-4380-10001 | INSTRUMENTATION | A02 | A02 | AFC 1 | IFA | ENGINEERING COMMENTS | ISSUED | IFA RETURNED AS CODE 2 | IFA RETURNED AS CODE 2 | Source data changed: Document Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | MASTER CONTROL PANEL LIST
BNO-MABU-300-IN-4380-10002 | INSTRUMENTATION | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | ALARM AND SET POINT LIST
BNO-MABU-300-IN-4380-10003 | INSTRUMENTATION | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | INSTRUMENT LIST
BNO-MABU-300-IN-5680-10001 | INSTRUMENTATION | A02 | A02 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | TRANSMITTAL | - |  | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | IP(F) NARRATIVES
BNO-MABU-300-IN-7303-10004 | INSTRUMENTATION | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | MATERIAL REQUISITION MAIN AUTOMATION CONTRACTOR
BNO-MABU-300-IN-7303-10008 | INSTRUMENTATION | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | MATERIAL REQUISITION FOR ULTRASONIC FLOWMETER
BNO-MABU-300-IN-7303-10021 | INSTRUMENTATION | A06 | A06 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ENGINEERING COMMENTS | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | MATERIAL REQUISITION FOR POINT TYPE GAS DETECTOR
BNO-MABU-300-IN-7303-10023 | INSTRUMENTATION | A06 | A06 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ENGINEERING COMMENTS | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | MATERIAL REQUISITION FOR IR FLAME DETECTOR
BNO-MABU-300-IN-7303-10026 | INSTRUMENTATION | A04 | A04 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ENGINEERING COMMENTS | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | MATERIAL REQUISITION FOR INSTRUMENTATION CABLES
BNO-MABU-300-IN-7303-10030 | INSTRUMENTATION | A03 | A03 | UNDER REVIEW | AFC 3 | ENGINEERING DISTRIBUTION | ENGINEERING COMMENTS | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | Source data changed: Document Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | MATERIAL REQUISITION FOR CABLE GLANDS
BNO-MABU-300-IN-8880-10001-001 | INSTRUMENTATION | A01 | A01 | AFC 3 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | INSTRUMENT WIRING DIAGRAMS
BNO-MABU-300-KA-7739-10004 | IT / IM | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | BONGA NORTH PCD - IT SECURITY DESIGN SPECIFICATION - FINAL
BNO-MABU-300-MP-1206-10002 | PIPING | A03 | A03 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | SUPPORT LOADS FOR STRUCTURE-LAUNCHER AND RECEIVER A-0820J
BNO-MABU-300-MP-1206-10003 | PIPING | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | SUPPORT LOADS FOR STRUCTURE-LAUNCHER AND RECEIVER A-0820K
BNO-MABU-300-MP-1206-10005 | PIPING | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | SPRING SUPPORTS SCHEDULE
BNO-MABU-300-MP-1206-10006 | PIPING | A03 | A03 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | SUPPORT LOADS FOR STRUCTURE-CORROSION INHIBITOR TANK T-4282
BNO-MABU-300-MP-2105-10001 | PIPING | A03 | A03 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | PIPING DATASHEETS FOR LARGE BORE BALL VALVES
BNO-MABU-300-MP-2105-10006 | PIPING | A03 | A03 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | PIPING DATASHEETS FOR SMALL BORE BALL VALVES
BNO-MABU-300-MP-2105-10007 | PIPING | A01 | A01 | AFC 3 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | PIPING DATASHEETS FOR BUTTERFLY VALVES
BNO-MABU-300-MP-2105-10016 | PIPING | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | DATASHEET FOR STRAINERS
BNO-MABU-300-MP-2343-10004 | PIPING | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | PIPING CONSTRUCT ISOMETRIC DRAWING: 12-PM-043091-100-IFJ
BNO-MABU-300-MP-2343-10007 | PIPING | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | PIPING CONSTRUCT ISOMETRIC DRAWING: 6-PM-043094-120-IFJ
BNO-MABU-300-MP-2343-10010 | PIPING | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-PM-043095-1800-IFJ
BNO-MABU-300-MP-2343-10013 | PIPING | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | PIPING CONSTRUCT ISOMETRIC DRAWING: 10"-PM-043100-1562-IFJ
BNO-MABU-300-MP-2343-10016 | PIPING | C03 | C03 | UNDER REVIEW | AFC 1 | ENGINEERING CONSOLIDATION | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-PM-043103-1125-IFJ
BNO-MABU-300-MP-2343-10017 | PIPING | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-PM-043111-100-CC
BNO-MABU-300-MP-2343-10031 | PIPING | C02 | C02 | UNDER REVIEW | AFC 3A | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 3 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 24"-WI-403225-10S-13841
BNO-MABU-300-MP-2343-10033 | PIPING | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-VA-403233-20-AV
BNO-MABU-300-MP-2343-10038 | PIPING | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473813-40-AW
BNO-MABU-300-MP-2343-10042 | PIPING | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-DN-473806-40-AW
BNO-MABU-300-MP-2343-10046 | PIPING | C02 | C02 | AFC 3 | AFC 1 | TRANSMITTAL | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-CC-423040-40S-SS
BNO-MABU-300-MP-2343-10048 | PIPING | C02 | C03 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-BH-463371-80-ALT
BNO-MABU-300-MP-2343-10049 | PIPING | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-BH-463372-80-A
BNO-MABU-300-MP-2343-10051 | PIPING | C02 | C02 | AFC 3 | AFC 1 | TRANSMITTAL | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 10"-BH-463374-40-ALT
BNO-MABU-300-MP-2343-10054 | PIPING | C02 | C02 | AFC 3 | AFC 1 | TRANSMITTAL | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-BH-463378-80-A
BNO-MABU-300-MP-2343-10056 | PIPING | C02 | C02 | AFC 3 | AFC 1 | TRANSMITTAL | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 10"-BH-463380-40-ALT
BNO-MABU-300-MP-2343-10057 | PIPING | C02 | C02 | UNDER REVIEW | AFC 3A | ENGINEERING CONSOLIDATION | ISSUED | - | AFC/AFU RETURNED AS CODE 3 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-BH-463381-40-ALT
BNO-MABU-300-MP-2343-10058 | PIPING | C02 | C02 | UNDER REVIEW | AFC 1 | ENGINEERING CONSOLIDATION | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-BH-463383-40S-SS
BNO-MABU-300-MP-2343-10059 | PIPING | C02 | C02 | AFC 3 | AFC 1 | TRANSMITTAL | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-BH-463384-40-ALT
BNO-MABU-300-MP-2343-10061 | PIPING | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-BH-463387-40-ALT
BNO-MABU-300-MP-2343-10064 | PIPING | C02 | C02 | AFC 3 | AFC 1 | TRANSMITTAL | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-BH-463394-40-ALT
BNO-MABU-300-MP-2343-10071 | PIPING | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473611-STD-G
BNO-MABU-300-MP-2343-10073 | PIPING | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473613-STD-G
BNO-MABU-300-MP-2343-10087 | PIPING | C01 | C01 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-DC-483015-80-A
BNO-MABU-300-MP-2343-10089 | PIPING | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-DN-473800-40-AW
BNO-MABU-300-MP-2343-10094 | PIPING | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473809-40-AW
BNO-MABU-300-MP-2343-10095 | PIPING | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473810-40-AW
BNO-MABU-300-MP-2343-10109 | PIPING | C02 | C02 | AFC 3 | AFC 3A | TRANSMITTAL | ISSUED | - | AFC/AFU RETURNED AS CODE 3 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-PG-313047-750-FFLT-1H
BNO-MABU-300-MP-2343-10110 | PIPING | C01 | C01 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-PG-313048-"750"-F1-1H
BNO-MABU-300-MP-2343-10119 | PIPING | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | PIPING CONSTRUCT ISOMETRIC DRAWING: 24"-BH-463001-STD-ALT
BNO-MABU-300-MP-2343-10124 | PIPING | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-FG-443101-80-B-P
BNO-MABU-300-MP-2343-10130 | PIPING | C02 | C02 | AFC 3 | AFC 1 | TRANSMITTAL | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-1/2"-PM-083105-XXS-CC
BNO-MABU-300-MP-2343-10131 | PIPING | C02 | C02 | AFC 3 | AFC 1 | TRANSMITTAL | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 6"-PM-043105-1125-JJ
BNO-MABU-300-MP-2343-10133 | PIPING | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | PIPING CONSTRUCT ISOMETRIC DRAWING: 6"-PM-043106-120-IFJ
BNO-MABU-300-MP-2343-10141 | PIPING | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | PIPING CONSTRUCT ISOMETRIC DRAWING: 1/2"-PM-043111-100-CC
BNO-MABU-300-MP-2343-10159 | PIPING | C02 | C02 | AFC 3 | AFC 1 | TRANSMITTAL | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-WI-403230-2000-J1
BNO-MABU-300-MP-2343-10160 | PIPING | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | PIPING CONSTRUCT ISOMETRIC DRAWING: 6"-WI-403231-"1000"-J1
BNO-MABU-300-MP-2343-10164 | PIPING | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 3/4"-VA-403237-40S-SS-P
BNO-MABU-300-MP-2343-10183 | PIPING | C01 | C01 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-BH-463376-STD-ALT
BNO-MABU-300-MP-2343-10184 | PIPING | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-BH-463382-750-FFLT-P
BNO-MABU-300-MP-2343-10186 | PIPING | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-BH-463389-80-A-P
BNO-MABU-300-MP-2343-10217 | PIPING | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 10"-DN-473801-40-AW
BNO-MABU-300-MP-2343-10218 | PIPING | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-BH-443102-80-B-P
BNO-MABU-300-MP-2343-10219 | PIPING | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-WF-613800-200-MV
BNO-MABU-300-MP-2343-10220 | PIPING | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-WF-613079-200-MVB
BNO-MABU-300-MP-2343-10221 | PIPING | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | PIPING CONSTRUCT ISOMETRIC DRAWING: 24"-WI-403065-STD-AW
BNO-MABU-300-MP-2343-10222 | PIPING | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 6"-CM-423002-40S-SS
BNO-MABU-300-MP-2343-10223 | PIPING | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-CM-423021-40S-SS
BNO-MABU-300-MP-2343-10224 | PIPING | C01 | C01 | UNDER REVIEW | AFC 3 | ENGINEERING CONSOLIDATION | ISSUED | - | AFC/AFU RETURNED AS CODE 3 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-DN-473372-STD-H
BNO-MABU-300-MP-2343-10225 | PIPING | C01 | C01 | UNDER REVIEW | AFC 1 | ENGINEERING CONSOLIDATION | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-IA-503501-80-G
BNO-MABU-300-MP-2343-10226 | PIPING | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-IA-503502-80-G
BNO-MABU-300-MP-2343-10231 | PIPING | C02 | C03 | AFC 3 | AFC 1 | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 1 | Source data changed: Revision, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-IA-503507-80-G
BNO-MABU-300-MP-2343-10246 | PIPING | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ISSUED | - | IFA RETURNED AS CODE 3 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING 6"-DN-473139-STD-H
BNO-MABU-300-MP-2343-10247 | PIPING | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ENGINEERING CONSOLIDATION | - |  | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING 6"-DN-473048-STD-H
BNO-MABU-300-MP-2343-10248 | PIPING | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING CONSOLIDATION | - |  | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING 2"-DN-473634-80-G
BNO-MABU-300-MP-2343-10249 | PIPING | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING CONSOLIDATION | - |  | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-1/2-DN-488837-160S-253841A
BNO-MABU-300-MP-2343-10250 | PIPING | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING CONSOLIDATION | - |  | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-1/2-DN-483817-160S-253841A
BNO-MABU-300-MP-2343-10251 | PIPING | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ISSUED | - | IFA RETURNED AS CODE 3 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING-2"-CM-423014-XXS-J
BNO-MABU-300-MP-2343-10252 | PIPING | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ENGINEERING CONSOLIDATION | - |  | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING-1"-UW-513779-80-G
BNO-MABU-300-MP-2343-10253 | PIPING | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ENGINEERING CONSOLIDATION | - |  | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING 6"-VA-403235-40S-SS
BNO-MABU-300-MP-2343-10254 | PIPING | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ENGINEERING CONSOLIDATION | - |  | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING 3"-CM-423051-40S-SS
BNO-MABU-300-MP-2343-10255 | PIPING | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING CONSOLIDATION | ISSUED | - | IFA RETURNED AS CODE 3 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING-2-IA- 503082-80-G
BNO-MABU-300-MP-2343-10256 | PIPING | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING CONSOLIDATION | - |  | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 2-DN-473635-80-G
BNO-MABU-300-MP-2343-10257 | PIPING | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING CONSOLIDATION | - |  | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING 2"-DN-473379-80-G
BNO-MABU-300-MP-2343-10258 | PIPING | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ISSUED | - | IFA RETURNED AS CODE 3 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING 2"-DN-473377-STD-H
BNO-MABU-300-MP-2343-10259 | PIPING | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ISSUED | - | IFA RETURNED AS CODE 1 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING 2"-DN-473380-80-G
BNO-MABU-300-MP-2343-10260 | PIPING | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ENGINEERING CONSOLIDATION | - |  | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING-2-DN-473378-STD-H
BNO-MABU-300-MP-2343-10261 | PIPING | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING CONSOLIDATION | ISSUED | - | IFA RETURNED AS CODE 3 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313051-750-FFLT-1H
BNO-MABU-300-MP-2343-10262 | PIPING | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING CONSOLIDATION | ISSUED | - | IFA RETURNED AS CODE 3 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313055-750-FFLT-1H
BNO-MABU-300-MP-2343-10263 | PIPING | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING CONSOLIDATION | ISSUED | - | IFA RETURNED AS CODE 3 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313058-750-FFLT-1H
BNO-MABU-300-MP-2343-10264 | PIPING | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING CONSOLIDATION | ISSUED | - | IFA RETURNED AS CODE 3 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313054-750-FFLT-1H
BNO-MABU-300-MP-2343-10265 | PIPING | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING CONSOLIDATION | ISSUED | - | IFA RETURNED AS CODE 3 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313057-750-FFLT-1H
BNO-MABU-300-MP-2343-10266 | PIPING | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING CONSOLIDATION | ISSUED | - | IFA RETURNED AS CODE 3 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313053-750-FFLT-1H
BNO-MABU-300-MP-2343-10267 | PIPING | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING CONSOLIDATION | ISSUED | - | IFA RETURNED AS CODE 3 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313052-750-FFLT-1H
BNO-MABU-300-MP-2343-10268 | PIPING | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING CONSOLIDATION | ISSUED | - | IFA RETURNED AS CODE 3 | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313056-750-FFLT-1H
BNO-MABU-300-MP-2343-10269 | PIPING | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING CONSOLIDATION | - |  | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-DN-483103-80-AW
BNO-MABU-300-MP-2343-10270 | PIPING | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING CONSOLIDATION | - |  | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1/2"-DN-433637-80-G
BNO-MABU-300-MP-2343-10272 | PIPING | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING CONSOLIDATION | ENGINEERING CONSOLIDATION | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PIPING CONSTRUCT ISOMETRIC DRAWING-1"-IA-503289-80-G
BNO-MABU-300-MP-3323-10006 | PIPING | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | TBE FOR VA LVES
BNO-MABU-300-MP-3323-10007 | PIPING | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | TBE FOR SPRING SUPPORTS
BNO-MABU-300-MP-3323-10009 | PIPING | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | TBE FOR PIPING SPECIAL ITEMS
BNO-MABU-300-MP-3323-10011 | PIPING | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | TBE FOR PIPING SUPPORT MATERIALS
BNO-MABU-300-MP-3323-10012 | PIPING | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | TBE FOR SPECIAL VALVES
BNO-MABU-300-MP-3323-10013 | PIPING | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | TBE FOR HUB CONNECTOR (GRAYLOC)
BNO-MABU-300-MP-4338-10002 | PIPING | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | CRITICAL LINE LIST
BNO-MABU-300-MP-4338-10003 | PIPING | A03 | A03 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | PIPING SPECIALTY ITEM LIST
BNO-MABU-300-MP-4368-10001 | PIPING | A03 | A03 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | VALVE LIST
BNO-MABU-300-MP-7303-10001 | PIPING | A02 | A03 | AFC 1 | IFA | ISSUED | ENGINEERING DISTRIBUTION | AFC/AFU RETURNED AS CODE 1 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | MATERIAL REQUISITION FOR BOLTS
BNO-MABU-300-MP-7303-10004 | PIPING | A01 | A01 | AFC 3 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | MATERIAL REQUISITION FOR PIPES
BNO-MABU-300-MP-7303-10005 | PIPING | A01 | A01 | AFC 3 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | MATERIAL REQUISITION FOR FITTINGS
BNO-MABU-300-MP-7303-10006 | PIPING | A03 | A04 | AFC 3 | IFA | ISSUED | ENGINEERING DISTRIBUTION | AFC/AFU RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | MATERIAL REQUISITION FOR GASKETS
BNO-MABU-300-MP-7303-10013 | PIPING | A02 | A03 | AFC 3 | IFA | ISSUED | ENGINEERING DISTRIBUTION | AFC/AFU RETURNED AS CODE 3 |  | Source data changed: Revision, Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | MATERIAL REQUISITION FOR SPECTACLE BLANK AND PADDLE BLANK
BNO-MABU-300-MP-7402-10003 | PIPING | A02 | A02 | UNDER REVIEW | IFA | ENGINEERING CONSOLIDATION | ENGINEERING CONSOLIDATION | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | 90% MODEL REVIEW REPORT (P2+)
BNO-MABU-300-MP-7737-10002 | PIPING | A03 | A03 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | SPECIFICATION FOR VALVES
BNO-MABU-300-MP-7737-10004 | PIPING | A03 | A03 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | SPECIFICATIONS FOR PIPING STRESS ANALYSIS PHILOSOPHY
BNO-MABU-300-MP-8005-10003 | PIPING | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | PIPING STRESS ANALYSIS REPORT - SYSTEMS 300-PP-S04_ 300-PP-S05_ 300-PP-S06 AND 300-PP-S16
BNO-MABU-300-MR-7303-10005 | MECHANICAL | A03 | A03 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | WATERFLOOD INJECTION PUMP SIZING CALCULATION AND REPORT (POWER REQUIREMENT)
BNO-MABU-300-PX-0580-10003 | PROCESS | A03 | A03 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING COMMENTS | - |  | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | EQUIPMENT & LINE SIZING VALIDATION REPORT
BNO-MABU-300-PX-1380-10002 | PROCESS | A03 | A03 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING COMMENTS | - |  | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | DRAINAGE SYSTEM CALCULATION NOTES
BNO-MABU-300-PX-1380-10011 | PROCESS | A05 | A05 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING COMMENTS | - |  | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | TEMPERATURE INSTRUMENTS CALCULATION NOTES
BNO-MABU-300-PX-1380-10015 | PROCESS | A03 | A03 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING COMMENTS | - |  | Source data changed: Document Status, Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | PROCESS SAFETY TIME CALCULATIONS
BNO-MABU-300-PX-2105-10008 | PROCESS | A05 | A05 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | PROCESS DATASHEETS FOR SHUTDOWN VALVES
BNO-MABU-300-PX-2105-10012 | PROCESS | A04 | A04 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | Classification rule/status mapping only | Classification mismatch: align status mapping rule or change EDROBO Final Status to Engineering value. | PROCESS DATASHEET FOR WATERFLOOD INJECTION PUMP NEW (P-4047)
BNO-MABU-300-RA-6919-10001 | MATERIALS | A02 | A02 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CORROSION MANAGEMENT FRAMEWORK AND INSPECTION PLAN
BNO-MABU-300-RA-7769-10002-002 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CORROSION MANAGEMENT DRAWING - 0.75-PM-043117-80-B
BNO-MABU-300-RA-7769-10002-003 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CORROSION MANAGEMENT DRAWING - 2-PL-233050-80-B
BNO-MABU-300-RA-7769-10006-002 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CORROSION MANAGEMENT DRAWING - 4-PG-313045-750-F1-1H
BNO-MABU-300-RA-7769-10006-003 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CORROSION MANAGEMENT DRAWING - 4-PG-313045-750-F1-1H
BNO-MABU-300-RA-7769-10006-004 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CORROSION MANAGEMENT DRAWING - 4-PG-313045-750-F1-1H
BNO-MABU-300-RA-7769-10006-005 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CORROSION MANAGEMENT DRAWING - 4-PG-313045-750-F1-1H
BNO-MABU-300-RA-7769-10006-006 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CORROSION MANAGEMENT DRAWING - 4-PG-313048-750-F1-1H
BNO-MABU-300-RA-7769-10006-007 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CORROSION MANAGEMENT DRAWING - 4-PG-313048-750-F1-1H
BNO-MABU-300-RA-7769-10006-008 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CORROSION MANAGEMENT DRAWING - 4-PG-313048-750-F1-1H
BNO-MABU-300-RA-7769-10006-009 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CORROSION MANAGEMENT DRAWING - 4-PG-313048-750-F1-1H
BNO-MABU-300-RA-7769-10006-010 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CORROSION MANAGEMENT DRAWING - 4-PG-313048-750-F1-1H
BNO-MABU-300-RA-7769-10006-011 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CORROSION MANAGEMENT DRAWING - 4-PG-313048-750-F1-1H
BNO-MABU-300-RA-7769-10006-012 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CORROSION MANAGEMENT DRAWING - TAM26-TP-07-4-PG-313045-750-F1-1H
BNO-MABU-300-RA-7769-10006-013 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CORROSION MANAGEMENT DRAWING - TAM26-TP-08-4-PG-313048-750-F1-1H
BNO-MABU-300-RA-7769-10007-002 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CORROSION MANAGEMENT DRAWING - 4-PG-313046-750-FLT-1H
BNO-MABU-300-RA-7769-10007-003 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CORROSION MANAGEMENT DRAWING - 4-PG-313046-750-FLT-1H
BNO-MABU-300-RA-7769-10007-004 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CORROSION MANAGEMENT DRAWING - 4-PG-313046-750-FLT-1H
BNO-MABU-300-RA-7769-10007-005 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CORROSION MANAGEMENT DRAWING - 4-PG-313046-750-FLT-1H
BNO-MABU-300-RA-7769-10007-006 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CORROSION MANAGEMENT DRAWING - 4-PG-313049-750-FLT-1H
BNO-MABU-300-RA-7769-10007-007 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CORROSION MANAGEMENT DRAWING - 4-PG-313049-750-FLT-1H
BNO-MABU-300-RA-7769-10007-008 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CORROSION MANAGEMENT DRAWING - 4-PG-313049-750-FLT-1H
BNO-MABU-300-RA-7769-10007-009 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | CORROSION MANAGEMENT DRAWING - 4-PG-313049-750-FLT-1H
BNO-MABU-300-RA-7769-10008-002 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-003 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-004 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-005 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-006 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-007 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-008 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & FLARE SYSTEM
BNO-MABU-300-RA-7769-10008-009 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-010 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-011 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-012 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-013 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & FLARE SYSTEM
BNO-MABU-300-RA-7769-10008-014 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & FLARE SYSTEM
BNO-MABU-300-RA-7769-10008-015 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & SLARE SYSTEM
BNO-MABU-300-RA-7769-10008-016 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & FLARE SYSTEM
BNO-MABU-300-RA-7769-10008-017 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-018 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-019 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-020 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-021 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BONGA NORTH CORROSION MANAGEMENT DRAWING GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-022 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-023 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-024 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-025 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-026 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-027 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-028 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & FLARE SYSTEM
BNO-MABU-300-RA-7769-10008-029 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BONGA NORTH CORROSION MANAGEMENT DRAWING RELIEF & FLARE SYSTEM
BNO-MABU-300-RA-7769-10008-030 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & FLARE SYSTEM
BNO-MABU-300-RA-7769-10008-031 | MATERIALS | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | Source data changed: Issue Status | To match Engineering Base: change EDROBO status to Engineering value. If EDROBO is source-of-truth, refresh Engineering Base because source fields changed. | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & FLARE SYSTEM

## Revision Differences
Revision Differences
Same document exists in both bases but revision differs
Document Number | Discipline | Engineering Revision | EDROBO Revision | Engineering Status | EDROBO Status | Eng Document Status | EDROBO Document Status | Eng Issue Status | EDROBO Issue Status | Required Action | Title
BNO-MABU-300-AA-5800-10001 | PMT | A02 | A03 | AFC 3 | IFA | ISSUED | ENGINEERING DISTRIBUTION | AFC/AFU RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | EPC-1 DETAILED ENGINEERING DESIGN (DED) - INTERFACE MANAGEMENT PLAN
BNO-MABU-300-BA-5537-10002 | CONSTRUCTION | A01 | A02 | IFA | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFA RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | CONSTRUCTION SCOPE OF WORK
BNO-MABU-300-CS-0520-10002 | STRUCTURAL | A04 | A05 | AFC 3 | IFA | ISSUED | TRANSMITTAL | AFC/AFU RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | STARBOARD SUBSEA MODULE INPLACE ANALYSIS REPORT -BONGA NORTH MODIFICATIONS
BNO-MABU-300-CS-4018-10021-001 | STRUCTURAL | C02 | C03 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING DISTRIBUTION | AFC/AFU RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | STARBOARD SUBSEA MODULE - STRUCTURE - MONORAIL/EQP FOUNDATION/CONTAINMENT BASIN TO PIG LAUNCHER/RECIEVER SHEET 1
BNO-MABU-300-CS-4018-10021-002 | STRUCTURAL | C02 | C03 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING DISTRIBUTION | AFC/AFU RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | STARBOARD SUBSEA MODULE - STRUCTURE - MONORAIL/EQP FOUNDATION/CONTAINMENT BASIN TO PIG LAUNCHER/RECIEVER SHEET 2
BNO-MABU-300-CS-4018-10043-001 | STRUCTURAL | C01 | C02 | AFC 3 | AFC 1 | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 1 | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | STARBOARD SUBSEA MODULE - STRUCTURE - BLOWDOWN PIPING AREA ACCESS 1
BNO-MABU-300-CS-4018-10043-002 | STRUCTURAL | C01 | C02 | AFC 3 | AFC 1 | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 1 | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | STARBOARD SUBSEA MODULE - STRUCTURE - BLOWDOWN PIPING AREA ACCESS 1
BNO-MABU-300-CS-4018-10051-011 | STRUCTURAL | A01 | C01 | IFA | UNDER REVIEW | ISSUED | TRANSMITTAL | IFA RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | STARBOARD SUBSEA MODULE - SPS-BN-SS-0022 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-012 | STRUCTURAL | A01 | C01 | IFA | UNDER REVIEW | ISSUED | TRANSMITTAL | IFA RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | STARBOARD SUBSEA MODULE - SPS-BN-SS-0022 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-032 | STRUCTURAL | A01 | C01 | IFA | UNDER REVIEW | ISSUED | TRANSMITTAL | IFA RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | STARBOARD SUBSEA MODULE - SPS-BN-SS-0032 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-033 | STRUCTURAL | A01 | C01 | IFA | UNDER REVIEW | ISSUED | TRANSMITTAL | IFA RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | STARBOARD SUBSEA MODULE - SPS-BN-SS-0032 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-043 | STRUCTURAL | A01 | C01 | IFA | AFC 1 | ISSUED | ISSUED | IFA RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 1 | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | STARBOARD SUBSEA MODULE - SPS-BN-SS-0055 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-044 | STRUCTURAL | A01 | C01 | IFA | AFC 3 | ISSUED | ISSUED | IFA RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | STARBOARD SUBSEA MODULE - SPS-BN-SS-0058 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-048 | STRUCTURAL | A01 | C01 | IFA | UNDER REVIEW | ISSUED | TRANSMITTAL | IFA RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | STARBOARD SUBSEA MODULE - SPS-BN-SS-0084 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-056 | STRUCTURAL | A01 | C01 | IFA | UNDER REVIEW | ISSUED | TRANSMITTAL | IFA RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | STARBOARD SUBSEA MODULE - SPS-BN-SS-0069 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-069 | STRUCTURAL | A01 | C01 | IFA | UNDER REVIEW | ISSUED | TRANSMITTAL | IFA RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | STARBOARD SUBSEA MODULE - SPS-BN-SS-0072 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-075 | STRUCTURAL | A01 | C01 | IFA | AFC 1 | ISSUED | ISSUED | IFA RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 1 | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | STARBOARD SUBSEA MODULE - SPS-BN-SS-0125 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-076 | STRUCTURAL | A01 | C01 | IFA | AFC 1 | ISSUED | ISSUED | IFA RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 1 | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | STARBOARD SUBSEA MODULE - SPS-BN-SS-0137 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-090 | STRUCTURAL | R01 | A01 | IFR | IFA | ISSUED | TRANSMITTAL | IFR RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | STARBOARD SUBSEA MODULE - SPS-BN-SS-0148 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-100 | STRUCTURAL | R01 | A01 | IFR | IFA | ISSUED | TRANSMITTAL | IFR RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | STARBOARD SUBSEA MODULE - SPS-BN-SS-0116 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-108 | STRUCTURAL | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | STARBOARD SUBSEA MODULE SPS-BN-SS-0172 - SPECIAL PIPE SUPPORT PLAN, SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-109 | STRUCTURAL | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | STARBOARD SUBSEA MODULE SPS-BN-SS-0173 - SPECIAL PIPE SUPPORT PLAN, SECTIONS, AND DETAILS
BNO-MABU-300-CS-4018-10052-007 | STRUCTURAL | A01 | C01 | IFA | UNDER REVIEW | ISSUED | TRANSMITTAL | IFA RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | WATERFLOOD MODULE - SPS-BN-SS-0019 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10052-017 | STRUCTURAL | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | WATERFLOOD MODULE - SPS-BN-MR2-0006 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10052-021 | STRUCTURAL | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | WATERFLOOD MODULE - SPS-BN-MR2-0046 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10052-031 | STRUCTURAL | A01 | C01 | IFA | UNDER REVIEW | ISSUED | TRANSMITTAL | IFA RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | WATERFLOOD MODULE - SPS-BN-MR2-0061 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10052-032 | STRUCTURAL | A01 | C01 | IFA | UNDER REVIEW | ISSUED | TRANSMITTAL | IFA RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | WATERFLOOD MODULE - SPS-BN-MR2-0061 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10052-036 | STRUCTURAL | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | WATERFLOOD MODULE - SPS-BN-SS-0011 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10052-037 | STRUCTURAL | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | WATERFLOOD MODULE - SPS-BN-SS-0011 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10052-041 | STRUCTURAL | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | WATERFLOOD MODULE - SPS-BN-WF-0004 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10052-042 | STRUCTURAL | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | WATERFLOOD MODULE SPS-BN-WF-0004 - SPECIAL PIPE SUPPORT PLAN, SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10052-043 | STRUCTURAL | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | WATERFLOOD MODULE - SPS-BN-WF-0017 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10052-044 | STRUCTURAL | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | WATERFLOOD MODULE SPS-BN-WF-0017—SPECIAL PIPE SUPPORT PLAN, SECTIONS, AND DETAILS
BNO-MABU-300-CS-4018-10052-045 | STRUCTURAL | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | WATERFLOOD MODULE SPS-BN-WF-0017 - SPECIAL PIPE SUPPORT PLAN, SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10055-009 | STRUCTURAL | A01 | C01 | IFA | AFC 1 | ISSUED | ISSUED | IFA RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 1 | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | MAINRACK 2 - SPS-BN-MR2-0018 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10055-010 | STRUCTURAL | A01 | C01 | IFA | AFC 1 | ISSUED | ISSUED | IFA RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 1 | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | MAINRACK 2 - SPS-BN-MR2-0018 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10055-011 | STRUCTURAL | A01 | C01 | IFA | AFC 3 | ISSUED | ISSUED | IFA RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | MAINRACK 2 - SPS-BN-MR2-0023 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10055-023 | STRUCTURAL | R01 | A01 | IFR | IFA | ISSUED | TRANSMITTAL | IFR RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | MAINRACK 2 - SPS-BN-MR2-0088 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-7180-10001 | STRUCTURAL | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | TBE FOR STRUCTURAL MATERIALS
BNO-MABU-300-EA-0980-10006-001 | ELECTRICAL | C02 | C03 | AFC 3 | UNDER REVIEW | ISSUED | TRANSMITTAL | AFC/AFU RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | BLOCK DIAGRAM FOR ALL THE UPS
BNO-MABU-300-EA-4005-10016-001 | ELECTRICAL | C02 | C03 | AFC 3 | UNDER REVIEW | ISSUED | TRANSMITTAL | AFC/AFU RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - MR2 LEVEL 1
BNO-MABU-300-EA-8260-10004 | ELECTRICAL | A02 | A03 | AFC 3 | IFA | ISSUED | ENGINEERING DISTRIBUTION | AFC/AFU RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | ELECTRICAL STUDIES REPORT - PROTECTION COORDINATION
BNO-MABU-300-HX-3323-10001 | TECHNICAL SAFETY | R01 | A01 | IFR | IFA | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | TBE FOR SAFETY ITEMS
BNO-MABU-300-IN-2335-10002-001 | INSTRUMENTATION | C01 | C02 | AFC 1 | UNDER REVIEW | ISSUED | ENGINEERING COMMENTS | AFC/AFU RETURNED AS CODE 1 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | SUPPORT HOOK UP DRAWING
BNO-MABU-300-IN-2341-10003-001 | INSTRUMENTATION | C02 | C03 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING COMMENTS | AFC/AFU RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | HPU/HCU INTERFACE HOOKUP DRAWINGS
BNO-MABU-300-IN-2341-10004-001 | INSTRUMENTATION | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING COMMENTS | AFC/AFU RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | PRODUCTION UMBILICAL INTERFACE HOOKUP DRAWINGS
BNO-MABU-300-IN-2341-10005-001 | INSTRUMENTATION | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING COMMENTS | AFC/AFU RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | GASLIFT UMBILICAL HOOKUP DRAWING
BNO-MABU-300-IN-2341-10007-001 | INSTRUMENTATION | C02 | C03 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING COMMENTS | AFC/AFU RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | CORROSION INHIBITOR & METHANOL SYSTEM TO TUPA INTERFACE HOOKUP DRAWINGS
BNO-MABU-300-IN-2341-10008-001 | INSTRUMENTATION | C02 | C03 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING COMMENTS | AFC/AFU RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | BUNDLE GASLIFT UMBILICAL (BGLU) TO GASLIFT TUPA HOOKUP DRAWINGS
BNO-MABU-300-IN-3323-10004 | INSTRUMENTATION | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | TBE FOR TUBING & BULK MATERIAL MTO
BNO-MABU-300-IN-3323-10005 | INSTRUMENTATION | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | TBE FOR SUPPORT
BNO-MABU-300-IN-3323-10007 | INSTRUMENTATION | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | TBE FOR CABLE TRAYS AND ACCESSORIES
BNO-MABU-300-IN-3323-10008 | INSTRUMENTATION | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | TBE FOR CHANNELS AND ACCESSORIES
BNO-MABU-300-IN-3323-10011 | INSTRUMENTATION | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | TBE FOR CABLE GLANDS
BNO-MABU-300-IN-3323-10012 | INSTRUMENTATION | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | TBE FOR CABLES AND MULTICABLES
BNO-MABU-300-IN-3323-10015 | INSTRUMENTATION | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | TBE FOR JUNCTION BOXES
BNO-MABU-300-IN-3323-10016 | INSTRUMENTATION | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | TBE FOR MISCELLANEOUS
BNO-MABU-300-IN-3323-10017 | INSTRUMENTATION | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | TBE FOR PIPING AND PIPING CONNECTIONS
BNO-MABU-300-IN-4306-10006 | INSTRUMENTATION | A02 | A03 | AFC 3 | IFA | ISSUED | ENGINEERING COMMENTS | AFC/AFU RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | MATERIAL LIST FOR INSTRUMENT & JUNCTION BOX SUPPORT HOOK UP ITEMS
BNO-MABU-300-IN-7303-10028 | INSTRUMENTATION | A02 | A03 | IFA | IFA | ISSUED | ENGINEERING COMMENTS | IFA RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | MATERIAL REQUISITION FOR TUBINGS AND COMPRESSION CONNSECTIONS
BNO-MABU-300-MP-2343-10010 | PIPING | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-PM-043095-1800-IFJ
BNO-MABU-300-MP-2343-10017 | PIPING | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-PM-043111-100-CC
BNO-MABU-300-MP-2343-10033 | PIPING | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-VA-403233-20-AV
BNO-MABU-300-MP-2343-10048 | PIPING | C02 | C03 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-BH-463371-80-ALT
BNO-MABU-300-MP-2343-10049 | PIPING | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-BH-463372-80-A
BNO-MABU-300-MP-2343-10094 | PIPING | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473809-40-AW
BNO-MABU-300-MP-2343-10095 | PIPING | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473810-40-AW
BNO-MABU-300-MP-2343-10124 | PIPING | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-FG-443101-80-B-P
BNO-MABU-300-MP-2343-10164 | PIPING | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | PIPING CONSTRUCT ISOMETRIC DRAWING: 3/4"-VA-403237-40S-SS-P
BNO-MABU-300-MP-2343-10217 | PIPING | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | PIPING CONSTRUCT ISOMETRIC DRAWING: 10"-DN-473801-40-AW
BNO-MABU-300-MP-2343-10219 | PIPING | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-WF-613800-200-MV
BNO-MABU-300-MP-2343-10220 | PIPING | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-WF-613079-200-MVB
BNO-MABU-300-MP-2343-10222 | PIPING | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | PIPING CONSTRUCT ISOMETRIC DRAWING: 6"-CM-423002-40S-SS
BNO-MABU-300-MP-2343-10223 | PIPING | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-CM-423021-40S-SS
BNO-MABU-300-MP-2343-10226 | PIPING | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-IA-503502-80-G
BNO-MABU-300-MP-2343-10230 | PIPING | C01 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING CONSOLIDATION | ENGINEERING CONSOLIDATION | - |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-IA-503506-80-G
BNO-MABU-300-MP-2343-10231 | PIPING | C02 | C03 | AFC 3 | AFC 1 | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 1 | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-IA-503507-80-G
BNO-MABU-300-MP-2343-10236 | PIPING | C01 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING CONSOLIDATION | ENGINEERING CONSOLIDATION | - |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-IA-503508-80-G
BNO-MABU-300-MP-2343-10237 | PIPING | C01 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING CONSOLIDATION | ENGINEERING CONSOLIDATION | - |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-IA-503509-80-G
BNO-MABU-300-MP-3323-10006 | PIPING | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | TBE FOR VA LVES
BNO-MABU-300-MP-3323-10007 | PIPING | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | TBE FOR SPRING SUPPORTS
BNO-MABU-300-MP-3323-10009 | PIPING | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | TBE FOR PIPING SPECIAL ITEMS
BNO-MABU-300-MP-3323-10011 | PIPING | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | TBE FOR PIPING SUPPORT MATERIALS
BNO-MABU-300-MP-3323-10012 | PIPING | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | TBE FOR SPECIAL VALVES
BNO-MABU-300-MP-3323-10013 | PIPING | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | TBE FOR HUB CONNECTOR (GRAYLOC)
BNO-MABU-300-MP-7303-10001 | PIPING | A02 | A03 | AFC 1 | IFA | ISSUED | ENGINEERING DISTRIBUTION | AFC/AFU RETURNED AS CODE 1 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | MATERIAL REQUISITION FOR BOLTS
BNO-MABU-300-MP-7303-10006 | PIPING | A03 | A04 | AFC 3 | IFA | ISSUED | ENGINEERING DISTRIBUTION | AFC/AFU RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | MATERIAL REQUISITION FOR GASKETS
BNO-MABU-300-MP-7303-10013 | PIPING | A02 | A03 | AFC 3 | IFA | ISSUED | ENGINEERING DISTRIBUTION | AFC/AFU RETURNED AS CODE 3 |  | Change EDROBO revision to Engineering revision to match Engineering Base. If EDROBO is current, refresh Engineering Base revision. | MATERIAL REQUISITION FOR SPECTACLE BLANK AND PADDLE BLANK

## Field Differences
All Field Differences
Documents with any compared field different: title, revision, document status, issue status, or final status
Document Number | Discipline | Different Fields | Eng Revision | EDROBO Revision | Engineering Status | EDROBO Status | Eng Document Status | EDROBO Document Status | Eng Issue Status | EDROBO Issue Status | Engineering Title | EDROBO Title
BNO-MABU-300-AA-5787-10002 | PMT | Final Status | R01 | R01 | AFC 1 | IFR | ISSUED | ISSUED | IFR RETURNED AS CODE 4 | IFR RETURNED AS CODE 4 | LEVEL 3 PROJECT SCHEDULE | LEVEL 3 PROJECT SCHEDULE
BNO-MABU-300-AA-5800-10001 | PMT | Revision, Document Status, Issue Status, Final Status | A02 | A03 | AFC 3 | IFA | ISSUED | ENGINEERING DISTRIBUTION | AFC/AFU RETURNED AS CODE 3 |  | EPC-1 DETAILED ENGINEERING DESIGN (DED) - INTERFACE MANAGEMENT PLAN | EPC-1 DETAILED ENGINEERING DESIGN (DED) - INTERFACE MANAGEMENT PLAN
BNO-MABU-300-AA-6945-10001 | PMT | Issue Status | R01 | R01 | NI | NI | NÃO SE APLICA | NÃO SE APLICA | - |  | DED CLOSE-OUT REPORT | DED CLOSE-OUT REPORT
BNO-MABU-300-BA-5537-10002 | CONSTRUCTION | Revision, Document Status, Issue Status | A01 | A02 | IFA | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFA RETURNED AS CODE 3 |  | CONSTRUCTION SCOPE OF WORK | CONSTRUCTION SCOPE OF WORK
BNO-MABU-300-BA-6065-10006 | CONSTRUCTION | Issue Status | R01 | R01 | IFR | IFR | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | METHANOL SKID ISOLATION MATERIALS - MATERIAL REQUISITION | METHANOL SKID ISOLATION MATERIALS - MATERIAL REQUISITION
BNO-MABU-300-BA-7753-10001 | CONSTRUCTION | Final Status | A01 | A01 | AFC 3 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | CONSTRUCTABILITY REVIEW TERMS OF REFERENCE | CONSTRUCTABILITY REVIEW TERMS OF REFERENCE
BNO-MABU-300-CS-0514-10002 | STRUCTURAL | Final Status | A03 | A03 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | CORROSION INHIBITOR PLATFORM IN PLACE ANALYSIS REPORT CORROSION INHIBITOR PLATFORM IN PLACE ANALYSIS REPORT | CORROSION INHIBITOR PLATFORM IN PLACE ANALYSIS REPORT CORROSION INHIBITOR PLATFORM IN PLACE ANALYSIS REPORT
BNO-MABU-300-CS-0514-10019 | STRUCTURAL | Final Status | A03 | A03 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | WATERFLOOD MODULE STOOL VERIFICATION REPORT | WATERFLOOD MODULE STOOL VERIFICATION REPORT
BNO-MABU-300-CS-0514-10021 | STRUCTURAL | Final Status | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | WATERFLOOD MODULE DECK EXTENSIONS IN PLACE ANALYSIS VERIFICATION REPORT | WATERFLOOD MODULE DECK EXTENSIONS IN PLACE ANALYSIS VERIFICATION REPORT
BNO-MABU-300-CS-0514-10022 | STRUCTURAL | Final Status | A03 | A03 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | LACT MODULE STOOL VERIFICATION | LACT MODULE STOOL VERIFICATION
BNO-MABU-300-CS-0520-10002 | STRUCTURAL | Revision, Document Status, Issue Status, Final Status | A04 | A05 | AFC 3 | IFA | ISSUED | TRANSMITTAL | AFC/AFU RETURNED AS CODE 3 |  | STARBOARD SUBSEA MODULE INPLACE ANALYSIS REPORT -BONGA NORTH MODIFICATIONS | STARBOARD SUBSEA MODULE INPLACE ANALYSIS REPORT -BONGA NORTH MODIFICATIONS
BNO-MABU-300-CS-1448-10001 | STRUCTURAL | Document Status, Issue Status, Final Status | A02 | A02 | UNDER REVIEW | AFC 3 | ENGINEERING DISTRIBUTION | ISSUED | - | AFC/AFU RETURNED AS CODE 4 | WEIGHT CONTROL REPORT - APRIL 2026 | WEIGHT CONTROL REPORT - APRIL 2026
BNO-MABU-300-CS-1448-10002 | STRUCTURAL | Issue Status, Final Status | A03 | A03 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | WATER INJECTION TURBINE SKID - STRUCTURAL CALCULATION REPORT - LIFTING ANALYSIS | WATER INJECTION TURBINE SKID - STRUCTURAL CALCULATION REPORT - LIFTING ANALYSIS
BNO-MABU-300-CS-3323-10001-001 | STRUCTURAL | Title | C02 | C02 | AFC 1 | AFC 1 | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 1 | AFC/AFU RETURNED AS CODE 1 | GENERAL NOTES, TYPICAL DETAILS - GRATING (STEEL), TYPICAL DETAILS - HANDRAIL, AND TYPICAL JOINT DETAILS | GENERAL NOTES_ TYPICAL DETAILS - GRATING (STEEL)_ TYPICAL DETAILS - HANDRAIL_ AND TYPICAL JOINT DETAILS
BNO-MABU-300-CS-4018-10006-001 | STRUCTURAL | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | DEMOLITION WORKS FOR WATERFLOOD MODULE DECK EXTENSION @LEVEL 1 AND LEVEL 3 | DEMOLITION WORKS FOR WATERFLOOD MODULE DECK EXTENSION @LEVEL 1 AND LEVEL 3
BNO-MABU-300-CS-4018-10006-002 | STRUCTURAL | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | DEMOLITION WORKS FOR WATERFLOOD MODULE DECK EXTENSION @LEVEL 1 AND LEVEL 3 | DEMOLITION WORKS FOR WATERFLOOD MODULE DECK EXTENSION @LEVEL 1 AND LEVEL 3
BNO-MABU-300-CS-4018-10008-002 | STRUCTURAL | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | WATER INJECTION TURBINE SKID - STRUCTURE - LEVEL 1 | WATER INJECTION TURBINE SKID - STRUCTURE - LEVEL 1
BNO-MABU-300-CS-4018-10008-003 | STRUCTURAL | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | WATER INJECTION TURBINE SKID - STRUCTURE - LEVEL 1 | WATER INJECTION TURBINE SKID - STRUCTURE - LEVEL 1
BNO-MABU-300-CS-4018-10009-001 | STRUCTURAL | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | WATER INJECTION TURBINE SKID - STRUCTURE - LEVEL 2 | WATER INJECTION TURBINE SKID - STRUCTURE - LEVEL 2
BNO-MABU-300-CS-4018-10009-002 | STRUCTURAL | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | WATER INJECTION TURBINE SKID - STRUCTURE - LEVEL 2 | WATER INJECTION TURBINE SKID - STRUCTURE - LEVEL 2
BNO-MABU-300-CS-4018-10009-003 | STRUCTURAL | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | WATER INJECTION TURBINE SKID - STRUCTURE - LEVEL 2 | WATER INJECTION TURBINE SKID - STRUCTURE - LEVEL 2
BNO-MABU-300-CS-4018-10009-004 | STRUCTURAL | Issue Status | C01 | C01 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | WATER INJECTION TURBINE SKID - STRUCTURE - LEVEL 2 | WATER INJECTION TURBINE SKID - STRUCTURE - LEVEL 2
BNO-MABU-300-CS-4018-10010-001 | STRUCTURAL | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | WATER INJECTION TURBINE SKID - STRUCTURE - ELEVATION - NORTH & SOUTH TRUSS | WATER INJECTION TURBINE SKID - STRUCTURE - ELEVATION - NORTH & SOUTH TRUSS
BNO-MABU-300-CS-4018-10011-001 | STRUCTURAL | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | WATER INJECTION TURBINE SKID - STRUCTURE - TRANSVERSAL SECTION (E 940000) | WATER INJECTION TURBINE SKID - STRUCTURE - TRANSVERSAL SECTION (E 940000)
BNO-MABU-300-CS-4018-10012-001 | STRUCTURAL | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | WATER INJECTION TURBINE SKID - STRUCTURE - TRANSVERSAL SECTION (E 945000) | WATER INJECTION TURBINE SKID - STRUCTURE - TRANSVERSAL SECTION (E 945000)
BNO-MABU-300-CS-4018-10013-001 | STRUCTURAL | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | WATER INJECTION TURBINE SKID - STRUCTURE - TRANSVERSAL SECTION (E 950000) | WATER INJECTION TURBINE SKID - STRUCTURE - TRANSVERSAL SECTION (E 950000)
BNO-MABU-300-CS-4018-10014-001 | STRUCTURAL | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | WATER INJECTION TURBINE SKID - STRUCTURE - DETAILS | WATER INJECTION TURBINE SKID - STRUCTURE - DETAILS
BNO-MABU-300-CS-4018-10016-001 | STRUCTURAL | Issue Status | C01 | C01 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | WATERFLOOD MODULE - DECK EXTENSION (LEVEL 3) MODIFICATIONS | WATERFLOOD MODULE - DECK EXTENSION (LEVEL 3) MODIFICATIONS
BNO-MABU-300-CS-4018-10016-002 | STRUCTURAL | Issue Status | C01 | C01 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | WATERFLOOD MODULE - DECK EXTENSION (LEVEL 3) MODIFICATIONS | WATERFLOOD MODULE - DECK EXTENSION (LEVEL 3) MODIFICATIONS
BNO-MABU-300-CS-4018-10016-003 | STRUCTURAL | Issue Status | C01 | C01 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | WATERFLOOD MODULE - DECK EXTENSION (LEVEL 3) MODIFICATIONS | WATERFLOOD MODULE - DECK EXTENSION (LEVEL 3) MODIFICATIONS
BNO-MABU-300-CS-4018-10016-004 | STRUCTURAL | Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | WATERFLOOD MODULE DECK EXTENSION (LEVEL 3) MODIFICATIONS | WATERFLOOD MODULE DECK EXTENSION (LEVEL 3) MODIFICATIONS
BNO-MABU-300-CS-4018-10021-001 | STRUCTURAL | Revision, Document Status, Issue Status, Final Status | C02 | C03 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING DISTRIBUTION | AFC/AFU RETURNED AS CODE 3 |  | STARBOARD SUBSEA MODULE - STRUCTURE - MONORAIL/EQP FOUNDATION/CONTAINMENT BASIN TO PIG LAUNCHER/RECIEVER SHEET 1 | STARBOARD SUBSEA MODULE - STRUCTURE - MONORAIL/EQP FOUNDATION/CONTAINMENT BASIN TO PIG LAUNCHER/RECIEVER SHEET 1
BNO-MABU-300-CS-4018-10021-002 | STRUCTURAL | Revision, Document Status, Issue Status, Final Status | C02 | C03 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING DISTRIBUTION | AFC/AFU RETURNED AS CODE 3 |  | STARBOARD SUBSEA MODULE - STRUCTURE - MONORAIL/EQP FOUNDATION/CONTAINMENT BASIN TO PIG LAUNCHER/RECIEVER SHEET 2 | STARBOARD SUBSEA MODULE - STRUCTURE - MONORAIL/EQP FOUNDATION/CONTAINMENT BASIN TO PIG LAUNCHER/RECIEVER SHEET 2
BNO-MABU-300-CS-4018-10025-001 | STRUCTURAL | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | WATER INJECTION TURBINE SKID - STRUCTURE - TRANSVERSAL SECTION (E 935000) | WATER INJECTION TURBINE SKID - STRUCTURE - TRANSVERSAL SECTION (E 935000)
BNO-MABU-300-CS-4018-10028-001 | STRUCTURAL | Issue Status | C01 | C01 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | WATER INJECTION TURBINE LIFTING ARRANGEMENT | WATER INJECTION TURBINE LIFTING ARRANGEMENT
BNO-MABU-300-CS-4018-10028-002 | STRUCTURAL | Issue Status | C01 | C01 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | WATER INJECTION TURBINE LIFTING ARRANGEMENT | WATER INJECTION TURBINE LIFTING ARRANGEMENT
BNO-MABU-300-CS-4018-10038-001 | STRUCTURAL | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | WATER INJECTION TURBINE SKID - TYPICAL DETAILS | WATER INJECTION TURBINE SKID - TYPICAL DETAILS
BNO-MABU-300-CS-4018-10038-002 | STRUCTURAL | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | WATER INJECTION TURBINE SKID - TYPICAL DETAILS | WATER INJECTION TURBINE SKID - TYPICAL DETAILS
BNO-MABU-300-CS-4018-10038-003 | STRUCTURAL | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | WATER INJECTION TURBINE SKID - TYPICAL DETAILS | WATER INJECTION TURBINE SKID - TYPICAL DETAILS
BNO-MABU-300-CS-4018-10038-004 | STRUCTURAL | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | WATER INJECTION TURBINE SKID - TYPICAL DETAILS | WATER INJECTION TURBINE SKID - TYPICAL DETAILS
BNO-MABU-300-CS-4018-10038-005 | STRUCTURAL | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | WATER INJECTION TURBINE SKID - TYPICAL DETAILS | WATER INJECTION TURBINE SKID - TYPICAL DETAILS
BNO-MABU-300-CS-4018-10043-001 | STRUCTURAL | Revision, Issue Status, Final Status | C01 | C02 | AFC 3 | AFC 1 | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 1 | STARBOARD SUBSEA MODULE - STRUCTURE - BLOWDOWN PIPING AREA ACCESS 1 | STARBOARD SUBSEA MODULE - STRUCTURE - BLOWDOWN PIPING AREA ACCESS 1
BNO-MABU-300-CS-4018-10043-002 | STRUCTURAL | Revision, Issue Status, Final Status | C01 | C02 | AFC 3 | AFC 1 | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 1 | STARBOARD SUBSEA MODULE - STRUCTURE - BLOWDOWN PIPING AREA ACCESS 1 | STARBOARD SUBSEA MODULE - STRUCTURE - BLOWDOWN PIPING AREA ACCESS 1
BNO-MABU-300-CS-4018-10044-001 | STRUCTURAL | Document Status, Issue Status, Final Status | C02 | C02 | UNDER REVIEW | AFC 3 | ENGINEERING DISTRIBUTION | ISSUED | - | AFC/AFU RETURNED AS CODE 3 | STARBOARD SUBSEA MODULE - STRUCTURE - BLOWDOWN PIPING AREA ACCESS 2 | STARBOARD SUBSEA MODULE - STRUCTURE - BLOWDOWN PIPING AREA ACCESS 2
BNO-MABU-300-CS-4018-10051-011 | STRUCTURAL | Revision, Document Status, Issue Status, Final Status | A01 | C01 | IFA | UNDER REVIEW | ISSUED | TRANSMITTAL | IFA RETURNED AS CODE 3 |  | STARBOARD SUBSEA MODULE - SPS-BN-SS-0022 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | STARBOARD SUBSEA MODULE - SPS-BN-SS-0022 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-012 | STRUCTURAL | Revision, Document Status, Issue Status, Final Status | A01 | C01 | IFA | UNDER REVIEW | ISSUED | TRANSMITTAL | IFA RETURNED AS CODE 3 |  | STARBOARD SUBSEA MODULE - SPS-BN-SS-0022 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | STARBOARD SUBSEA MODULE - SPS-BN-SS-0022 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-032 | STRUCTURAL | Revision, Document Status, Issue Status, Final Status | A01 | C01 | IFA | UNDER REVIEW | ISSUED | TRANSMITTAL | IFA RETURNED AS CODE 3 |  | STARBOARD SUBSEA MODULE - SPS-BN-SS-0032 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | STARBOARD SUBSEA MODULE - SPS-BN-SS-0032 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-033 | STRUCTURAL | Revision, Document Status, Issue Status, Final Status | A01 | C01 | IFA | UNDER REVIEW | ISSUED | TRANSMITTAL | IFA RETURNED AS CODE 3 |  | STARBOARD SUBSEA MODULE - SPS-BN-SS-0032 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS | STARBOARD SUBSEA MODULE - SPS-BN-SS-0032 - SPECIAL PIPE SUPPORTS - PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-043 | STRUCTURAL | Revision, Issue Status, Final Status | A01 | C01 | IFA | AFC 1 | ISSUED | ISSUED | IFA RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 1 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0055 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STARBOARD SUBSEA MODULE - SPS-BN-SS-0055 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-044 | STRUCTURAL | Revision, Issue Status, Final Status | A01 | C01 | IFA | AFC 3 | ISSUED | ISSUED | IFA RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0058 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STARBOARD SUBSEA MODULE - SPS-BN-SS-0058 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-045 | STRUCTURAL | Document Status, Issue Status, Final Status | C01 | C01 | UNDER REVIEW | AFC 3 | ENGINEERING DISTRIBUTION | ISSUED | - | AFC/AFU RETURNED AS CODE 3 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0060 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STARBOARD SUBSEA MODULE - SPS-BN-SS-0060 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-048 | STRUCTURAL | Revision, Document Status, Issue Status, Final Status | A01 | C01 | IFA | UNDER REVIEW | ISSUED | TRANSMITTAL | IFA RETURNED AS CODE 3 |  | STARBOARD SUBSEA MODULE - SPS-BN-SS-0084 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STARBOARD SUBSEA MODULE - SPS-BN-SS-0084 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-056 | STRUCTURAL | Revision, Document Status, Issue Status, Final Status | A01 | C01 | IFA | UNDER REVIEW | ISSUED | TRANSMITTAL | IFA RETURNED AS CODE 3 |  | STARBOARD SUBSEA MODULE - SPS-BN-SS-0069 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STARBOARD SUBSEA MODULE - SPS-BN-SS-0069 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-069 | STRUCTURAL | Revision, Document Status, Issue Status, Final Status | A01 | C01 | IFA | UNDER REVIEW | ISSUED | TRANSMITTAL | IFA RETURNED AS CODE 3 |  | STARBOARD SUBSEA MODULE - SPS-BN-SS-0072 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STARBOARD SUBSEA MODULE - SPS-BN-SS-0072 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-075 | STRUCTURAL | Revision, Issue Status, Final Status | A01 | C01 | IFA | AFC 1 | ISSUED | ISSUED | IFA RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 1 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0125 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STARBOARD SUBSEA MODULE - SPS-BN-SS-0125 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-076 | STRUCTURAL | Revision, Issue Status, Final Status | A01 | C01 | IFA | AFC 1 | ISSUED | ISSUED | IFA RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 1 | STARBOARD SUBSEA MODULE - SPS-BN-SS-0137 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STARBOARD SUBSEA MODULE - SPS-BN-SS-0137 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-090 | STRUCTURAL | Revision, Document Status, Issue Status, Final Status | R01 | A01 | IFR | IFA | ISSUED | TRANSMITTAL | IFR RETURNED AS CODE 3 |  | STARBOARD SUBSEA MODULE - SPS-BN-SS-0148 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STARBOARD SUBSEA MODULE - SPS-BN-SS-0148 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-100 | STRUCTURAL | Revision, Document Status, Issue Status, Final Status | R01 | A01 | IFR | IFA | ISSUED | TRANSMITTAL | IFR RETURNED AS CODE 3 |  | STARBOARD SUBSEA MODULE - SPS-BN-SS-0116 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | STARBOARD SUBSEA MODULE - SPS-BN-SS-0116 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-107 | STRUCTURAL | Title | R01 | R01 | IFR | IFR | ISSUED | ISSUED | IFR RETURNED AS CODE 3 | IFR RETURNED AS CODE 3 | STARBOARD SUBSEA MODULE SPS-BN-SS-0171 - SPECIAL PIPE SUPPORT PLAN, | STARBOARD SUBSEA MODULE SPS-BN-SS-0171 - SPECIAL PIPE SUPPORT PLAN_
BNO-MABU-300-CS-4018-10051-108 | STRUCTURAL | Title, Revision, Document Status, Issue Status, Final Status | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | STARBOARD SUBSEA MODULE SPS-BN-SS-0172 - SPECIAL PIPE SUPPORT PLAN, SECTIONS AND DETAILS | STARBOARD SUBSEA MODULE SPS-BN-SS-0172 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10051-109 | STRUCTURAL | Title, Revision, Document Status, Issue Status, Final Status | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | STARBOARD SUBSEA MODULE SPS-BN-SS-0173 - SPECIAL PIPE SUPPORT PLAN, SECTIONS, AND DETAILS | STARBOARD SUBSEA MODULE SPS-BN-SS-0173 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS_ AND DETAILS
BNO-MABU-300-CS-4018-10052-007 | STRUCTURAL | Revision, Document Status, Issue Status, Final Status | A01 | C01 | IFA | UNDER REVIEW | ISSUED | TRANSMITTAL | IFA RETURNED AS CODE 3 |  | WATERFLOOD MODULE - SPS-BN-SS-0019 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | WATERFLOOD MODULE - SPS-BN-SS-0019 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10052-017 | STRUCTURAL | Revision, Document Status, Issue Status, Final Status | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | WATERFLOOD MODULE - SPS-BN-MR2-0006 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | WATERFLOOD MODULE - SPS-BN-MR2-0006 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10052-021 | STRUCTURAL | Revision, Document Status, Issue Status, Final Status | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | WATERFLOOD MODULE - SPS-BN-MR2-0046 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | WATERFLOOD MODULE - SPS-BN-MR2-0046 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10052-031 | STRUCTURAL | Revision, Document Status, Issue Status, Final Status | A01 | C01 | IFA | UNDER REVIEW | ISSUED | TRANSMITTAL | IFA RETURNED AS CODE 3 |  | WATERFLOOD MODULE - SPS-BN-MR2-0061 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | WATERFLOOD MODULE - SPS-BN-MR2-0061 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10052-032 | STRUCTURAL | Revision, Document Status, Issue Status, Final Status | A01 | C01 | IFA | UNDER REVIEW | ISSUED | TRANSMITTAL | IFA RETURNED AS CODE 3 |  | WATERFLOOD MODULE - SPS-BN-MR2-0061 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | WATERFLOOD MODULE - SPS-BN-MR2-0061 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10052-036 | STRUCTURAL | Revision, Document Status, Issue Status, Final Status | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | WATERFLOOD MODULE - SPS-BN-SS-0011 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | WATERFLOOD MODULE - SPS-BN-SS-0011 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10052-037 | STRUCTURAL | Revision, Document Status, Issue Status, Final Status | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | WATERFLOOD MODULE - SPS-BN-SS-0011 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | WATERFLOOD MODULE - SPS-BN-SS-0011 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10052-041 | STRUCTURAL | Revision, Document Status, Issue Status, Final Status | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | WATERFLOOD MODULE - SPS-BN-WF-0004 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | WATERFLOOD MODULE - SPS-BN-WF-0004 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10052-042 | STRUCTURAL | Title, Revision, Document Status, Issue Status, Final Status | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | WATERFLOOD MODULE SPS-BN-WF-0004 - SPECIAL PIPE SUPPORT PLAN, SECTIONS AND DETAILS | WATERFLOOD MODULE SPS-BN-WF-0004 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10052-043 | STRUCTURAL | Revision, Document Status, Issue Status, Final Status | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | WATERFLOOD MODULE - SPS-BN-WF-0017 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | WATERFLOOD MODULE - SPS-BN-WF-0017 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10052-044 | STRUCTURAL | Title, Revision, Document Status, Issue Status, Final Status | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | WATERFLOOD MODULE SPS-BN-WF-0017—SPECIAL PIPE SUPPORT PLAN, SECTIONS, AND DETAILS | WATERFLOOD MODULE SPS-BN-WF-0017-SPECIAL PIPE SUPPORT PLAN_ SECTIONS_ AND DETAILS
BNO-MABU-300-CS-4018-10052-045 | STRUCTURAL | Title, Revision, Document Status, Issue Status, Final Status | R01 | A01 | IFR | IFA | ISSUED | ENGINEERING DISTRIBUTION | IFR RETURNED AS CODE 3 |  | WATERFLOOD MODULE SPS-BN-WF-0017 - SPECIAL PIPE SUPPORT PLAN, SECTIONS AND DETAILS | WATERFLOOD MODULE SPS-BN-WF-0017 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10052-046 | STRUCTURAL | Title | R01 | R01 | IFR | IFR | ISSUED | ISSUED | IFR RETURNED AS CODE 3 | IFR RETURNED AS CODE 3 | WATERFLOOD MODULE SPS-BN-WF-0065 SPECIAL PIPE SUPPORT PLAN, SECTIONS, AND DETAILS | WATERFLOOD MODULE SPS-BN-WF-0065 SPECIAL PIPE SUPPORT PLAN_ SECTIONS_ AND DETAILS
BNO-MABU-300-CS-4018-10052-047 | STRUCTURAL | Title | R01 | R01 | IFR | IFR | ISSUED | ISSUED | IFR RETURNED AS CODE 3 | IFR RETURNED AS CODE 3 | WATERFLOOD MODULE SPS-BN-WF-0073 SPECIAL PIPE SUPPORT PLAN, SECTIONS, AND DETAILS | WATERFLOOD MODULE SPS-BN-WF-0073 SPECIAL PIPE SUPPORT PLAN_ SECTIONS_ AND DETAILS
BNO-MABU-300-CS-4018-10055-009 | STRUCTURAL | Revision, Issue Status, Final Status | A01 | C01 | IFA | AFC 1 | ISSUED | ISSUED | IFA RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 1 | MAINRACK 2 - SPS-BN-MR2-0018 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | MAINRACK 2 - SPS-BN-MR2-0018 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10055-010 | STRUCTURAL | Revision, Issue Status, Final Status | A01 | C01 | IFA | AFC 1 | ISSUED | ISSUED | IFA RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 1 | MAINRACK 2 - SPS-BN-MR2-0018 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | MAINRACK 2 - SPS-BN-MR2-0018 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10055-011 | STRUCTURAL | Revision, Issue Status, Final Status | A01 | C01 | IFA | AFC 3 | ISSUED | ISSUED | IFA RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | MAINRACK 2 - SPS-BN-MR2-0023 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | MAINRACK 2 - SPS-BN-MR2-0023 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10055-023 | STRUCTURAL | Revision, Document Status, Issue Status, Final Status | R01 | A01 | IFR | IFA | ISSUED | TRANSMITTAL | IFR RETURNED AS CODE 3 |  | MAINRACK 2 - SPS-BN-MR2-0088 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS | MAINRACK 2 - SPS-BN-MR2-0088 - SPECIAL PIPE SUPPORT PLAN_ SECTIONS AND DETAILS
BNO-MABU-300-CS-4018-10055-026 | STRUCTURAL | Title | R01 | R01 | IFR | IFR | ISSUED | ISSUED | IFR RETURNED AS CODE 3 | IFR RETURNED AS CODE 3 | MAINRACK 2 SPS-BN-MR2-0078 SPECIAL PIPE SUPPORT PLAN, SECTIONS, AND DETAILS | MAINRACK 2 SPS-BN-MR2-0078 SPECIAL PIPE SUPPORT PLAN_ SECTIONS_ AND DETAILS
BNO-MABU-300-CS-4018-10084-001 | STRUCTURAL | Document Status, Issue Status, Final Status | C02 | C02 | AFC 3 | AFC 1 | TRANSMITTAL | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | DEMOLITION STARBOARD SUBSEA MODULE DROPPED OBJECT PROTECTION | DEMOLITION STARBOARD SUBSEA MODULE DROPPED OBJECT PROTECTION
BNO-MABU-300-CS-4018-10088-001 | STRUCTURAL | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | MAIN RACK 2 MODULE - WATER INJECTION TURBINE SKID LEVEL1 ACCESS PLATFORM | MAIN RACK 2 MODULE - WATER INJECTION TURBINE SKID LEVEL1 ACCESS PLATFORM
BNO-MABU-300-CS-4018-10088-003 | STRUCTURAL | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | MAIN RACK 2 MODULE - WATER INJECTION TURBINE SKID LEVEL1 ACCESS PLATFORM | MAIN RACK 2 MODULE - WATER INJECTION TURBINE SKID LEVEL1 ACCESS PLATFORM
BNO-MABU-300-CS-4018-10088-004 | STRUCTURAL | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | MAIN RACK 2 MODULE - WATER INJECTION TURBINE SKID LEVEL1 ACCESS PLATFORM | MAIN RACK 2 MODULE - WATER INJECTION TURBINE SKID LEVEL1 ACCESS PLATFORM
BNO-MABU-300-CS-4018-10088-005 | STRUCTURAL | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | MAIN RACK 2 MODULE - WATER INJECTION TURBINE SKID LEVEL1 ACCESS PLATFORM | MAIN RACK 2 MODULE - WATER INJECTION TURBINE SKID LEVEL1 ACCESS PLATFORM
BNO-MABU-300-CS-4018-10088-006 | STRUCTURAL | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | MAIN RACK 2 MODULE - WATER INJECTION TURBINE SKID LEVEL1 ACCESS PLATFORM | MAIN RACK 2 MODULE - WATER INJECTION TURBINE SKID LEVEL1 ACCESS PLATFORM
BNO-MABU-300-CS-4018-10088-007 | STRUCTURAL | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | MAIN RACK 2 MODULE - WATER INJECTION TURBINE SKID LEVEL1 ACCESS PLATFORM | MAIN RACK 2 MODULE - WATER INJECTION TURBINE SKID LEVEL1 ACCESS PLATFORM
BNO-MABU-300-CS-4018-10097-001 | STRUCTURAL | Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | HANDRAIL DEMOLITION FOR LACT MODULE LEVEL 2 - LADDER LANDING FOR MR2 | HANDRAIL DEMOLITION FOR LACT MODULE LEVEL 2 - LADDER LANDING FOR MR2
BNO-MABU-300-CS-7180-10001 | STRUCTURAL | Revision, Document Status, Issue Status, Final Status | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | TBE FOR STRUCTURAL MATERIALS | TBE FOR STRUCTURAL MATERIALS
BNO-MABU-300-CS-7303-10003 | STRUCTURAL | Issue Status, Final Status | A02 | A02 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | WATER INJECTION TURBINE SKID - STRUCTURE - MATERIAL LIST (MTO) | WATER INJECTION TURBINE SKID - STRUCTURE - MATERIAL LIST (MTO)
BNO-MABU-300-CS-7303-10004 | STRUCTURAL | Issue Status, Final Status | A02 | A02 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | PORT SUBSEA MODULE - STRUCTURE DECK EXTENSIONS - MATERIAL LIST (MTO)PORTSIDE SUBSEA MODULE - STRUCTURE DECK EXTENSIONS - MATERIAL LIST (MTO) | PORT SUBSEA MODULE - STRUCTURE DECK EXTENSIONS - MATERIAL LIST (MTO)PORTSIDE SUBSEA MODULE - STRUCTURE DECK EXTENSIONS - MATERIAL LIST (MTO)
BNO-MABU-300-CS-7303-10006 | STRUCTURAL | Issue Status, Final Status | A03 | A03 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | STARBOARD SUBSEA MODULE - STRUCTURE DUE TO BONGA NORTH MODIFICATIONS - MATERIAL LIST (MTO) | STARBOARD SUBSEA MODULE - STRUCTURE DUE TO BONGA NORTH MODIFICATIONS - MATERIAL LIST (MTO)
BNO-MABU-300-CS-7303-10008 | STRUCTURAL | Issue Status, Final Status | A02 | A02 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | MAIN RACK 2 - STRUCTURE - WI PUMP HANDLING AREA - MATERIAL LIST (MTO) | MAIN RACK 2 - STRUCTURE - WI PUMP HANDLING AREA - MATERIAL LIST (MTO)
BNO-MABU-300-CS-7303-10012 | STRUCTURAL | Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | STRUCTURAL PIPE SUPPORTS MTO | STRUCTURAL PIPE SUPPORTS MTO
BNO-MABU-300-CS-7303-10017 | STRUCTURAL | Issue Status, Final Status | A02 | A02 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | WATERFLOOD MODULE - STRUCTURE DUE TO BONGA NORTH MODIFICATIONS - MATERIAL LIST (MTO) | WATERFLOOD MODULE - STRUCTURE DUE TO BONGA NORTH MODIFICATIONS - MATERIAL LIST (MTO)
BNO-MABU-300-CS-8180-10003 | STRUCTURAL | Final Status | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | WATER INJECTION TURBINE SKID - STRUCTURAL VERIFICATION REPORT - IN PLACE ANALYSIS | WATER INJECTION TURBINE SKID - STRUCTURAL VERIFICATION REPORT - IN PLACE ANALYSIS
BNO-MABU-300-CS-8180-10013 | STRUCTURAL | Document Status, Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ISSUED | - | IFA RETURNED AS CODE 3 | STRUCTURAL CABLE TRAY SUPPORTS CALCULATIONS REPORT | STRUCTURAL CABLE TRAY SUPPORTS CALCULATIONS REPORT
BNO-MABU-300-CS-8180-10014 | STRUCTURAL | Final Status | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | WI TURBINE & WF MODULE DECK EXTENSIONS MISCELLANEOUS CALCULATION REPORT | WI TURBINE & WF MODULE DECK EXTENSIONS MISCELLANEOUS CALCULATION REPORT
BNO-MABU-300-EA-0980-10002-001 | ELECTRICAL | Document Status, Issue Status | C04 | C04 | UNDER REVIEW | UNDER REVIEW | ENGINEERING COMMENTS | TRANSMITTAL | - |  | BLOCK DIAGRAM FOR HV MCC | BLOCK DIAGRAM FOR HV MCC
BNO-MABU-300-EA-0980-10006-001 | ELECTRICAL | Revision, Document Status, Issue Status, Final Status | C02 | C03 | AFC 3 | UNDER REVIEW | ISSUED | TRANSMITTAL | AFC/AFU RETURNED AS CODE 3 |  | BLOCK DIAGRAM FOR ALL THE UPS | BLOCK DIAGRAM FOR ALL THE UPS
BNO-MABU-300-EA-1380-10002 | ELECTRICAL | Document Status, Issue Status, Final Status | A05 | A05 | UNDER REVIEW | AFC 1 | ENGINEERING DISTRIBUTION | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | CALCULATION REPORT - ELECTRICAL LOAD BALANCE SB-7401A/B-E-01 | CALCULATION REPORT - ELECTRICAL LOAD BALANCE SB-7401A/B-E-01
BNO-MABU-300-EA-2335-10001-001 | ELECTRICAL | Document Status, Issue Status, Final Status | C03 | C03 | UNDER REVIEW | AFC 3 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 3 | ELECTRICAL JUNCTION BOX ( EJB) TO SPCU INTERFACE HOOKUP DRAWINGS | ELECTRICAL JUNCTION BOX ( EJB) TO SPCU INTERFACE HOOKUP DRAWINGS
BNO-MABU-300-EA-2384-10007-001 | ELECTRICAL | Document Status, Issue Status, Final Status | C03 | C03 | UNDER REVIEW | AFC 1 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | KEY AC UPS SINGLE LINE DIAGRAM | KEY AC UPS SINGLE LINE DIAGRAM
BNO-MABU-300-EA-2384-10008-001 | ELECTRICAL | Document Status, Issue Status, Final Status | C02 | C02 | UNDER REVIEW | AFC 1 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | KEY DC UPS SINGLE LINE DIAGRAM | KEY DC UPS SINGLE LINE DIAGRAM
BNO-MABU-300-EA-2398-10001-001 | ELECTRICAL | Document Status, Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING COMMENTS | - |  | INSTALLATION DETAILS: HEAT TRACING | INSTALLATION DETAILS: HEAT TRACING
BNO-MABU-300-EA-2901-10001 | ELECTRICAL | Final Status | A03 | A03 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | AC AND DC UPS SIZING CALCULATIONS | AC AND DC UPS SIZING CALCULATIONS
BNO-MABU-300-EA-2901-10002 | ELECTRICAL | Final Status | A05 | A05 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | CABLE SELECTION AND SIZING CALCULATION | CABLE SELECTION AND SIZING CALCULATION
BNO-MABU-300-EA-3323-10010 | ELECTRICAL | Final Status | A01 | A01 | AFC 3 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 2 | IFA RETURNED AS CODE 2 | TECHNICAL BID EVALUATION REPORT FOR EARTHING MATERIALS | TECHNICAL BID EVALUATION REPORT FOR EARTHING MATERIALS
BNO-MABU-300-EA-3323-10011 | ELECTRICAL | Document Status, Issue Status, Final Status | A02 | A02 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ISSUED | - | IFA RETURNED AS CODE 1 | TECHNICAL BID EVALUATION REPORT FOR BLANKING PLUGS AND REDUCING BUSHING | TECHNICAL BID EVALUATION REPORT FOR BLANKING PLUGS AND REDUCING BUSHING
BNO-MABU-300-EA-3323-10013 | ELECTRICAL | Document Status, Issue Status, Final Status | A02 | A02 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ISSUED | - | IFA RETURNED AS CODE 1 | TECHNICAL BID EVALUATION REPORT FOR CABLE LUGS | TECHNICAL BID EVALUATION REPORT FOR CABLE LUGS
BNO-MABU-300-EA-3323-10014 | ELECTRICAL | Final Status | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | TECHNICAL BID EVALUATION REPORT FOR REMOTE CONTROL STATIONS | TECHNICAL BID EVALUATION REPORT FOR REMOTE CONTROL STATIONS
BNO-MABU-300-EA-4005-10009-001 | ELECTRICAL | Document Status, Issue Status, Final Status | C03 | C03 | UNDER REVIEW | AFC 3 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 3 | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - MR3 LEVEL 1 | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - MR3 LEVEL 1
BNO-MABU-300-EA-4005-10016-001 | ELECTRICAL | Revision, Document Status, Issue Status, Final Status | C02 | C03 | AFC 3 | UNDER REVIEW | ISSUED | TRANSMITTAL | AFC/AFU RETURNED AS CODE 3 |  | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - MR2 LEVEL 1 | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - MR2 LEVEL 1
BNO-MABU-300-EA-4005-10025-001 | ELECTRICAL | Document Status, Issue Status, Final Status | C02 | C02 | UNDER REVIEW | AFC 3 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 3 | CABLE LADDER LAYOUT SUPPORTS - MR2 LEVEL 1 | CABLE LADDER LAYOUT SUPPORTS - MR2 LEVEL 1
BNO-MABU-300-EA-4005-10026-001 | ELECTRICAL | Document Status, Issue Status, Final Status | C01 | C01 | UNDER REVIEW | AFC 1 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | CABLE LADDER LAYOUT SUPPORTS - MR3 LEVEL 1 | CABLE LADDER LAYOUT SUPPORTS - MR3 LEVEL 1
BNO-MABU-300-EA-4005-10027-001 | ELECTRICAL | Document Status, Issue Status, Final Status | C02 | C02 | UNDER REVIEW | AFC 1 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | CABLE LADDER LAYOUT SUPPORTS - MR3 LEVEL 4 | CABLE LADDER LAYOUT SUPPORTS - MR3 LEVEL 4
BNO-MABU-300-EA-4005-10028-001 | ELECTRICAL | Document Status, Issue Status, Final Status | C01 | C01 | UNDER REVIEW | AFC 1 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | CABLE LADDER LAYOUT SUPPORTS - PS LEVEL 1 | CABLE LADDER LAYOUT SUPPORTS - PS LEVEL 1
BNO-MABU-300-EA-4005-10029-001 | ELECTRICAL | Document Status, Issue Status, Final Status | C01 | C01 | UNDER REVIEW | AFC 3 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 3 | CABLE LADDER LAYOUT SUPPORTS - MR2 LEVEL 4 | CABLE LADDER LAYOUT SUPPORTS - MR2 LEVEL 4
BNO-MABU-300-EA-4005-10030-001 | ELECTRICAL | Document Status, Issue Status, Final Status | C01 | C01 | UNDER REVIEW | AFC 1 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | CABLE LADDER LAYOUT SUPPORTS - SS LEVEL 1 | CABLE LADDER LAYOUT SUPPORTS - SS LEVEL 1
BNO-MABU-300-EA-4005-10036-001 | ELECTRICAL | Document Status, Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ISSUED | - | IFA RETURNED AS CODE 3 | CABLE LADDER LAYOUT SUPPORTS - HULL | CABLE LADDER LAYOUT SUPPORTS - HULL
BNO-MABU-300-EA-4024-10006-001 | ELECTRICAL | Document Status, Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING COMMENTS | TRANSMITTAL | - |  | LIGHTING DISTRIBUTION PLAN - MR LEVELS | LIGHTING DISTRIBUTION PLAN - MR LEVELS
BNO-MABU-300-EA-4024-10018-001 | ELECTRICAL | Document Status, Issue Status, Final Status | C03 | C03 | UNDER REVIEW | AFC 1 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | LIGHTING DISTRIBUTION PLAN FOR MR3 LEVEL 4_ HPU AREA | LIGHTING DISTRIBUTION PLAN FOR MR3 LEVEL 4_ HPU AREA
BNO-MABU-300-EA-4024-10019-001 | ELECTRICAL | Document Status, Issue Status, Final Status | C03 | C03 | UNDER REVIEW | AFC 1 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | LIGHTING & SMALL POWER LAYOUT STARBOARD SUBSEA MODULE | LIGHTING & SMALL POWER LAYOUT STARBOARD SUBSEA MODULE
BNO-MABU-300-EA-4024-10021-001 | ELECTRICAL | Issue Status | C01 | C01 | UNDER REVIEW | UNDER REVIEW | ENGINEERING COMMENTS | ENGINEERING COMMENTS | - |  | LIGHTING DISTRIBUTION PLAN MR4 LEVEL 4 BVP AREA | LIGHTING DISTRIBUTION PLAN MR4 LEVEL 4 BVP AREA
BNO-MABU-300-EA-4024-10022-001 | ELECTRICAL | Document Status, Issue Status, Final Status | C02 | C02 | UNDER REVIEW | AFC 1 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | GROUNDING DISTRIBUTION PLAN MR4 LEVEL 4 BVP AREA | GROUNDING DISTRIBUTION PLAN MR4 LEVEL 4 BVP AREA
BNO-MABU-300-EA-4024-10023-001 | ELECTRICAL | Document Status, Issue Status, Final Status | C02 | C02 | UNDER REVIEW | AFC 1 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | GROUNDING DISTRIBUTION PLAN - MR3 LEVEL 4_ HPU AREA | GROUNDING DISTRIBUTION PLAN - MR3 LEVEL 4_ HPU AREA
BNO-MABU-300-EA-4025-10001-001 | ELECTRICAL | Document Status, Issue Status, Final Status | C02 | C02 | UNDER REVIEW | AFC 1 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | UPDATE OF EXISTING LIGHTING AND SMALL POWER LAYOUT | UPDATE OF EXISTING LIGHTING AND SMALL POWER LAYOUT
BNO-MABU-300-EA-4308-10001 | ELECTRICAL | Final Status | A06 | A06 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | ELECTRICAL CABLE LIST | ELECTRICAL CABLE LIST
BNO-MABU-300-EA-4329-10001 | ELECTRICAL | Document Status, Issue Status, Final Status | A04 | A04 | UNDER REVIEW | AFC 1 | ENGINEERING DISTRIBUTION | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | ELECTRICAL LOAD LIST | ELECTRICAL LOAD LIST
BNO-MABU-300-EA-4380-10007 | ELECTRICAL | Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ENGINEERING COMMENTS | - |  | PROTECTION SCHEME & RELAY SETTING SCHEDULES | PROTECTION SCHEME & RELAY SETTING SCHEDULES
BNO-MABU-300-EA-4380-10008 | ELECTRICAL | Document Status, Issue Status, Final Status | C02 | C02 | UNDER REVIEW | AFC 3 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 3 | DISTRIBUTION BOARD SCHEDULE FOR ALL THE DB | DISTRIBUTION BOARD SCHEDULE FOR ALL THE DB
BNO-MABU-300-EA-4380-10009 | ELECTRICAL | Final Status | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | LV SWITCHGEAR SCHEDULE UPDATE FOR BM | LV SWITCHGEAR SCHEDULE UPDATE FOR BM
BNO-MABU-300-EA-4380-10012 | ELECTRICAL | Document Status, Issue Status, Final Status | A04 | A04 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | TRANSMITTAL | - |  | CONTROL. ALARM AND MONITORING TABLE | CONTROL. ALARM AND MONITORING TABLE
BNO-MABU-300-EA-7180-10005 | ELECTRICAL | Document Status, Issue Status, Final Status | A03 | A03 | UNDER REVIEW | AFC 1 | ENGINEERING DISTRIBUTION | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | BN PROJECT SAFOP CLOSE OUT REPORT | BN PROJECT SAFOP CLOSE OUT REPORT
BNO-MABU-300-EA-7180-10012 | ELECTRICAL | Final Status | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | ELECTRICAL SITE VISIT REPORT | ELECTRICAL SITE VISIT REPORT
BNO-MABU-300-EA-7770-10001 | ELECTRICAL | Document Status, Issue Status, Final Status | A06 | A06 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | TRANSMITTAL | - |  | SPECIFICATION FOR ELECTRICAL EQUIPMENT SIZING REVALIDATION | SPECIFICATION FOR ELECTRICAL EQUIPMENT SIZING REVALIDATION
BNO-MABU-300-EA-7771-10003 | ELECTRICAL | Final Status | A04 | A04 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | SPECIFICATION FOR ELECTRIC MOTOR | SPECIFICATION FOR ELECTRIC MOTOR
BNO-MABU-300-EA-7771-10010 | ELECTRICAL | Final Status | A03 | A03 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | SPECIFICATION FOR DC UPS | SPECIFICATION FOR DC UPS
BNO-MABU-300-EA-8260-10003 | ELECTRICAL | Document Status, Issue Status, Final Status | A03 | A03 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ISSUED | - | IFA RETURNED AS CODE 1 | ELECTRICAL STUDIES REPORT - SHORT-CIRCUIT CURRENTS | ELECTRICAL STUDIES REPORT - SHORT-CIRCUIT CURRENTS
BNO-MABU-300-EA-8260-10004 | ELECTRICAL | Revision, Document Status, Issue Status, Final Status | A02 | A03 | AFC 3 | IFA | ISSUED | ENGINEERING DISTRIBUTION | AFC/AFU RETURNED AS CODE 3 |  | ELECTRICAL STUDIES REPORT - PROTECTION COORDINATION | ELECTRICAL STUDIES REPORT - PROTECTION COORDINATION
BNO-MABU-300-EA-8260-10006 | ELECTRICAL | Document Status, Issue Status, Final Status | A02 | A02 | UNDER REVIEW | AFC 3 | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 3 | ELECTRICAL STUDIES REPORT - ARC FLASH | ELECTRICAL STUDIES REPORT - ARC FLASH
BNO-MABU-300-HX-1212-10001 | TECHNICAL SAFETY | Document Status, Issue Status, Final Status | A05 | A05 | UNDER REVIEW | AFC 1 | ENGINEERING CONSOLIDATION | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | FIRE WATER DEMAND VERIFICATION - CALCULATION NOTES | FIRE WATER DEMAND VERIFICATION - CALCULATION NOTES
BNO-MABU-300-HX-3323-10001 | TECHNICAL SAFETY | Revision, Issue Status, Final Status | R01 | A01 | IFR | IFA | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | TBE FOR SAFETY ITEMS | TBE FOR SAFETY ITEMS
BNO-MABU-300-HX-6019-10001 | TECHNICAL SAFETY | Document Status, Issue Status, Final Status | A02 | A02 | UNDER REVIEW | AFC 1 | ENGINEERING CONSOLIDATION | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | EMERGENCY SYSTEMS SURVIVABILITY ASSESSMENT | EMERGENCY SYSTEMS SURVIVABILITY ASSESSMENT
BNO-MABU-300-HX-6180-10003 | TECHNICAL SAFETY | Issue Status | R01 | R01 | IFR | IFR | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | PACKAGED EQUIPMENT REVIEW- WATER INJECTION SYSTEM | PACKAGED EQUIPMENT REVIEW- WATER INJECTION SYSTEM
BNO-MABU-300-HX-6180-10004 | TECHNICAL SAFETY | Issue Status | R01 | R01 | IFR | IFR | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | PACKAGED EQUIPMENT REVIEW- METHANOL INJECTION SYSTEM | PACKAGED EQUIPMENT REVIEW- METHANOL INJECTION SYSTEM
BNO-MABU-300-HX-6873-10001 | TECHNICAL SAFETY | Issue Status | R01 | R01 | IFR | IFR | ENGINEERING CONSOLIDATION | ENGINEERING CONSOLIDATION | - |  | PACKAGED EQUIPMENT REVIEW- CORROSION INHIBITION SYSTEM | PACKAGED EQUIPMENT REVIEW- CORROSION INHIBITION SYSTEM
BNO-MABU-300-HX-6873-10006 | TECHNICAL SAFETY | Issue Status, Final Status | A02 | A02 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | CONSTRUCTION HAZID CLOSE-OUT REPORT | CONSTRUCTION HAZID CLOSE-OUT REPORT
BNO-MABU-300-HX-6874-10001 | TECHNICAL SAFETY | Document Status, Issue Status | A03 | A03 | AFC 1 | AFC 1 | ENGINEERING CONSOLIDATION | ISSUED | APPROVED FOR USE (AFU) | AFC/AFU RETURNED AS CODE 1 | GAS DISPERSION MODELLING STUDY REPORT | GAS DISPERSION MODELLING STUDY REPORT
BNO-MABU-300-HX-6875-10008 | TECHNICAL SAFETY | Issue Status, Final Status | A02 | A02 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | HAZOP CLOSEOUT REPORT (DED) | HAZOP CLOSEOUT REPORT (DED)
BNO-MABU-300-HX-6881-10002 | TECHNICAL SAFETY | Document Status, Issue Status, Final Status | A02 | A02 | UNDER REVIEW | AFC 1 | ENGINEERING CONSOLIDATION | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | DESIGN SAFETY CASE REPORT | DESIGN SAFETY CASE REPORT
BNO-MABU-300-HX-6881-10003 | TECHNICAL SAFETY | Final Status | A01 | A01 | AFC 3 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | HFE 60% 3D MODEL REVIEW AND VALVE CRITICALITY ASSESSMENT REPORT | HFE 60% 3D MODEL REVIEW AND VALVE CRITICALITY ASSESSMENT REPORT
BNO-MABU-300-HX-7180-10001 | TECHNICAL SAFETY | Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | HUMAN FACTORS ENGINEERING REVIEW OF ALARM RATIONALISATION REPORT | HUMAN FACTORS ENGINEERING REVIEW OF ALARM RATIONALISATION REPORT
BNO-MABU-300-HX-7303-10003 | TECHNICAL SAFETY | Document Status, Issue Status, Final Status | A02 | A02 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ISSUED | - | IFA RETURNED AS CODE 1 | BILL OF MATERIALS (FIRE & SAFETY) | BILL OF MATERIALS (FIRE & SAFETY)
BNO-MABU-300-HX-7739-10003 | TECHNICAL SAFETY | Document Status, Issue Status, Final Status | A05 | A05 | UNDER REVIEW | AFC 1 | ENGINEERING CONSOLIDATION | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | SAFETY EQUIPMENT SPECIFICATION | SAFETY EQUIPMENT SPECIFICATION
BNO-MABU-300-HX-7739-10004 | TECHNICAL SAFETY | Document Status, Issue Status, Final Status | A02 | A02 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ISSUED | - | IFA RETURNED AS CODE 1 | SAFETY EQUIPMENT MTO | SAFETY EQUIPMENT MTO
BNO-MABU-300-HX-7753-10006 | TECHNICAL SAFETY | Final Status | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | DESIGN SAFETY CASE TERMS OF REFERENCE | DESIGN SAFETY CASE TERMS OF REFERENCE
BNO-MABU-300-IN-0780-10001 | INSTRUMENTATION | Final Status | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 2 | IFA RETURNED AS CODE 2 | SIL DETERMINATION REPORT | SIL DETERMINATION REPORT
BNO-MABU-300-IN-0780-10009 | INSTRUMENTATION | Document Status, Issue Status, Final Status | A03 | A03 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ENGINEERING CONSOLIDATION | - |  | ALARM RATIONALISATION WORKSHOP - TOR | ALARM RATIONALISATION WORKSHOP - TOR
BNO-MABU-300-IN-1979-10002 | INSTRUMENTATION | Final Status | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | MASTER ALARM DATABASE (VARIABLE TABLE) | MASTER ALARM DATABASE (VARIABLE TABLE)
BNO-MABU-300-IN-1979-10003 | INSTRUMENTATION | Final Status | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | ESD TRIP SCHEDULE (INPUT ONLY) | ESD TRIP SCHEDULE (INPUT ONLY)
BNO-MABU-300-IN-2105-10009 | INSTRUMENTATION | Document Status, Final Status | A04 | A04 | UNDER REVIEW | AFC 3 | ENGINEERING DISTRIBUTION | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | INSTRUMENTATION & AUTOMATION DATASHEET FOR RESTRICTION ORIFICE | INSTRUMENTATION & AUTOMATION DATASHEET FOR RESTRICTION ORIFICE
BNO-MABU-300-IN-2105-10012 | INSTRUMENTATION | Final Status | A04 | A04 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | INSTRUMENTATION & AUTOMATION DATASHEET FOR PRESSURE GAUGE | INSTRUMENTATION & AUTOMATION DATASHEET FOR PRESSURE GAUGE
BNO-MABU-300-IN-2105-10015 | INSTRUMENTATION | Final Status | A05 | A05 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | INSTRUMENTATION & AUTOMATION DATASHEET FOR PRESSURE RELIEF VALVE | INSTRUMENTATION & AUTOMATION DATASHEET FOR PRESSURE RELIEF VALVE
BNO-MABU-300-IN-2105-10018 | INSTRUMENTATION | Final Status | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | INSTRUMENTATION & AUTOMATION DATASHEET FOR HYDRAULIC HAND VALVE AND SHUTDOWN VALVE | INSTRUMENTATION & AUTOMATION DATASHEET FOR HYDRAULIC HAND VALVE AND SHUTDOWN VALVE
BNO-MABU-300-IN-2105-10021 | INSTRUMENTATION | Final Status | A05 | A05 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | INSTRUMENTATION & AUTOMATION DATASHEET FOR OPEN PATH GAS DETECTOR | INSTRUMENTATION & AUTOMATION DATASHEET FOR OPEN PATH GAS DETECTOR
BNO-MABU-300-IN-2335-10002-001 | INSTRUMENTATION | Revision, Document Status, Issue Status, Final Status | C01 | C02 | AFC 1 | UNDER REVIEW | ISSUED | ENGINEERING COMMENTS | AFC/AFU RETURNED AS CODE 1 |  | SUPPORT HOOK UP DRAWING | SUPPORT HOOK UP DRAWING
BNO-MABU-300-IN-2341-10003-001 | INSTRUMENTATION | Revision, Document Status, Issue Status, Final Status | C02 | C03 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING COMMENTS | AFC/AFU RETURNED AS CODE 3 |  | HPU/HCU INTERFACE HOOKUP DRAWINGS | HPU/HCU INTERFACE HOOKUP DRAWINGS
BNO-MABU-300-IN-2341-10004-001 | INSTRUMENTATION | Revision, Document Status, Issue Status, Final Status | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING COMMENTS | AFC/AFU RETURNED AS CODE 3 |  | PRODUCTION UMBILICAL INTERFACE HOOKUP DRAWINGS | PRODUCTION UMBILICAL INTERFACE HOOKUP DRAWINGS
BNO-MABU-300-IN-2341-10005-001 | INSTRUMENTATION | Revision, Document Status, Issue Status, Final Status | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING COMMENTS | AFC/AFU RETURNED AS CODE 3 |  | GASLIFT UMBILICAL HOOKUP DRAWING | GASLIFT UMBILICAL HOOKUP DRAWING
BNO-MABU-300-IN-2341-10007-001 | INSTRUMENTATION | Revision, Document Status, Issue Status, Final Status | C02 | C03 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING COMMENTS | AFC/AFU RETURNED AS CODE 3 |  | CORROSION INHIBITOR & METHANOL SYSTEM TO TUPA INTERFACE HOOKUP DRAWINGS | CORROSION INHIBITOR & METHANOL SYSTEM TO TUPA INTERFACE HOOKUP DRAWINGS
BNO-MABU-300-IN-2341-10008-001 | INSTRUMENTATION | Revision, Document Status, Issue Status, Final Status | C02 | C03 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING COMMENTS | AFC/AFU RETURNED AS CODE 3 |  | BUNDLE GASLIFT UMBILICAL (BGLU) TO GASLIFT TUPA HOOKUP DRAWINGS | BUNDLE GASLIFT UMBILICAL (BGLU) TO GASLIFT TUPA HOOKUP DRAWINGS
BNO-MABU-300-IN-2347-10001-001 | INSTRUMENTATION | Final Status | A01 | A01 | AFC 3 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | INSTRUMENT LOOP DIAGRAMS | INSTRUMENT LOOP DIAGRAMS
BNO-MABU-300-IN-2389-10002-001 | INSTRUMENTATION | Final Status | A01 | A01 | AFC 3 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | RIO PANEL TERMINATION DRAWINGS | RIO PANEL TERMINATION DRAWINGS
BNO-MABU-300-IN-3323-10004 | INSTRUMENTATION | Revision, Document Status, Issue Status, Final Status | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | TBE FOR TUBING & BULK MATERIAL MTO | TBE FOR TUBING & BULK MATERIAL MTO
BNO-MABU-300-IN-3323-10005 | INSTRUMENTATION | Revision, Document Status, Issue Status, Final Status | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | TBE FOR SUPPORT | TBE FOR SUPPORT
BNO-MABU-300-IN-3323-10007 | INSTRUMENTATION | Revision, Document Status, Issue Status, Final Status | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | TBE FOR CABLE TRAYS AND ACCESSORIES | TBE FOR CABLE TRAYS AND ACCESSORIES
BNO-MABU-300-IN-3323-10008 | INSTRUMENTATION | Revision, Document Status, Issue Status, Final Status | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | TBE FOR CHANNELS AND ACCESSORIES | TBE FOR CHANNELS AND ACCESSORIES
BNO-MABU-300-IN-3323-10011 | INSTRUMENTATION | Revision, Document Status, Issue Status, Final Status | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | TBE FOR CABLE GLANDS | TBE FOR CABLE GLANDS
BNO-MABU-300-IN-3323-10012 | INSTRUMENTATION | Revision, Document Status, Issue Status, Final Status | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | TBE FOR CABLES AND MULTICABLES | TBE FOR CABLES AND MULTICABLES
BNO-MABU-300-IN-3323-10015 | INSTRUMENTATION | Revision, Document Status, Issue Status, Final Status | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | TBE FOR JUNCTION BOXES | TBE FOR JUNCTION BOXES
BNO-MABU-300-IN-3323-10016 | INSTRUMENTATION | Revision, Document Status, Issue Status, Final Status | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | TBE FOR MISCELLANEOUS | TBE FOR MISCELLANEOUS
BNO-MABU-300-IN-3323-10017 | INSTRUMENTATION | Revision, Document Status, Issue Status, Final Status | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | TBE FOR PIPING AND PIPING CONNECTIONS | TBE FOR PIPING AND PIPING CONNECTIONS
BNO-MABU-300-IN-4018-10002-001 | INSTRUMENTATION | Document Status, Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | TRANSMITTAL | - |  | INSTRUMENT TUBING ROUTING DRAWINGS | INSTRUMENT TUBING ROUTING DRAWINGS
BNO-MABU-300-IN-4024-10004-001 | INSTRUMENTATION | Document Status, Issue Status | C03 | C03 | UNDER REVIEW | UNDER REVIEW | ENGINEERING COMMENTS | TRANSMITTAL | - |  | F&G LOCATION LAYOUT & PLAN FLOWLINE CORROSION INHIBITOR SKID | F&G LOCATION LAYOUT & PLAN FLOWLINE CORROSION INHIBITOR SKID
BNO-MABU-300-IN-4024-10008-001 | INSTRUMENTATION | Document Status, Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING COMMENTS | ENGINEERING CONSOLIDATION | - |  | PNEUMATIC & HYDRAULIC INSTRUMENTATION PLAN & LOCATION WATERFLOOD INJECTION PACKAGE | PNEUMATIC & HYDRAULIC INSTRUMENTATION PLAN & LOCATION WATERFLOOD INJECTION PACKAGE
BNO-MABU-300-IN-4024-10101-001 | INSTRUMENTATION | Issue Status | R01 | R01 | NI | NI | NÃO SE APLICA | NÃO SE APLICA | - |  | PNEUMATIC & HYDRAULIC INSTRUMENTATION LOCATION PLAN | PNEUMATIC & HYDRAULIC INSTRUMENTATION LOCATION PLAN
BNO-MABU-300-IN-4024-10102-001 | INSTRUMENTATION | Issue Status | R01 | R01 | NI | NI | NÃO SE APLICA | NÃO SE APLICA | - |  | PNEUMATIC & HYDRAULIC TUBING TRAY INSTRUMENTATION ROUTE PLAN | PNEUMATIC & HYDRAULIC TUBING TRAY INSTRUMENTATION ROUTE PLAN
BNO-MABU-300-IN-4024-10103-001 | INSTRUMENTATION | Issue Status | R01 | R01 | NI | NI | NÃO SE APLICA | NÃO SE APLICA | - |  | PNEUMATIC & HYDRAULIC TUBING TRAY INSTRUMENTATION SUPPORT PLAN | PNEUMATIC & HYDRAULIC TUBING TRAY INSTRUMENTATION SUPPORT PLAN
BNO-MABU-300-IN-4024-10104-001 | INSTRUMENTATION | Issue Status | R01 | R01 | NI | NI | NÃO SE APLICA | NÃO SE APLICA | - |  | ELECTRICAL & INSTRUMENTATION LOCATION PLAN | ELECTRICAL & INSTRUMENTATION LOCATION PLAN
BNO-MABU-300-IN-4024-10105-001 | INSTRUMENTATION | Issue Status | R01 | R01 | NI | NI | NÃO SE APLICA | NÃO SE APLICA | - |  | ELECTRICAL & INSTRUMENTATION CABLE TRAY ROUTE PLAN | ELECTRICAL & INSTRUMENTATION CABLE TRAY ROUTE PLAN
BNO-MABU-300-IN-4024-10106-001 | INSTRUMENTATION | Issue Status | R01 | R01 | NI | NI | NÃO SE APLICA | NÃO SE APLICA | - |  | ELECTRICAL & INSTRUMENTATION CABLE TRAY SUPPORT PLAN | ELECTRICAL & INSTRUMENTATION CABLE TRAY SUPPORT PLAN
BNO-MABU-300-IN-4024-10107-001 | INSTRUMENTATION | Issue Status | R01 | R01 | NI | NI | NÃO SE APLICA | NÃO SE APLICA | - |  | FIRE AND GAS INSTRUMENTATION LOCATION PLAN | FIRE AND GAS INSTRUMENTATION LOCATION PLAN
BNO-MABU-300-IN-4024-10108-001 | INSTRUMENTATION | Issue Status | R01 | R01 | NI | NI | NÃO SE APLICA | NÃO SE APLICA | - |  | FIRE AND GAS INSTRUMENTATION CABLE TRAY ROUTE PLAN | FIRE AND GAS INSTRUMENTATION CABLE TRAY ROUTE PLAN
BNO-MABU-300-IN-4024-10109-001 | INSTRUMENTATION | Issue Status | R01 | R01 | NI | NI | NÃO SE APLICA | NÃO SE APLICA | - |  | FIRE AND GAS INSTRUMENTATION CABLE TRAY SUPPORT PLAN | FIRE AND GAS INSTRUMENTATION CABLE TRAY SUPPORT PLAN
BNO-MABU-300-IN-4306-10006 | INSTRUMENTATION | Revision, Document Status, Issue Status, Final Status | A02 | A03 | AFC 3 | IFA | ISSUED | ENGINEERING COMMENTS | AFC/AFU RETURNED AS CODE 3 |  | MATERIAL LIST FOR INSTRUMENT & JUNCTION BOX SUPPORT HOOK UP ITEMS | MATERIAL LIST FOR INSTRUMENT & JUNCTION BOX SUPPORT HOOK UP ITEMS
BNO-MABU-300-IN-4306-10016 | INSTRUMENTATION | Issue Status, Final Status | A03 | A03 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ENGINEERING COMMENTS | - |  | MATERIAL LIST FOR PROCESS HOOK UP DRAWING | MATERIAL LIST FOR PROCESS HOOK UP DRAWING
BNO-MABU-300-IN-4306-10017 | INSTRUMENTATION | Issue Status, Final Status | A03 | A03 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ENGINEERING COMMENTS | - |  | MATERIAL LIST FOR ELECTRICAL HOOK UP DRAWING | MATERIAL LIST FOR ELECTRICAL HOOK UP DRAWING
BNO-MABU-300-IN-4308-10001 | INSTRUMENTATION | Title, Document Status, Issue Status, Final Status | A02 | A02 | UNDER REVIEW | IFA | ENGINEERING CONSOLIDATION | ISSUED | NOT ISSUED | IFA RETURNED AS CODE 3 | INSTRUMENT CABLE SCHEDULE | INSTRUMENTATION CABLE SCHEDULE
BNO-MABU-300-IN-4380-10001 | INSTRUMENTATION | Document Status, Final Status | A02 | A02 | AFC 1 | IFA | ENGINEERING COMMENTS | ISSUED | IFA RETURNED AS CODE 2 | IFA RETURNED AS CODE 2 | MASTER CONTROL PANEL LIST | MASTER CONTROL PANEL LIST
BNO-MABU-300-IN-4380-10002 | INSTRUMENTATION | Final Status | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | ALARM AND SET POINT LIST | ALARM AND SET POINT LIST
BNO-MABU-300-IN-4380-10003 | INSTRUMENTATION | Final Status | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | INSTRUMENT LIST | INSTRUMENT LIST
BNO-MABU-300-IN-5680-10001 | INSTRUMENTATION | Document Status, Issue Status, Final Status | A02 | A02 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | TRANSMITTAL | - |  | IP(F) NARRATIVES | IP(F) NARRATIVES
BNO-MABU-300-IN-7303-10004 | INSTRUMENTATION | Final Status | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | MATERIAL REQUISITION MAIN AUTOMATION CONTRACTOR | MATERIAL REQUISITION MAIN AUTOMATION CONTRACTOR
BNO-MABU-300-IN-7303-10008 | INSTRUMENTATION | Final Status | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | MATERIAL REQUISITION FOR ULTRASONIC FLOWMETER | MATERIAL REQUISITION FOR ULTRASONIC FLOWMETER
BNO-MABU-300-IN-7303-10021 | INSTRUMENTATION | Issue Status, Final Status | A06 | A06 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ENGINEERING COMMENTS | - |  | MATERIAL REQUISITION FOR POINT TYPE GAS DETECTOR | MATERIAL REQUISITION FOR POINT TYPE GAS DETECTOR
BNO-MABU-300-IN-7303-10023 | INSTRUMENTATION | Issue Status, Final Status | A06 | A06 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ENGINEERING COMMENTS | - |  | MATERIAL REQUISITION FOR IR FLAME DETECTOR | MATERIAL REQUISITION FOR IR FLAME DETECTOR
BNO-MABU-300-IN-7303-10026 | INSTRUMENTATION | Issue Status, Final Status | A04 | A04 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ENGINEERING COMMENTS | - |  | MATERIAL REQUISITION FOR INSTRUMENTATION CABLES | MATERIAL REQUISITION FOR INSTRUMENTATION CABLES
BNO-MABU-300-IN-7303-10028 | INSTRUMENTATION | Revision, Document Status, Issue Status | A02 | A03 | IFA | IFA | ISSUED | ENGINEERING COMMENTS | IFA RETURNED AS CODE 3 |  | MATERIAL REQUISITION FOR TUBINGS AND COMPRESSION CONNSECTIONS | MATERIAL REQUISITION FOR TUBINGS AND COMPRESSION CONNSECTIONS
BNO-MABU-300-IN-7303-10030 | INSTRUMENTATION | Document Status, Final Status | A03 | A03 | UNDER REVIEW | AFC 3 | ENGINEERING DISTRIBUTION | ENGINEERING COMMENTS | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | MATERIAL REQUISITION FOR CABLE GLANDS | MATERIAL REQUISITION FOR CABLE GLANDS
BNO-MABU-300-IN-8880-10001-001 | INSTRUMENTATION | Final Status | A01 | A01 | AFC 3 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | INSTRUMENT WIRING DIAGRAMS | INSTRUMENT WIRING DIAGRAMS
BNO-MABU-300-KA-7739-10004 | IT / IM | Final Status | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | BONGA NORTH PCD - IT SECURITY DESIGN SPECIFICATION - FINAL | BONGA NORTH PCD - IT SECURITY DESIGN SPECIFICATION - FINAL
BNO-MABU-300-MP-1206-10002 | PIPING | Final Status | A03 | A03 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | SUPPORT LOADS FOR STRUCTURE-LAUNCHER AND RECEIVER A-0820J | SUPPORT LOADS FOR STRUCTURE-LAUNCHER AND RECEIVER A-0820J
BNO-MABU-300-MP-1206-10003 | PIPING | Final Status | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | SUPPORT LOADS FOR STRUCTURE-LAUNCHER AND RECEIVER A-0820K | SUPPORT LOADS FOR STRUCTURE-LAUNCHER AND RECEIVER A-0820K
BNO-MABU-300-MP-1206-10005 | PIPING | Final Status | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | SPRING SUPPORTS SCHEDULE | SPRING SUPPORTS SCHEDULE
BNO-MABU-300-MP-1206-10006 | PIPING | Final Status | A03 | A03 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | SUPPORT LOADS FOR STRUCTURE-CORROSION INHIBITOR TANK T-4282 | SUPPORT LOADS FOR STRUCTURE-CORROSION INHIBITOR TANK T-4282
BNO-MABU-300-MP-2105-10001 | PIPING | Final Status | A03 | A03 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | PIPING DATASHEETS FOR LARGE BORE BALL VALVES | PIPING DATASHEETS FOR LARGE BORE BALL VALVES
BNO-MABU-300-MP-2105-10006 | PIPING | Final Status | A03 | A03 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | PIPING DATASHEETS FOR SMALL BORE BALL VALVES | PIPING DATASHEETS FOR SMALL BORE BALL VALVES
BNO-MABU-300-MP-2105-10007 | PIPING | Final Status | A01 | A01 | AFC 3 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | PIPING DATASHEETS FOR BUTTERFLY VALVES | PIPING DATASHEETS FOR BUTTERFLY VALVES
BNO-MABU-300-MP-2105-10016 | PIPING | Final Status | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | DATASHEET FOR STRAINERS | DATASHEET FOR STRAINERS
BNO-MABU-300-MP-2343-10004 | PIPING | Final Status | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING: 12-PM-043091-100-IFJ | PIPING CONSTRUCT ISOMETRIC DRAWING: 12-PM-043091-100-IFJ
BNO-MABU-300-MP-2343-10007 | PIPING | Final Status | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING: 6-PM-043094-120-IFJ | PIPING CONSTRUCT ISOMETRIC DRAWING: 6-PM-043094-120-IFJ
BNO-MABU-300-MP-2343-10010 | PIPING | Revision, Document Status, Issue Status, Final Status | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-PM-043095-1800-IFJ | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-PM-043095-1800-IFJ
BNO-MABU-300-MP-2343-10013 | PIPING | Final Status | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING: 10"-PM-043100-1562-IFJ | PIPING CONSTRUCT ISOMETRIC DRAWING: 10"-PM-043100-1562-IFJ
BNO-MABU-300-MP-2343-10016 | PIPING | Document Status, Issue Status, Final Status | C03 | C03 | UNDER REVIEW | AFC 1 | ENGINEERING CONSOLIDATION | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-PM-043103-1125-IFJ | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-PM-043103-1125-IFJ
BNO-MABU-300-MP-2343-10017 | PIPING | Revision, Document Status, Issue Status, Final Status | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-PM-043111-100-CC | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-PM-043111-100-CC
BNO-MABU-300-MP-2343-10031 | PIPING | Document Status, Issue Status, Final Status | C02 | C02 | UNDER REVIEW | AFC 3A | ENGINEERING COMMENTS | ISSUED | - | AFC/AFU RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING: 24"-WI-403225-10S-13841 | PIPING CONSTRUCT ISOMETRIC DRAWING: 24"-WI-403225-10S-13841
BNO-MABU-300-MP-2343-10032 | PIPING | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING CONSOLIDATION | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-1/2"-VA-403232-80-AV | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-1/2"-VA-403232-80-AV
BNO-MABU-300-MP-2343-10033 | PIPING | Revision, Document Status, Issue Status, Final Status | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-VA-403233-20-AV | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-VA-403233-20-AV
BNO-MABU-300-MP-2343-10035 | PIPING | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING CONSOLIDATION | ENGINEERING CONSOLIDATION | - |  | PIPING_ISOMETRIC_DRAWING: 4-LO-403235-40S-SS | PIPING_ISOMETRIC_DRAWING: 4-LO-403235-40S-SS
BNO-MABU-300-MP-2343-10038 | PIPING | Final Status | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473813-40-AW | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473813-40-AW
BNO-MABU-300-MP-2343-10040 | PIPING | Document Status, Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING CONSOLIDATION | TRANSMITTAL | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-DN-473805-80-AW | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-DN-473805-80-AW
BNO-MABU-300-MP-2343-10042 | PIPING | Final Status | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-DN-473806-40-AW | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-DN-473806-40-AW
BNO-MABU-300-MP-2343-10046 | PIPING | Document Status, Issue Status, Final Status | C02 | C02 | AFC 3 | AFC 1 | TRANSMITTAL | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-CC-423040-40S-SS | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-CC-423040-40S-SS
BNO-MABU-300-MP-2343-10048 | PIPING | Revision, Document Status, Issue Status, Final Status | C02 | C03 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-BH-463371-80-ALT | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-BH-463371-80-ALT
BNO-MABU-300-MP-2343-10049 | PIPING | Revision, Document Status, Issue Status, Final Status | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-BH-463372-80-A | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-BH-463372-80-A
BNO-MABU-300-MP-2343-10051 | PIPING | Document Status, Issue Status, Final Status | C02 | C02 | AFC 3 | AFC 1 | TRANSMITTAL | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | PIPING CONSTRUCT ISOMETRIC DRAWING: 10"-BH-463374-40-ALT | PIPING CONSTRUCT ISOMETRIC DRAWING: 10"-BH-463374-40-ALT
BNO-MABU-300-MP-2343-10054 | PIPING | Document Status, Issue Status, Final Status | C02 | C02 | AFC 3 | AFC 1 | TRANSMITTAL | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-BH-463378-80-A | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-BH-463378-80-A
BNO-MABU-300-MP-2343-10056 | PIPING | Document Status, Issue Status, Final Status | C02 | C02 | AFC 3 | AFC 1 | TRANSMITTAL | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | PIPING CONSTRUCT ISOMETRIC DRAWING: 10"-BH-463380-40-ALT | PIPING CONSTRUCT ISOMETRIC DRAWING: 10"-BH-463380-40-ALT
BNO-MABU-300-MP-2343-10057 | PIPING | Document Status, Issue Status, Final Status | C02 | C02 | UNDER REVIEW | AFC 3A | ENGINEERING CONSOLIDATION | ISSUED | - | AFC/AFU RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-BH-463381-40-ALT | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-BH-463381-40-ALT
BNO-MABU-300-MP-2343-10058 | PIPING | Document Status, Issue Status, Final Status | C02 | C02 | UNDER REVIEW | AFC 1 | ENGINEERING CONSOLIDATION | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-BH-463383-40S-SS | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-BH-463383-40S-SS
BNO-MABU-300-MP-2343-10059 | PIPING | Document Status, Issue Status, Final Status | C02 | C02 | AFC 3 | AFC 1 | TRANSMITTAL | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-BH-463384-40-ALT | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-BH-463384-40-ALT
BNO-MABU-300-MP-2343-10061 | PIPING | Final Status | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-BH-463387-40-ALT | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-BH-463387-40-ALT
BNO-MABU-300-MP-2343-10064 | PIPING | Document Status, Issue Status, Final Status | C02 | C02 | AFC 3 | AFC 1 | TRANSMITTAL | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-BH-463394-40-ALT | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-BH-463394-40-ALT
BNO-MABU-300-MP-2343-10071 | PIPING | Final Status | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473611-STD-G | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473611-STD-G
BNO-MABU-300-MP-2343-10073 | PIPING | Final Status | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473613-STD-G | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473613-STD-G
BNO-MABU-300-MP-2343-10077 | PIPING | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING CONSOLIDATION | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-DN-473617-80-G | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-DN-473617-80-G
BNO-MABU-300-MP-2343-10080 | PIPING | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING CONSOLIDATION | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-DN-473621-80-G | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-DN-473621-80-G
BNO-MABU-300-MP-2343-10083 | PIPING | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING CONSOLIDATION | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-DN-473624-80-G | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-DN-473624-80-G
BNO-MABU-300-MP-2343-10084 | PIPING | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING CONSOLIDATION | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-DN-473625-80-G | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-DN-473625-80-G
BNO-MABU-300-MP-2343-10085 | PIPING | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING CONSOLIDATION | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-DN-473626-80-G | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-DN-473626-80-G
BNO-MABU-300-MP-2343-10087 | PIPING | Final Status | C01 | C01 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-DC-483015-80-A | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-DC-483015-80-A
BNO-MABU-300-MP-2343-10089 | PIPING | Final Status | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-DN-473800-40-AW | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-DN-473800-40-AW
BNO-MABU-300-MP-2343-10091 | PIPING | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING CONSOLIDATION | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-DN-473807-10S-13841 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-DN-473807-10S-13841
BNO-MABU-300-MP-2343-10093 | PIPING | Document Status, Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING COMMENTS | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-DN-473808-40-AW | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-DN-473808-40-AW
BNO-MABU-300-MP-2343-10094 | PIPING | Revision, Document Status, Issue Status, Final Status | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473809-40-AW | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473809-40-AW
BNO-MABU-300-MP-2343-10095 | PIPING | Revision, Document Status, Issue Status, Final Status | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473810-40-AW | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473810-40-AW
BNO-MABU-300-MP-2343-10097 | PIPING | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING CONSOLIDATION | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-IA-503287-80-G | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-IA-503287-80-G
BNO-MABU-300-MP-2343-10098 | PIPING | Document Status, Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING COMMENTS | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-IA-503288-80-G | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-IA-503288-80-G
BNO-MABU-300-MP-2343-10099 | PIPING | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING CONSOLIDATION | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-PM-083101-120-IFJ | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-PM-083101-120-IFJ
BNO-MABU-300-MP-2343-10101 | PIPING | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING CONSOLIDATION | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-DN-473811-40-AW | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-DN-473811-40-AW
BNO-MABU-300-MP-2343-10109 | PIPING | Document Status, Issue Status, Final Status | C02 | C02 | AFC 3 | AFC 3A | TRANSMITTAL | ISSUED | - | AFC/AFU RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-PG-313047-750-FFLT-1H | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-PG-313047-750-FFLT-1H
BNO-MABU-300-MP-2343-10110 | PIPING | Final Status | C01 | C01 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-PG-313048-"750"-F1-1H | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-PG-313048-"750"-F1-1H
BNO-MABU-300-MP-2343-10119 | PIPING | Final Status | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING: 24"-BH-463001-STD-ALT | PIPING CONSTRUCT ISOMETRIC DRAWING: 24"-BH-463001-STD-ALT
BNO-MABU-300-MP-2343-10124 | PIPING | Revision, Document Status, Issue Status, Final Status | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-FG-443101-80-B-P | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-FG-443101-80-B-P
BNO-MABU-300-MP-2343-10130 | PIPING | Document Status, Issue Status, Final Status | C02 | C02 | AFC 3 | AFC 1 | TRANSMITTAL | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-1/2"-PM-083105-XXS-CC | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-1/2"-PM-083105-XXS-CC
BNO-MABU-300-MP-2343-10131 | PIPING | Document Status, Issue Status, Final Status | C02 | C02 | AFC 3 | AFC 1 | TRANSMITTAL | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | PIPING CONSTRUCT ISOMETRIC DRAWING: 6"-PM-043105-1125-JJ | PIPING CONSTRUCT ISOMETRIC DRAWING: 6"-PM-043105-1125-JJ
BNO-MABU-300-MP-2343-10133 | PIPING | Final Status | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING: 6"-PM-043106-120-IFJ | PIPING CONSTRUCT ISOMETRIC DRAWING: 6"-PM-043106-120-IFJ
BNO-MABU-300-MP-2343-10141 | PIPING | Final Status | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1/2"-PM-043111-100-CC | PIPING CONSTRUCT ISOMETRIC DRAWING: 1/2"-PM-043111-100-CC
BNO-MABU-300-MP-2343-10158 | PIPING | Document Status, Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING CONSOLIDATION | TRANSMITTAL | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-WI-403229-2205-251432 | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-WI-403229-2205-251432
BNO-MABU-300-MP-2343-10159 | PIPING | Document Status, Issue Status, Final Status | C02 | C02 | AFC 3 | AFC 1 | TRANSMITTAL | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-WI-403230-2000-J1 | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-WI-403230-2000-J1
BNO-MABU-300-MP-2343-10160 | PIPING | Final Status | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING: 6"-WI-403231-"1000"-J1 | PIPING CONSTRUCT ISOMETRIC DRAWING: 6"-WI-403231-"1000"-J1
BNO-MABU-300-MP-2343-10162 | PIPING | Document Status, Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING COMMENTS | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-LO-403236-40S-SS-P | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-LO-403236-40S-SS-P
BNO-MABU-300-MP-2343-10164 | PIPING | Revision, Document Status, Issue Status, Final Status | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 3/4"-VA-403237-40S-SS-P | PIPING CONSTRUCT ISOMETRIC DRAWING: 3/4"-VA-403237-40S-SS-P
BNO-MABU-300-MP-2343-10166 | PIPING | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING CONSOLIDATION | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-WI-403240-1771-J1 | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-WI-403240-1771-J1
BNO-MABU-300-MP-2343-10168 | PIPING | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING CONSOLIDATION | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-WI-403244-2205-251432 | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-WI-403244-2205-251432
BNO-MABU-300-MP-2343-10172 | PIPING | Document Status, Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING COMMENTS | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-WI-403251-1890-251432 | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-WI-403251-1890-251432
BNO-MABU-300-MP-2343-10173 | PIPING | Document Status, Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING CONSOLIDATION | TRANSMITTAL | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-WI-403252-1890-251432 | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-WI-403252-1890-251432
BNO-MABU-300-MP-2343-10178 | PIPING | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING CONSOLIDATION | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 16"-WI-403259-1900-F | PIPING CONSTRUCT ISOMETRIC DRAWING: 16"-WI-403259-1900-F
BNO-MABU-300-MP-2343-10183 | PIPING | Final Status | C01 | C01 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-BH-463376-STD-ALT | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-BH-463376-STD-ALT
BNO-MABU-300-MP-2343-10184 | PIPING | Final Status | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-BH-463382-750-FFLT-P | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-BH-463382-750-FFLT-P
BNO-MABU-300-MP-2343-10186 | PIPING | Final Status | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-BH-463389-80-A-P | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-BH-463389-80-A-P
BNO-MABU-300-MP-2343-10188 | PIPING | Document Status, Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING COMMENTS | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473619-40-G | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473619-40-G
BNO-MABU-300-MP-2343-10189 | PIPING | Document Status, Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING COMMENTS | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473628-40-G | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-DN-473628-40-G
BNO-MABU-300-MP-2343-10214 | PIPING | Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING CONSOLIDATION | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 6"-FG-443007-40S-SSB-ET | PIPING CONSTRUCT ISOMETRIC DRAWING: 6"-FG-443007-40S-SSB-ET
BNO-MABU-300-MP-2343-10217 | PIPING | Revision, Document Status, Issue Status, Final Status | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 10"-DN-473801-40-AW | PIPING CONSTRUCT ISOMETRIC DRAWING: 10"-DN-473801-40-AW
BNO-MABU-300-MP-2343-10218 | PIPING | Final Status | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-BH-443102-80-B-P | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-BH-443102-80-B-P
BNO-MABU-300-MP-2343-10219 | PIPING | Revision, Document Status, Issue Status, Final Status | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-WF-613800-200-MV | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-WF-613800-200-MV
BNO-MABU-300-MP-2343-10220 | PIPING | Revision, Document Status, Issue Status, Final Status | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-WF-613079-200-MVB | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-WF-613079-200-MVB
BNO-MABU-300-MP-2343-10221 | PIPING | Final Status | C02 | C02 | AFC 3 | AFC 3A | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING: 24"-WI-403065-STD-AW | PIPING CONSTRUCT ISOMETRIC DRAWING: 24"-WI-403065-STD-AW
BNO-MABU-300-MP-2343-10222 | PIPING | Revision, Document Status, Issue Status, Final Status | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 6"-CM-423002-40S-SS | PIPING CONSTRUCT ISOMETRIC DRAWING: 6"-CM-423002-40S-SS
BNO-MABU-300-MP-2343-10223 | PIPING | Revision, Document Status, Issue Status, Final Status | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-CM-423021-40S-SS | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-CM-423021-40S-SS
BNO-MABU-300-MP-2343-10224 | PIPING | Document Status, Issue Status, Final Status | C01 | C01 | UNDER REVIEW | AFC 3 | ENGINEERING CONSOLIDATION | ISSUED | - | AFC/AFU RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-DN-473372-STD-H | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-DN-473372-STD-H
BNO-MABU-300-MP-2343-10225 | PIPING | Document Status, Issue Status, Final Status | C01 | C01 | UNDER REVIEW | AFC 1 | ENGINEERING CONSOLIDATION | ISSUED | - | AFC/AFU RETURNED AS CODE 1 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-IA-503501-80-G | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-IA-503501-80-G
BNO-MABU-300-MP-2343-10226 | PIPING | Revision, Document Status, Issue Status, Final Status | C01 | C02 | AFC 3 | UNDER REVIEW | ISSUED | ENGINEERING CONSOLIDATION | AFC/AFU RETURNED AS CODE 3 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-IA-503502-80-G | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-IA-503502-80-G
BNO-MABU-300-MP-2343-10230 | PIPING | Revision, Issue Status | C01 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING CONSOLIDATION | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-IA-503506-80-G | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-IA-503506-80-G
BNO-MABU-300-MP-2343-10231 | PIPING | Revision, Issue Status, Final Status | C02 | C03 | AFC 3 | AFC 1 | ISSUED | ISSUED | AFC/AFU RETURNED AS CODE 3 | AFC/AFU RETURNED AS CODE 1 | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-IA-503507-80-G | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-IA-503507-80-G
BNO-MABU-300-MP-2343-10236 | PIPING | Revision, Issue Status | C01 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING CONSOLIDATION | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-IA-503508-80-G | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-IA-503508-80-G
BNO-MABU-300-MP-2343-10237 | PIPING | Revision, Issue Status | C01 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING CONSOLIDATION | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-IA-503509-80-G | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-IA-503509-80-G
BNO-MABU-300-MP-2343-10246 | PIPING | Document Status, Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ISSUED | - | IFA RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING 6"-DN-473139-STD-H | PIPING CONSTRUCT ISOMETRIC DRAWING 6"-DN-473139-STD-H
BNO-MABU-300-MP-2343-10247 | PIPING | Document Status, Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING 6"-DN-473048-STD-H | PIPING CONSTRUCT ISOMETRIC DRAWING 6"-DN-473048-STD-H
BNO-MABU-300-MP-2343-10248 | PIPING | Document Status, Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING 2"-DN-473634-80-G | PIPING CONSTRUCT ISOMETRIC DRAWING 2"-DN-473634-80-G
BNO-MABU-300-MP-2343-10249 | PIPING | Document Status, Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-1/2-DN-488837-160S-253841A | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-1/2-DN-488837-160S-253841A
BNO-MABU-300-MP-2343-10250 | PIPING | Document Status, Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-1/2-DN-483817-160S-253841A | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-1/2-DN-483817-160S-253841A
BNO-MABU-300-MP-2343-10251 | PIPING | Document Status, Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ISSUED | - | IFA RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING-2"-CM-423014-XXS-J | PIPING CONSTRUCT ISOMETRIC DRAWING-2"-CM-423014-XXS-J
BNO-MABU-300-MP-2343-10252 | PIPING | Document Status, Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING-1"-UW-513779-80-G | PIPING CONSTRUCT ISOMETRIC DRAWING-1"-UW-513779-80-G
BNO-MABU-300-MP-2343-10253 | PIPING | Document Status, Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING 6"-VA-403235-40S-SS | PIPING CONSTRUCT ISOMETRIC DRAWING 6"-VA-403235-40S-SS
BNO-MABU-300-MP-2343-10254 | PIPING | Document Status, Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING 3"-CM-423051-40S-SS | PIPING CONSTRUCT ISOMETRIC DRAWING 3"-CM-423051-40S-SS
BNO-MABU-300-MP-2343-10255 | PIPING | Document Status, Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING CONSOLIDATION | ISSUED | - | IFA RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING-2-IA- 503082-80-G | PIPING CONSTRUCT ISOMETRIC DRAWING-2-IA- 503082-80-G
BNO-MABU-300-MP-2343-10256 | PIPING | Document Status, Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2-DN-473635-80-G | PIPING CONSTRUCT ISOMETRIC DRAWING: 2-DN-473635-80-G
BNO-MABU-300-MP-2343-10257 | PIPING | Document Status, Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING 2"-DN-473379-80-G | PIPING CONSTRUCT ISOMETRIC DRAWING 2"-DN-473379-80-G
BNO-MABU-300-MP-2343-10258 | PIPING | Document Status, Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ISSUED | - | IFA RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING 2"-DN-473377-STD-H | PIPING CONSTRUCT ISOMETRIC DRAWING 2"-DN-473377-STD-H
BNO-MABU-300-MP-2343-10259 | PIPING | Document Status, Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ISSUED | - | IFA RETURNED AS CODE 1 | PIPING CONSTRUCT ISOMETRIC DRAWING 2"-DN-473380-80-G | PIPING CONSTRUCT ISOMETRIC DRAWING 2"-DN-473380-80-G
BNO-MABU-300-MP-2343-10260 | PIPING | Document Status, Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING COMMENTS | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING-2-DN-473378-STD-H | PIPING CONSTRUCT ISOMETRIC DRAWING-2-DN-473378-STD-H
BNO-MABU-300-MP-2343-10261 | PIPING | Document Status, Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING CONSOLIDATION | ISSUED | - | IFA RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313051-750-FFLT-1H | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313051-750-FFLT-1H
BNO-MABU-300-MP-2343-10262 | PIPING | Document Status, Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING CONSOLIDATION | ISSUED | - | IFA RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313055-750-FFLT-1H | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313055-750-FFLT-1H
BNO-MABU-300-MP-2343-10263 | PIPING | Document Status, Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING CONSOLIDATION | ISSUED | - | IFA RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313058-750-FFLT-1H | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313058-750-FFLT-1H
BNO-MABU-300-MP-2343-10264 | PIPING | Document Status, Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING CONSOLIDATION | ISSUED | - | IFA RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313054-750-FFLT-1H | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313054-750-FFLT-1H
BNO-MABU-300-MP-2343-10265 | PIPING | Document Status, Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING CONSOLIDATION | ISSUED | - | IFA RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313057-750-FFLT-1H | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313057-750-FFLT-1H
BNO-MABU-300-MP-2343-10266 | PIPING | Document Status, Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING CONSOLIDATION | ISSUED | - | IFA RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313053-750-FFLT-1H | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313053-750-FFLT-1H
BNO-MABU-300-MP-2343-10267 | PIPING | Document Status, Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING CONSOLIDATION | ISSUED | - | IFA RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313052-750-FFLT-1H | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313052-750-FFLT-1H
BNO-MABU-300-MP-2343-10268 | PIPING | Document Status, Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING CONSOLIDATION | ISSUED | - | IFA RETURNED AS CODE 3 | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313056-750-FFLT-1H | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1 2-PG-313056-750-FFLT-1H
BNO-MABU-300-MP-2343-10269 | PIPING | Document Status, Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-DN-483103-80-AW | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-DN-483103-80-AW
BNO-MABU-300-MP-2343-10270 | PIPING | Document Status, Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1/2"-DN-433637-80-G | PIPING CONSTRUCT ISOMETRIC DRAWING-1-1/2"-DN-433637-80-G
BNO-MABU-300-MP-2343-10272 | PIPING | Issue Status, Final Status | A01 | A01 | UNDER REVIEW | IFA | ENGINEERING CONSOLIDATION | ENGINEERING CONSOLIDATION | - |  | PIPING CONSTRUCT ISOMETRIC DRAWING-1"-IA-503289-80-G | PIPING CONSTRUCT ISOMETRIC DRAWING-1"-IA-503289-80-G
BNO-MABU-300-MP-3323-10004 | PIPING | Issue Status | R01 | R01 | IFR | IFR | ISSUED | ISSUED | - |  | TECHNICAL BID EVALUATION FOR GASKETS | TECHNICAL BID EVALUATION FOR GASKETS
BNO-MABU-300-MP-3323-10006 | PIPING | Revision, Document Status, Issue Status, Final Status | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | TBE FOR VA LVES | TBE FOR VA LVES
BNO-MABU-300-MP-3323-10007 | PIPING | Revision, Document Status, Issue Status, Final Status | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | TBE FOR SPRING SUPPORTS | TBE FOR SPRING SUPPORTS
BNO-MABU-300-MP-3323-10009 | PIPING | Revision, Document Status, Issue Status, Final Status | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | TBE FOR PIPING SPECIAL ITEMS | TBE FOR PIPING SPECIAL ITEMS
BNO-MABU-300-MP-3323-10011 | PIPING | Revision, Document Status, Issue Status, Final Status | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | TBE FOR PIPING SUPPORT MATERIALS | TBE FOR PIPING SUPPORT MATERIALS
BNO-MABU-300-MP-3323-10012 | PIPING | Revision, Document Status, Issue Status, Final Status | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | TBE FOR SPECIAL VALVES | TBE FOR SPECIAL VALVES
BNO-MABU-300-MP-3323-10013 | PIPING | Revision, Document Status, Issue Status, Final Status | A01 | R01 | AFC 3 | NI | ISSUED | NÃO SE APLICA | - |  | TBE FOR HUB CONNECTOR (GRAYLOC) | TBE FOR HUB CONNECTOR (GRAYLOC)
BNO-MABU-300-MP-4338-10002 | PIPING | Final Status | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | CRITICAL LINE LIST | CRITICAL LINE LIST
BNO-MABU-300-MP-4338-10003 | PIPING | Final Status | A03 | A03 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | PIPING SPECIALTY ITEM LIST | PIPING SPECIALTY ITEM LIST
BNO-MABU-300-MP-4368-10001 | PIPING | Final Status | A03 | A03 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | VALVE LIST | VALVE LIST
BNO-MABU-300-MP-7303-10001 | PIPING | Revision, Document Status, Issue Status, Final Status | A02 | A03 | AFC 1 | IFA | ISSUED | ENGINEERING DISTRIBUTION | AFC/AFU RETURNED AS CODE 1 |  | MATERIAL REQUISITION FOR BOLTS | MATERIAL REQUISITION FOR BOLTS
BNO-MABU-300-MP-7303-10004 | PIPING | Final Status | A01 | A01 | AFC 3 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | MATERIAL REQUISITION FOR PIPES | MATERIAL REQUISITION FOR PIPES
BNO-MABU-300-MP-7303-10005 | PIPING | Final Status | A01 | A01 | AFC 3 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | MATERIAL REQUISITION FOR FITTINGS | MATERIAL REQUISITION FOR FITTINGS
BNO-MABU-300-MP-7303-10006 | PIPING | Revision, Document Status, Issue Status, Final Status | A03 | A04 | AFC 3 | IFA | ISSUED | ENGINEERING DISTRIBUTION | AFC/AFU RETURNED AS CODE 3 |  | MATERIAL REQUISITION FOR GASKETS | MATERIAL REQUISITION FOR GASKETS
BNO-MABU-300-MP-7303-10013 | PIPING | Revision, Document Status, Issue Status, Final Status | A02 | A03 | AFC 3 | IFA | ISSUED | ENGINEERING DISTRIBUTION | AFC/AFU RETURNED AS CODE 3 |  | MATERIAL REQUISITION FOR SPECTACLE BLANK AND PADDLE BLANK | MATERIAL REQUISITION FOR SPECTACLE BLANK AND PADDLE BLANK
BNO-MABU-300-MP-7402-10003 | PIPING | Issue Status, Final Status | A02 | A02 | UNDER REVIEW | IFA | ENGINEERING CONSOLIDATION | ENGINEERING CONSOLIDATION | - |  | 90% MODEL REVIEW REPORT (P2+) | 90% MODEL REVIEW REPORT (P2+)
BNO-MABU-300-MP-7737-10002 | PIPING | Final Status | A03 | A03 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | SPECIFICATION FOR VALVES | SPECIFICATION FOR VALVES
BNO-MABU-300-MP-7737-10004 | PIPING | Final Status | A03 | A03 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | SPECIFICATIONS FOR PIPING STRESS ANALYSIS PHILOSOPHY | SPECIFICATIONS FOR PIPING STRESS ANALYSIS PHILOSOPHY
BNO-MABU-300-MP-8005-10003 | PIPING | Final Status | A02 | A02 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | PIPING STRESS ANALYSIS REPORT - SYSTEMS 300-PP-S04_ 300-PP-S05_ 300-PP-S06 AND 300-PP-S16 | PIPING STRESS ANALYSIS REPORT - SYSTEMS 300-PP-S04_ 300-PP-S05_ 300-PP-S06 AND 300-PP-S16
BNO-MABU-300-MR-7303-10005 | MECHANICAL | Final Status | A03 | A03 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | WATERFLOOD INJECTION PUMP SIZING CALCULATION AND REPORT (POWER REQUIREMENT) | WATERFLOOD INJECTION PUMP SIZING CALCULATION AND REPORT (POWER REQUIREMENT)
BNO-MABU-300-PX-0580-10003 | PROCESS | Document Status, Issue Status, Final Status | A03 | A03 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING COMMENTS | - |  | EQUIPMENT & LINE SIZING VALIDATION REPORT | EQUIPMENT & LINE SIZING VALIDATION REPORT
BNO-MABU-300-PX-1380-10002 | PROCESS | Document Status, Issue Status, Final Status | A03 | A03 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING COMMENTS | - |  | DRAINAGE SYSTEM CALCULATION NOTES | DRAINAGE SYSTEM CALCULATION NOTES
BNO-MABU-300-PX-1380-10003 | PROCESS | Document Status | A04 | A04 | AFC 1 | AFC 1 | ENGINEERING DISTRIBUTION | ENGINEERING COMMENTS | APPROVED FOR USE (AFU) | APPROVED FOR USE (AFU) | METHANOL PUMP PROCESS CALCULATION NOTES | METHANOL PUMP PROCESS CALCULATION NOTES
BNO-MABU-300-PX-1380-10011 | PROCESS | Document Status, Issue Status, Final Status | A05 | A05 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING COMMENTS | - |  | TEMPERATURE INSTRUMENTS CALCULATION NOTES | TEMPERATURE INSTRUMENTS CALCULATION NOTES
BNO-MABU-300-PX-1380-10015 | PROCESS | Document Status, Issue Status, Final Status | A03 | A03 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING COMMENTS | - |  | PROCESS SAFETY TIME CALCULATIONS | PROCESS SAFETY TIME CALCULATIONS
BNO-MABU-300-PX-2105-10008 | PROCESS | Final Status | A05 | A05 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | PROCESS DATASHEETS FOR SHUTDOWN VALVES | PROCESS DATASHEETS FOR SHUTDOWN VALVES
BNO-MABU-300-PX-2105-10012 | PROCESS | Final Status | A04 | A04 | AFC 1 | IFA | ISSUED | ISSUED | IFA RETURNED AS CODE 1 | IFA RETURNED AS CODE 1 | PROCESS DATASHEET FOR WATERFLOOD INJECTION PUMP NEW (P-4047) | PROCESS DATASHEET FOR WATERFLOOD INJECTION PUMP NEW (P-4047)
BNO-MABU-300-PX-2365-10009-001 | PROCESS | Document Status, Issue Status | C04 | C04 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING COMMENTS | - |  | P&ID - BN PRODUCTION SYSTEMS GAS RISER LIFT METER | P&ID - BN PRODUCTION SYSTEMS GAS RISER LIFT METER
BNO-MABU-300-PX-2365-10010-001 | PROCESS | Document Status, Issue Status | C04 | C04 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING COMMENTS | - |  | P&ID - BN PRODUCTION SYSTEM PIG LAUNCHER /RECEIVER (A-0820J) | P&ID - BN PRODUCTION SYSTEM PIG LAUNCHER /RECEIVER (A-0820J)
BNO-MABU-300-PX-2365-10011-001 | PROCESS | Document Status, Issue Status | C04 | C04 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING COMMENTS | - |  | P&ID - BN PRODUCTION SYSTEM PIG LAUNCHER /RECEIVER (A-0820K) | P&ID - BN PRODUCTION SYSTEM PIG LAUNCHER /RECEIVER (A-0820K)
BNO-MABU-300-PX-2365-10012-001 | PROCESS | Document Status, Issue Status | C05 | C05 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING COMMENTS | - |  | P&ID PRODUCTION SYSTEMS - PRODUCTION MANIFOLD - MODIFICATION | P&ID PRODUCTION SYSTEMS - PRODUCTION MANIFOLD - MODIFICATION
BNO-MABU-300-PX-2365-10021-001 | PROCESS | Document Status, Issue Status | C04 | C04 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING COMMENTS | - |  | P&ID - BN WATERFLOOD SYSTEM - WATERFLOOD INJECTION PUMP | P&ID - BN WATERFLOOD SYSTEM - WATERFLOOD INJECTION PUMP
BNO-MABU-300-PX-2365-10022-001 | PROCESS | Document Status | C03 | C03 | AFC 1 | AFC 1 | ENGINEERING DISTRIBUTION | ENGINEERING COMMENTS | APPROVED FOR USE (AFU) | APPROVED FOR USE (AFU) | P&ID - BN UTILITY SYSTEMS - WATERFLOOD INJECTION PUMP TURBINE PACKAGE | P&ID - BN UTILITY SYSTEMS - WATERFLOOD INJECTION PUMP TURBINE PACKAGE
BNO-MABU-300-PX-2365-10029-001 | PROCESS | Document Status, Issue Status | C04 | C04 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING COMMENTS | - |  | P&ID - UTILITY SYSTEM HYDRATE INHIBITOR SYSTEM MODIFICATION | P&ID - UTILITY SYSTEM HYDRATE INHIBITOR SYSTEM MODIFICATION
BNO-MABU-300-PX-2366-10006-001 | PROCESS | Document Status, Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING COMMENTS | - |  | PFS - BONGA NORTH WELLS FLOWLINES LAUNCHER RECEIVERS | PFS - BONGA NORTH WELLS FLOWLINES LAUNCHER RECEIVERS
BNO-MABU-300-PX-2366-10011-001 | PROCESS | Document Status, Issue Status | C02 | C02 | UNDER REVIEW | UNDER REVIEW | ENGINEERING DISTRIBUTION | ENGINEERING COMMENTS | - |  | PFS - WATERFLOOD SRS AND INJECTION - MODIFICATION | PFS - WATERFLOOD SRS AND INJECTION - MODIFICATION
BNO-MABU-300-PX-2908-10001 | PROCESS | Document Status | A04 | A04 | AFC 1 | AFC 1 | ENGINEERING DISTRIBUTION | ENGINEERING COMMENTS | APPROVED FOR USE (AFU) | APPROVED FOR USE (AFU) | RELIEF VALVES CALCULATION NOTES | RELIEF VALVES CALCULATION NOTES
BNO-MABU-300-RA-6919-10001 | MATERIALS | Issue Status, Final Status | A02 | A02 | UNDER REVIEW | IFA | ENGINEERING DISTRIBUTION | ENGINEERING DISTRIBUTION | - |  | CORROSION MANAGEMENT FRAMEWORK AND INSPECTION PLAN | CORROSION MANAGEMENT FRAMEWORK AND INSPECTION PLAN
BNO-MABU-300-RA-7769-10002-002 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | CORROSION MANAGEMENT DRAWING - 0.75-PM-043117-80-B | CORROSION MANAGEMENT DRAWING - 0.75-PM-043117-80-B
BNO-MABU-300-RA-7769-10002-003 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | CORROSION MANAGEMENT DRAWING - 2-PL-233050-80-B | CORROSION MANAGEMENT DRAWING - 2-PL-233050-80-B
BNO-MABU-300-RA-7769-10006-002 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | CORROSION MANAGEMENT DRAWING - 4-PG-313045-750-F1-1H | CORROSION MANAGEMENT DRAWING - 4-PG-313045-750-F1-1H
BNO-MABU-300-RA-7769-10006-003 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | CORROSION MANAGEMENT DRAWING - 4-PG-313045-750-F1-1H | CORROSION MANAGEMENT DRAWING - 4-PG-313045-750-F1-1H
BNO-MABU-300-RA-7769-10006-004 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | CORROSION MANAGEMENT DRAWING - 4-PG-313045-750-F1-1H | CORROSION MANAGEMENT DRAWING - 4-PG-313045-750-F1-1H
BNO-MABU-300-RA-7769-10006-005 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | CORROSION MANAGEMENT DRAWING - 4-PG-313045-750-F1-1H | CORROSION MANAGEMENT DRAWING - 4-PG-313045-750-F1-1H
BNO-MABU-300-RA-7769-10006-006 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | CORROSION MANAGEMENT DRAWING - 4-PG-313048-750-F1-1H | CORROSION MANAGEMENT DRAWING - 4-PG-313048-750-F1-1H
BNO-MABU-300-RA-7769-10006-007 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | CORROSION MANAGEMENT DRAWING - 4-PG-313048-750-F1-1H | CORROSION MANAGEMENT DRAWING - 4-PG-313048-750-F1-1H
BNO-MABU-300-RA-7769-10006-008 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | CORROSION MANAGEMENT DRAWING - 4-PG-313048-750-F1-1H | CORROSION MANAGEMENT DRAWING - 4-PG-313048-750-F1-1H
BNO-MABU-300-RA-7769-10006-009 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | CORROSION MANAGEMENT DRAWING - 4-PG-313048-750-F1-1H | CORROSION MANAGEMENT DRAWING - 4-PG-313048-750-F1-1H
BNO-MABU-300-RA-7769-10006-010 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | CORROSION MANAGEMENT DRAWING - 4-PG-313048-750-F1-1H | CORROSION MANAGEMENT DRAWING - 4-PG-313048-750-F1-1H
BNO-MABU-300-RA-7769-10006-011 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | CORROSION MANAGEMENT DRAWING - 4-PG-313048-750-F1-1H | CORROSION MANAGEMENT DRAWING - 4-PG-313048-750-F1-1H
BNO-MABU-300-RA-7769-10006-012 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | CORROSION MANAGEMENT DRAWING - TAM26-TP-07-4-PG-313045-750-F1-1H | CORROSION MANAGEMENT DRAWING - TAM26-TP-07-4-PG-313045-750-F1-1H
BNO-MABU-300-RA-7769-10006-013 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | CORROSION MANAGEMENT DRAWING - TAM26-TP-08-4-PG-313048-750-F1-1H | CORROSION MANAGEMENT DRAWING - TAM26-TP-08-4-PG-313048-750-F1-1H
BNO-MABU-300-RA-7769-10007-002 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | CORROSION MANAGEMENT DRAWING - 4-PG-313046-750-FLT-1H | CORROSION MANAGEMENT DRAWING - 4-PG-313046-750-FLT-1H
BNO-MABU-300-RA-7769-10007-003 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | CORROSION MANAGEMENT DRAWING - 4-PG-313046-750-FLT-1H | CORROSION MANAGEMENT DRAWING - 4-PG-313046-750-FLT-1H
BNO-MABU-300-RA-7769-10007-004 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | CORROSION MANAGEMENT DRAWING - 4-PG-313046-750-FLT-1H | CORROSION MANAGEMENT DRAWING - 4-PG-313046-750-FLT-1H
BNO-MABU-300-RA-7769-10007-005 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | CORROSION MANAGEMENT DRAWING - 4-PG-313046-750-FLT-1H | CORROSION MANAGEMENT DRAWING - 4-PG-313046-750-FLT-1H
BNO-MABU-300-RA-7769-10007-006 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | CORROSION MANAGEMENT DRAWING - 4-PG-313049-750-FLT-1H | CORROSION MANAGEMENT DRAWING - 4-PG-313049-750-FLT-1H
BNO-MABU-300-RA-7769-10007-007 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | CORROSION MANAGEMENT DRAWING - 4-PG-313049-750-FLT-1H | CORROSION MANAGEMENT DRAWING - 4-PG-313049-750-FLT-1H
BNO-MABU-300-RA-7769-10007-008 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | CORROSION MANAGEMENT DRAWING - 4-PG-313049-750-FLT-1H | CORROSION MANAGEMENT DRAWING - 4-PG-313049-750-FLT-1H
BNO-MABU-300-RA-7769-10007-009 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | CORROSION MANAGEMENT DRAWING - 4-PG-313049-750-FLT-1H | CORROSION MANAGEMENT DRAWING - 4-PG-313049-750-FLT-1H
BNO-MABU-300-RA-7769-10008-002 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-003 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-004 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-005 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-006 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-007 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-008 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & FLARE SYSTEM | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & FLARE SYSTEM
BNO-MABU-300-RA-7769-10008-009 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-010 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-011 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-012 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-013 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & FLARE SYSTEM | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & FLARE SYSTEM
BNO-MABU-300-RA-7769-10008-014 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & FLARE SYSTEM | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & FLARE SYSTEM
BNO-MABU-300-RA-7769-10008-015 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & SLARE SYSTEM | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & SLARE SYSTEM
BNO-MABU-300-RA-7769-10008-016 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & FLARE SYSTEM | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & FLARE SYSTEM
BNO-MABU-300-RA-7769-10008-017 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-018 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-019 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-020 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-021 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | BONGA NORTH CORROSION MANAGEMENT DRAWING GAS LIFT SYSTEM | BONGA NORTH CORROSION MANAGEMENT DRAWING GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-022 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-023 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-024 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-025 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-026 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-027 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM | BONGA NORTH CORROSION MANAGEMENT DRAWINGS GAS LIFT SYSTEM
BNO-MABU-300-RA-7769-10008-028 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & FLARE SYSTEM | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & FLARE SYSTEM
BNO-MABU-300-RA-7769-10008-029 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | BONGA NORTH CORROSION MANAGEMENT DRAWING RELIEF & FLARE SYSTEM | BONGA NORTH CORROSION MANAGEMENT DRAWING RELIEF & FLARE SYSTEM
BNO-MABU-300-RA-7769-10008-030 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & FLARE SYSTEM | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & FLARE SYSTEM
BNO-MABU-300-RA-7769-10008-031 | MATERIALS | Issue Status, Final Status | R01 | R01 | NI | IFR | NÃO SE APLICA | NÃO SE APLICA | - |  | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & FLARE SYSTEM | BONGA NORTH CORROSION MANAGEMENT DRAWINGS RELIEF & FLARE SYSTEM

## Status Transitions
Status Transition Counts
How EDROBO status differs from Engineering Base status
Engineering Status | EDROBO Status | Documents
UNDER REVIEW | IFA | 64
NI | IFR | 52
AFC 1 | IFA | 45
AFC 3 | UNDER REVIEW | 24
UNDER REVIEW | AFC 1 | 21
AFC 3 | AFC 3A | 21
AFC 3 | NI | 16
AFC 3 | IFA | 15
IFR | IFA | 15
AFC 3 | AFC 1 | 13
UNDER REVIEW | AFC 3 | 12
IFA | UNDER REVIEW | 10
IFA | AFC 1 | 5
IFA | AFC 3 | 2
UNDER REVIEW | AFC 3A | 2
AFC 1 | IFR | 1
AFC 1 | UNDER REVIEW | 1

## Base Number Check
Base Document Number Check
Audit-only: strips trailing -001 / -002 style suffix before comparing
Only in Engineering Base Number | Only in EDROBO Base Number
BNO-MABU-300-CS-4018-10024 | BNO-MABU-300-AA-7180-10100
BNO-MABU-300-CS-8102-10010 | BNO-MABU-300-EA-3323-10006
BNO-MABU-300-CS-8180-10011 | BNO-MABU-300-HX-1415-10001
BNO-MABU-300-IN-7303-10035 | BNO-MABU-300-HX-6613-10002
BNO-MABU-300-MP-3323-10008 | BNO-MABU-300-MP-2343-10092
BNO-MABU-300-MP-3323-10010 | BNO-MABU-300-MP-2358-10015
BNO-MABU-300-MP-4018-10014
BNO-MABU-300-MP-4306-10003
BNO-MABU-300-MP-4306-10004
BNO-MABU-300-MP-7880-10002
BNO-MABU-300-PX-2365-10019
BNO-MABU-300-RA-7180-00001